## Sheet1
Project | JIRA_CONST_TICKET_ID | Summary | Cleaned_Summary | Province | Issue Type | Status | Priority | Resolution | Assignee | Reporter | Creator | Created | Last Viewed | Updated | Resolved | Component/s | Due Date | Votes | Watchers | Images | Work Ratio | Sub-Tasks | Linked Issues | Description | Labels | Contact Attempts | Follow Up Date | Company LinkedIn | Team | Company Website | Revenue Estimate | Target start | Employee Estimate | Parent Link | Account Rep - Upsell | Original story points | Target end | Rank | Customer ID | customfield_10809 | Industry Group | Industry Segment | Sprint | End date | Epic Link | Rank (Obsolete) | Flagged | Epic/Theme | Current Phone Provider | Customer Address | Current Phone Expiry Date | BOSS_LINK | Development | SWAT_LINK | DUNS # | Building_Link | customfield_10809.1 | Building Name | Customer Phone Number | Date Time Contacted | Current Internet Expiry Date | Current Internet Provider | Switch Budget | Theme | customfield_10809.2 | Last Action | Customer Phone | Customer Email | Location Z Email | Location A Phone | Location Z Phone | Service Type | Scheduling Priority | Location A Name | Location Z Name | Location A Email | Package Link | Customer | Workstream | Customer Attention | Customer Delivery Instructions | Security Level | Planned Start | Planned End | Original Due Date | Follow-up | Scheduled Time | Past Due | Total Due | Fix Version/s | customfield_10809.3 | Installation Date | Work By | Building On Net | Start date | Distance (M) | # Floors | # Units | Sub-Project | Completed Date | Contractor Budget | Actual | Difference | Building Browser Link | Confluence Link | Project # | Construction Priority | Original Due Date.1 | City | Materials Budget | Labour Budget | Installer | Work Started | Prewired | Rent or Own | Email Address | Supporting Manager | Story Link | Approved By | Rejected By | Location | Reason for Leave | Return to Work Date | Budget Type | Monthly Payment | Planning Priority | Wop Funding | Application | Class of Service
Construction | CONST-3134 | 8 Dovercourt - ART Condos | 8 Dovercourt | Ontario | Condo | Restoration |  | Unresolved | Harvey Tran | Olawale Olaniyan [X] | Samantha Russell | 2015-02-25 13:16 |  | 2024-07-17 08:10 |  |  | 2024-03-08 | 0 | 2 | _thumb_52333.png _thumb_52332.png |  | CONST-3135, CONST-3136, CONST-3137, CONST-3718, CONST-3796, CONST-3915, CONST-3916, CONST-3917, CONST-3939, CONST-27704, CONST-30134, CONST-30135, CONST-30136, CONST-30137, CONST-30138, CONST-30139, CONST-30140, CONST-30141, CONST-30142, CONST-30143, CONST-30144, CONST-30145, CONST-30146, CONST-30147, CONST-35448, CONST-35449, CONST-36387, CONST-38802, CONST-38803 | CONST-9777, CONST-30055, CONST-27867 | Bring residential building onnet https://buildings.beanfield.com/buildings/view/2300 Linda Pressman linda.pressman@fsresidential.com 416 847 7225 145 Suites 7 Amenities Pop on ground floor beside loading dock 2 telecom risers -6-100 mm to risers zhone conduits , power in suites Fed from Queen and Dovercourt new BFMH enter from Sudbury side | FSactive, Fiberstreamagreement, Residential | [12 empty] | 0¦i07rdj: | [7 empty] | 45261 | [19 empty] | October 21st - City Permit granted and expires April 21st, 2023. May 01/23 - Extension approved. Expires November 1st 2023 Aug 15/23 - Pending locates Oct 11/23 - Construction scheduled to start Nov 23rd. Due dates updated. Oct 16/23 - Requested city permit extension Nov 02/23 - City permit extension approved. Jan 03/24 - Construction completed. Jan 31/24 - Conduit build scheduled for Feb 12th. Cable pull scheduled for Feb 26th Feb 01/24 - PO sent for conduit build Feb 12/24 - Conduit build completed Feb 26/24 - Cable pull completed Feb 29/24 - OSP splicing completed Mar 01/24 - ISP splicing scheduled Mar 08/24 - Building On-Net | [6 empty] | 3 - Normal | [19 empty] | Internal |  | 2022-08-23 |  |  |  | Integration | 2024-03-08 | 26469 |  |  | https://buildings.beanfield.com/buildings/view/2300 |  | 500431 | 3 - Normal | 2016-03-28 | West Queen West | 3943 | 10395
Construction | CONST-29504 | 75 Dalhousie St/ 76 Shutter St, Toronto - The Boot | 75 Dalhousie St/ 76 Shutter St, Toronto | Ontario | Condo | Restoration |  | Unresolved | Harvey Tran | Olawale Olaniyan [X] | Jessica Markiewicz | 2022-07-15 14:49 |  | 2024-06-28 11:03 |  |  | 2024-06-27 | 0 | 1 |  |  | CONST-29505, CONST-29506, CONST-30727, CONST-30728, CONST-31724, CONST-31726, CONST-33292, CONST-33293, CONST-33294, CONST-33295, CONST-33296, CONST-33297, CONST-33298, CONST-33299, CONST-33300, CONST-33301, CONST-33302, CONST-33303, CONST-33304, CONST-33305, CONST-35379, CONST-35580, CONST-35581, CONST-35950, CONST-36034, CONST-38835, CONST-38836 | CONST-30726 | Requested by Jay Fernandes Hi, These are the Fibrestream condos we have agreements for that don’t seem to fit into any groups (although I maybe wrong). Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. ¦Group¦Building Name¦Address¦suites¦ ¦Independent¦Eleven Superior¦11 Superior AVE Etobicoke ON M8V 0A7¦130¦ ¦Independent¦The James Club¦1135 Royal York RD Toronto ON M9A 4A7¦209¦ ¦Independent¦Independence Way¦115 George Appleton WAY North York ON M3M 2E9¦244¦ ¦Independent¦Danforth Village Estates¦1346 Danforth RD Toronto ON M4J1M9¦249¦ ¦Independent¦beBloor¦1369 Bloor ST Toronto ON M6P 4J3¦238¦ ¦Independent¦Ion Condos¦15 James Finlay WAY Toronto ON M3M 0B3¦200¦ ¦Independent¦Paradice at the Oasis¦1720 Eglinton AVE Toronto ON M4A2X9¦190¦ ¦Independent¦Havenon the Bluffs¦20 East Haven DR Toronto ON M1N1M2¦259¦ ¦Independent¦Kilgour Estate II¦21 Burkebrook PL Toronto ON M4G4K8¦228¦ ¦Independent¦Canvas Condos¦2301 Danforth AVE Toronto ON M4C 1L5¦156¦ ¦Independent¦3018 Yonge Condos¦3018 Yonge ST Toronto ON M4N 0A5¦188¦ ¦Independent¦Cranbrooke Village¦35 Saranac BLVD Toronto ON M6A 2G4¦341¦ ¦Independent¦39 Brant St¦39 Brant ST Toronto ON M5V0M8¦236¦ ¦Independent¦The Wave¦4 Elsinore PATH Toronto ON M8V 4G7¦185¦ ¦Independent¦Clock Tower Lofts¦700 King ST Toronto ON M5V 2Y6¦216¦ ¦Independent¦The Boot¦75 Dalhousie ST Toronto ON M5B 2R9¦153¦ ¦Independent¦B.Street Condos¦783 Bathurst ST Toronto ON M6G 1K1¦ ¦ ¦Independent¦85 Bloor St¦85 Bloor ST Toronto ON M4W3G9¦252¦ | Bolton, Fiberstreamagreement | [12 empty] | 0¦i3hm73: | [7 empty] | 9.2234e+18 | [19 empty] | October 28th - Budget pending approval. March 13th - Project initiated, design and permit in progress. Aug 15/23 - City permit approved. Oct 3/23 - Construction scheduled to start Nov 1st Oct 11/23 - Construction rescheduled to start Oct 26th June 28th 2024 - CONST-29504 Oct 25/23 - Construction rescheduled to start Nov 9th. Due dates updated Dec 08/23 - Delay with construction schedule. Due dates updated. Feb 15/24 - Transferred $100.00 from construction to cable pull budget to send conduit build PO. Conduit build PO sent. Feb 21/24 - The City has asked us to check back with them in March to see if the contractor working in the area is complete. Due dates updated. Feb 22/24 - Conduit build completed. Invoice received. Mar 12/24 - City permit granted May 1, 2024 - Our team is ready to start construction in May 13th, however we still need the building approval to get the work started. May 7th, 2024 - We still dont have the green light to start construction yet. Project due date is temporarily pushed back to end of June 2024. June 20th, 2024 - Splicing is in progress. We are aiming to get this building onnet in June 2024. | [6 empty] | 3 - Normal | [19 empty] | Internal |  | 2023-03-13 |  |  |  |  | 2024-06-27 | 37786 |  |  | https://buildings.beanfield.com/buildings/view/3131 |  | CONST-29504 | 3 - Normal | 2023-09-22 |  | 3744 | 20825
Construction | CONST-29099 | 830 Lawrence Ave, Toronto - Treviso II | 830 Lawrence Ave, Toronto | Ontario | Condo | Restoration |  | Unresolved | Lorna Kurok | Lorna Kurok | Jessica Markiewicz | 2022-07-08 14:31 |  | 2025-01-31 15:53 |  |  | 2024-10-24 | 0 | 0 |  |  | CONST-29100, CONST-29101, CONST-32896, CONST-32897, CONST-32898, CONST-32899, CONST-32900, CONST-32901, CONST-32902, CONST-32903, CONST-32904, CONST-32905, CONST-32906, CONST-32907, CONST-32908, CONST-32909, CONST-32910, CONST-32911, CONST-32912, CONST-34790, CONST-36997, CONST-37467, CONST-37468, CONST-37655, CONST-38961, CONST-38962 | CONST-29093, CONST-32587, CONST-32800, CONST-35906 | *Updated PM Sept 5, 2024:* *Ana Betancourt* ¦ Condominium Manager ¦ *DUKA Property Management Inc.* As Agents for and on Behalf of T.S.C.C. No. 2705 3091 Dufferin Street, Toronto, ON M6A0C4 Tel: 416.787.7377 ¦ Fax: 416.787.4505 Requested by Jay Fernandes Hi, I’ve gone through the remaining Fibrestream condos we have agreements for in the GTA and have grouped them in a way that I think makes sense for site visits and builds. There will be another list coming of buildings that don’t really fall into groups. Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. There are some current backbone (Sheppard) or NPOP (960 Lawrence) projects that will need to be completed to connect these but this will get everything into the system. Thanks! *PM: Taulant Dedja* *taulant.d@dukamanagement.com* *416.256.9991* | 960Lawrence, Bolton, FSactive, Fiberstreamagreement | [12 empty] | 0¦i3h28n: | [7 empty] | 9.2234e+18 | [19 empty] | January 27th - Budget approved, design and permits in progress. Aug 3/23 - City permit delay, due dates updated. Oct 12/23 - Due dates updated. Oct 20/23 - City permit approved. Jan 26/24 - Revised city drawing has been submitted. Apr 24/24 - Locates completed May 7th, 2024 - Still pending on City permit, we should receive the permit soon.] May 21st, 2024 - City permit is delaying, our design team is following up with the City. As our Bolton team's schedule is full up to Jun 24th, we need to push back this building due date to July 2024. June 6th, 2024 - City permit is granted. Our team scheduled a tentative construction start date Aug 2024. Aug 8, 2024 - Construction is affected by TTC work in the area. Aug 9, 2024 - TTC work is completed, once locates are completed, Rodars can be obtained to proceed with the Const. Aug 21st, 2024 - UG construction is scheduled to be completed mid Sep 2024. Revising project due date to Oct 2024. Sep 10, 2024_Bolton Construction Expected to be completed by Sept 20, 2024 Sep 11, 2024_Bolton Construction note expecting to perform coring in parking spot C18 on Sept 12, 2024. PM Ana has notified. Sep 18, 2024_Bolton Construction needs to extend the completion date to Wednesday Sept 25, 2024 Sep 23, 2024-Riser Fiber pull in process. Oct 7, Riser Fibre Pull all cables have been dressed to panel location. Oct 15, 2024 Cable Asbuilt attached Nov 18, 2024 - Construction Asbuilt is attached. | [6 empty] | 3 - Normal | [19 empty] | Internal |  | 2023-01-26 |  |  | 586 | Integration | 2024-10-24 | 46925 |  |  | https://buildings.beanfield.com/buildings/view/5072 |  | CONST-29099 | 3 - Normal | 2023-10-02 |  | 12617 | 18940
Montreal Construction | MTLCONST-1779 | 700 Saint-Paul St E, Montreal | 700 Saint-Paul St E, Montreal | Quebec | Condo | Not a candidate |  | Unresolved | Marianne Yanni | Oguz Avci [X] | Oguz Avci [X] | 2020-09-30 09:38 |  | 2022-01-31 10:04 |  |  |  | 0 | 3 |  |  | MTLCONST-1780 | MTLCONST-1781, MTLCONST-1783 | (condo; managed by Solution Condo) 136 units (phase-5) Kristopher Lalletti. kristopher@lelletti.ca | mtlcondo | [12 empty] | 0¦i26v7z: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
Montreal Construction | MTLCONST-1771 | 7000 rue Allard, Lasalle | 7000 rue Allard, Lasalle | Quebec | Condo | Not a candidate |  | Unresolved | Marianne Yanni | Oguz Avci [X] | Oguz Avci [X] | 2020-09-30 09:30 |  | 2022-01-31 10:04 |  |  |  | 0 | 4 |  |  | MTLCONST-1774 |  | 7000 rue Allard Lasalle, Quebec H8N 1Y7 Contact is: Stephen Krujelskis 514-583-5052 [stephen.krujelskis@gmail.com¦mailto:stephen.krujelskis@gmail.com] | mtlcondo | [12 empty] | 0¦i26v67: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
Montreal Construction | MTLCONST-1772 | 715 William St W, Montreal | 715 William St W, Montreal | Quebec | Condo | Not a candidate |  | Unresolved | Marianne Yanni | Oguz Avci [X] | Oguz Avci [X] | 2020-09-30 09:32 |  | 2022-01-31 10:05 |  |  |  | 0 | 3 |  |  | MTLCONST-1775 | MTLCONST-1773, MTLCONST-1777 | (rentals; managed by Bentall Green Oak) 125 units (phase1) - [http://www.appartementsboutique.ca¦http://www.appartementsboutique.ca/] Kristopher Lalletti. [kristopher@lelletti.ca¦mailto:kristopher@lelletti.ca] | mtlcondo | [12 empty] | 0¦i26v6f: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
Montreal Construction | MTLCONST-1773 | 705 William St W, Montreal | 705 William St W, Montreal | Quebec | Condo | Not a candidate |  | Unresolved | Marianne Yanni | Oguz Avci [X] | Oguz Avci [X] | 2020-09-30 09:33 |  | 2022-01-31 10:04 |  |  |  | 0 | 3 |  |  | MTLCONST-1776 | MTLCONST-1772, MTLCONST-1777 | (condo; managed by Solution Condo) 86 units (phase-2) Kristopher Lalletti. [kristopher@lelletti.ca¦mailto:kristopher@lelletti.ca] | mtlcondo | [12 empty] | 0¦i26v6n: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
Montreal Construction | MTLCONST-1777 | 738 Saint-Paul St W, Montreal | 738 Saint-Paul St W, Montreal | Quebec | Condo | Not a candidate |  | Unresolved | Marianne Yanni | Oguz Avci [X] | Oguz Avci [X] | 2020-09-30 09:36 |  | 2022-01-31 10:05 |  |  |  | 0 | 3 |  |  | MTLCONST-1778 | MTLCONST-1772, MTLCONST-1773 | (condo; managed by Solution Condo) 128 units (phase-1) 104 units (phase-3) Kristopher Lalletti. [kristopher@lelletti.ca¦mailto:kristopher@lelletti.ca] | mtlcondo | [12 empty] | 0¦i26v7j: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
Montreal Construction | MTLCONST-1781 | 754 Saint-Paul St E, Montreal | 754 Saint-Paul St E, Montreal | Quebec | Condo | Not a candidate |  | Unresolved | Marianne Yanni | Oguz Avci [X] | Oguz Avci [X] | 2020-09-30 09:40 |  | 2022-01-31 10:05 |  |  |  | 0 | 3 |  |  | MTLCONST-1782 | MTLCONST-1779, MTLCONST-1783 | (condo; managed by Solution Condo) 141 units (phase-4) Kristopher Lalletti. kristopher@lelletti.ca | mtlcondo | [12 empty] | 0¦i26v8v: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
Construction | CONST-15991 | 170 Galloway Rd, Scarborough | 170 Galloway Rd, Scarborough | Ontario | Condo | Not a candidate |  | Unresolved | Harvey Tran | Harvey Tran | Harvey Tran | 2020-11-13 12:56 |  | 2022-01-31 14:57 |  |  |  | 0 | 1 |  |  | CONST-15992 |  | +*Contact information:*+ 170 Galloway Ave Jerry Reitsma, Property Manager [annmariehill@rogers.com¦mailto:annmariehill@rogers.com] | [13 empty] | 0¦i2a5vr: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [30 empty] | https://buildings.beanfield.com/buildings/view/12720#!contacts |  |  | 3 - Normal
Construction | CONST-26496 | 160 Baldwin, Toronto | 160 Baldwin, Toronto | Ontario | Condo | Not a candidate |  | Unresolved | Jessica Markiewicz | Jessica Markiewicz | Harvey Tran | 2022-01-25 09:23 |  | 2022-09-27 14:27 |  |  |  | 0 | 1 |  |  | CONST-26497, CONST-26498 | CONST-26499 | Requested from Katie Hodgson for a site walk for 160 Baldwin St & 21 Nassau St May I please request a site walk for 160 Baldwin St & 21 Nassau St *PM Info:* Jermaine Scarlett [kml@360cm.ca¦mailto:kml@360cm.ca] [¦https://buildings.beanfield.com/buildings/view/4530] | [13 empty] | 0¦i35o47: | [7 empty] | 9.2234e+18 | [19 empty] | PM did not provide access. | [6 empty] | 3 - Normal | [30 empty] | https://buildings.beanfield.com/buildings/view/4530 |  |  | 3 - Normal
Construction | CONST-12606 | Corktown District I - 569 King St East | 569 King St East | Ontario | Condo | Not a candidate |  | Unresolved | Harvey Tran | Harvey Tran | Oguz Avci [X] | 2020-06-02 14:38 |  | 2022-02-01 16:46 |  |  |  | 0 | 1 |  |  | CONST-12607, CONST-12984, CONST-12985 | CONST-12584, CONST-12608 | *+Site walk instruction:+* Please go to 510 King St. East in order to get access as they manage all of the buildings. +*Contact information:*+ Your ICON Property Management Team Icon Property Management Ltd. 510 King Street East Toronto ON M5A 0E5 Site Office Phone: 416-363-0438 ¦ Security Phone: 416-363-9392 ¦ Emergency Phone: 416 201 3887 Head Office Phone: 416-236-7979 ¦ Head Office Fax: 416-236-7977 | [13 empty] | 0¦i1z90n: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [30 empty] | https://buildings.beanfield.com/buildings/view/2912 |  |  | 3 - Normal
Montreal Construction | MTLCONST-1783 | 693 William St E, Montreal | 693 William St E, Montreal | Quebec | Condo | Not a candidate |  | Unresolved | Marianne Yanni | Oguz Avci [X] | Oguz Avci [X] | 2020-09-30 09:41 |  | 2024-02-22 10:28 |  |  |  | 0 | 4 |  |  | MTLCONST-1784 | MTLCONST-1779, MTLCONST-1781 | (rentals; managed by Bentall Green Oak) 155 units (phase-2) - http://www.appartementsboutique.ca Kristopher Lalletti. kristopher@lelletti.ca | mtlcondo | [12 empty] | 0¦i26v9b: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
Construction | CONST-25096 | 77 Brickworks Lane, Toronto | 77 Brickworks Lane, Toronto | Ontario | Condo | Not a candidate |  | Unresolved | Harvey Tran | Harvey Tran | Harvey Tran | 2021-10-14 09:05 |  | 2022-01-31 17:00 |  |  |  | 0 | 1 |  |  | CONST-25097, CONST-25098 |  | BB: [https://buildings.beanfield.com/buildings/view/15247#!contacts] Property Manager Monika Gdula [{color:#000000}905-605-7788{color}¦tel:905-605-7788] {color:#777733}[monikag@comfortpm.ca¦mailto:monikag@comfortpm.ca]{color} | [13 empty] | 0¦i2zchz: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [30 empty] | https://buildings.beanfield.com/buildings/view/15247#!contacts |  |  | 3 - Normal
Construction | CONST-23584 | 120 Perth Ave, Toronto | 120 Perth Ave, Toronto | Ontario | Condo | Not a candidate |  | Unresolved | Harvey Tran | Harvey Tran | Harvey Tran | 2021-06-09 14:12 |  | 2021-06-18 10:47 |  |  |  | 0 | 1 |  |  | CONST-23585 |  | Property Manager: Gabriela Ventura [gabrielaventura93@hotmail.com¦mailto:gabrielaventura93@hotmail.com] BB: [https://buildings.beanfield.com/buildings/view/14727] Thank you! | [13 empty] | 0¦i2q1d3: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [30 empty] | https://buildings.beanfield.com/buildings/view/14727 |  |  | 3 - Normal
Construction | CONST-5658 | 7 St Michael Power Pl - Port Royal Place Ⅴ | 7 St Michael Power Pl | Ontario | Condo | Not a candidate |  | Unresolved | Russell Francey | Russell Francey | Russell Francey | 2017-02-28 16:09 |  | 2017-04-05 14:04 |  |  |  | 0 | 0 |  |  |  |  | Dave Casha portroyalplace.pm@delcondo.ca 4166377700 Management | [13 empty] | 0¦i0olzr: | [7 empty] | 9.2234e+18 | [19 empty] | Working on project with Jay, holding for now. | [6 empty] | 3 - Normal | [30 empty] | https://buildings.beanfield.com/buildings/view/4061 |  |  | 3 - Normal
Construction | CONST-11029 | Portland Park Village - 11 Niagara | 11 Niagara | Ontario | Condo | Not a candidate |  | Unresolved | Russell Francey | Russell Francey | Russell Francey | 2019-08-29 16:22 |  | 2019-11-04 10:22 |  |  |  | 0 | 0 |  |  | CONST-11030 |  | Jim Alli ppv1371@portlandpark.ca *Daisy Chained* | [13 empty] | 0¦i1no2v: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [33 empty] | 3 - Normal
Construction | CONST-4970 | 109 Front St - New Times Square | 109 Front St | Ontario | Condo | Not a candidate |  | Unresolved | Russell Francey | Russell Francey | Russell Francey | 2016-10-11 09:07 |  | 2017-03-13 19:59 |  |  |  | 0 | 3 | _thumb_77603.png _thumb_77602.png _thumb_77601.png |  | CONST-4971, CONST-4972, CONST-4973 |  | Daniel Bonea Property Manager Brookfield Condominium Services Ltd. As agent for and on behalf of MTCC 1280 and MTCC 1385 109 Front Street East, Toronto, ON, M5A 4P7 E-mail: managernewtimessq@rogers.com Phone: 416-504-7298 two corporations MTCC 1280 - facing front st 186 suites MTCC 1385- Facing Jarvis 193 suites Main pop in P1 beside parking spot 30 enough room for our equipment , although to get to other riser/pop located on ground floor Jarvis side ( audio Room ) conduits are congested and may not have enough room for power Multiple risers in both towers This building is daisy chained and all zone conduits lead to 6th floor telecom closet for Bell | [13 empty] | 0¦i0l57z: | [7 empty] | 9.2234e+18 | [19 empty] | No individual zhone conduits | [6 empty] | 3 - Normal | [30 empty] | https://buildings.beanfield.com/buildings/view/1609 |  |  | 3 - Normal |  | Corktown
Construction | CONST-5497 | 160 The Esplanade | 160 The Esplanade | Ontario | Condo | Not a candidate |  | Unresolved | Russell Francey | Russell Francey | Russell Francey | 2017-01-25 15:26 |  | 2018-01-29 14:35 |  |  |  | 0 | 2 | _thumb_82702.png _thumb_83980.png _thumb_83981.png _thumb_83982.png _thumb_83983.png _thumb_83984.png _thumb_83985.png _thumb_83986.png _thumb_83987.png _thumb_83988.png _thumb_83989.png _thumb_83990.png |  | CONST-5498, CONST-5499, CONST-5500, CONST-5508 |  | Bulk Deal | [13 empty] | 0¦i0nq87: | [7 empty] | 9.2234e+18 | [19 empty] | Co-op could not get votes to leave Rogers VIP package. | [6 empty] | 3 - Normal | [30 empty] | https://buildings.beanfield.com/buildings/view/5560 |  |  | 3 - Normal |  | St. Lawrence
BC Construction | BCCONST-447 | 500 Royal Ave (Dominion), New Westminster BC | 500 Royal Ave (Dominion), New Westminster BC | British Columbia | Condo | Not a candidate |  | Complete | Yawn Paular | Yawn Paular | Yawn Paular | 2023-10-30 19:18 |  | 2023-12-28 13:09 | 2023-11-16 12:30 |  | 2024-01-05 | 0 | 0 |  |  | BCCONST-448, BCCONST-449, BCCONST-450, BCCONST-451, BCCONST-452, BCCONST-453, BCCONST-454 |  | 118 units BAA approved Property Manager: Harlan Kaur Site Contact: Grace Phone Number: 778-835-7791 Availability: Mon-Fri 9-1pm The building has been added to building browser: [https://buildings.beanfield.com/buildings/view/19384] Please keep me posted on installation of our network here. | Bridgenet, confirmed | [12 empty] | 0¦i4ex8v: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
BC Construction | BCCONST-326 | 7 Rialto Court, New Westminster | 7 Rialto Court, New Westminster | British Columbia | Condo | Not a candidate |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2023-07-10 18:37 |  | 2023-12-28 13:23 |  |  | 2023-12-01 | 0 | 0 |  |  | BCCONST-327, BCCONST-328, BCCONST-329, BCCONST-330, BCCONST-331, BCCONST-332, BCCONST-358 |  | 85 units, tie into with 10 Renaissance Sq Entrance cable located in the MTR - tie in cable from here to 10 Renaissance Sq Bridgenet in the bldg | Pre-Sales | [12 empty] | 0¦i45vjr: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [36 empty] | 4800 | 4200
BC Construction | BCCONST-489 | 13819 100 Avenue (Carriage Lanes), Surrey BC | 13819 100 Avenue (Carriage Lanes), Surrey BC | British Columbia | Condo | Not a candidate |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2023-11-16 17:30 |  | 2024-05-27 13:10 |  |  | 2024-09-27 | 0 | 0 |  |  | BCCONST-691 |  | 145 units NWS2223 Bayside Property Mgmt - 604-432-7774 | [13 empty] | 0¦i4g8qf: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [25 empty] | Backbone
BC Construction | BCCONST-482 | 9868 Whalley Blvd (Balmoral Tower), Surrey BC | 9868 Whalley Blvd (Balmoral Tower), Surrey BC | British Columbia | Condo | Not a candidate |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2023-11-16 17:16 |  | 2024-05-27 13:14 |  |  | 2024-06-28 | 0 | 0 |  |  | BCCONST-689, BCCONST-690 |  | 121 units LMS1622 Crossroads - 778-578-4445 | [13 empty] | 0¦i4g8o7: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [25 empty] | Backbone
BC Construction | BCCONST-794 | 2933, 3001, & 3005 Murray Street, Port Moody BC | 2933, 3001, & 3005 Murray Street, Port Moody BC | British Columbia | Condo | Not a candidate |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2024-09-16 14:55 |  | 2024-12-06 19:27 |  |  | 2025-02-21 | 0 | 0 |  |  | BCCONST-795, BCCONST-796, BCCONST-797, BCCONST-798, BCCONST-799, BCCONST-800, BCCONST-801 |  | Murray Street, Port Moody - 2933, 3001, & 3005 Murray Street (207 total units) This proposal envisions a 12-storey Mass Timber building, providing for 207 rental residential units, the majority of which are designed to be dual-aspect homes with access to significant daylight and views to encourage livability. 10% of the homes will also be committed to below market rates (at Housing Income Limits rents) to ensure affordability, and resident amenities will be provided with access to extensive indoor and outdoor amenity space, including bicycle and kayak storage space, rooftop decks, children’s play area, fitness centre and rooftop urban agriculture plots. | [13 empty] | 0¦i576yf: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
BC Construction | BCCONST-638 | 13458 95 Avenue, (Galilea), Surrey BC | 13458 95 Avenue, (Galilea), Surrey BC | British Columbia | Condo | Not a candidate |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2024-04-04 13:43 |  | 2024-12-09 13:36 |  |  | 2025-12-26 | 0 | 0 |  |  | BCCONST-649 |  | New Bldg DES Surrey 129 Units/6 floors | DES | [12 empty] | 0¦i4q56n: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
BC Construction | BCCONST-481 | 9866 Whalley Blvd (Balmoral Court), Surrey BC | 9866 Whalley Blvd (Balmoral Court), Surrey BC | British Columbia | Condo | Not a candidate |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2023-11-16 17:16 |  | 2024-12-09 17:34 |  |  | 2024-11-29 | 0 | 0 |  |  |  |  | 87 units LMAS1622 Crossroads - 778-578-4445 | [13 empty] | 0¦i4g8nz: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [25 empty] | Backbone
Construction | CONST-12608 | Corktown District I - 52 Sumach St, Toronto | 52 Sumach St, Toronto | Ontario | Condo | Not a candidate |  | Unresolved | Lorna Kurok | Lorna Kurok | Oguz Avci [X] | 2020-06-02 14:39 |  | 2024-12-11 09:34 |  |  |  | 0 | 2 |  |  | CONST-12609, CONST-12986, CONST-12987, CONST-39434 | CONST-12584, CONST-12606 | *+Site walk instruction:+* Please go to 510 King St. East in order to get access as they manage all of the buildings. +*Contact information:*+ Your ICON Property Management Team Icon Property Management Ltd. 510 King Street East Toronto ON M5A 0E5 Site Office Phone: 416-363-0438 ¦ Security Phone: 416-363-9392 ¦ Emergency Phone: 416 201 3887 Head Office Phone: 416-236-7979 ¦ Head Office Fax: 416-236-7977 | [13 empty] | 0¦i1z913: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [23 empty] | 7 | 134 | [5 empty] | https://buildings.beanfield.com/buildings/view/2912 |  |  | 3 - Normal
BC Construction | BCCONST-834 | 5980 Kathleen Ave (Broadview), Burnaby BC | 5980 Kathleen Ave (Broadview), Burnaby BC | British Columbia | Condo | Not a candidate |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2024-12-11 17:24 |  | 2024-12-26 12:29 |  |  | 2025-12-26 | 0 | 0 |  |  |  | BCCONST-353, BCCONST-352 | 35 flrs 295 units Condo Rental Tower | [13 empty] | 0¦i5ebk7: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [23 empty] | 35 | 295
Montreal Construction | MTLCONST-9753 | 6993 Décarie | 6993 Décarie | Quebec | Condo | Not a candidate |  | Unresolved | Marianne Yanni | Marianne Yanni | Marianne Yanni | 2024-02-22 10:29 |  | 2025-02-04 09:39 |  |  |  | 0 | 0 |  |  | MTLCONST-9754, MTLCONST-9755 |  | Requested by [~mamaral] We have a Residential opportunity at 6993 Décarie for a 104 unit bulk internet deal. We spoke with Mike Massie and he requires a estimate for the internal costs of deployment in order to assess the opportunity. The site contact is David 514-516-2723. | [13 empty] | 0¦i4mzjb: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [30 empty] | https://buildings.beanfield.com/buildings/view/19528
BC Construction | BCCONST-360 | 977 Mainland Street, Vancouver (Yaletown Park 3) | 977 Mainland Street, Vancouver (Yaletown Park 3) | British Columbia | Condo | Condo Not Interested |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2023-08-02 13:03 |  | 2023-12-12 12:13 |  |  | 2024-05-31 | 0 | 0 |  |  | BCCONST-369, BCCONST-370, BCCONST-371, BCCONST-372, BCCONST-373, BCCONST-374, BCCONST-375 | BCCONST-1, BCCONST-333 | 30 flrs/277 units Waiting for Michael to setup site check | [13 empty] | 0¦i47xq7: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
BC Construction | BCCONST-644 | 13387 Old Yale Rd, Holland Townline 2, Surrey BC | 13387 Old Yale Rd, Holland Townline 2, Surrey BC | British Columbia | Condo | Condo Not Interested |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2024-04-04 16:57 |  | 2024-05-02 19:37 |  |  | 2024-06-01 | 0 | 0 |  |  |  |  | DES Conduit Entrance [Sergio.Jimenez@townline.com¦mailto:Sergio.Jimenez@townline.com] 308 units 32 Flrs In service date - June 1st | DES | [12 empty] | 0¦i4q6tz: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
Construction | CONST-10366 | Garden District Condos - 79 Shuter | 79 Shuter | Ontario | Condo | Condo Not Interested |  | Unresolved | Russell Francey | Russell Francey | Russell Francey | 2019-05-02 09:28 |  | 2019-08-14 11:02 |  |  |  | 0 | 0 |  |  | CONST-10367, CONST-10368 |  | Chris is working with - Shakeel. shakeel@shercorp.ca Estimated Occupancy : Jan 2020 | [13 empty] | 0¦i1iy0n: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [30 empty] | https://buildings.beanfield.com/buildings/view/6975 |  |  | 3 - Normal
Construction | CONST-7223 | 59 - 71 Mutual St - Ivy Condos | 59 - 71 Mutual St - Ivy Condos | Ontario | Condo | Condo Not Interested |  | Unresolved | Russell Francey | Russell Francey | Samantha Russell | 2017-12-13 08:11 |  | 2019-02-25 14:38 |  |  |  | 0 | 2 |  |  |  |  | Pre Construction, Chris to advise Jory | [13 empty] | 0¦i0ydn3: | [7 empty] | 9.2234e+18 | [19 empty] | No response from developer | [6 empty] | 3 - Normal | [30 empty] | https://buildings.beanfield.com/buildings/view/6806 |  |  | 3 - Normal |  | Church & Wellesley Village
Construction | CONST-7302 | The Summit - 701 King, 705 King, 725 King | 701 King, 705 King, 725 King | Ontario | Condo | Condo Not Interested |  | Unresolved | Russell Francey | Russell Francey | Russell Francey | 2018-01-09 14:09 |  | 2018-01-25 11:18 |  |  |  | 0 | 0 |  |  | CONST-7303 | [15 empty] | 0¦i0z6hj: | [7 empty] | 9.2234e+18 | [19 empty] | Presentation sent for the 3 MTCC, will see if any of them are interested. | [6 empty] | 3 - Normal | [30 empty] | https://buildings.beanfield.com/buildings/view/818 |  |  | 3 - Normal |  | King West
Construction | CONST-5649 | U Condominium - 65 St. Mary St | 65 St. Mary St | Ontario | Condo | Condo Not Interested |  | Unresolved | Russell Francey | Russell Francey | Russell Francey | 2017-02-27 09:30 |  | 2022-09-28 13:54 |  |  |  | 0 | 2 | _thumb_91175.png _thumb_91177.png |  | CONST-5650, CONST-5651, CONST-5652, CONST-6204 | CONST-25883 | Mark Shaffelburg R.C.M. Property Manager T.S.C.C. 2525 - U Condominiums 65 St. Mary St./1080 Bay St. 647 346 3277 mshaffelburg@scpl.ca 65 St Mary connects to 1080 Bay both have telephone rooms and look like they are interconnected POP for 1080 Bay on P1 beside V43 tight for space POP for 65 St Mary P1 beside V7- no access on day of site visit Also has townhouse Zone conduits have space , bothBell and Rogers have fiber to suites | [13 empty] | 0¦i0oio7: | [7 empty] | 9.2234e+18 | [16 empty] | 10000 |  |  | "The Board is not moving forward with this type of project in the foreseeable future." from the PM | [6 empty] | 3 - Normal | [27 empty] | 15000 |  |  | https://buildings.beanfield.com/buildings/view/5713 |  |  | 3 - Normal |  | Bay St Corridor | 3000
Construction | CONST-5255 | 7 Broadway - Broadway Plaza | 7 Broadway | Ontario | Condo | Condo Not Interested |  | Unresolved | Russell Francey | Russell Francey | Russell Francey | 2016-12-12 11:18 |  | 2017-03-13 19:57 |  |  |  | 0 | 0 |  |  | CONST-5256, CONST-5257 | [15 empty] | 0¦i0mrbz: | [7 empty] | 9.2234e+18 | [19 empty] | Did not end up moving forward. | [6 empty] | 3 - Normal | [30 empty] | https://buildings.beanfield.com/buildings/view/5204 |  |  | 3 - Normal |  | Yonge & Eglinton (incl. North Yonge)
Construction | CONST-10512 | Ten93 Queen West Condos - 106 Dovercourt Rd | 106 Dovercourt Rd | Ontario | Condo | Condo Not Interested |  | Unresolved | Russell Francey | Russell Francey | Russell Francey | 2019-05-21 11:14 |  | 2019-08-20 11:55 |  |  |  | 0 | 0 |  |  | CONST-10513, CONST-10514, CONST-10515 |  | Shena Grouse Property Management TSCC 2698 647-346-1471 shena.grouse@scpl.ca | [13 empty] | 0¦i1jm9z: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [30 empty] | https://buildings.beanfield.com/buildings/view/7360 |  |  | 3 - Normal |  | West Queen West
BC Construction | BCCONST-645 | 9656/9651 King George Blvd (Rize Medical), Surrey BC | 9656/9651 King George Blvd (Rize Medical), Surrey BC | British Columbia | Condo | Condo Not Interested |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2024-04-04 17:14 |  | 2024-09-20 19:36 |  |  | 2025-01-31 | 0 | 0 |  |  | BCCONST-658 |  | DES Conduit Entrance Rize Medical 392 units 38 flrs (4 CRUs) Joyce Shen [j.shen@rizealliance.com¦mailto:j.shen@rizealliance.com] Jericho Velarde [j.velarde@hovercraftbuilders.ca¦mailto:j.velarde@hovercraftbuilders.ca] In Service Date Jun 1st BOSA Bldg | DES | [12 empty] | 0¦i4q6wf: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
BC Construction | BCCONST-715 | Fiberstream Buildings Budget Phase 1 | Fiberstream Buildings Budget Phase 1 | British Columbia | Condo | On Hold |  | Unresolved | Michael Tsamkiranis | Yawn Paular | Yawn Paular | 2024-05-31 11:56 |  | 2024-12-06 21:50 |  |  | 2026-01-02 | 0 | 0 |  |  | BCCONST-716, BCCONST-717, BCCONST-718, BCCONST-719, BCCONST-720, BCCONST-721, BCCONST-722 |  | FS Addresses within the ring that can be fed from 1040 Hamilton, 555 W Hastings ¦969 & 989 Richards St¦ ¦1055 Richards St¦ ¦1155 & 1199 Seymour St¦ ¦535 and 565 Smithe St¦ ¦833 Seymour St¦ ¦788 Richards St¦ ¦610 Granville St¦ This ticket is for budget estimate only | [13 empty] | 0¦i4wmwf: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
BC Construction | BCCONST-611 | 288 Ungless Way (Crescendo), Port Moody BC | 288 Ungless Way (Crescendo), Port Moody BC | British Columbia | Condo | On Hold |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2024-02-01 17:06 |  | 2024-12-09 13:36 |  |  | 2025-12-26 | 0 | 0 |  |  | BCCONST-612, BCCONST-613, BCCONST-614, BCCONST-615, BCCONST-616, BCCONST-617 |  | 138 units | QNET, migration | [12 empty] | 0¦i4lpdj: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
BC Construction | BCCONST-563 | 958 Ridgeway Avenue (The Austin), Coquitlam BC | 958 Ridgeway Avenue (The Austin), Coquitlam BC | British Columbia | Condo | On Hold |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2023-12-13 12:54 |  | 2024-12-09 13:58 |  |  | 2025-12-26 | 0 | 0 |  |  | BCCONST-564, BCCONST-565, BCCONST-566, BCCONST-567, BCCONST-568, BCCONST-569, BCCONST-570 |  | 19 floors 125 units 4 townhouses Keys and Fob available in our room | QNET, migration | [12 empty] | 0¦i4i8wf: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [36 empty] | 7100 | 8500
BC Construction | BCCONST-562 | 1185 The High Street (Claremont), Coquitlam BC | 1185 The High Street (Claremont), Coquitlam BC | British Columbia | Condo | On Hold |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2023-12-13 12:43 |  | 2024-12-09 13:58 |  |  | 2025-12-26 | 0 | 0 |  |  | BCCONST-585, BCCONST-586, BCCONST-587, BCCONST-588, BCCONST-589, BCCONST-590, BCCONST-591 |  | 125 units 21 floors Keys and Fobs available in the room | QNET, migration | [12 empty] | 0¦i4i8u7: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [36 empty] | 10600 | 2700
BC Construction | BCCONST-561 | 2980 Atlantic Ave (Levo), Coquitlam BC | 2980 Atlantic Ave (Levo), Coquitlam BC | British Columbia | Condo | On Hold |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2023-12-13 12:41 |  | 2024-12-09 14:15 |  |  | 2025-12-19 | 0 | 0 |  |  | BCCONST-578, BCCONST-579, BCCONST-580, BCCONST-581, BCCONST-582, BCCONST-583, BCCONST-584 |  | 257 units 37 flrs Keys and Fob available in our room | QNET, migration | [12 empty] | 0¦i4i8tz: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [36 empty] | 14000 | 2900
BC Construction | BCCONST-560 | 1155 The High Street (M1), Coquitlam BC | 1155 The High Street (M1), Coquitlam BC | British Columbia | Condo | On Hold |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2023-12-13 12:38 |  | 2024-12-09 14:17 |  |  | 2025-12-26 | 0 | 0 |  |  | BCCONST-571, BCCONST-572, BCCONST-573, BCCONST-574, BCCONST-575, BCCONST-576, BCCONST-577 |  | 194 units 30 flrs Entrance Fob access - Call caretakers for MTR and Riser Access | QNET, migration | [12 empty] | 0¦i4i8tj: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [36 empty] | 8000 | 11000
BC Construction | BCCONST-518 | 39 6th St (Quantum), New Westminster BC | 39 6th St (Quantum), New Westminster BC | British Columbia | Condo | On Hold |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2023-12-05 16:21 |  | 2024-12-09 14:24 |  |  | 2025-11-28 | 0 | 0 |  |  | BCCONST-540, BCCONST-541, BCCONST-542, BCCONST-543, BCCONST-544, BCCONST-545, BCCONST-546 |  | Lubo 604-612-6323 [lubo@raidanthome.ca¦mailto:lubo@raidanthome.ca] 122 units/19 flrs | Bridgenet, migration | [12 empty] | 0¦i4hnbj: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [36 empty] | 8000 | 3000
BC Construction | BCCONST-517 | 892 Carnarvorn St (Azure 2), New Westminster BC | 892 Carnarvorn St (Azure 2), New Westminster BC | British Columbia | Condo | On Hold |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2023-12-05 16:20 |  | 2024-12-09 14:26 |  |  | 2025-12-26 | 0 | 0 |  |  | BCCONST-525, BCCONST-526, BCCONST-527, BCCONST-528, BCCONST-529, BCCONST-530, BCCONST-531 |  | Cyrille Stoelzaed [manager.azure2@quaypacific.com¦mailto:manager.azure2@quaypacific.com] Jorge/Kim Pailamilla 604-442-1435 [azure2mannager@gmail.com¦mailto:azure2mannager@gmail.com] 204 Units/32 flrs | Bridgenet, migration | [12 empty] | 0¦i4hnav: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [36 empty] | 11800 | 2900
BC Construction | BCCONST-516 | 898 Carnarvon St (Azure 1), New Westminster BC | 898 Carnarvon St (Azure 1), New Westminster BC | British Columbia | Condo | On Hold |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2023-12-05 16:18 |  | 2024-12-09 14:31 |  |  | 2025-12-26 | 0 | 0 |  |  | BCCONST-533, BCCONST-534, BCCONST-535, BCCONST-536, BCCONST-537, BCCONST-538, BCCONST-539 |  | Ryan Walmsley 604-431-1818 [rwalmsley@ascentpm.com¦mailto:rwalmsley@ascentpm.com] Victor Aristizabal 778-223-8025 [azure1manager@gmail.com¦mailto:azure1manager@gmail.com] 204 units/32 flrs | Bridgenet, migration | [12 empty] | 0¦i4hn9b: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
BC Construction | BCCONST-148 | 1199 Marinaside St, Vancouver- FS to OnNET | 1199 Marinaside St, Vancouver | British Columbia | Condo | On Hold |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2023-05-29 14:20 |  | 2024-12-09 18:28 |  |  | 2025-12-26 | 0 | 0 |  |  |  |  | Bldg #: 306 Units: 180 Subs: 21 Penetration: 12% Last Promo: 7/24/2020 Days Since: 689 Fliers Check: - Last Check: Comps: In Progress Notes: | confirmed | [12 empty] | 0¦i429x3: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
BC Construction | BCCONST-515 | 888 Carnarvon St (Marinus), New Westminster, BC | 888 Carnarvon St (Marinus), New Westminster, BC | British Columbia | Condo | On Hold |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2023-12-05 16:14 |  | 2024-10-25 18:10 |  |  | 2025-01-31 | 0 | 0 |  |  | BCCONST-519, BCCONST-520, BCCONST-521, BCCONST-522, BCCONST-523, BCCONST-524, BCCONST-532 |  | Mark Yee Fung [Mark.YeeFung@fsresidential.com¦mailto:Mark.YeeFung@fsresidential.com] Fitu 604-725-7802 [managemermarinus@gmail.com¦mailto:managemermarinus@gmail.com] 238/36 flrs | Bridgenet, migration | [12 empty] | 0¦i4hn87: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [36 empty] | 7500 | 2900
BC Construction | BCCONST-457 | 161 W Georgia, Vancouver BC | 161 W Georgia, Vancouver BC | British Columbia | Condo | On Hold |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2023-11-01 20:43 |  | 2024-10-25 18:11 |  |  | 2025-01-31 | 0 | 0 |  |  | BCCONST-458, BCCONST-459, BCCONST-460, BCCONST-461, BCCONST-462, BCCONST-463 | BCCONST-438 | 253 units 23 floors 4 4inch from MER - Risers 3 4inch from 3rd flr - Risers 3rd flr - EC 5flr - EC with space 6th - TEL with space 7th - EC with space 8th TEL with space 9th - EC with space 10th - TEL empty 11th - EC not much space 12th - TEL with space 15th - EC not much space 16th - Empty 9 units! 17th - EC 18th - TEL with little space 19th - EC with no space 20th - Empty space 21st - EC with no space 22nd - TEL with some space 23rd - EC 25th - Empty 26th 27th | [13 empty] | 0¦i4f5yf: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
BC Construction | BCCONST-71 | 1155 Seymour St, Vancouver - FS to OnNet | 1155 Seymour St, Vancouver | British Columbia | Condo | On Hold |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2023-05-02 16:31 |  | 2024-10-15 17:05 |  |  | 2025-12-19 | 0 | 0 |  |  | BCCONST-157, BCCONST-158, BCCONST-159, BCCONST-286, BCCONST-594 | BCCONST-72 | Bldg #: 282 Units: 188 Subs: 28 Penetration: 15% Last Promo: 4/7/2021 Days Since: 432 Fliers Check: 5/2/2022 Last Check: 42 | [13 empty] | 0¦i40fsf: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
Construction | CONST-30859 | 135 East Liberty St, Toronto | 135 East Liberty St, Toronto | Ontario | Condo | On Hold |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Jessica Markiewicz | 2022-10-05 10:02 |  | 2025-01-07 20:12 |  |  |  | 0 | 2 |  |  | CONST-30860, CONST-30861, CONST-31031 |  | Constructed in 2021 Requested by Oliver Davies. Can you please request a site walk from James for 135 E Liberty St, the “Liberty Market Tower Condos”? We have already built into the commercial portion at 171 E Liberty St and 125 E Liberty St, and we would like to determine what is required to bring the residential units online. BB Link: [https://buildings.beanfield.com/buildings/view/16023] *NEW PM Info:* *Klé McKoy* Property Manager Tel. 905-605-7788 Fax. 905-605-7799 E-mail. +[klem@comfortpm.ca¦mailto:klem@comfortpm.ca] PM Info: Natalie Tomasella nataliet@comfortpm.ca | [13 empty] | 0¦i3mte7: | [7 empty] | 9.2234e+18 | [19 empty] | January 30th - building on-hold pending Rogers bulk expiry in 2026. As per Oliver Davies Jan 2023_Project on hold_The solicitor for 135 E Liberty St has confirmed the corporation is locked into a bulk agreement w/ Rogers until 2026. | [6 empty] | 3 - Normal | [23 empty] | 23 | 279 | [5 empty] | https://buildings.beanfield.com/buildings/view/16023 |  |  | 3 - Normal |  | Toronto
Construction | CONST-26574 | 275 Village Green, Toronto - Avani at Metrogate | 275 Village Green, Toronto | Ontario | Condo | On Hold |  | Unresolved | James Mowers | Harvey Tran | Harvey Tran | 2022-01-28 13:20 |  | 2025-02-14 10:52 |  |  |  | 0 | 1 |  |  | CONST-26575, CONST-26576 | CONST-26336, CONST-32622, CONST-32623, CONST-40076, CONST-40077, CONST-26571 | Requested by Katie Hodgson PM Info: Momir Petkovic [Avani.PM@Delcondo.com¦mailto:Avani.PM@Delcondo.com] (647)342-7641 | [13 empty] | 0¦i3608v: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2019 | [6 empty] | 3 - Normal | [23 empty] | 35 | 360 | [8 empty] | 3 - Normal |  | Scarborough
Construction | CONST-26571 | 255 Village Green, Toronto | 255 Village Green, Toronto | Ontario | Condo | On Hold |  | Unresolved | James Mowers | Harvey Tran | Harvey Tran | 2022-01-28 13:00 |  | 2025-02-14 10:52 |  |  |  | 0 | 1 |  |  | CONST-26572, CONST-26573 | CONST-26336, CONST-32609, CONST-32622, CONST-32623, CONST-40076, CONST-40077, CONST-26574 | Requested by Katie Hodgson PM Info: Momir Petkovic [Avani.PM@Delcondo.com¦mailto:Avani.PM@Delcondo.com] (647)342-7641 | [13 empty] | 0¦i3606f: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2016 | [6 empty] | 3 - Normal | [23 empty] | 36 | 363 | [5 empty] | https://buildings.beanfield.com/buildings/view/16175 |  |  | 3 - Normal |  | Scarborough
Construction | CONST-29495 | 85 Bloor St, Toronto - 85 Bloor | 85 Bloor St, Toronto - 85 Bloor | Ontario | Condo | On Hold |  | Unresolved | James Mowers | Lorna Kurok | Jessica Markiewicz | 2022-07-15 10:32 |  | 2025-02-20 11:05 |  |  |  | 0 | 4 |  |  | CONST-29496, CONST-29497, CONST-31400, CONST-31419, CONST-31420, CONST-31421, CONST-31422, CONST-31423, CONST-31424, CONST-31425, CONST-31426, CONST-31427, CONST-31428, CONST-31429, CONST-31430, CONST-31431, CONST-31432, CONST-31433, CONST-31434, CONST-35380, CONST-36733, CONST-37288, CONST-37289 |  | Requested by Jay Fernandes Hi, These are the Fibrestream condos we have agreements for that don’t seem to fit into any groups (although I maybe wrong). Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. ¦Group¦Building Name¦Address¦suites¦ ¦Independent¦Eleven Superior¦11 Superior AVE Etobicoke ON M8V 0A7¦130¦ ¦Independent¦The James Club¦1135 Royal York RD Toronto ON M9A 4A7¦209¦ ¦Independent¦Independence Way¦115 George Appleton WAY North York ON M3M 2E9¦244¦ ¦Independent¦Danforth Village Estates¦1346 Danforth RD Toronto ON M4J1M9¦249¦ ¦Independent¦beBloor¦1369 Bloor ST Toronto ON M6P 4J3¦238¦ ¦Independent¦Ion Condos¦15 James Finlay WAY Toronto ON M3M 0B3¦200¦ ¦Independent¦Paradice at the Oasis¦1720 Eglinton AVE Toronto ON M4A2X9¦190¦ ¦Independent¦Havenon the Bluffs¦20 East Haven DR Toronto ON M1N1M2¦259¦ ¦Independent¦Kilgour Estate II¦21 Burkebrook PL Toronto ON M4G4K8¦228¦ ¦Independent¦Canvas Condos¦2301 Danforth AVE Toronto ON M4C 1L5¦156¦ ¦Independent¦3018 Yonge Condos¦3018 Yonge ST Toronto ON M4N 0A5¦188¦ ¦Independent¦Cranbrooke Village¦35 Saranac BLVD Toronto ON M6A 2G4¦341¦ ¦Independent¦39 Brant St¦39 Brant ST Toronto ON M5V0M8¦236¦ ¦Independent¦The Wave¦4 Elsinore PATH Toronto ON M8V 4G7¦185¦ ¦Independent¦Clock Tower Lofts¦700 King ST Toronto ON M5V 2Y6¦216¦ ¦Independent¦The Boot¦75 Dalhousie ST Toronto ON M5B 2R9¦153¦ ¦Independent¦B.Street Condos¦783 Bathurst ST Toronto ON M6G 1K1¦ ¦ ¦Independent¦85 Bloor St¦85 Bloor ST Toronto ON M4W3G9¦252¦ | Bolton, FSactive, Fiberstreamagreement | [12 empty] | 0¦i3hl6n: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2005 December 13th - Manhole Surveys completed. Hydro permit submitted. February 2nd - Building On-Hold, city is planning a water main replacement at this location. As per Troy Browne and James Mowers. February 9th - Hydro permit conditionally granted. March 9th - Building In-Progress, pending city permit. May 16/23 - CoT is currently doing a watermain project and has informed us that we cannot do any work until Sept 2023. Project due date revised. Aug 9/23 - Hydro permit extension issued Aug 22/23 - City permit granted. Oct 25/23 - Locates completed. Jan 17/24 - Delay with construction schedule. Due dates updated Mar 01/24 - Vault access (site visit) PO sent to AP to be paid Mar 05/24 - Vault access invoice received. Apr 03/24 - Delay with construction schedule. Due dates updated. Apr 04/24 - Vault access requested Apr 09/24 - Transferred $200.00 from Cable Pull to vault access budget. Apr 17/24 - Vault access invoice received May 13th, 2024 - Project is placed on-hold due to TTC roadwork blocking our access to the building. Removing due date for now. Feb 19, 2025 - We are directed to put on On schedule. Lorna scheduled for Due date of August 19, 2025. Feb 20, 2025 - there is discussion to confirm with higher level about the budget, instructed to take off schedule until we have a stronger plan. Need to reconfirm budget amount. | [6 empty] | 3 - Normal | [19 empty] | Internal |  | 2022-10-25 |  | 20 | 252 | Integration |  | 35691 |  |  | https://buildings.beanfield.com/buildings/view/3124 |  | 500487 | 3 - Normal | 2023-06-09 | Toronto | 5858 | 12440
Construction | CONST-35712 | Four Springs Ave Condo Backbone, Mississauga (Part 1) | Four Springs Ave Condo Backbone, Mississauga (Part 1) | Ontario | Condo | New Condo |  | Unresolved | Denise King | Denise King | Denise King | 2023-11-09 12:33 |  | 2023-12-07 11:58 |  |  |  | 0 | 3 | _thumb_779337.png |  | CONST-35713, CONST-35714 | CONST-28793, CONST-35716, CONST-35717, CONST-35718, CONST-35719, CONST-35720 | Requested by Oliver Davies: Could you please create a new ticket, linking the below addresses so we can move forward with an estimate for backbone to connect this pocket of buildings in Mississauga? We only have an agreement with the Amber Condos, the other locations will need to be negotiated once we have a plan in place. | [13 empty] | 0¦i4fp6n: | [7 empty] | 9.2234e+18 | [19 empty] | Dec 5/23 - Budget submitted for approval. Will need to wait for lateral budgets to consider together before moving forward. | [6 empty] | 3 - Normal | [25 empty] | Backbone | [7 empty] | 3 - Normal |  | Mississauga
Construction | CONST-33395 | 1233 Queen St E, Toronto | 1233 Queen St E, Toronto | Ontario | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2023-03-22 14:08 |  | 2023-03-30 10:56 |  |  |  | 0 | 0 |  |  | CONST-33400 | CONST-33394, CONST-33396, CONST-33397, CONST-33398 | Requested by Oliver Davies Can you please have OSP tickets created for Mark at the following 5x addresses? These are all planned purpose-built rental communities being constructed by Core Development Group that have yet to break ground, so no site-walk is required. We would like to get an idea of what will be required to connect these locations to the Beanfield network. 929 Queen E & 252 Parliament are likely to be the most difficult. Core is looking for an ISP partner to provide connectivity to all of the units in their upcoming rental communities. * 929 Queen St E: 68 units / July 2025 occupancy (Leslieville Pumps location - BFMH located nearby via CDSM10723) * 1233 Queen St: 142 units / June 2025 occupancy (off-net -Queen / Leslie - no fibre in the immediate vicinity) * 1111 Danforth: 208 units / June 2025 occupancy (near-net CC#6083 outside of building) * 403 Keele: 261 units / September 2025 occupancy (near-net BF-0781 outside of building, this is just below the active build at 60/61 Heintzman) * 252 Parliament: 80 units / November 2024 occupancy (off-net no fibre between Queen to Dundas on Parliament) scheduled to break ground this year Each location is expected to have a number of retail units at grade. They have provided drawings/plans for all 5x locations, I will upload them to the JIRA tickets once created. Thanks! | CoreDevelopmentGroup | [12 empty] | 0¦i3xmmn: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [30 empty] | https://buildings.beanfield.com/buildings/view/18100 |  |  | 3 - Normal
Construction | CONST-38550 | 425 Front - Site walk for building internal cat5 | 425 Front | Ontario | Condo | New Condo |  | Unresolved | Michael Ng | Jeff Moore | Jeff Moore | 2024-09-19 09:42 |  | 2024-10-07 14:09 |  |  |  | 0 | 0 | _thumb_1023123.png _thumb_1023122.png _thumb_1023121.png _thumb_1023120.png _thumb_1023119.png _thumb_1023118.png _thumb_1023117.png _thumb_1023116.png _thumb_1023115.png _thumb_1023114.png _thumb_1023113.png _thumb_1023112.png _thumb_1023111.png _thumb_1023110.png _thumb_1023109.png _thumb_1023108.png _thumb_1023107.png _thumb_1023106.png _thumb_1023105.png |  |  | CONST-38521, SUPPORT-45027, SUPPORT-45036 | We need to arrange a meeting with Arshdeep at 425 Front. He had requested that we terminate some cat5 cables for him but it appears they have already installed a patch panel. We need to find out if these require keystone jacks and if the building is providing those or if they expect us to. | [13 empty] | 0¦i57f8v: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [33 empty] | 3 - Normal
Construction | CONST-35461 | 256 Royal York Rd & 8 Drummond St, Etobicoke - Royal Towns | 256 Royal York Rd & 8 Drummond St, Etobicoke | Ontario | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2023-10-11 08:44 |  | 2025-01-01 16:43 |  |  |  | 0 | 0 |  |  | CONST-35462, CONST-35463 |  | Requested by Oliver Davies, When you have a moment, can you please create new tickets for OSP & Site Walk for the “Royal Towns” at 256 Royal York Rd & 8 Drummond St? We have fibre running along this stretch of Royal York and we may have an efficient route into the property via BFHW-0494. PM info: Bertiana Fregjaj Condominium Manager 6205A Airport Road, Suite 301 ¦ Mississauga, ON L4V 1E1 Tel: 905.673.7338 ¦ Toll-Free: 1.888.392.DUKA (3852) ¦ Fax: 905.673.8952 [www.dukamanagement.com¦http://www.dukamanagement.com/] ¦ Email: [royaltowns@dukamanagement.com¦mailto:royaltowns@dukamanagement.com] Thank you, | [13 empty] | 0¦i4dfsn: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2017 | [6 empty] | 3 - Normal | [23 empty] | 2 | 104 | [5 empty] | https://buildings.beanfield.com/buildings/view/8510 |  |  | 3 - Normal |  | Etobicoke
Construction | CONST-31056 | 50 Green Belt Dr, North York | 50 Green Belt Dr, North York | Ontario | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Jessica Markiewicz | 2022-10-12 12:59 |  | 2025-01-02 14:36 |  |  |  | 0 | 0 |  |  | CONST-31057, CONST-31058 |  | Requested by Oliver Davies. We are looking for a budget to build fibre to a new development at 50 Green Belt Dr. Could you please create a ticket for this? Katie & Brittany Hamilton’s father, John Hamilton, is the Managing Principal at Pensio Global who has oversight on this development. [https://urbantoronto.ca/database/projects/40-moccasin-trail-50-greenbelt-drive] BB Link: [https://buildings.beanfield.com/buildings/view/17232] No Site Contact. We only require a budget for the OSP work as this project has yet to break ground. It is scheduled for completion in 2025. 1x condo building with approx. 189 units, 1x purpose built rental building with 100 units. I spoke with James about this earlier in the year, and he estimated up to $150k to build fibre from the closest MH. We should get an accurate figure in place for us to work with. FS is active nearby at 120 Dallimore Cir. ([https://buildings.beanfield.com/buildings/view/15464]), and 16 Dallimore ([https://buildings.beanfield.com/buildings/view/3655]) is also up the street. | [13 empty] | 0¦i3n9d3: | [7 empty] | 9.2234e+18 | [19 empty] | October 28th - Site Visit requested. | [6 empty] | 3 - Normal | [24 empty] | 289 | [5 empty] | https://buildings.beanfield.com/buildings/view/17232 |  |  | 3 - Normal |  | North York
Construction | CONST-35906 | 760 Lawrence Ave, Toronto | 760 Lawrence Ave, Toronto | Ontario | Condo | New Condo |  | Unresolved | Harvey Tran | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2023-12-05 12:00 |  | 2024-12-30 18:06 |  |  |  | 0 | 0 |  |  | CONST-35907, CONST-35908 | CONST-29093, CONST-32587, CONST-29099 | Requested by Oliver Davies, Can you please queue up a site walk & OSP plan for the Liberty Walk Townhomes at 760 Lawrence Ave W? There are 245 residential units here and we may be able to include them in our active FBIP for the nearby Treviso buildings: # CONST-29093 # CONST-29099 # CONST-32587 PM Info: April Jackman Property Manager City Sites Property Management Inc. Tel: 416-781-0691 / Fax: 905-232-1270 Email: [tscc1513@rogers.com¦mailto:tscc1513@rogers.com] 760 Lawrence Ave West, Toronto ON M6A 3E7 {color:#201f1e}These townhomes are located approximately. 150m east of Via Bagnato on the north side of Lawrence Ave W.{color} {color:#201f1e}Thank you,{color} | [13 empty] | 0¦i4hlr3: | [7 empty] | 9.2234e+18 | [19 empty] | May 9th, 2024 - Depending on the progress of OSP work in 830 Lawrence Ave build | [6 empty] | 3 - Normal | [23 empty] | 3 | 245 | [5 empty] | https://buildings.beanfield.com/buildings/view/2978 |  |  | 3 - Normal |  | Toronto
Construction | CONST-28791 | 208 Enfield PL Mississauga - Wide Suites | 208 Enfield PL Mississauga | Ontario | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Harvey Tran | 2022-06-14 12:56 |  | 2024-12-30 18:58 |  |  |  | 0 | 0 |  |  | CONST-28810, CONST-28811 |  |  | Fiberstreamagreement | [12 empty] | 0¦i3flsf: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2011 | [6 empty] | 3 - Normal | [23 empty] | 37 | 278 | [5 empty] | https://buildings.beanfield.com/buildings/view/15653 |  |  | 3 - Normal |  | Mississauga
Construction | CONST-35720 | 5020-5040 Four Springs Ave & 110-160 Little Creek Rd, Mississauga | 5020-5040 Four Springs Ave & 110-160 Little Creek Rd, Mississauga | Ontario | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2023-11-09 12:44 |  | 2024-12-31 11:24 |  |  |  | 0 | 0 |  |  | CONST-35731, CONST-35732 | CONST-28793, CONST-35712, CONST-35716, CONST-35717, CONST-35718, CONST-35719 | Requested by Oliver Davies, Could you please create a new ticket, linking the below addresses so we can move forward with an estimate for backbone to connect this pocket of buildings in Mississauga? We only have an agreement with the Amber Condos, the other locations will need to be negotiated once we have a plan in place. ¦Name¦Address¦Agreement¦Units¦Status¦BB Link¦ ¦Amber Condos¦5025 & 5033 Four Springs Ave¦YES¦446¦Off-Net¦[https://buildings.beanfield.com/buildings/view/15798]¦ ¦Crystal¦55 & 75 Eglinton Ave W¦NO¦463¦Off-Net¦[https://buildings.beanfield.com/buildings/view/4007]¦ ¦Pinnacle Uptown: Watergarden¦5044 Hurontario St¦NO¦316¦Off-Net¦[https://buildings.beanfield.com/buildings/view/16767]¦ ¦Perla Towers¦35-65 Watergarden Dr¦NO¦468¦Off-Net¦[https://buildings.beanfield.com/buildings/view/19420]¦ ¦Gemma Condos¦15 Watergarden Dr¦NO¦406¦Off-Net¦[https://buildings.beanfield.com/buildings/view/19421]¦ ¦Little Creek Condos¦5020-5040 Four Springs Ave & 110-160 Little Creek Rd¦NO¦57¦Off-Net¦[https://buildings.beanfield.com/buildings/view/19422]¦ Thank you! | [13 empty] | 0¦i4fp8v: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [23 empty] | 3 | 100 | [5 empty] | https://buildings.beanfield.com/buildings/view/19422 |  |  | 3 - Normal |  | Mississauga
Montreal Construction | MTLCONST-10731 | 2300 - 2320 Tupper street, Montréal | 2300 - 2320 Tupper street, Montréal | Quebec | Condo | New Condo |  | Unresolved | Marianne Yanni | Marianne Yanni | Marianne Yanni | 2025-01-13 16:16 |  | 2025-01-13 16:22 |  |  |  | 0 | 0 |  |  | MTLCONST-10732, MTLCONST-10733 |  | Ce projet est créé afin d'évaluer le possibilité de faire un déploiement résidentiel pour le complexe de condo au 2300 et 2320 rue Tupper, Montréal. *Property Manager:* Caroline : [estwest@bureauplus.net¦mailto:estwest@bureauplus.net] *+Addresses:+* 2300 Tupper Street Montreal, Qc, Canada H3H0B9 And 2320 Tupper Street Montreal, Qc, Canada H3H0B8 | [13 empty] | 0¦i5gbfz: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
Construction | CONST-38027 | 349 Rathburn Rd W_Mississauga_Grand Mirage | 349 Rathburn Rd W_Mississauga_Grand Mirage | Ontario | Condo | New Condo |  | Unresolved | Lorna Kurok | Lorna Kurok | Lorna Kurok | 2024-07-31 08:09 | 2025-02-12 09:43 | 2025-01-02 13:28 |  |  |  | 0 | 0 |  |  | CONST-38028, CONST-38029 | CONST-37795 | h3. Units for 349 Rathburn Rd W only_344 Could you please create a new ticket for an OSP plan & site walk for the Grande Mirage at 349 Rathburn Rd W? This condo has 344 units and was built in 2021. Their next board meeting is *{color:#de350b}+Aug 23rd.+{color}* Could we have the site walk completed before then? I'd like to have some additional information for Grisilda to bring to the board. This likely connects to Mirage at 339 Rathburn Rd W ([https://buildings.beanfield.com/buildings/view/20424]) and Universal at 335 Rathburn Rd W ([https://buildings.beanfield.com/buildings/view/20423]) This location is part of a biggert build, please connect with Ticket: CONST-37795 - Mississauga Square One - Condo Backbone BB Link:[https://buildings.beanfield.com/buildings/view/20171] h2. {color:#403294}*Site Contact:*{color} *Grisilda Hajrullahi OLCM* Condominium Manager¦ Wilson Blanchard Management Grande Mirage Condominiums 349 Rathburn Road West Mississauga, ON, L5B 0G9 Phone: 905.232.3494 Fax: 905.232.3490 | [13 empty] | 0¦i53hkv: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2020 July 31, 2024_Next Board Meeting Aug 23rd, requesting site walk be completed prior to this date. | [6 empty] | 3 - Normal | [23 empty] | 22 | 344 | [5 empty] | https://buildings.beanfield.com/buildings/view/20171 |  |  | 3 - Normal |  | Mississauga
Construction | CONST-26499 | 21 Nassau St Toronto - Kensington Market Lofts | 21 Nassau St Toronto | Ontario | Condo | New Condo |  | Unresolved | Harvey Tran | Harvey Tran | Harvey Tran | 2022-01-25 09:26 |  | 2025-01-02 15:22 |  |  |  | 0 | 1 |  |  | CONST-26500, CONST-26501 | CONST-26496 | Requested from Katie Hodgson for a site walk for 160 Baldwin St & 21 Nassau St May I please request a site walk for 160 Baldwin St & 21 Nassau St *PM Info:* Jermaine Scarlett [kml@360cm.ca¦mailto:kml@360cm.ca] [https://buildings.beanfield.com/buildings/view/4530] | [13 empty] | 0¦i35o53: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2000 | [6 empty] | 3 - Normal | [23 empty] | 7 | 145 | [5 empty] | https://buildings.beanfield.com/buildings/view/5814 |  |  | 3 - Normal |  | Toronto
BC Construction | BCCONST-786 | 60 Williams & 3006-3020 Spring Street, Port Moody BC | 60 Williams & 3006-3020 Spring Street, Port Moody BC | British Columbia | Condo | New Condo |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2024-09-16 14:21 |  | 2025-01-24 17:47 |  |  | 2025-09-26 | 0 | 0 |  |  | BCCONST-787, BCCONST-788, BCCONST-789, BCCONST-790, BCCONST-791, BCCONST-792, BCCONST-793 |  | Moody Centre Station - Integrated Development, Port Moody - 60 Williams & 3006-3020 Spring Street (857 total units) two 39-storey purpose-built rental towers above a 2-storey commercial podium, adjacent to the Moody Center Transit Station. | [13 empty] | 0¦i576pr: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
BC Construction | BCCONST-806 | 5977 Wilson Ave (CentralPark), Burnaby BC | 5977 Wilson Ave (CentralPark), Burnaby BC | British Columbia | Condo | New Condo |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2024-09-19 16:04 |  | 2025-02-04 13:03 |  |  | 2025-04-01 | 0 | 0 |  |  | BCCONST-807, BCCONST-808, BCCONST-809, BCCONST-810 | BCCONST-353, BCCONST-352 | 365 units BOSA project 200m backbone required Q2 of 2025 Occupancy Date {color:#222222}Mike Pover{color} {color:#222222}604-789-0518{color} {color:#222222}mpover@axiombuilders.ca{color} | BudgetPending | [12 empty] | 0¦i57hh3: | [7 empty] | 9.2234e+18 | [19 empty] | Site check scheduled on Jan 13 9:30 AM Look for NPOP space and do the riser audit Jan 30 - No space in MTR for a potential NPOP. Looking to see if we can inquire space in Solhouse early enough since occupancy date is not until 2028 Novus already splicing fibers during our site visit Occupancy date is set for April 2025 Diverse entrance path can be done but needs to let BOSA knows about civil plans early in the development Existing TELUS manholes also found by the poles on Wilson Ave Found other new buildings within the area: 6039 Mckay Ave = Onyx (261 units/34flrs) = Polygon 6075 Wilson Ave = Nuvo (354 units) = Anthem Properties 5985 Barker Ave = early excavation = Concord Pacific | [6 empty] | 3 - Normal | [24 empty] | 365 | [10 empty] | Burnaby
BC Construction | BCCONST-822 | 10460 Parkway, Surrey BC (Brightside Tower 1) | 10460 Parkway, Surrey BC (Brightside Tower 1) | British Columbia | Condo | New Condo |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2024-10-21 11:25 |  | 2025-02-04 13:35 |  |  | 2025-10-31 | 0 | 0 |  |  | BCCONST-825, BCCONST-826 | BCCONST-845, BCCONST-646, BCCONST-823 | 418 Units 40 Flrs 1350m backbone required DES Conduit Entrance In Service Date: Dec 1st 2024 ¦Jill Wanklyn [jwanklyn@bosaproperties.com¦mailto:jwanklyn@bosaproperties.com] Mehrad Azimi [mazimi@axiombuilders.ca¦mailto:mazimi@axiombuilders.ca]¦ | BudgetPending, DES | [12 empty] | 0¦i59slj: | [7 empty] | 9.2234e+18 | [19 empty] | Jan 9 - Waiting for Mike to review budget to send for approval Jan 29 - Created backbone project for PM purposes | [6 empty] | 3 - Normal | [23 empty] | 40 | 418 | [10 empty] | Surrey
BC Construction | BCCONST-509 | 13768 100 Avenue (Park George I), Surrey BC | 13768 100 Avenue (Park George I), Surrey BC | British Columbia | Condo | New Condo |  | Unresolved | Michael Tsamkiranis | Yawn Paular | Yawn Paular | 2023-12-04 13:52 |  | 2025-02-04 13:36 |  |  | 2025-11-28 | 0 | 0 |  |  | BCCONST-511, BCCONST-665, BCCONST-666, BCCONST-827 | BCCONST-510 | Under Construction 339 units 39Flrs Entrance could be shared with Park George II Concord Pacific Colyvan Pacific Real Estate Management Services Ltd. info@colyvanpacific.com | BudgetPending | [12 empty] | 0¦i4hir3: | [7 empty] | 9.2234e+18 | [19 empty] | Jan 9 - Mike to review quote including ILCs | [6 empty] | 3 - Normal | [23 empty] | 39 | 339 | [10 empty] | Surrey
BC Construction | BCCONST-643 | 10749/10745 King George Blvd, 10750 135A St (The Grand), Surrey BC | 10749/10745 King George Blvd, 10750 135A St (The Grand), Surrey BC | British Columbia | Condo | New Condo |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2024-04-04 16:45 |  | 2025-02-04 13:37 |  |  | 2026-09-25 | 0 | 0 |  |  | BCCONST-656 | BCCONST-642 | July 1st in service date Manit Saiyadh - KCM [msaiyadh@kanin.ca¦mailto:msaiyadh@kanin.ca] DES Conduit entrance 341 units 46 flrs | DES | [12 empty] | 0¦i4q6t3: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [23 empty] | 46 | 341 | [10 empty] | Surrey
BC Construction | BCCONST-833 | 13866 100 Avenue (Skyliving), Surrey BC | 13866 100 Avenue (Skyliving), Surrey BC | British Columbia | Condo | New Condo |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2024-12-10 14:00 |  | 2025-02-04 13:38 |  |  | 2026-12-26 | 0 | 0 |  |  | BCCONST-837 |  | Mar 2027 Construction Completion Date 375 units 32 floors Allure Ventures | BudgetPending | [12 empty] | 0¦i5e8h3: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [23 empty] | 32 | 375 | [10 empty] | Surrey
BC Construction | BCCONST-805 | 6031 Wilson Avenue (Solhouse), Burnaby BC | 6031 Wilson Avenue (Solhouse), Burnaby BC | British Columbia | Condo | New Condo |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2024-09-19 16:04 |  | 2025-02-04 13:38 |  |  | 2028-01-03 | 0 | 0 |  |  | BCCONST-811, BCCONST-812, BCCONST-813, BCCONST-814 | BCCONST-353, BCCONST-352 | BOSA building 411 Units 52 flrs Occupancy Date: Q4 2028 200m required of backbone | BudgetPending | [12 empty] | 0¦i57hgv: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [23 empty] | 52 | 411 | [10 empty] | Burnaby
BC Construction | BCCONST-646 | 10333 133 St, Melrose, Surrey BC | 10333 133 St, Melrose, Surrey BC | British Columbia | Condo | New Condo |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2024-04-04 17:39 |  | 2025-02-04 14:25 |  |  | 2025-11-28 | 0 | 0 |  |  | BCCONST-653 | BCCONST-845, BCCONST-822 | Moe Dhillon [moe@brasfield.ca¦mailto:moe@brasfield.ca] Jacqueline Huynh [jhuynh@mlemporio.ca¦mailto:jhuynh@mlemporio.ca] 223 units 26 flrs DES Entrance conduit In Service date need to be adjusted. Building was slated for Mar 1st 2025 | BudgetPending, DES | [12 empty] | 0¦i4q6yv: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [23 empty] | 26 | 223 | [10 empty] | Surrey
BC Construction | BCCONST-823 | 13301 104 Ave, Surrey BC (Bristol Tower 1) | 13301 104 Ave, Surrey BC (Bristol Tower 1) | British Columbia | Condo | New Condo |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2024-10-21 11:26 |  | 2025-02-04 19:49 |  |  | 2025-10-31 | 0 | 0 |  |  | BCCONST-824 | BCCONST-845, BCCONST-822 | 440 units Up to 5 towers 2030 Q1 Occupancy Date 1750m required of backbone - to be done with Brightside Towers | BudgetPending | [12 empty] | 0¦i59slz: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 440 | [10 empty] | Surrey
Construction | CONST-38919 | 10 Old York Mills Road, North York (BULK) | 10 Old York Mills Road, North York (BULK) | Ontario | Condo | New Condo |  | Unresolved | Lorna Kurok | Lorna Kurok | Lorna Kurok | 2024-10-21 10:56 |  | 2025-02-11 08:57 |  |  |  | 0 | 0 |  |  | CONST-38920, CONST-38921, CONST-38922 |  | Requested by james Fox {color:#de350b}*Priority for site visit*{color} Bulk Opportunity {color:#172b4d}Units 113{color} {color:#172b4d}Floors 9{color} {color:#172b4d}Constructed in 2001{color} {color:#172b4d}Location is near-net{color} {color:#172b4d}Expected minimal OSP work require to enter building{color} *{color:#000000}site contact as of Oct 21, 2024:{color}* *{color:#000000}Elise Deschamps, OLCM{color}* {color:#000000}Senior Condominium Manager/ MTCC 1401{color} {color:#000000} {color} {color:#000000}10 Old York Mills Road, Toronto, ON M2P 2G9{color} {color:#000000}Telephone: 416-560-5988{color} {color:#000000}E-mail: [pm@mtcc1401.ca¦mailto:pm@mtcc1401.ca]{color} {color:#000000}Could you please create a new ticket for an OSP plan & site walk for 10 Old York MIlls Road Condos at 10 Old York Mills Road, North York? This condo has 134 residential units and was constructed in 2001 *This is a bulk opportunity. Please make this a priority.* This location is near-net and ideally we will have minimal OSP work required to enter the building. BB Link:[https://buildings.beanfield.com/buildings/view/12004]{color} *{color:#000000} site contact:{color}* *{color:#000000}Elise Deschamps, OLCM{color}* {color:#000000}Senior Condominium Manager/ MTCC 1401{color} {color:#000000} {color} {color:#000000}10 Old York Mills Road, Toronto, ON M2P 2G9{color} {color:#000000}Telephone: 416-560-5988{color} {color:#000000}E-mail: [pm@mtcc1401.ca¦mailto:pm@mtcc1401.ca]{color} | BulkDeal, BulkOpportunity | [12 empty] | 0¦i59sfb: | [7 empty] | 9.2234e+18 | [19 empty] | Oct 21, 2024 Email Request for OSP plan and Site walk_James Fox | [6 empty] | 3 - Normal | [23 empty] | 9 | 113 | [5 empty] | https://buildings.beanfield.com/buildings/view/12004 |  |  | 3 - Normal |  | North York
BC Construction | BCCONST-648 | 9677 King George Blvd (Belvedere), Surrey BC | 9677 King George Blvd (Belvedere), Surrey BC | British Columbia | Condo | New Condo |  | Unresolved | John Thomson | Yawn Paular | Yawn Paular | 2024-04-04 17:58 |  | 2025-02-19 14:52 |  |  | 2025-04-25 | 0 | 0 |  |  | BCCONST-657, BCCONST-844 |  | 275 units Manish Sharma [manish@squarenine.ca¦mailto:manish@squarenine.ca] In Service Date: June 1st 2024 DES Conduite Entrance | BudgetPending, DES | [12 empty] | 0¦i4q713: | [7 empty] | 9.2234e+18 | [19 empty] | Jan 23 - Provided budget for Mike/John to review | [6 empty] | 3 - Normal | [22 empty] | 500 |  | 275 | [10 empty] | Surrey
BC Construction | BCCONST-647 | 10428 Whalley Blvd, (Ascent), Surrey BC | 10428 Whalley Blvd, (Ascent), Surrey BC | British Columbia | Condo | New Condo |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2024-04-04 17:51 |  | 2025-02-19 14:52 |  |  | 2025-09-26 | 0 | 0 |  |  | BCCONST-652 | BCCONST-826, BCCONST-845 | 234 units 31 flrs DES Conduit Entrance ¦Satish Sharma [satish@mlhcan.ca¦mailto:satish@mlhcan.ca] Andrei Chutskoff [achutskoff@itc-group.com¦mailto:achutskoff@itc-group.com]¦ In Service Date Aug 1st 2024 | BudgetPending, DES | [12 empty] | 0¦i4q6zr: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [23 empty] | 31 | 234 | [10 empty] | Surrey
BC Construction | BCCONST-642 | 10760 136A, 10767 Whalley Blvd, (Flamingo), Surrey BC | 10760 136A, 10767 Whalley Blvd, (Flamingo), Surrey BC | British Columbia | Condo | New Condo |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2024-04-04 14:49 |  | 2025-02-19 14:53 |  |  | 2025-12-26 | 0 | 0 |  |  | BCCONST-655 | BCCONST-643 | DES conduit in the building, in service date July 1st 2024 ¦Zikreia Nessari [ZNessari@itc-group.com¦mailto:ZNessari@itc-group.com] Franco Gimenez [franco@tiensher.com¦mailto:franco@tiensher.com]¦ 374 units 34 floors | DES | [12 empty] | 0¦i4q5nb: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [23 empty] | 34 | 374 | [10 empty] | Surrey
BC Construction | BCCONST-510 | 13778 100 Avenue (Park George II), Surrey BC | 13778 100 Avenue (Park George II), Surrey BC | British Columbia | Condo | New Condo |  | Unresolved | John Thomson | Yawn Paular | Yawn Paular | 2023-12-04 13:52 |  | 2025-02-19 15:07 |  |  | 2025-04-25 | 0 | 0 |  |  | BCCONST-667, BCCONST-668 | BCCONST-509 | Under Construction 337 units 38Flrs Entrance could be shared with Park George I Concord Pacific Colyvan Pacific Real Estate Management Services Ltd. info@colyvanpacific.com | BudgetPending | [12 empty] | 0¦i4hirj: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [23 empty] | 38 | 337 | [10 empty] | Surrey
BC Construction | BCCONST-480 | 13693 George Jct (The Line), Surrey BC | 13693 George Jct (The Line), Surrey BC | British Columbia | Condo | New Condo |  | Unresolved | Michael Tsamkiranis | Yawn Paular | Yawn Paular | 2023-11-16 17:10 | 2025-02-12 15:52 | 2025-02-19 16:05 |  |  | 2025-12-26 | 0 | 0 |  |  | BCCONST-687, BCCONST-688, BCCONST-830 |  | 439 Units 34 flrs Rental Properties Warrington Residential [rentals@warringtonresidential.com¦mailto:rentals@warringtonresidential.com] 604-602-1187 | BudgetPending | [12 empty] | 0¦i4g8nj: | [7 empty] | 9.2234e+18 | [19 empty] | Jan 9 - Waiting for BAA, Budget sent for approval Feb19 - Verbal interest received in Dec. To follow up | [6 empty] | 3 - Normal | [23 empty] | 34 | 439 | Backbone | [9 empty] | Surrey | 14000 | 32800
Construction | CONST-35794 | 775 Vaughan Rd, York | 775 Vaughan Rd, York | Ontario | Condo | Agreement |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2023-11-22 10:45 |  | 2024-12-30 17:45 |  |  |  | 0 | 0 |  |  | CONST-35796, CONST-35797, CONST-37305 |  | Requested by Oliver Davies, Can you please create new tickets for an OSP plan for the 2x locations below? There is an (early) opportunity with Shannondale Developments for a 469 unit rental building that is being constructed at 775 Vaughan Rd. Occupancy is not expected until 2026-2027, but they are discussing telcos now. Also nearby is 1603 Eglinton Ave W, we have not received permission to complete a site walk, but I would like to determine what is involved outside of the building to connect them to our network. Thank you, | [13 empty] | 0¦i4gl6v: | [7 empty] | 9.2234e+18 | [19 empty] | May 9, 2024 - Expected occupancy is actually 2028. (Not until 2028. Breaking ground Q4 this year2024.) | [6 empty] | 3 - Normal | [23 empty] | 36 | 500 | [5 empty] | https://buildings.beanfield.com/buildings/view/19434 |  |  | 3 - Normal |  | York
Montreal Construction | MTLCONST-10011 | Westwalk Anjou – 7400-7450 boul. Des Galleries d’Anjou – 3 phases, 15 stories + parking, +/- 500units | 7450 boul. Des Galleries d’Anjou | Quebec | Condo | Agreement |  | Unresolved | Marianne Yanni | Marianne Yanni | Marianne Yanni | 2024-04-29 14:15 |  | 2025-01-20 14:49 |  |  |  | 0 | 0 |  |  | MTLCONST-10014, MTLCONST-10015, MTLCONST-10742 | MTLCONST-10742, MTLCONST-10012, MTLCONST-10013 | There is an opportunity to provide bulk-internet services to 3x new greenfield residential projects being constructed by Devmont. As these locations are still in the planning phase, no site walk can be scheduled yet. The electrical drawings from the developer will be requested. * *_Westwalk Anjou – 7400-7450 boul. Des Galleries d’Anjou – 3 phases, 15 stories + parking, +/- 500units_* [https://buildings.beanfield.com/buildings/view/20186] * *_Westbury 9 - 4955/5055 Courtrai – 2 phases, 12 stories + parking, +/- 330 units - MTLCONST-10012_* [https://buildings.beanfield.com/buildings/view/20187] * *_Westwalk Pointe-Claire – 360 Labrosse/988 St-Jean – 2 phases, 12 stories + parking, +/- 374units - MTLCONST-10013_* [https://buildings.beanfield.com/buildings/view/20188] | [13 empty] | 0¦i4swpz: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
Construction | CONST-35871 | 2916 Highway 7, Concord - Nord West | 2916 Highway 7, Concord | Ontario | Condo | Agreement |  | Unresolved | Lorna Kurok | Lorna Kurok | Olawale Olaniyan [X] | 2023-11-30 10:20 |  | 2024-12-24 14:30 |  |  |  | 0 | 0 |  |  | CONST-35872, CONST-35873, CONST-37876, CONST-37877 | CONST-37926, CONST-32717, CONST-32677, CONST-32680 | Requested by Oliver Davies: Constructed in 2020 PM Info: Erika Belicky [exponord.pm@delcondo.com¦mailto:exponord.pm@delcondo.com] | [13 empty] | 0¦i4h8br: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [23 empty] | 48 | 430 | [5 empty] | https://buildings.beanfield.com/buildings/view/16628 |  |  | 3 - Normal |  | Concord
Construction | CONST-32717 | 2908 Highway 7, Concord - Nord East | 2908 Highway 7, Concord | Ontario | Condo | Agreement |  | Unresolved | Lorna Kurok | Lorna Kurok | Denise King | 2023-01-12 15:06 |  | 2024-12-24 15:17 |  |  |  | 0 | 2 |  |  | CONST-32718, CONST-32719, CONST-37874, CONST-37875 | CONST-37926, CONST-35871, CONST-32677, CONST-32680 | Requested by Oliver Davies: Constructed 2020 PM Info: Erika Belicky [exponord.pm@delcondo.com¦mailto:exponord.pm@delcondo.com] | [13 empty] | 0¦i3t19z: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [23 empty] | 430 | 38 | [5 empty] | https://buildings.beanfield.com/buildings/view/16628 |  |  | 3 - Normal |  | Concord
BC Construction | BCCONST-484 | 13696 100 Avenue (Park Avenue West), Surrey BC | 13696 100 Avenue (Park Avenue West), Surrey BC | British Columbia | Condo | Agreement |  | Unresolved | Josh Wignall | Yawn Paular | Yawn Paular | 2023-11-16 17:20 |  | 2025-02-04 12:55 |  |  | 2025-06-27 | 0 | 0 |  |  | BCCONST-502, BCCONST-503, BCCONST-504, BCCONST-505, BCCONST-664, BCCONST-820 | BCCONST-483 | 462 units 45 flrs EPS4403 Ranch Mgmt - 604-684-4508 Gus Ramirez <GRamirez@ranchogroup.com> Habil Otieno Building Supervisor - Park Avenue West 13696 100 Avenue Surrey BC V3T 0L5 Phone: 604-240-4063 | Budget_Allocated | [12 empty] | 0¦i4g8on: | [7 empty] | 9.2234e+18 | [19 empty] | Jan 9 - CA form created, Mike to add ILC and send it to Steven Jan 23 - Budget approved, Josh to reach out to Gus for BAA updates | [6 empty] | 3 - Normal | [23 empty] | 45 | 462 | [10 empty] | Surrey | 36300 | 46750
BC Construction | BCCONST-483 | 13750 100 Avenue (Park Avenue East), Surrey BC | 13750 100 Avenue (Park Avenue East), Surrey BC | British Columbia | Condo | Agreement |  | Unresolved | Josh Wignall | Yawn Paular | Yawn Paular | 2023-11-16 17:18 |  | 2025-02-04 12:59 |  |  | 2025-06-27 | 0 | 0 |  |  | BCCONST-506, BCCONST-507, BCCONST-508, BCCONST-663 | BCCONST-484 | 424 units 46 flrs EPS3859 Rancho Mgmt - 604-684-4508 Gus Ramirez <GRamirez@ranchogroup.com> | Budget_Allocated | [12 empty] | 0¦i4g8of: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [23 empty] | 46 | 424 | [10 empty] | Surrey
BC Construction | BCCONST-742 | 13740 Fraser Hwy, Tether (Phase E PCI), Surrey BC | 13740 Fraser Hwy, Tether (Phase E PCI), Surrey BC | British Columbia | Condo | Agreement |  | Unresolved | Josh Wignall | Yawn Paular | Yawn Paular | 2024-06-21 19:33 | 2025-02-12 15:52 | 2025-02-13 12:06 |  |  | 2026-01-02 | 0 | 0 |  |  | BCCONST-743, BCCONST-744, BCCONST-745, BCCONST-746, BCCONST-747, BCCONST-748, BCCONST-749, BCCONST-750 |  | 402 rental units 2 electrical parkade drawings where the main comms room located, P1 electrical parkade drawings where the DES and main electrical room is located, detailed drawing with electrical room layout, and detail drawing with comms room layout + typical comms closets locations. L1 = 10 residential units, amenity lounge, co-working space, workshop space, and building manager’s office. There is also a separated amenity building with the gym (I’m not sure if it’s relevant){+}{{+}}{+}{{+}} L2 = 10 residential units.{+}{{+}}{+}{{+}} L3, L4 = 12 residential units per floor.{+}{{+}}{+}{{+}} L5 – L39 = 10 residential units per floor{+}{{+}}{+}{{+}} L40 = 8 residential units.{+}{{+}}{+}{{+}} L41 = amenity floor with 2 dining lounges and one open amenity lounge Q4 of 2026 Occupancy Date Building Name: Tether | Budget_Allocated, DES | [12 empty] | 0¦i4ygan: | [7 empty] | 9.2234e+18 | [19 empty] | Jan 22 - With Steven B for CA creation and submission. Agreements not signed yet | [6 empty] | 3 - Normal | [24 empty] | 402 | [10 empty] | Surrey | 16500 | 33400
BC Construction | BCCONST-704 | Century City Phase 2 SouthWest Bldg (TBD Address), Surrey BC | Century City Phase 2 SouthWest Bldg (TBD Address), Surrey BC | British Columbia | Condo | Agreement |  | Unresolved | Josh Wignall | Yawn Paular | Yawn Paular | 2024-05-28 16:44 |  | 2025-02-19 16:06 |  |  | 2025-08-01 | 0 | 0 |  |  | BCCONST-705, BCCONST-706, BCCONST-707 |  | Phase 2 Building next to Century City Century City Ph 2 bldgs - Sep 2025 Occupancy Date - no CRUs AWM - Ph2 condo 408 units | Budget_Allocated | [12 empty] | 0¦i4wczz: | [7 empty] | 9.2234e+18 | [19 empty] | Jan 10 - With Luke and Steven for CA creation and approval. Will be the first priority to possibly meet occupancy date Feb 19 - Josh has meeting with Jeremy Feb 21st | [6 empty] | 3 - Normal | [24 empty] | 408 | [10 empty] | Surrey | 17700 | 17600
Construction | CONST-25883 | 1080 Bay Street, Toronto | 1080 Bay Street, Toronto | Ontario | Condo | Clean Up |  | Unresolved | Jessica Markiewicz | Jessica Markiewicz | Harvey Tran | 2021-11-29 14:29 |  | 2022-10-20 08:08 |  |  | 2022-11-04 | 0 | 1 |  |  | CONST-25884, CONST-25885, CONST-25947, CONST-26006, CONST-26007, CONST-26008, CONST-26009, CONST-26010, CONST-26011, CONST-26012, CONST-26013, CONST-26014, CONST-26015, CONST-26016, CONST-26017, CONST-26018, CONST-26078, CONST-26323, CONST-27298, CONST-27705 | CONST-5649 |  | Fiberstreamagreement | [12 empty] | 0¦i32cq7: | [7 empty] | 9.2234e+18 | [19 empty] | October 19th - Building on-net. | [6 empty] | 3 - Normal | [21 empty] | 2021-12-02 | [5 empty] | 20321 |  |  | https://buildings.beanfield.com/buildings/view/5713 |  | 500332 | 3 - Normal | 2022-04-15 |  | 11960 | 22610
Montreal Construction | MTLCONST-344 | Zibi Block 10 - 10 Rue Jos-Montferrand, Gatineau, QC | 10 Rue Jos - Montferrand, Gatineau, QC | Quebec | Condo | Clean Up |  | Unresolved | Danny Da Silva | Marianne Yanni | Oguz Avci [X] | 2020-05-25 10:01 |  | 2022-03-07 11:04 |  |  |  | 0 | 3 | _thumb_434431.png _thumb_434423.png _thumb_434425.png _thumb_434428.png _thumb_434429.png _thumb_434421.png _thumb_434424.png _thumb_434426.png _thumb_434430.png _thumb_434422.png _thumb_434432.png _thumb_434427.png _thumb_421419.png |  | MTLCONST-345, MTLCONST-6515, MTLCONST-6648, MTLCONST-6649, MTLCONST-6650, MTLCONST-6651, MTLCONST-6652, MTLCONST-6653, MTLCONST-6654 | CONST-11351, CONST-17442 | Address is: 10 Rue Jos-Montferrand Gatineau, QC KRISTEN JORGENSEN Project Manager Zibi Vertical Build Team 6 Booth St (Albert Island), Ottawa, ON K1R 6K8 C 613.864.9448 E {color:#0000ff}[kristen.jorgensen@zibi.ca¦mailto:kristen.jorgensen@zibi.ca]{color} | mtlcondo | [12 empty] | 0¦i1yrzb: | [7 empty] | 9.2234e+18 | [19 empty] | 2021.11.23 Site visit completed. This agreement will be a sub-agreement to a much larger agreement for the whole project. | [6 empty] | 3 - Normal
Construction | CONST-7399 | 629 King - Thompson Residences | 629 King | Ontario | Condo | Clean Up |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Russell Francey | 2018-01-29 10:42 |  | 2024-07-17 08:10 |  |  | 2024-02-28 | 0 | 0 |  |  | CONST-7400, CONST-7401, CONST-7402, CONST-27702, CONST-31477, CONST-31478, CONST-31479, CONST-31480, CONST-31481, CONST-31482, CONST-31483, CONST-31484, CONST-31485, CONST-31486, CONST-31487, CONST-31488, CONST-31489, CONST-31490, CONST-31491, CONST-35241, CONST-36270, CONST-36507, CONST-36508 |  | Sureka Scarlett Property Manager Elite Property Management Inc. 629 King St West Toronto, ON M5V 0G9 & 38 Stewart St Toronto, ON M5V 0H1 sscarlett@elitepminc.com Tel: 416-366-3251 | FSactive, Fiberstreamagreement | [12 empty] | 0¦i0zuzr: | [7 empty] | 9.2234e+18 | [19 empty] | November 30th - Route Drawing completed. February 10th - Manhole Survey completed. February 27th - Hydro Permit in progress. April 18/23 - Hydro permit conditionally granted. July 12/23 - Hydro permit granted. Aug 28/23 - Cable pull only. Construction not required. Jan 18/24 - Conduit build scheduled for Jan 24th. Cable pull scheduled for Feb 5th Jan 22/24 - Conduit build PO sent Jan 25/24 - Conduit build completed. Invoice received. Jan 31/24 - Cable pull scheduled for Feb 5th Feb 05/24 - Cable pull completed. Pending SOW Feb 13/24 - Splicing scheduled for Feb 22nd - 23rd Feb 21/24 - Splicing completed Feb 28/24 - Building On-Net | [6 empty] | 3 - Normal | [19 empty] | Internal |  | 2022-10-26 |  |  |  | Integration | 2024-02-28 | 41475 |  |  | https://buildings.beanfield.com/buildings/view/4163 |  | 500490 | 3 - Normal | 2024-02-23 | King West | 624 | 0
Construction | CONST-9777 | King West Townhomes - 1 - 47 Sudbury | 1 - 47 Sudbury | Ontario | Condo | Clean Up |  | Unresolved | Harvey Tran | Olawale Olaniyan [X] | Russell Francey | 2019-02-06 12:28 |  | 2024-07-18 14:50 |  |  | 2024-07-18 | 0 | 0 | _thumb_403502.png _thumb_403890.png |  | CONST-9778, CONST-20236, CONST-24305, CONST-24306, CONST-24307, CONST-24308, CONST-24309, CONST-24310, CONST-24311, CONST-24312, CONST-24313, CONST-24314, CONST-24315, CONST-25072, CONST-25406, CONST-25984, CONST-30320, CONST-30398, CONST-36224, CONST-36225, CONST-36488 | NET-37999, CONST-30055, CONST-3134, CONST-27867 | Lily Barbosa ¦ Senior Condominium Manager BA, RCM Goldview Property Management Ltd. 51 Toro Road, Suite 200 ¦Toronto, Ontario ¦ M3J 2A4 t: 416-630-1234 ext 249 ¦ f: 416-630-3132 e: lily@goldview.ca ¦ w: goldview.ca | Fiberstreamagreement | [12 empty] | 0¦i1fmf3: | [7 empty] | 9.2234e+18 | [19 empty] | September 13th - Only ISP required. Will be fed from 8 Dovercourt and 12 Sudbury. Oct 12/23 - Due dates updated. Jan 23/24 - Due dates updated Jan 26/24 - Cable pull completed. Jan 31/23 - Splicing in progress Feb 08/24 - Transferred $1,920.00 (splicing quote) from construction budget to splicing budget. Feb 12/24 - Splicing PO sent to Litewave. Splicing in progress Feb 14/24 - SOW redesign required. Delay to splicing. Feb 16/24 - Migration required to bring building On-Net. May 9th, 2024 - Still pending SOW due to migration. Requested an update from GIS. Project due date is possibly pushed back if migration delays. Jun 28th, 2024 - Project is pushed back to July as the OLT insertion needs to be completed in prior (NET-37999) Jul 11th, 2203 - OLT insertion completed. Our team will schedule to get back to complete the cross connect. Due date is updated to July 19th Jul 18th, 2024 - Building is onnet. | [6 empty] | 3 - Normal | [21 empty] | 2022-09-13 |  |  |  |  | 2024-07-18 | 10893 |  |  | https://buildings.beanfield.com/buildings/view/3257 |  | 500323 | 3 - Normal | 2023-11-17 | West King West | 1200
Construction | CONST-29261 | 35 Finch Ave, North York - Chicago Residences | 35 Finch Ave, North York | Ontario | Condo | Clean Up |  | Unresolved | Lorna Kurok | Lorna Kurok | Jessica Markiewicz | 2022-07-11 16:20 |  | 2024-11-21 09:12 |  |  | 2024-11-20 | 0 | 1 |  |  | CONST-29262, CONST-29263, CONST-34867, CONST-34881, CONST-34882, CONST-34883, CONST-34884, CONST-34885, CONST-34886, CONST-34887, CONST-34888, CONST-34889, CONST-34890, CONST-34891, CONST-34892, CONST-34893, CONST-34894, CONST-34895, CONST-38123, CONST-38277, CONST-38278, CONST-39277, CONST-39278 |  | Updated PM as of July 30, 2024 Below is the updated PM info: *Project Management Contact information:* Ilirjana Asani Property Manager [thechicago@mrcm.ca¦mailto:thechicago@mrcm.ca] *Maple Ridge Community Management – An Associa® Company* O: 905-507-6726 extension 507 *Below is the initial project information:* Requested by Jay Fernandes Hi, I’ve gone through the remaining Fibrestream condos we have agreements for in the GTA and have grouped them in a way that I think makes sense for site visits and builds. There will be another list coming of buildings that don’t really fall into groups. Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. There are some current backbone (Sheppard) or NPOP (960 Lawrence) projects that will need to be completed to connect these but this will get everything into the system. Thanks! *PM: Sergio Besir* *thechicago@mrcm.ca* *905.507.6726 x311* | FSactive, Fiberstreamagreement, Yonge&Finch | [12 empty] | 0¦i3h8xb: | [7 empty] | 9.2234e+18 | [19 empty] | July 27/23 - Project initiated. Design & Permit in progress. Feb 23/24 - City permit granted Aug 27th, 2024 - Locates are in, construction will be scheduled soon. Sept 5, 2024 Cable pull scheduled for Oct 3rd, need conduit built Sept 9, 2024 - Riser Build Completed - Panels and ISP splicing remain Sept 12, 2024 - conduit Build _ waiting of PM to receive approval from Board. Floor plans required. Sept 13, 2024_ Asbuilt sent to the city of Toronto Oct 15, 2024 - Construction to return to site on Oct 17th to connect building. Oct 16, 2024 No restoration required October 2, 2024 -Note - Pm has approved conduit work Nov 20, 2024 - Building On Net Nov 20, 2024 Clean Up Lorna to reconcile Sap | [6 empty] | 3 - Normal | [19 empty] | Internal |  | 2023-07-27 |  |  | 233 | Integration | 2024-11-20 | 19584 |  |  | https://buildings.beanfield.com/buildings/view/15447 |  | CONST-29261 | 3 - Normal | 2024-04-26 |  | 5483 | 15455
Construction | CONST-31856 | 8/ 10/ 18 Rouge Valley Dr W - The York Condos | 8/ 10/ 18 Rouge Valley Dr W | Ontario | Condo | Clean Up |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Jessica Markiewicz | 2022-11-10 09:15 |  | 2024-12-12 07:45 |  |  | 2024-03-06 | 0 | 3 |  |  | CONST-31857, CONST-31858, CONST-33266, CONST-35222, CONST-35223, CONST-35224, CONST-35225, CONST-35226, CONST-35227, CONST-35228, CONST-35229, CONST-35230, CONST-35231, CONST-35232, CONST-35233, CONST-35234, CONST-35235, CONST-35236, CONST-35237, CONST-35238, CONST-35239, CONST-35310, CONST-36290, CONST-36302, CONST-36576, CONST-36577, CONST-38806, CONST-38807 | CONST-26911, CONST-29425, CONST-26906, CONST-26909, CONST-26910 | Requested by Oliver Davies. Can you please queue up a site walk for 8-18 Rouge Valley Dr W “The York Condos”? This would become part of the Markham condos group that are reliant on the Birchmount and Enterprise backbone (https://tickets.beanfield.com/browse/CONST-29425) BB Link: [https://buildings.beanfield.com/buildings/view/14671] PM Info: *Wendy Tao* *¦* *Residential Property Manager* *REM Facilities Management Inc.* 10 Rouge Valley Drive West ¦ Unionville, Ontario ¦ L6G 0G9 T: 905-604-2877 [*wtao@remfmi.com*¦mailto:wtao@remfmi.com] | Bolton, Markham, NUA+MA | [12 empty] | 0¦i3p71r: | [7 empty] | 9.2234e+18 | [19 empty] | Aug 30/23 - Project initiated. Permits and Design completed on CONST-29425 Sep 14/23 - Construction scheduled to start on CONST-29425 Sep 21st Oct 12/23 - Construction started Oct 3rd on CONST-29425 Jan 24/24 - Transferred conduit build quote ($3,095.00) from Design & Permit budget to Cable pull budget (Conduit build).PO sent Jan 31/24 - Conduit build scheduled for Feb 1st. Cable pull scheduled for Feb 21st Feb 07/24 - Conduit build completed. Conduit build invoice received. Feb 12/24 - PO sent to Conview for scan & core drill. Feb 13/24 - pending SOW Feb 21/24 - Conview invoice received. Cable pull completed. Feb 22/24 - Due date will be pushed back due to still not having SOW from GIS Dept. Feb 26/24 - Transferred $7,500.00 from construction to splicing budget. PO sent for splicing. Feb 27/24 - Delay to SOW in turn caused delay to splicing. Due dates updated. Feb 28/24 - OSP splicing completed Mar 01/24 - ISP splicing in progress Mar 06/24 - Building On-Net | [6 empty] | 3 - Normal | [19 empty] | Internal |  | 2023-08-30 |  |  |  |  | 2024-03-06 | 18675 |  |  | https://buildings.beanfield.com/buildings/view/14671 |  | CONST-31856 | 3 - Normal | 2023-12-29 |  | 8955 | 18140
Construction | CONST-29111 | 7 & 9 Michael Power PL - Port Royal Place Ⅳ | 7 & 9 Michael Power PL | Ontario | Condo | Clean Up |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Jessica Markiewicz | 2022-07-08 14:59 |  | 2024-05-16 15:36 |  |  | 2024-04-10 | 0 | 3 |  |  | CONST-29112, CONST-29113, CONST-30440, CONST-30441, CONST-30442, CONST-30744, CONST-30745, CONST-30746, CONST-30747, CONST-30748, CONST-30749, CONST-30750, CONST-30751, CONST-30752, CONST-30753, CONST-30754, CONST-30755, CONST-30756, CONST-30757, CONST-30758, CONST-30759, CONST-33887, CONST-36322, CONST-36838, CONST-36839, CONST-38815, CONST-38816 | CONST-29102, CONST-29105, CONST-36642, CONST-36641, CONST-36748 | Requested by Jay Fernandes Hi, I’ve gone through the remaining Fibrestream condos we have agreements for in the GTA and have grouped them in a way that I think makes sense for site visits and builds. There will be another list coming of buildings that don’t really fall into groups. Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. There are some current backbone (Sheppard) or NPOP (960 Lawrence) projects that will need to be completed to connect these but this will get everything into the system. Thanks! *PM: Mark Bartoloni* | Bloor&Isl, Bolton, FSactive, Fiberstreamagreement | [12 empty] | 0¦i3h2dz: | [7 empty] | 9.2234e+18 | [19 empty] | October 4th - Project initiated. Design and Permits to be in progress. February 27th - Still waiting for the city permit. May 17/23 - Still pending city permit, due date updated. June 06/23 - Conduit Build scheduled for June 12th. July 04/23 - City permit still with Utility Review. July 17/23 - City permit taking longer than anticipated. Due dates updated. Aug 29/23 - City permit approved Sep 14/23 - Delay with construction schedule. Due dates updated. Jan 26/24 - Construction scheduled to start Feb 5th. Feb 07/24 - Short stream city permit submitted for replacement of GLB. Feb 08/24 - PO sent to ReadyVac (Wendy). SS permit granted. Feb 14/25 - Construction completed. Conduit build in progress. Cable pull scheduled for Feb 29th. Mobilization PO sent for conduit build. Feb 15/24 - Conduit build completed. Feb 22/24 - Readyvac invoice received. Feb 29/24 - Cable pull completed Mar 01/24 - Pending SOW. Mar 15/24 - SOW uploaded. Splicing scheduled for Mar 19th - 21st Mar 22/24 - Due to delay from GIS for SOW and unavailability of XGS line cards. Due dates updated. Mar 27/24 - OSP splicing completed Apr 05/24 - Troubleshooting required. ISP cables incorrectly spliced. Apr 10/24 - Building On-Net | [6 empty] | 3 - Normal | [19 empty] | Internal |  | 2022-10-04 |  |  |  | Integration | 2024-04-10 | 50102 |  |  | https://buildings.beanfield.com/buildings/view/3420 |  | 500450 | 3 - Normal | 2023-07-07 |  | 5211 | 11210
Construction | CONST-28348 | 100 Mill St. - Block 10 Rentals, Toronto | 100 Mill St. | Ontario | Condo | Clean Up |  | Unresolved | Harvey Tran | Olawale Olaniyan [X] | Harvey Tran | 2022-05-11 14:18 |  | 2024-10-29 10:16 |  |  | 2024-05-31 | 0 | 0 |  |  | CONST-28382, CONST-28383, CONST-28394, CONST-35645, CONST-35646, CONST-35647, CONST-35648, CONST-35649, CONST-35650, CONST-35651, CONST-35754, CONST-37250, CONST-37318, CONST-37888, CONST-38280, CONST-38900, CONST-38983 | CONST-30240 | +*PM Contact:*+ Omar Vivas, EIT M&E Coordinator C.437.235.4183 [{color:#000000}ovivas@EllisDon.com{color}¦mailto:ovivas@EllisDon.com] | [13 empty] | 0¦i3dhc7: | [7 empty] | 9.2234e+18 | [19 empty] | Nov 03/23 - ISP only. Will be fed from 425 Front St E, Toronto May 3rd 2024 - Riser cable pull is in progress. SOW is pending. May 31st, 2024 - Testing completed. Building is onnet. Only pending pre-wiring work as the building is not ready yet. | [6 empty] | 3 - Normal | [21 empty] | 2023-11-03 |  |  |  |  | 2024-05-31 |  |  |  | https://buildings.beanfield.com/buildings/view/16127 |  | 500501(sub) | 3 - Normal | 2024-10-25
Construction | CONST-29180 | 115 McMahon Dr, North York - Omega and Opus | 115 McMahon Dr, North York | Ontario | Condo | Clean Up |  | Unresolved | Lorna Kurok | Lorna Kurok | Jessica Markiewicz | 2022-07-11 14:27 |  | 2024-09-26 11:28 |  |  | 2024-09-27 | 0 | 0 | _thumb_922125.png _thumb_922122.png _thumb_973808.png _thumb_973807.png _thumb_973347.png _thumb_925460.png _thumb_973809.png _thumb_973810.png _thumb_973348.png _thumb_925463.png _thumb_973349.png _thumb_925464.png |  | CONST-29181, CONST-29182, CONST-32720, CONST-32760, CONST-32761, CONST-32762, CONST-32763, CONST-32764, CONST-32765, CONST-32766, CONST-32767, CONST-32768, CONST-32769, CONST-32770, CONST-32771, CONST-32772, CONST-32773, CONST-32774, CONST-32775, CONST-37801, CONST-37863, CONST-38167, CONST-38168, CONST-38599, CONST-38607, CONST-38880 | CONST-29186, CONST-32336, CONST-32339, CONST-32342, CONST-32592, CONST-32595, CONST-32880, CONST-33876, CONST-32349, CONST-33014 | Requested by Jay Fernandes Hi, I’ve gone through the remaining Fibrestream condos we have agreements for in the GTA and have grouped them in a way that I think makes sense for site visits and builds. There will be another list coming of buildings that don’t really fall into groups. Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. There are some current backbone (Sheppard) or NPOP (960 Lawrence) projects that will need to be completed to connect these but this will get everything into the system. Thanks! PM Info: *Sandi Plesa, OLCM, RCM, CPM* Property Manager As Agents for and on behalf of TSCC 2741 *Opus and Omega on the Park* 117 McMahon Drive, North York, Ontario M2K 0E4 Telephone: (647) 358-5560 E-mail: ** +[omegaandopus@crossbridgecs.com¦mailto:omegaandopus@crossbridgecs.com]+ | Fiberstreamagreement, Sheppard | [12 empty] | 0¦i3h7qf: | [7 empty] | 9.2234e+18 | [19 empty] | Jan 13/23 - Project initiated, pending design and permits. May 11/23 - ISP only will be fed from CONST-33876 Jun 7th, 2024 This is where we will work on the UG construction to enter the whole building group. Bolton team is working on the tentative schedule for this building. Aug 2024_ Backbone Cable pull is completed, waiting on Backbone SOW. Aug 2024_Splicing scheduled to be completed Aug 29th 30th. Sep 18, 2024_On Net email sent. ruby testing completed. | [6 empty] | 3 - Normal | [21 empty] | 2023-01-13 |  |  |  |  | 2024-09-18 | 3862 |  |  | https://buildings.beanfield.com/buildings/view/15762 |  | CONST-29180 | 3 - Normal | 2024-02-23 | North York | 11150 | 27100
Construction | CONST-29171 | 15 - 17 Zorra St, Etobicoke - Park Towers Condominiums at IQ | 15 - 17 Zorra St, Etobicoke | Ontario | Condo | Clean Up |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Jessica Markiewicz | 2022-07-11 14:10 |  | 2024-11-05 10:41 |  |  | 2024-02-07 | 0 | 0 |  |  | CONST-29172, CONST-29173, CONST-31979, CONST-31980, CONST-31981, CONST-31982, CONST-31983, CONST-31984, CONST-31985, CONST-31986, CONST-31987, CONST-31988, CONST-31989, CONST-31990, CONST-31991, CONST-31992, CONST-31993, CONST-31994, CONST-31995, CONST-31996, CONST-31997, CONST-31998, CONST-36142, CONST-36163, CONST-36185, CONST-36186, CONST-36808, CONST-38749 | CONST-27001, CONST-17747 | Requested by Jay Fernandes Hi, I’ve gone through the remaining Fibrestream condos we have agreements for in the GTA and have grouped them in a way that I think makes sense for site visits and builds. There will be another list coming of buildings that don’t really fall into groups. Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. There are some current backbone (Sheppard) or NPOP (960 Lawrence) projects that will need to be completed to connect these but this will get everything into the system. Thanks! *PM: James Docherty* *jdocherty@remingtongroupinc.com* *647.350.5881* | Fiberstreamagreement, Queensway | [12 empty] | 0¦i3h7kv: | [7 empty] | 9.2234e+18 | [19 empty] | November 18th - Project initiated. Design and permits to be in progress. May 15/23 - Hydro permit conditionally granted. Oct 11/23 - City permit approved Oct 11/23 - Construction scheduled to start Nov 13th Dec 14/23 - Construction completed Dec 22/23 - Conduit build scheduled for Jan 16th - 18th. Cable pull scheduled for Jan 24th Jan 16/24 - Conduit build completed Jan 17/24 - GIS updated SOW to show splicing will be blocked by CONST-27001. Due dates updated. Jan 17/24 - GIS found a workaround to bring this condo On-Net. Due dates updated. Jan 24/24 - Cable pull completed. Jan 31/24 - Delay with SOW and splicing. Due dates updated. Feb 05/24 - OSP splicing completed Feb 07/24 - Building On-Net | [6 empty] | 3 - Normal | [19 empty] | Internal | [6 empty] | 2024-02-07 | 90046 |  |  | https://buildings.beanfield.com/buildings/view/6725 |  | 500509 | 3 - Normal | 2023-06-16 |  | 12217 | 1120
Construction | CONST-27533 | 115/125 Blue Jays Way, Toronto - King Blue | 115/125 Blue Jays Way, Toronto | Ontario | Condo | Clean Up |  | Unresolved | Harvey Tran | Olawale Olaniyan [X] | Harvey Tran | 2022-03-31 11:56 |  | 2025-02-10 11:04 |  |  | 2024-07-30 | 0 | 1 |  |  | CONST-27534, CONST-27535, CONST-28703, CONST-28704, CONST-28705, CONST-28706, CONST-28707, CONST-28708, CONST-28709, CONST-28710, CONST-28711, CONST-28712, CONST-28713, CONST-28714, CONST-28715, CONST-28716, CONST-28717, CONST-31859, CONST-31860, CONST-31861, CONST-31862, CONST-35455, CONST-35456, CONST-35468, CONST-36959, CONST-38549, CONST-38789, CONST-38790 | CONST-31527, CONST-31357 | Condo constructed in 2028. Requested by Oliver. +*PM Updated Information Sept 24, 2024*+ John Wilson, OLCM, RCM Regional Manager ¦ ICC Property Management Ltd. [jwilson@iccpropertymanagement.com¦mailto:jwilson@iccpropertymanagement.com] Could you kindly request a site walk from James for 115-125 Blue Jays Way + 355 King St W (King Blue). [https://buildings.beanfield.com/buildings/view/12016] Agreement subtask can be created immediately as we have an executed FibreStream agreement. +*PM info:*+ Katherine Newman RCM, OLCM Senior Property Manager King Blue 115/125 Blue Jays Way ¦ Toronto, ON M5V 0N5 Direct 416.901.6445 Email [katherine.newman@fsresidential.com¦mailto:katherine.newman@fsresidential.com] | Bolton, Fibrestream | [12 empty] | 0¦i3asgn: | [7 empty] | 9.2234e+18 | [19 empty] | December 20th - Hydro permit granted. City permit in progress. March 10th - City Permit granted, expires September 10th. Apr 17/23 - There is active construction at this intersection. City will not approve our construction, asked to follow up again in August. Aug 18/23 - City permit extension requested Aug 21/23 - Locates Submitted. Hydro permit extension requested Aug 23/23 - City & Hydro permit extension approved Sep 18/23 - Locates completed. Pending construction schedule Oct 12/23 - Construction tentatively scheduled to start Dec 4th. Due dates updated. Dec 11/23 - Delay with construction schedule. Due dates updated. Mar 22/24 - Redesign required. Due dates updated. Mar 26/24 - Revised Hydro permit submitted Apr 01/24 - Hydro permit PO sent May 28th, 2024 - Construction is scheduled for June 10th, cable pull will be done after that. We are able to move up the project due date to July 2024. Jul 2nd, 2024 - Construction is completed. Cable pull is scheduled. Jul 15th, 2024 - Cable pull is completed. Splicing is tentatively scheduled. July 30th, 2024 - Splicing completed, we are working on the testing. July 30th, 2024 - Testing completed, building is onnet. | [6 empty] | 3 - Normal | [19 empty] | Internal |  | 2022-06-07 |  | 48 | 911 |  | 2024-07-30 | 71171 |  |  | https://buildings.beanfield.com/buildings/view/12016 |  | 500444 | 3 - Normal | 2023-06-09 | Toronto | 11999 | 24745
Construction | CONST-5348 | One Bloor - 1 Bloor St. East | 1 Bloor St. East | Ontario | Condo | Resolved |  | Unresolved | Oguz Avci [X] | Russell Francey | Russell Francey | 2017-01-11 08:08 |  | 2019-09-06 09:19 |  |  | 2019-02-14 | 0 | 4 |  |  | CONST-2524, CONST-5349, CONST-5350, CONST-5351, CONST-5671, CONST-5672, CONST-5673, CONST-5674, CONST-6240, CONST-6241, CONST-6647, CONST-6900, CONST-6901, CONST-6930, CONST-6995, CONST-7145, CONST-7549, CONST-9190, CONST-9451, CONST-9457, CONST-9587, CONST-9588, CONST-9631, CONST-9736, CONST-9788, CONST-9789, CONST-9790 | CONST-5388, CONST-7180 | suzanne.toole@balancerm.com New site contact for Tucker HiRise. Martin Orbanic 416-206-1468 martin.orbanic@tuckerhirise.com | Sentrex | [12 empty] | 0¦i0neaf: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [27 empty] | 17000 |  |  | https://buildings.beanfield.com/buildings/view/2125 |  | 500106 | 3 - Normal | 2017-09-22 |  | 9000 | 3000
Construction | CONST-6562 | Trinity Lofts - 90 Trinity St | 90 Trinity St | Ontario | Condo | Resolved |  | Unresolved | Oguz Avci [X] | Russell Francey | Russell Francey | 2017-07-10 10:42 |  | 2019-09-06 09:19 |  |  | 2019-02-08 | 0 | 3 | _thumb_141144.png |  | CONST-6563, CONST-6662, CONST-7548, CONST-8181, CONST-8182, CONST-8359, CONST-8360, CONST-8361, CONST-8362, CONST-8363, CONST-8364, CONST-8365, CONST-8366, CONST-8367, CONST-8368, CONST-8369, CONST-8370, CONST-8371, CONST-8372, CONST-8780, CONST-9299, CONST-9632, CONST-9633, CONST-9761, CONST-12362 | CONST-8736 | Katia Savvaidou, RCM, Licensed Senior Property Manager Crossbridge Condominium Services As Agents for and on behalf of TSCC#2263 90 Trinity Street Toronto, Ontario Tel: 416-230-6501 trinityloftsmanagement@gmail.com | [13 empty] | 0¦i0sn67: | [7 empty] | 9.2234e+18 | [19 empty] | Condo's lawyers are insisting that Beanfield pay for the complimentary services hardware. Jory working with them to see if we can come to a agreement. | [6 empty] | 3 - Normal | [30 empty] | https://buildings.beanfield.com/buildings/view/3479 |  | 500149 | 3 - Normal |  | King East
Construction | CONST-6186 | Infinity Ⅲ Condo - 19 Grand Trunk | 19 Grand Trunk | Ontario | Condo | Resolved |  | Unresolved | Oguz Avci [X] | Russell Francey | Russell Francey | 2017-05-25 11:04 |  | 2020-07-21 15:14 |  |  | 2018-07-27 | 0 | 4 | _thumb_108717.png |  | CONST-6187, CONST-6255, CONST-6299, CONST-6747, CONST-6803, CONST-7047, CONST-7048, CONST-7049, CONST-7050, CONST-7051, CONST-7052, CONST-7137, CONST-7138, CONST-7174, CONST-7576, CONST-7633, CONST-7640, CONST-7747, CONST-8373, CONST-8375, CONST-8389, CONST-12168, CONST-14052 | CONST-6573, PUR-416, CONST-6574 | *New Info:* Dritan Logli, Property Manager [Manager@19GrandTrunk.com¦mailto:Manager@19GrandTrunk.com] 647-343-0382 Nazzani Graziano, Project Manager [nazzanig@orlandocorp.com¦mailto:nazzanig@orlandocorp.com] 416-886-0567 *Old Info:* Andy Bazoian, R.C.M. Property Manager andy@iconpm.ca Office: 647-343-0382 408 Units 39 floors + PH Pop P1 level beside parking spot 136 interconnects to 25 Simcoe Space is limited in ex conduit with Rogers - the other conduit that goes to riser has large copper cables and no capacity There are other conduits but cannot see where they go | NXUtilities | [12 empty] | 0¦i0r6rb: | [7 empty] | 9.2234e+18 | [19 empty] | Agreement signed. | [6 empty] | 3 - Normal | [27 empty] | 23000 |  |  | https://buildings.beanfield.com/buildings/view/1241 |  | 500131 | 3 - Normal | 2018-04-20 | Southcore | 7000 | 4000
Construction | CONST-8166 | Grid Condos - 181 Dundas St E | 181 Dundas St E | Ontario | Condo | Resolved |  | Complete | Danny Da Silva | Danny Da Silva | Russell Francey | 2018-06-14 10:53 |  | 2019-08-07 17:48 | 2019-08-07 17:48 |  | 2019-01-25 | 0 | 2 |  |  | CONST-8167, CONST-8206, CONST-8219, CONST-8228, CONST-8229, CONST-8230, CONST-8231, CONST-8232, CONST-8233, CONST-8234, CONST-8235, CONST-8236, CONST-8237, CONST-8238, CONST-8239, CONST-8240, CONST-8241, CONST-8242, CONST-8243, CONST-8244, CONST-9320, CONST-9342, CONST-9385, CONST-9436, CONST-9536, CONST-9548 | [15 empty] | 0¦i161wf: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [27 empty] | 26000 |  |  | https://buildings.beanfield.com/buildings/view/5737 |  |  | 3 - Normal |  | Yonge & Dundas | 1000
Construction | CONST-7913 | Rezen - 205 Fredrick St. | 205 Fredrick St. | Ontario | Condo | Resolved |  | Complete | Oguz Avci [X] | Russell Francey | Russell Francey | 2018-04-19 14:01 |  | 2019-09-06 09:19 | 2019-02-13 08:30 |  | 2019-02-28 | 0 | 4 | _thumb_120868.png _thumb_120869.png _thumb_120870.png |  | CONST-7914, CONST-7915, CONST-9133, CONST-9136, CONST-9137, CONST-9138, CONST-9139, CONST-9140, CONST-9141, CONST-9142, CONST-9143, CONST-9144, CONST-9145, CONST-9146, CONST-9147, CONST-9148, CONST-9149, CONST-9150, CONST-9181, CONST-9182, CONST-9698 |  | Melody Property Manager As Agents for and on Behalf of T.S.C.C. 2005 205 Frederick Street, Toronto, ON M5A 4V3 rezenpropertymanager@rogers.com Tel: 416 214 0887 Fax: 416 214 0886 Website: [www.rezencondo.ca¦http://www.rezencondo.ca/] | [13 empty] | 0¦i137u7: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [27 empty] | 0 |  |  | https://buildings.beanfield.com/buildings/view/2465 |  | 500175 | 3 - Normal |  | Downtown East | 2000 | 4100
Construction | CONST-4361 | 210 Eastern Ave (170 Bayview) | 210 Eastern Ave (170 Bayview) | Ontario | Condo | Resolved |  | Unresolved | Oguz Avci [X] | Samantha Russell | Samantha Russell | 2016-04-04 09:27 |  | 2019-09-06 09:19 |  |  | 2018-06-01 | 0 | 2 | _thumb_67004.png |  | CONST-4879, CONST-5092, CONST-5093, CONST-5803, CONST-7028, CONST-7111, CONST-7125, CONST-7261, CONST-7295, CONST-7315, CONST-7420, CONST-7440, CONST-7464, CONST-7471, CONST-7575, CONST-7745, CONST-8004, CONST-8135, CONST-8136 | ACCT-30669 | Bring building onnet | BudgetPending | [12 empty] | 0¦i0g2mn: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [32 empty] | 500126 | 3 - Normal | 2018-03-02 |  | 14000
Construction | CONST-6907 | The Printing Factory - 201 Carlaw Ave. | 201 Carlaw Ave. | Ontario | Condo | Resolved |  | Unresolved | Oguz Avci [X] | Russell Francey | Russell Francey | 2017-10-04 08:58 |  | 2019-09-16 11:51 |  |  | 2018-10-12 | 0 | 4 | _thumb_118500.png _thumb_105323.png _thumb_105324.png _thumb_105325.png _thumb_105326.png _thumb_105327.png _thumb_105328.png _thumb_105329.png |  | CONST-6908, CONST-6909, CONST-6910, CONST-7803, CONST-7804, CONST-7805, CONST-7806, CONST-7807, CONST-7808, CONST-7809, CONST-7810, CONST-7811, CONST-7812, CONST-7813, CONST-7840, CONST-7841, CONST-7871, CONST-7901, CONST-7921, CONST-8333, CONST-8374, CONST-8411, CONST-11836 |  | Adrian Sebu, RCM Property Manager Crossbridge Condominium Services Ltd. As Agents for and on behalf of TSCC 2073 The Printing Factory Lofts - 201 Carlaw Ave. Toronto, ON, M4M 2S3 Tel: 647-340-4291 Fax:647-340-4304 theprintingfactory@rogers.com pop on p1 in main electrical room 44 townhouses fed from telephone room in unbridle room on east side of parking lot beside V19 riser in p1 south side of building for lower suites Bell prewired for fiber but have not brought their new trunk in yet zone conduits to suites | Onnetdate17Aug | [12 empty] | 0¦i0vzt3: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [27 empty] | 31000 |  |  | https://buildings.beanfield.com/buildings/view/2333 |  | 500146 | 3 - Normal | 2018-10-12 | Carlaw (Leslieville) | 3000 | 1000
Construction | CONST-4596 | 60 Bathurst - Sixty Lofts | 60 Bathurst | Ontario | Condo | Resolved |  | Unresolved | Oguz Avci [X] | Russell Francey | Russell Francey | 2016-06-24 12:48 |  | 2019-09-06 09:19 |  |  | 2018-11-30 | 0 | 1 | _thumb_124220.png _thumb_124221.png _thumb_124222.png _thumb_124223.png _thumb_124224.png |  | CONST-4597, CONST-4598, CONST-4599, CONST-8064, CONST-8106, CONST-8107, CONST-8293, CONST-8294, CONST-8295, CONST-8296, CONST-8297, CONST-8298, CONST-8299, CONST-8300, CONST-8301, CONST-8303, CONST-8304, CONST-8305, CONST-8306, CONST-8341, CONST-8504, CONST-9276, CONST-9291, CONST-9383 | [15 empty] | 0¦i0i7mv: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [27 empty] | 20600 |  |  | https://buildings.beanfield.com/buildings/view/1800 |  | 500148 | 5 - Very Low |  | West King West
Construction | CONST-3444 | 43 Hanna Lofts prewire | 43 Hanna Lofts prewire | Ontario | Condo | Resolved |  | Complete | Phil Sabourin | Phil Sabourin | Phil Sabourin | 2015-05-13 08:17 |  | 2015-06-24 14:09 | 2015-06-24 14:09 |  |  | 0 | 1 |  |  | CONST-3470 |  | [~danny][~perry]The following lofts 423, 439,440,441, 442 will be prewired Contractor is installing conduit from 4th floor electrical closet to each loft They should be ready for the week of May 18 - i will let you know dates when he calls me | [13 empty] | 0¦i08ypb: | [7 empty] | 52280 | [26 empty] | 3 - Normal | [33 empty] | 3 - Normal
Construction | CONST-3406 | Harbour View Estates | Harbour View Estates | Ontario | Condo | Resolved |  | Complete | Russell Francey | Jay Fernandes | Jay Fernandes | 2015-05-05 08:31 |  | 2017-05-12 13:43 | 2017-05-12 13:43 |  |  | 0 | 2 |  |  | CONST-3407, CONST-3408, CONST-3409, CONST-9323, CONST-36162 | CONST-5460, CONST-5463, CONST-5467, CONST-5920, CONST-5922 | TSCC#1694- 10 Navy Wharf Court and 9 Spadina ave TSCC#1713 – 35 mariner Terrace Tscc#1764 – 3 navy wharf court and 5 Mariner Terrace | [13 empty] | 0¦i08tnz: | [7 empty] | 51464 | [19 empty] | Apart of project blue jay | [6 empty] | 3 - Normal | [30 empty] | https://buildings.beanfield.com/buildings/view/1168# |  |  | 5 - Very Low |  | Concord Cityplace
BC Construction | BCCONST-81 | 9873 King George Blvd, Surrey BC Century City | 9873 King George Blvd, Surrey BC Century City | British Columbia | Condo | Resolved |  | Complete | Michael Tsamkiranis | Michael Tsamkiranis | Michael Tsamkiranis | 2023-05-15 15:00 |  | 2024-11-07 14:03 | 2024-03-27 17:11 |  | 2024-03-28 | 0 | 0 |  |  | BCCONST-82, BCCONST-83, BCCONST-128, BCCONST-490, BCCONST-491, BCCONST-492, BCCONST-637 | BCCONST-5, PUR-29622, PUR-29850 | Will require wiring to all suites. 243 Units - 3 CRUs Contacts: *REESE WILKINSON* Project Manager C 604.830.7797 BlueCity Construction 604.270.1889 +[www.BlueCity.ca¦http://www.bluecity.ca/]+ *JEREMY GRUMAN* (he/him/his) Director, Information Systems D 604.338.4268 Century Group 604.943.2203 [www.CenturyGroup.ca¦https://centurygroup.ca/] | Budget_Allocated, confirmed | [12 empty] | 0¦i419xz: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [20 empty] | 2024-03-27 | 2023-05-15 |  | 19 | 243 | [11 empty] | 28000 | 18000
Construction | CONST-27847 | Marine Parade Backbone | Marine Parade Backbone | Ontario | Condo | Resolved |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Harvey Tran | 2022-04-13 12:33 |  | 2024-12-10 10:41 |  |  |  | 0 | 0 |  |  | CONST-27848, CONST-27849 | CONST-25610, CONST-25612 | After meeting with James and Danny it was decided we needed to build some backbone along Marine Parade Drive in order to reduce costs and more importantly hydro duct rental costs. There is a $200K budget for this which we should include in the residential budget for this build. The high level build and budget are attached. The rest of these buildings are all approved. These all need the new NPOP at 30 Shorebreeze up which I just heard is signed. With the backbone included we’re still under $150 per unit which is great! | HumberBay, MysticPointe | [12 empty] | 0¦i3boon: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [25 empty] | Backbone | [7 empty] | 3 - Normal
BC Construction | BCCONST-762 | Site Walk - 947 E Hastings St | 947 E Hastings St | British Columbia | Condo | Resolved |  | Unresolved | Jasminder Boparai [X] | Jasminder Boparai [X] | Jasminder Boparai [X] | 2024-07-29 16:41 |  | 2024-10-10 17:33 |  |  |  | 0 | 0 | _thumb_970019.png _thumb_970020.png _thumb_970021.png _thumb_970022.png _thumb_970023.png |  |  |  | Site walk to determine if we can feed 947 E Hastings St from 955 E Hastings St. Nian P: 604-336-9230 | [13 empty] | 0¦i53bsn: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
BC Construction | BCCONST-89 | 210 Salter Street, New Westminster, BC | 210 Salter Street, New Westminster, BC | British Columbia | Condo | Resolved |  | Complete | Yawn Paular | Yawn Paular | Yawn Paular | 2023-05-23 13:25 |  | 2024-12-20 21:23 | 2024-01-31 17:17 |  | 2024-01-31 | 0 | 0 |  |  | BCCONST-90, BCCONST-172, BCCONST-242, BCCONST-243, BCCONST-244, BCCONST-245, BCCONST-246, BCCONST-619 | ORDER-212079, ORDER-212084, ORDER-212089, ORDER-212094, ORDER-212099, ORDER-212104, ACCT-135174, PUR-25910 | Strong Lead request from a customer as per Michael Setting up Site check. Bridgenet maybe in the bldg already 164 units = 22 floors Terry Bunke EPS 4303 Peninsula Port Royal {color:#000000}Cell 604-418-3553{color} *MAHYAR ATTAR* Senior Strata Manager 200 Granville Street ¦ Suite 700 ¦ Vancouver, BC, Canada V6C 1S4 1.855.333.5149 ¦ Office 604.683.8900 ¦ Fax 604.689.4829 Toll Free 1.855.683.8900 ¦ Customer Care Centre 1.855.273.1967 Email [_Mahyar.Attar@fsresidential.com_¦mailto:Mahyar.Attar@fsresidential.com] [*www.fsresidential.com*¦http://www.fsresidential.com/] Follow us on ¦ [Facebook¦https://www.facebook.com/pages/Firstservice-Residential-BC/664991976868719#!%20/pages/Firstservice-Residential-BC/664991976868719] ¦ [LinkedIn¦http://www.linkedin.com/company/firstservice-residential-bc?trk=company_name] ¦ [YouTube¦http://www.youtube.com/FSResidential] | Bridgenet, Budget_Allocated, Pre-Sales, Pre-planning | [12 empty] | 0¦i41sjj: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [20 empty] | 2024-01-31 |  |  | 22 | 164 | [11 empty] | 7300 | 4200
BC Construction | BCCONST-92 | 3086 Lincoln Ave (1123 Westwood), Coquitlam BC | 3086 Lincoln Ave (1123 Westwood), Coquitlam BC | British Columbia | Condo | Resolved |  | Complete | Jasminder Boparai [X] | Yawn Paular | Yawn Paular | 2023-05-25 17:46 |  | 2024-12-20 21:25 | 2023-12-28 13:25 |  | 2023-12-08 | 0 | 0 |  |  | BCCONST-93, BCCONST-94, BCCONST-95, BCCONST-96, BCCONST-97, BCCONST-98, BCCONST-145, BCCONST-200, BCCONST-785 | PUR-25393 | 30 Com units 249 Resi units | Budget_Allocated, QNET, confirmed, conversion | [12 empty] | 0¦i4228n: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [20 empty] | 2023-11-20 |  |  | 30 | 249 | [11 empty] | 9230 | 6800
BC Construction | BCCONST-120 | 3007 Glen Dr (Evergreen), Coquitlam BC | 3007 Glen Dr (Evergreen), Coquitlam BC | British Columbia | Condo | Resolved |  | Complete | Jasminder Boparai [X] | Yawn Paular | Yawn Paular | 2023-05-25 19:37 |  | 2024-12-20 21:26 | 2023-12-28 13:24 |  | 2023-12-08 | 0 | 0 |  |  | BCCONST-121, BCCONST-122, BCCONST-123, BCCONST-124, BCCONST-125, BCCONST-126, BCCONST-141, BCCONST-194 | PUR-24768 | Evergreen - 3007 Glen Drive, Coquitlam, BC V3B 2P7, Canada. Strata plan number BCP45694. Crossroads are Pinetree Way and The High Street. Evergreen is 30 stories with 195 units. Estimated completion is September 2015. Developed by Bosa Properties Inc.. Architecture by Rafii Architects Inc.. Interior design by BYU Design | Budget_Allocated, QNET, confirmed, conversion | [12 empty] | 0¦i422k7: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [20 empty] | 2023-12-07 | 2023-05-31 |  | 30 | 195 | [11 empty] | 4800
BC Construction | BCCONST-317 | 10 Renaissance Sq, New Westminster | 10 Renaissance Sq, New Westminster | British Columbia | Condo | Resolved |  | Complete | Jasminder Boparai [X] | Yawn Paular | Yawn Paular | 2023-07-10 13:43 |  | 2024-12-20 21:24 | 2023-12-28 13:23 |  | 2023-12-29 | 0 | 0 |  |  | BCCONST-318, BCCONST-319, BCCONST-320, BCCONST-321, BCCONST-322, BCCONST-323, BCCONST-359, BCCONST-618 | PUR-29862 | 237 units for all 3 bldgs 8 Renaissance Sq and 7 Rialto Crt Bridgenet in the Bldg 154 units for this bldg, shared conduits in some closets | Bridgenet, Budget_Allocated | [12 empty] | 0¦i45u9b: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [20 empty] | 2023-12-28 |  |  |  | 154 | [11 empty] | 11250 | 3400
BC Construction | BCCONST-99 | 2979 Glen Drive (Altamonte), Coquitlam BC | 2979 Glen Drive (Altamonte), Coquitlam BC | British Columbia | Condo | Resolved |  | Complete | Jasminder Boparai [X] | Yawn Paular | Yawn Paular | 2023-05-25 18:06 |  | 2024-12-20 21:22 | 2024-03-19 13:45 |  | 2024-02-23 | 0 | 0 |  |  | BCCONST-100, BCCONST-101, BCCONST-102, BCCONST-103, BCCONST-104, BCCONST-105, BCCONST-144, BCCONST-213 |  | LEVELS: 30 SUITES: 165 STATUS: Completed BUILT: 2008 TYPE: Freehold Strata STRATA PLAN: BCS2656 BLDG#: 3575 Keith Cuyong SIte Manager 604-554-0115 altamontemanager@gmail.com | Budget_Allocated, QNET, confirmed, conversion | [12 empty] | 0¦i422b3: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [20 empty] | 2024-02-23 | 2023-06-06 |  | 30 | 165 | [11 empty] | 4460
BC Construction | BCCONST-626 | 188 Agnes St. (The Elliot), New Westminster, BC | 188 Agnes St. (The Elliot), New Westminster, BC | British Columbia | Condo | Resolved |  | Complete | Yawn Paular | Yawn Paular | Yawn Paular | 2024-03-01 18:00 |  | 2024-12-20 21:31 | 2024-06-10 12:23 |  | 2024-06-28 | 0 | 0 | _thumb_909962.png |  | BCCONST-627, BCCONST-628, BCCONST-629, BCCONST-630, BCCONST-631, BCCONST-632, BCCONST-633, BCCONST-634, BCCONST-751 | PUR-35799 | 190 units - 9 townhouses 19 floors | Bridgenet, Budget_Allocated | [12 empty] | 0¦i4npjz: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [20 empty] | 2024-06-10 |  |  | 19 | 199 | [11 empty] | 5900 | 1200
BC Construction | BCCONST-113 | 2978 Glen Dr (Grand Central 1), Coquitlam BC | 2978 Glen Dr (Grand Central 1), Coquitlam BC | British Columbia | Condo | Resolved |  | Complete | Jasminder Boparai [X] | Yawn Paular | Yawn Paular | 2023-05-25 19:28 |  | 2024-12-20 21:28 | 2024-03-27 13:11 |  | 2024-03-28 | 0 | 0 |  |  | BCCONST-114, BCCONST-115, BCCONST-116, BCCONST-117, BCCONST-118, BCCONST-119, BCCONST-142, BCCONST-280 | BCCONST-249, BCCONST-250, PUR-25557 | Grand Central 1 is one of three Grand Central MDUs, total 625 units. LEVELS: 28 SUITES: 146 STATUS: Completed BUILT: 2009 TYPE: Freehold Strata STRATA PLAN: BCS3495 Bldg#: 5410 ***Please note that Jason Greene is not authorized to make any changes regarding the Grand Central building. *{*}Update: May 2022{*}* New Building manager - Amar 236-833-7998, [grandcentralpbs@gmail.com¦mailto:grandcentralpbs@gmail.com] | Budget_Allocated, QNET, confirmed, conversion | [12 empty] | 0¦i422if: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [20 empty] | 2024-03-27 |  |  | 28 | 146 | [11 empty] | 3900 | 2700
BC Construction | BCCONST-250 | 2975 Atlantic Ave (Grand Central 3), Coquitlam BC | 2975 Atlantic Ave (Grand Central 3), Coquitlam BC | British Columbia | Condo | Resolved |  | Complete | Jasminder Boparai [X] | Yawn Paular | Yawn Paular | 2023-06-14 14:23 |  | 2024-12-20 21:31 | 2024-06-17 12:53 |  | 2024-06-28 | 0 | 0 |  |  | BCCONST-258, BCCONST-259, BCCONST-260, BCCONST-261, BCCONST-262, BCCONST-263, BCCONST-264 | BCCONST-113, BCCONST-249, PUR-25660 | 37 Floors 248 Units Skips Floors 4, 13, 14, and 24 | Budget_Allocated, Conversion, QNET, confirmed | [12 empty] | 0¦i43ug7: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [20 empty] | 2024-06-17 |  |  | 37 | 248 | [11 empty] | 8600 | 4200
BC Construction | BCCONST-249 | 2968 Glen Dr (Grand Central 2), Coquitlam BC | 2968 Glen Dr (Grand Central 2), Coquitlam BC | British Columbia | Condo | Resolved |  | Complete | Jasminder Boparai [X] | Yawn Paular | Yawn Paular | 2023-06-14 14:23 |  | 2024-12-20 21:32 | 2024-07-22 11:15 |  | 2024-07-31 | 0 | 0 |  |  | BCCONST-251, BCCONST-252, BCCONST-253, BCCONST-254, BCCONST-255, BCCONST-256, BCCONST-257 | BCCONST-113, BCCONST-250, PUR-25645 | 32 Floors - 212 units Skips Floors 4, 13, 14, and 24 MTR all connected with FT6 12F 2 fibers to switch 6 each at GC2 and 3 12 available for each GC 2 and GC 3 from MTR outdoor cable | Budget_Allocated, QNET, confirmed, conversion | [12 empty] | 0¦i43ufr: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [20 empty] | 2024-07-22 |  |  | 32 | 212 | [11 empty] | 6200 | 3400
BC Construction | BCCONST-382 | 1188 Pinetree Way (MThree), Coquitlam BC | 1188 Pinetree Way (MThree), Coquitlam BC | British Columbia | Condo | Resolved |  | Complete | Yawn Paular | Yawn Paular | Yawn Paular | 2023-08-14 17:02 |  | 2024-12-20 21:30 | 2024-05-24 18:42 |  | 2024-05-31 | 0 | 0 |  |  | BCCONST-391, BCCONST-392, BCCONST-393, BCCONST-394, BCCONST-395, BCCONST-396, BCCONST-397 | PUR-31458 | 42 floors 319 Units | Budget_Allocated, Migration, QNET | [12 empty] | 0¦i48unj: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [20 empty] | 2024-05-24 |  |  | 42 | 319 | [11 empty] | 14500 | 5200
BC Construction | BCCONST-427 | 200 Keary St, New Westminster | 200 Keary St, New Westminster | British Columbia | Condo | Resolved |  | Complete | Yawn Paular | Yawn Paular | Yawn Paular | 2023-10-18 17:33 |  | 2024-12-20 21:29 | 2024-04-19 15:56 |  | 2024-04-19 | 0 | 0 |  |  | BCCONST-428, BCCONST-429, BCCONST-430, BCCONST-431, BCCONST-432, BCCONST-433, BCCONST-434 | PUR-33255 | The Anvil - 100 units Bridgenet not in the bldg yet. Spare conduit found coming into MTR https://buildings.beanfield.com/buildings/view/19892 | Bridgenet, Budget_Allocated | [12 empty] | 0¦i4e11b: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [20 empty] | 2024-04-19 |  |  |  | 100 | [11 empty] | 6100 | 2900
BC Construction | BCCONST-383 | 2955 Atlantic Avenue (Oasis), Coquitlam BC | 2955 Atlantic Avenue (Oasis), Coquitlam BC | British Columbia | Condo | Resolved |  | Complete | Yawn Paular | Yawn Paular | Yawn Paular | 2023-08-14 17:04 |  | 2024-12-20 21:20 | 2024-03-13 17:42 |  | 2024-03-15 | 0 | 0 |  |  | BCCONST-384, BCCONST-385, BCCONST-386, BCCONST-387, BCCONST-388, BCCONST-389, BCCONST-390 | PUR-31459 | 255 units, 42 flrs According to Jas the extra fiber we're paying for GC is being used for backup that's connected to this bldg from GC | Budget_Allocated, Migraton, QNET | [12 empty] | 0¦i48uo7: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [20 empty] | 2024-03-13 |  |  | 42 | 255 | [11 empty] | 12100 | 5200
Construction | CONST-38230 | 7 King St E_Toronto_The Metropole | 7 King St E_Toronto_The Metropole | Ontario | Condo | Resolved |  | Unresolved | Lorna Kurok | Lorna Kurok | Lorna Kurok | 2024-08-23 07:28 |  | 2024-12-24 12:45 |  |  |  | 0 | 0 |  |  | CONST-38231, CONST-38232 | CONST-4544 | _Requested by Oliver Davies_Aug 22, 2024_ *Units for 7 King St E is 314* {color:#0747a6}*PM Info:*{color}{*}{{*}} *Nancy Bijelic* President & CEO PropertyWright™ Management Inc. [Nancy.Bijelic@propertywright.ca¦mailto:Nancy.Bijelic@propertywright.ca] Office:416-549-1412 _Email Request:_ _Could you please proceed with creating a new ticket for an OSP plan & Site Walk at 7 King St E? There are 314 residential units at this condo._ _Note, a visit was previously conducted here in 2016 when it was deemed not a candidate due to the requirement of pre-wiring the suites (CONST-4544)_ _BB Link:_ _[https://buildings.beanfield.com/buildings/view/2577]_ _PM Info:_ *Nancy Bijelic* President & CEO PropertyWright™ Management Inc. [Nancy.Bijelic@propertywright.ca¦mailto:Nancy.Bijelic@propertywright.ca] Office:416-549-1412 | [13 empty] | 0¦i55di7: | [7 empty] | 9.2234e+18 | [19 empty] | Aug 22, 2024_Ticket created Cancel refer to ticket Const-4544 | [6 empty] | 3 - Normal | [23 empty] | 23 | 314 | [5 empty] | https://buildings.beanfield.com/buildings/view/2577 |  |  | 3 - Normal |  | Toronto
Construction | CONST-39807 | 60 Fairfax Cres, Scarborough, Wilshire on the Green | 60 Fairfax Cres, Scarborough, Wilshire on the Green | Ontario | Condo | Resolved |  | Unresolved | Unassigned | Lorna Kurok | Lorna Kurok | 2025-01-23 14:39 |  | 2025-01-24 08:08 |  |  |  | 0 | 0 |  |  |  |  | Condo Constructed in 2011 *Property Manager Contact Information as of Jan 22, 2025* PM Contact Name: Aleksia Bijelic PM Contact #: 416-752-5700 PM Email Address: [management@60fairfax.org¦mailto:management@60fairfax.org] *Newbuilds email January 22, 2025* Please see attached the signed agreements and CA/Budget form for 60 Fairfax that was approved today at CAPEX. MDU Address: 60 Fairfax Cres City: Scarborough Building Name: Wilshire on the Green # of Units:{*}198{*} # of Floors: 7 Building Constructed Year: 2011 Building First Occupancy Date or or time period of year, (eg. Mid 2026) PM Contact Name: Aleksia Bijelic PM Contact #: 416-752-5700 PM Email Address: [management@60fairfax.org¦mailto:management@60fairfax.org] Type of Contract (Fibre agreement or NUA & MA): A+M Building linked to other Buildings: n/a Bulk Related: No Comp Services on agreement: 2 internet, 2 phone lines Thank you Luke | [13 empty] | 0¦i5h8m7: | [7 empty] | 9.2234e+18 | [19 empty] | Jan 22, 2025_CA approved Closed this is a duplicate ticket please refer to CONST-28154 for the actually ticket | [6 empty] | 3 - Normal | [21 empty] | 2025-01-22 |  | 7 | 198 | [5 empty] | https://buildings.beanfield.com/buildings/view/16650 |  |  | 3 - Normal |  | Scarborough
Construction | CONST-34079 | Warden Avenue & Hwy 7 - Markham Condos Backbone | Warden Avenue & Hwy 7 - Markham | Ontario | Condo | Reopened |  | Unresolved | Denise King | Denise King | Denise King | 2023-05-30 09:30 |  | 2024-11-08 08:12 |  |  | 2024-09-24 | 0 | 0 |  |  | CONST-33158, CONST-34080, CONST-34086, CONST-34087, CONST-34088, CONST-34089, CONST-34090, CONST-34091, CONST-34092, CONST-34093, CONST-34094, CONST-34095, CONST-34096, CONST-34097, CONST-34098, CONST-34099, CONST-34100, CONST-34382, CONST-37221, CONST-37222 | CONST-29325, CONST-29425, CONST-26913, CONST-26914, PUR-26472, PUR-32357, PUR-40115, CONST-36969 | We encountered an issue that has changed our design to feed 268 Buchanan (CONST-26913) and 18 and 28 Uptown (CONST-26914) due to bridge reconstruction on Birchmount Rd crossing the Rouge River that would have significantly delayed the turn-up of these sites. Good news is that we have received an approved Bell SSA north up Warden and east across Hwy 7 to feed these sites. As part of the SSA we also applied for breakouts to service multiple existing condo’s not yet in our plans as well as condo’s in the development stages. This being said, we would like to create a separate project in Jira with it’s own sub-task’s separate from the Enterprise & Birchmount Build as the date for this new condo backbone will likely be completed a couple of months later. We will remove the budget amount from CONST-29425 to extension north up Birchmount crossing Hwy 7. The budget amount is similar because of the future breakouts to feed the several condo’s that exist and are in the development stages. [https://www.google.com/maps/d/edit?mid=1apyItX05rDnfcPDWs2lpwtGSLYq0KfQ&usp=sharing] | Backbone | [12 empty] | 0¦i42cn3: | [7 empty] | 9.2234e+18 | [19 empty] | June 7/23 - Bell SSA - Sent in 4721, SSA sent to Al Sproule to schedule with Gerry. June 14/23 - York Region permit (Hwy 7 & Uptown Drive / William Saville St - Bell breakout and 2 new manhole placement) - Circulations submitted. June 14/23 - City of Markham Permit - William Saville St - Circulations submitted. July 11/23 - York Region Permit (Hwy 7 & Uptown Drive / William Saville St - Bell breakout and 2 new manhole placement) - DFX followed up on circulations. July 13/23 - York Region permit (Warden Avenue & Cedarland Drive) - Bell breakout and new manhole placement) - DFX - In review, case #354698. July 13/23 - York Region permit (Warden Avenue & Hwy 7) - Bell breakout and new manhole placement) - DFX - In review, case #3546943. July 13/23 - York Region permit (Hwy 7 & Uptown Drive / William Saville St - Bell breakout and 2 new manhole placement) - DFX - In review, case #3546974 August 4/23 - York Region permit (Warden Avenue & Cedarland Drive) - Bell breakout and new manhole placement) DFX - Application being approved, pending issuance MC23-00400 August 4/23 - York Region Permit - Hwy 7 & Verclaire Gate - Bell breakout and new handwell placement - DFX - Followed up on status August 4/23 - York Region Permit - Warden Avenue & Hwy 7- Bell breakout and new handwell placement - DFX - Followed up on status August 14/23 -York Region Permit - Warden Avenue & Hwy 7- Bell breakout and new handwell placement - DFX - Revisions being done. August 29/23 - York Region Permit - Warden Avenue & Cedarland Drive - Bell breakout and new handwell placement - DFX - Update requested. August 29/23 - City of Markham Permit - Application submitted. August 31/23 - York Region Permit - Warden Avenue & Cedarland Drive - Bell breakout and new handwell placement - APPROVED, MC23-00400 September 5/23 - Wendy meeting with Sear from the city Sept 6, 2023 - Locates to be submitted. September 13/23 - York Region Permit - Warden Avenue & Hwy 7- Bell breakout and new handwell placement - Revisions sent back to the region September 18/23 - As per DK, GLB at HWY 7 & Verdale will not be installed. If building connection is needed at a later date, we will apply for conduit directly into building from the Bell chamber CONST-34095 & CONST-34090 tasks closed. September 27/23 - Locate packages complete for CONST-34088, CONST-34089 & CONST-34091 - Pending construction schedule. September 28/23 - City of Markham Permit - Revised drawings sent from DFX - Dave K to review. October 3/23 -City of Markham Permit - Revised drawings sent from DFX - Dave K approved. With DFX to resubmit to City of Markham. October 17/23 - York Region Permit - Warden Avenue & Hwy 7- Bell breakout and new handwell placement - DFX - Permit approved (MC23-00401 - Expires October 17, 2024 November 3/23 - City of Markham Permit - William Saville St - DFX - Submitted revised drawing on October 31, 2023. November 2/23 - York Region Permit - Hwy 7 & Uptown Drive / William Saville St - Bell breakout and 2 new manhole placement - DFX - Permit in progress November 6/23 - City of Markham Permit - William Saville St - DFX - Permit is approved pending city inspection. Nov 6/23 - Project moved to 2024. Nov 6/23 - City of Markham Permit - William Saville St - DFX - Submitted revised drawing to city for review. Nov 14/23 - York Region Permit - Hwy 7 & Uptown Drive / William Saville St - Bell breakout and 2 new manhole placement - DFX - Permit granted, expires November 9, 2024. February 13/24 - OSP Construction - Hwy 7 & Uptown Drive / William Saville St - Bell breakout and 2 new manhole placement - Bolton -- New locates submitted. March 1/24 - OSP Construction - Hwy 7 & Uptown Drive / William Saville St - Bell breakout and 2 new manhole placement - Bolton - Locates received. March 6/24 - Pending city site meet to start construction, dates may need to be adjusted. March 19/24 - Site meet scheduled for Wednesday March 27 @ 1:30pm. April 11/24 - Construction scheduled to start April 15th. May 2/24 - OSP Construction -Warden Avenue & Hwy 7- Bell breakout and new handwell placement - Locates Submitted. June 20/24 - OSP Construction -Warden Avenue & Hwy 7- Bell breakout and new handwell placement - Completed - NO RESTORATION REQUIRED June 27/24 - Construction York Region Permit - Warden Ave: Enterprise Blvd to Clegg Rd (CIK Joint Build) - Pending extension August 6/24 - Cable Pull - Warden Avenue & Hwy 7 - Bell Option - SENTREX - Crews are out today with Bell Canada inspector, should be completed by the end of week. July 30/24 - York Region MC - Cable Pull - Warden Avenue & Hwy 7 - Requested the extension on Permit MC23-00402. August 12/24 - Construction asbuilt attached CONST-34099 August 16/24 - Cable Pull - The crew could not get the last piece of 288 in on Warden due to elevation changes in the Bell structure to the Bell Manholes. Sentrex is putting in for rush locates to dig up the structure to complete the cable pull. Locates pending. August 21/24 - York Region MC - Cable Pull - Warden Avenue & Hwy 7 - Revised permit received - Extended until August 12, 2025 September 3/24 - Cable Pull - Warden Avenue & Hwy 7 - Bell Option - SENTREX - City of Markham and Zayo locates are still pending. September 11/24 - Locates are complete, Sentrex has reached out to Bell inspector for availability. Inspector is scheduled for Friday Sep 13/24 September 17/24 - Cable Pull - Warden Avenue & Hwy 7 - Bell Option - SENTREX - Cable placement complete September 23/24 - Last splice location will be completed today. September 24/24 - Splicing complete November 8/24 - Project reopened Financials Consolidated, project complete. | [6 empty] | 3 - Normal | [19 empty] | Internal | [5 empty] | Backbone | 2024-09-24 | 196000 |  |  |  |  | CONST-34079 | 3 - Normal |  | Markham | 67000 | 10000
Construction | CONST-17428 | 160 Flemington Road, North York | 160 Flemington Road, North York | Ontario | Condo | Reopened |  | Unresolved | Harvey Tran | Harvey Tran | Harvey Tran | 2020-12-09 16:16 |  | 2025-01-01 16:04 |  |  |  | 0 | 2 |  |  | CONST-17429 |  | We have a property interested, and would need to schedule a site visit. See below for details: *Property Address:* 160 Flemington Rd, North York ON M6A 0A9 *BB Link:* [https://buildings.beanfield.com/buildings/view/7765] *Property Manager:* Ed Johnson (647) 400-2389 [manager.yorkdaleresidences@gmail.com¦mailto:manager.yorkdaleresidences@gmail.com] | [13 empty] | 0¦i2c7rz: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [23 empty] | 15 | 314 | [5 empty] | https://buildings.beanfield.com/buildings/view/7765 |  |  | 3 - Normal |  | North York
Construction | CONST-32806 | 15 & 25 Beverley Street_Toronto_12 Degrees | 15 & 25 Beverley Street_Toronto_12 Degrees | Ontario | Condo | Reopened |  | Unresolved | Lorna Kurok | Lorna Kurok | Denise King | 2023-01-18 10:56 |  | 2024-12-24 16:08 |  |  |  | 0 | 2 |  |  | CONST-32807, CONST-32808, CONST-38344 |  | Requested by Oliver Davies: Can you please queue up a site walk for 15 Beverley St? This is a smaller MDU at 96 units, however my hope is that we can complete this build in conjunction with CONST-15132 which is directly across the street. PM Info: Pranvera Musaraj Condominium Manager *Crossbridge Condominium Services* Managing Agent for: 12 Degrees- TSCC 2497 15 Beverley St, Toronto ON, M5T 0B3, 416-519-9914 [Manager12degrees@rogers.com¦mailto:Manager12degrees@rogers.com] [12degrees@crossbridgecs.com¦mailto:12degrees@crossbridgecs.com] | [13 empty] | 0¦i3tdsv: | [7 empty] | 9.2234e+18 | [19 empty] | January 17th - as per Mark Houston and Oliver Davies project status was updated to Not a Candidate Sept 13, 2024 Note from site Visit (There is a connection between BFMH-0341 (john and Stephanie) and THES that I would like to complete . However It looks like the buildings are possible fed from the north and down the east side of Beverly. only the Audits will tell where we really need to go Beverly St.pdflink_attachment_7.gif) Constructed 2015 | [6 empty] | 3 - Normal | [23 empty] | 11 | 96 | [5 empty] | https://buildings.beanfield.com/buildings/view/3937 |  |  | 3 - Normal |  | Toronto
Construction | CONST-4629 | 330 Adelaide Street East- Imperial Square | 330 Adelaide Street East | Ontario | Condo | Reopened |  | Unresolved | Lorna Kurok | Lorna Kurok | Russell Francey | 2016-06-29 09:20 |  | 2024-12-24 16:28 |  |  |  | 0 | 2 | _thumb_71096.png _thumb_71095.png _thumb_71094.png _thumb_71092.png _thumb_71093.png |  | CONST-4630, CONST-4631, CONST-4632, CONST-37819, CONST-37820 | CONST-3402 | +*New 2024 Project Information:*+ The Imperial Square condos were built in 2000 and include 95 residential units. Beanfield last investigated an expansion of service to this building in 2016 (https://tickets.beanfield.com/browse/CONST-4629), during this visit it was discovered that the suites are daisy chained and a pre-wire/ISW is required. As we are now beginning to target condos that require ISW - this location is close to our network and the work can very likely be approved. The condo board remains very interested in adding Beanfield for their residents. BB Link: [https://buildings.beanfield.com/buildings/view/3798] +Site Contact:+ Erin Property Management Associate Horizon Property Management Inc.416-332-4988 ¦ [info@330adelaideeast.com¦mailto:info@330adelaideeast.com] Direct: (416) 820-9720 +*Old Project Information:*+ STEPHEN W. MUNENE Property Manager Direct 416.847.7225 Email stephen.munene@fsresidentail.com | [13 empty] | 0¦i0ibz3: | [7 empty] | 9.2234e+18 | [19 empty] | Condo is daisy chained. | [6 empty] | 3 - Normal | [23 empty] | 11 | 96 | [5 empty] | https://buildings.beanfield.com/buildings/view/3798 |  |  | 3 - Normal |  | Toronto Downtown East
Construction | CONST-29425 | Birchmount and Enterprise Condo Backbone | Birchmount and Enterprise Condo Backbone | Ontario | Condo | In Progress |  | Unresolved | Denise King | Denise King | Harvey Tran | 2022-07-13 14:12 |  | 2025-01-12 21:25 |  |  | 2025-05-30 | 0 | 2 | _thumb_566872.png |  | CONST-29426, CONST-29444, CONST-29457, CONST-29458, CONST-29459, CONST-29460, CONST-29462, CONST-29464, CONST-31064, CONST-31065, CONST-33017, CONST-35781, CONST-38090 | CONST-29893, CONST-30021, CONST-26911, CONST-34079, CONST-26906, PUR-26383, PUR-26471, PUR-26473, PUR-28557, CONST-26909, CONST-26910, CONST-31856 | Residential backbone build for the Markham condos group. *NOTE May 30/23 - Birchmount Rd north of Verlaire Gt will not be built due to bridge rehab on Birchmount. New project on Warden & Hwy 7 will service the condos on Hwy 7, see CONST-34079.* !Birchmount & Enterprise BB Plan (CONST-29425) (1).png! | Backbone, Bolton | [12 empty] | 0¦i3hgfr: | [7 empty] | 9.2234e+18 | [16 empty] | 28960 |  |  | Dec 12/22 - Budget approved, issued to Sentrex for permits, design in progress. Feb 16/23 - 80% of the drawings sent back to Sentrex to revise and add a couple building feeds. Dave K is working with Markham on the bridge attachment on Birchmount. Feb 17/23 - Sentrex design being updated. Also, waiting on markups from CIK-Tel and York Net, conflicts with MDE, Bell and Enbridge. Feb 22/23 - Updated design received from Sentrex, Dave K to review. March 1/23 - Bell SSA application submitted. March 2/23 - Bell SSA requires revisions on dwg to show the coredrills on MH's, also need to agree to cost of coredrills (Approx $10,500) March 13/23 - Coredrill cost has been approved and has been sent back to Bell. March 14/23 - Bell SSA - 23-0065RO has been assigned, review should be completed by April 13 2023 (Two b/o removed, revised to $7500) March 21/23 - City permit - Sentrex received the detailed plans from MDE, still pending review from Dave K on how to proceed. April 6/23 - Dave K sent revisions. April 10/23 - Bell SSA granted, 4721 needs to be sent to Bell - Expires June 9 2023 April 17/23 - City permit revision are with Dave K to review. April 19/23 - City permit updated by Dave K - Crossing added, pending revision. May 3/23 - City permit - Sentrex is clearing Markham District Energy, Bell and Enbridge circulations that were re-submitted April 22nd May 23/23 - City permit - Sentrex received new conflicts with Gas and CIK Telecom - revisions being sent today. June 7/23 - York Region permit - Submitted pages 1-3 June 7/23 - City permit - Application submitted to The City Of Markham, confirmation #349042706366 - New drawings pages 3-21. July 4/23 - City permit approved. July 10 & July 14/23 - York region permit update requested. July 21/23 - York Region Permit - Birchmount and Enterprise Backbone - In review August 7/23 - York Region Permit - Ref#9192 case reference 3565259 was created. August 17/23 -York Region Permit - Birchmount and Enterprise Backbone - SENTREX - Update requested. August 18/23 - York Region Permit - Birchmount and Enterprise Backbone - SENTREX - Region will not approve the bus lane, it is the jurisdiction of Markham. Still pending regional road permit August 18/23 - City Permit - Birchmount and Enterprise Backbone - SENTREX - As per York Region, the bus lane on Enterprise Road should be reviewed by City of Markham - Email has been sent. August 25/23 - Locate package complete - See notes in CONST-29458 August 28/23 - City Permit - Birchmount and Enterprise Backbone - Sentrex followed up w/C.O Markham re: lane situation. August 31/23 -City Permit APPROVED with minor adjustments (bus lane) see CONST-29457 attachment. September 8/23 - York Region Permit - Birchmount and Enterprise Backbone (Sentrex) - Update requested. September 14/ 23 - York Region Permit - Birchmount and Enterprise Backbone - SENTREX - Approved September 14/23 - York region road occ requested September 25/23 - City Permit - Partial PRE Inspection completed (Pages 1-15) Line change added. Construction may start on pages 1-15 only September 26/23 - Jacquie has notified Bolton construction of partial redline. September 29/23 - York Region Road occ granted. October 30/23 - Dave K had a meeting w/ the PM of the condo build & it looks like we are going to be delayed until the 20th of Nov. They have trenched in several ducts including a 16 duct hydro structure down the sidewalk. We will need to wait for their ROP to expire & then call in locates & schedule a redline site walk w/ the city. Nov 21/23 - Splice Schematic/Add proposed cable to patch manager - Birchmount and Enterprise Condo Backbone (Phase 1) - Splice schematic added. Nov 21/23 - WO#20367, cables #39725, 39726 & 39727 has been added on patch manager Nov 22/23 - Pending SOW Project moved to 2024. Jan 24/24 - City Permit - Birchmount and Enterprise Backbone - Permit expired, needs extension. Jan 25/24 - City Permit - Birchmount and Enterprise Backbone - SENTREX - Extension request sent to the city - Permit extension granted, expires August 31, 2024. Feb 8/24 - Cable Pull - Cable 1 completed and cable 2 completed Feb 21/24 - Cable Pull - 576 has been pulled from CDSH10148 to our new BFHW at Enterprise and Birchmount. We need to pull one 125m section to the handwell north but is dependant on construction being completed in the spring. March 12/24 - Partial asbuilts attached CONST-29462 March 13/24 - Construction partial asbuilt added to PM. August 8/24 - Partial restoration completed for the priority required by the city. Remaining restoration will be sent to Ferpac once asbuilt is complete for an estimate. August 23/24 - CIK is currently waiting for the extended permit to continue. They have been told they should have it by the end of this month. August 30/24 - CIK have received all the approvals for Birchmount Rd but not for Verdale Xing. They have applied for this section and hopefully they have it back before they have finished Birchmount. They will be starting Warden week of September 3rd and Birchmount the week after. October 17/24 - CIK Telecom has completed and roped on conduit for the Backbone from Enterprise to the ViVa Bus-lane. And roped into 8081 Birchmount. Ent and cable pulls can be scheduled. This will let us pull into all building except 111 Upperduke. This is still on hold as per City of Markham until next spring. October 18/24 - Pending cable pull to be scheduled. October 21/24 - Remainder of cable pull scheduled for November 8th November 13/24 - Asbuilts added to patch manager December 9/24 - Moved to 2025, due to laterals needing to be completed on CONST-36911 | [6 empty] | 3 - Normal | [19 empty] | Internal | [5 empty] | Backbone |  | 150000 |  |  |  |  | 500399 | 3 - Normal |  | Markham | 54626 | 9435
Construction | CONST-28345 | 432 Cherry St. - Block 4, Toronto | 432 Cherry St. | Ontario | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Harvey Tran | 2022-05-11 14:10 |  | 2025-01-16 08:01 |  |  | 2025-06-25 | 0 | 0 |  |  | CONST-28378, CONST-28379, CONST-28473, CONST-33820, CONST-33821, CONST-33823, CONST-33824, CONST-33825, CONST-35351, CONST-37861, CONST-39176, CONST-39412, CONST-39413, CONST-39414, CONST-39436, CONST-39515, CONST-39701, CONST-39702, CONST-39703 | ORDER-269474, CONST-28344, CONST-28346, CONST-33762 | We’ve got a bunch of buildings popping up in the West Don Lands so need to add them to our build schedule. Since we have the agreements already, feel free to create the full build of subtasks - including site walk, agreement and base building services. I think James has already done most of the site walks - he just needs a place to put the info. There are 2 groups of 3 towers going up but we should treat them as separate builds in JIRA - even if they can tie together through the underground. Then there are 2 additional, separate buildings. So 8 new tickets in total. Please use the municipal address as the title for each so it will tie into Building Browser. 131 Mill St. 151 Mill St. 181 Mill St. 422 Cherry 432 Cherry 65 Trinity Contact: ¦*_Alain Costa_* ¦ ¦MEP Manager, Toronto Division¦ ¦!https://mail.google.com/mail/u/0?ui=2&ik=e63ae99e5e&attid=0.53&permmsgid=msg-f:1805381308421027332&th=190e00bc1490b604&view=fimg&fur=ip&sz=s0-l75-ft&attbid=ANGjdJ_YuHvXw__tcyrHve9wYS8i9dMBxyqI969XpIIbXIWbqMZRmatWRSip8GCOY2dQDd6VCw0KWzyKMgfC_ByxqzUA4U2yLi5yLsPcTFIhMR1VtwqVfyfTBRUkncw&disp=emb!{*}C{*}: 416.356.1900¦ ¦!https://mail.google.com/mail/u/0?ui=2&ik=e63ae99e5e&attid=0.54&permmsgid=msg-f:1805381308421027332&th=190e00bc1490b604&view=fimg&fur=ip&sz=s0-l75-ft&attbid=ANGjdJ-UZIGZLlIkRJ180v7g8IePs5YmGhRxSY4__gMDWg6rHhFJdptk5S1uEkfVk7fPI51btvo_XQhCrN6wOI8kdJ1M43E3R-sRrN8UtLWAbbC1ZFXCLLjFX6NRJOE&disp=emb! [acosta@ellisdon.com¦mailto:acosta@ellisdon.com]¦ ¦!https://mail.google.com/mail/u/0?ui=2&ik=e63ae99e5e&attid=0.55&permmsgid=msg-f:1805381308421027332&th=190e00bc1490b604&view=fimg&fur=ip&sz=s0-l75-ft&attbid=ANGjdJ9_HxfIDzAc4rtO2HhfamZKKI8fmbQ-_qSMVy6X1yL41KzTICiIdOso4JUpSeT3Kt15nY5G-lXHVtJqpZdR5Zc1ztncyzdc_qI7XCtIJmQ7KbDxM2UwMh1XX9o&disp=emb! 1004 Middlegate Rd., Suite 1000, Mississauga, ON L4Y 1M4¦ ¦!https://mail.google.com/mail/u/0?ui=2&ik=e63ae99e5e&attid=0.56&permmsgid=msg-f:1805381308421027332&th=190e00bc1490b604&view=fimg&fur=ip&sz=s0-l75-ft&attbid=ANGjdJ_4an-FqDTHLuxVeDHSk8aGCLkh8i0JT3eBCdFT0lTcZFHutd_pxOFfDq0VquR5JbsTQ2nObCio0x8iXLYUmJhvcJgG8kwxDlMwGXGZXBUh_-28qaprcedRuyo&disp=emb! [www.ellisdon.com¦http://www.ellisdon.com/]¦ | [13 empty] | 0¦i3dhaf: | [7 empty] | 9.2234e+18 | [19 empty] | May 04/23 - Project initiated, Cable Pull only. Nov 15, 2024 - Pulled rope from 422 Cherry to Main Pop through 2 pull boxes. Jan 6, 2025- Meeting Notes_ due to this Building Construction, we are moving these project to June 2025 from May 2025 | [6 empty] | 3 - Normal | [23 empty] | 12 | 388 | [5 empty] | https://buildings.beanfield.com/buildings/view/16125 |  | CONST-28345 | 3 - Normal | 2025-05-30 | Toronto | 38682
Construction | CONST-28346 | 65 Trinity - Block 3, Toronto | 65 Trinity | Ontario | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Harvey Tran | 2022-05-11 14:12 |  | 2025-01-21 15:02 |  |  | 2025-06-27 | 0 | 0 |  |  | CONST-28375, CONST-28381, CONST-28474, CONST-33802, CONST-33803, CONST-33804, CONST-33805, CONST-33806, CONST-33807, CONST-33808, CONST-33809, CONST-33810, CONST-33811, CONST-33812, CONST-33813, CONST-33814, CONST-33815, CONST-33816, CONST-33817, CONST-33936, CONST-37862, CONST-39364, CONST-39415, CONST-39435, CONST-39513 | CONST-28344, CONST-28345, CONST-33763 | We’ve got a bunch of buildings popping up in the West Don Lands so need to add them to our build schedule. Since we have the agreements already, feel free to create the full build of subtasks - including site walk, agreement and base building services. I think James has already done most of the site walks - he just needs a place to put the info. There are 2 groups of 3 towers going up but we should treat them as separate builds in JIRA - even if they can tie together through the underground. Then there are 2 additional, separate buildings. So 8 new tickets in total. Please use the municipal address as the title for each so it will tie into Building Browser. 131 Mill St. 151 Mill St. 181 Mill St. 422 Cherry 432 Cherry 65 Trinity Contact: ¦*_Alain Costa_* ¦ ¦MEP Manager, Toronto Division¦ ¦!https://mail.google.com/mail/u/0?ui=2&ik=e63ae99e5e&attid=0.53&permmsgid=msg-f:1805381308421027332&th=190e00bc1490b604&view=fimg&fur=ip&sz=s0-l75-ft&attbid=ANGjdJ_YuHvXw__tcyrHve9wYS8i9dMBxyqI969XpIIbXIWbqMZRmatWRSip8GCOY2dQDd6VCw0KWzyKMgfC_ByxqzUA4U2yLi5yLsPcTFIhMR1VtwqVfyfTBRUkncw&disp=emb!{*}C{*}: 416.356.1900¦ ¦!https://mail.google.com/mail/u/0?ui=2&ik=e63ae99e5e&attid=0.54&permmsgid=msg-f:1805381308421027332&th=190e00bc1490b604&view=fimg&fur=ip&sz=s0-l75-ft&attbid=ANGjdJ-UZIGZLlIkRJ180v7g8IePs5YmGhRxSY4__gMDWg6rHhFJdptk5S1uEkfVk7fPI51btvo_XQhCrN6wOI8kdJ1M43E3R-sRrN8UtLWAbbC1ZFXCLLjFX6NRJOE&disp=emb! [acosta@ellisdon.com¦mailto:acosta@ellisdon.com]¦ ¦!https://mail.google.com/mail/u/0?ui=2&ik=e63ae99e5e&attid=0.55&permmsgid=msg-f:1805381308421027332&th=190e00bc1490b604&view=fimg&fur=ip&sz=s0-l75-ft&attbid=ANGjdJ9_HxfIDzAc4rtO2HhfamZKKI8fmbQ-_qSMVy6X1yL41KzTICiIdOso4JUpSeT3Kt15nY5G-lXHVtJqpZdR5Zc1ztncyzdc_qI7XCtIJmQ7KbDxM2UwMh1XX9o&disp=emb! 1004 Middlegate Rd., Suite 1000, Mississauga, ON L4Y 1M4¦ ¦!https://mail.google.com/mail/u/0?ui=2&ik=e63ae99e5e&attid=0.56&permmsgid=msg-f:1805381308421027332&th=190e00bc1490b604&view=fimg&fur=ip&sz=s0-l75-ft&attbid=ANGjdJ_4an-FqDTHLuxVeDHSk8aGCLkh8i0JT3eBCdFT0lTcZFHutd_pxOFfDq0VquR5JbsTQ2nObCio0x8iXLYUmJhvcJgG8kwxDlMwGXGZXBUh_-28qaprcedRuyo&disp=emb! [www.ellisdon.com¦http://www.ellisdon.com/]¦ | Bolton, ExecutionAgreement, PREWIRE | [12 empty] | 0¦i3dhb3: | [7 empty] | 9.2234e+18 | [19 empty] | May 04/23 - Project initiated, pending Permits & Design Aug 3/23 - No permit required. Aug 15/23 - Waiting on building for approval to schedule construction. Feb 23/24 - Construction scheduled to start Feb 26th Feb 29/24 - Construction completed. Jan 2, 2024 - Tie cables completed on both sides. Jan 6, 2025- Meeting Notes_ due to this Building Construction, we are moving these project to June 2025 from May 2025 Jan 13, 2025 - noting that the OSP has already been pulled. Jan 10, 2025_ OSP SOW Jan 21, 2025 - OSP Sow pending redesign, due to embargo Hydro CC2911 | [6 empty] | 3 - Normal | [24 empty] | 397 |  |  | 37911 |  |  | https://buildings.beanfield.com/buildings/view/16123 |  | CONST-28346 | 3 - Normal | 2025-05-30 | Toronto | 39064 | 13240
Construction | CONST-28344 | 422 Cherry St. - Block 7, Toronto | 422 Cherry St. | Ontario | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Harvey Tran | 2022-05-11 14:09 |  | 2025-01-07 12:07 |  |  | 2025-06-25 | 0 | 0 |  |  | CONST-28376, CONST-28377, CONST-28393, CONST-33826, CONST-33827, CONST-33828, CONST-33829, CONST-33830, CONST-33831, CONST-33832, CONST-33833, CONST-33834, CONST-33835, CONST-33836, CONST-33837, CONST-33838, CONST-33839, CONST-33840, CONST-33841, CONST-37860, CONST-37910, CONST-37927, CONST-37928, CONST-37930 | ORDER-270600, CONST-28345, CONST-28346, CONST-33761 | We’ve got a bunch of buildings popping up in the West Don Lands so need to add them to our build schedule. Since we have the agreements already, feel free to create the full build of subtasks - including site walk, agreement and base building services. I think James has already done most of the site walks - he just needs a place to put the info. There are 2 groups of 3 towers going up but we should treat them as separate builds in JIRA - even if they can tie together through the underground. Then there are 2 additional, separate buildings. So 8 new tickets in total. Please use the municipal address as the title for each so it will tie into Building Browser. 131 Mill St. 151 Mill St. 181 Mill St. 422 Cherry 432 Cherry 65 Trinity Contact: ¦*_Alain Costa_* ¦ ¦MEP Manager, Toronto Division¦ ¦!https://mail.google.com/mail/u/0?ui=2&ik=e63ae99e5e&attid=0.53&permmsgid=msg-f:1805381308421027332&th=190e00bc1490b604&view=fimg&fur=ip&sz=s0-l75-ft&attbid=ANGjdJ_YuHvXw__tcyrHve9wYS8i9dMBxyqI969XpIIbXIWbqMZRmatWRSip8GCOY2dQDd6VCw0KWzyKMgfC_ByxqzUA4U2yLi5yLsPcTFIhMR1VtwqVfyfTBRUkncw&disp=emb!{*}C{*}: 416.356.1900¦ ¦!https://mail.google.com/mail/u/0?ui=2&ik=e63ae99e5e&attid=0.54&permmsgid=msg-f:1805381308421027332&th=190e00bc1490b604&view=fimg&fur=ip&sz=s0-l75-ft&attbid=ANGjdJ-UZIGZLlIkRJ180v7g8IePs5YmGhRxSY4__gMDWg6rHhFJdptk5S1uEkfVk7fPI51btvo_XQhCrN6wOI8kdJ1M43E3R-sRrN8UtLWAbbC1ZFXCLLjFX6NRJOE&disp=emb! [acosta@ellisdon.com¦mailto:acosta@ellisdon.com]¦ ¦!https://mail.google.com/mail/u/0?ui=2&ik=e63ae99e5e&attid=0.55&permmsgid=msg-f:1805381308421027332&th=190e00bc1490b604&view=fimg&fur=ip&sz=s0-l75-ft&attbid=ANGjdJ9_HxfIDzAc4rtO2HhfamZKKI8fmbQ-_qSMVy6X1yL41KzTICiIdOso4JUpSeT3Kt15nY5G-lXHVtJqpZdR5Zc1ztncyzdc_qI7XCtIJmQ7KbDxM2UwMh1XX9o&disp=emb! 1004 Middlegate Rd., Suite 1000, Mississauga, ON L4Y 1M4¦ ¦!https://mail.google.com/mail/u/0?ui=2&ik=e63ae99e5e&attid=0.56&permmsgid=msg-f:1805381308421027332&th=190e00bc1490b604&view=fimg&fur=ip&sz=s0-l75-ft&attbid=ANGjdJ_4an-FqDTHLuxVeDHSk8aGCLkh8i0JT3eBCdFT0lTcZFHutd_pxOFfDq0VquR5JbsTQ2nObCio0x8iXLYUmJhvcJgG8kwxDlMwGXGZXBUh_-28qaprcedRuyo&disp=emb! [www.ellisdon.com¦http://www.ellisdon.com/]¦ | PREWIRE | [12 empty] | 0¦i3dh8v: | [7 empty] | 9.2234e+18 | [19 empty] | May 04/23 - Project initiated, pending Permits & Design July 11/23 - City permit granted. Aug 15/23 - Pending road restriction and schedule Aug 24/23 - Construction tentatively scheduled to start Sept 5th Sep 8/23 - Construction completed. July 10th, 2023 - Ellis Don requested we need to complete this by end of July 2024. Pending approval to use contractor for cable pull and splicing. Building onnet is still in 2025 due to riser works. July 11th, 2024 - Design of Cable pull drawing completed, note that MainTelecom room located on 2nd floor July 12th, 2024 - OSP SOW plan has been completed. P;an includes Fibers needed for splitters in POP room as well as extra Fibers for the Elevator lines. July 24, 2024 - Was not able to gain access to the building to work on ISP Splicing. Building is still under construction. Sep 19, 2024 - All cables pulled to pop and dressed it. Riser Fiber Pull Completed Sep 19, 2024 - Riser Panels completed. Jan 6, 2025- Meeting Notes_ due to this Building Construction, we are moving these project to June 2025 from May 2025 | [6 empty] | 3 - Normal | [21 empty] | 2023-05-04 |  | 11 | 68 |  |  | 30874 |  |  | https://buildings.beanfield.com/buildings/view/16124 |  | CONST-28344 | 3 - Normal | 2025-05-30 | Toronto | 1710 | 8680
Construction | CONST-33722 | Contractor Pre-Wiring - 131/151/181 Mill St. - Block 8 | 131/151/181 Mill St. | Ontario | Condo | In Progress |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2023-04-21 10:16 |  | 2025-01-27 09:51 |  |  |  | 0 | 1 |  |  | CONST-38237, CONST-39281 | CONST-15306, ACCT-136266 |  | Cybertec, PREWIRE, Rogers | [12 empty] | 0¦i3zn07: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 664 |  |  | 20692 |  |  | https://buildings.beanfield.com/buildings/view/16126 |  | CONST-33722 | 3 - Normal |  | Toronto
Construction | CONST-33763 | Contractor Pre-Wiring - 65 Trinity - Block 3, Toronto | 65 Trinity - Block 3, Toronto | Ontario | Condo | In Progress |  | Unresolved | Lorna Kurok | Lorna Kurok | Olawale Olaniyan [X] | 2023-04-27 13:28 |  | 2025-01-27 09:48 |  |  | 2025-06-25 | 0 | 1 | _thumb_1128848.png |  | CONST-38143, CONST-38210 | CONST-28346, CONST-33762 |  | Cybertec, PREWIRE, Rogers | [12 empty] | 0¦i401v3: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 397 |  |  | 5161 |  |  | https://buildings.beanfield.com/buildings/view/16123 |  | CONST-33763 | 3 - Normal | 2025-05-30 | Toronto
Construction | CONST-33754 | Contractor Pre-Wiring - 425 Front St E, Toronto - Block 10 condos | 425 Front St E, Toronto - Block 10 condos | Ontario | Condo | In Progress |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2023-04-26 09:47 |  | 2025-01-27 09:48 |  |  |  | 0 | 0 |  |  | CONST-38203, CONST-38212 | CONST-30240 |  | Cybertec, PREWIRE, Rogers | [12 empty] | 0¦i3zxf3: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [23 empty] | 13 | 206 | [5 empty] | https://buildings.beanfield.com/buildings/view/16197 |  | CONST-33754 | 3 - Normal |  | Toronto
Construction | CONST-33762 | Contractor Pre-Wiring - 432 Cherry St. - Block 4, Toronto | 432 Cherry St. - Block 4, Toronto | Ontario | Condo | In Progress |  | Unresolved | Lorna Kurok | Lorna Kurok | Olawale Olaniyan [X] | 2023-04-27 13:26 |  | 2025-01-27 10:03 |  |  | 2025-06-25 | 0 | 1 |  |  | CONST-38201, CONST-38211 | CONST-38143, CONST-28345, CONST-33763 |  | Cybertec, PREWIRE, Rogers | [12 empty] | 0¦i401uv: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [23 empty] | 12 | 388 |  |  | 5044 |  |  |  |  | CONST-33762 | 3 - Normal | 2025-05-30 | Toronto
Construction | CONST-33761 | Contractor Pre-Wiring - 422 Cherry St. - Block 7, Toronto | 422 Cherry St. - Block 7, Toronto | Ontario | Condo | In Progress |  | Unresolved | Lorna Kurok | Lorna Kurok | Olawale Olaniyan [X] | 2023-04-27 13:24 |  | 2025-01-27 10:22 |  |  | 2025-06-25 | 0 | 1 |  |  | CONST-38186, CONST-38209 | CONST-28344 |  | Cybertec, PREWIRE, Rogers | [12 empty] | 0¦i401un: | [7 empty] | 9.2234e+18 | [19 empty] | Sep 11, 2024_Cybertec contractor has indicated that all the cables have been completed up to the 5th floor, and nothing above this is ready for any in-suit work. Sept 11, 2024_Contractor status notes:Contractor has informed SC that 1ct cables have been completed up to the 5th floor, and I. Suite InSuite jacks are completed up to the 7th floor. Nothing above this is ready to be pulled currently. Nov 15, 2024_ 1 floor remains to be pulled for the Homeruns. | [6 empty] | 3 - Normal | [23 empty] | 11 | 68 |  |  | 844 |  |  | https://buildings.beanfield.com/buildings/view/16124 |  | CONST-33761 | 3 - Normal | 2025-05-30 | Toronto
Construction | CONST-36323 | Contractor Pre-Wiring - 155 Merchants' Wharf - Aqualuna, Toronto | 155 Merchants' Wharf - Aqualuna, Toronto | Ontario | Condo | In Progress |  | Unresolved | Lorna Kurok | Lorna Kurok | Olawale Olaniyan [X] | 2024-01-26 14:17 |  | 2025-01-27 09:50 |  |  | 2025-03-31 | 0 | 2 |  |  | CONST-36511, CONST-38208, CONST-39908 | CONST-35943, ACCT-136267, CONST-19082 |  | Cybertec, PREWIRE, Rogers | [12 empty] | 0¦i4l6nr: | [7 empty] | 9.2234e+18 | [19 empty] | Feb 07/24 - Quote from Cybertec approved under CONST-36323. Feb 08/24 - Transferred $7,500.00 from CONST-19082 (restoration budget) to CONST-36323 (design and permits budget). Sent PO to Cybertec. Nov 22, 2024 Move In date January 2024 January 17, 2025 _1st occupancy inspection is now scheduled for Feb. 18, with the building inspectors, for all below-grade levels, ground floor, and residential floors from L2 to L7 with life-safety on L8, and mechanical penthouses. | [6 empty] | 3 - Normal | [23 empty] | 16 | 225 |  |  | 7500 |  |  | https://buildings.beanfield.com/buildings/view/13366 |  | CONST-36323 | 3 - Normal | 2024-05-31 | Toronto
Construction | CONST-29399 | 1369 Bloor St, Toronto - beBloor | 1369 Bloor St, Toronto | Ontario | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Jessica Markiewicz | 2022-07-13 12:21 |  | 2025-01-28 10:56 |  |  | 2025-05-19 | 0 | 1 |  |  | CONST-29400, CONST-29401, CONST-31402, CONST-31436, CONST-31437, CONST-31438, CONST-31439, CONST-31440, CONST-31441, CONST-31442, CONST-31444, CONST-31445, CONST-31446, CONST-31447, CONST-31448, CONST-31449, CONST-31450, CONST-37657, CONST-37658, CONST-37914, CONST-38037, CONST-39358, CONST-39551 | CONST-36570, CONST-35199 | Requested by Jay Fernandes Hi, These are the Fibrestream condos we have agreements for that don’t seem to fit into any groups (although I maybe wrong). Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. ¦Group¦Building Name¦Address¦suites¦ ¦Independent¦Eleven Superior¦11 Superior AVE Etobicoke ON M8V 0A7¦130¦ ¦Independent¦The James Club¦1135 Royal York RD Toronto ON M9A 4A7¦209¦ ¦Independent¦Independence Way¦115 George Appleton WAY North York ON M3M 2E9¦244¦ ¦Independent¦Danforth Village Estates¦1346 Danforth RD Toronto ON M4J1M9¦249¦ ¦Independent¦beBloor¦1369 Bloor ST Toronto ON M6P 4J3¦238¦ ¦Independent¦Ion Condos¦15 James Finlay WAY Toronto ON M3M 0B3¦200¦ ¦Independent¦Paradice at the Oasis¦1720 Eglinton AVE Toronto ON M4A2X9¦190¦ ¦Independent¦Havenon the Bluffs¦20 East Haven DR Toronto ON M1N1M2¦259¦ ¦Independent¦Kilgour Estate II¦21 Burkebrook PL Toronto ON M4G4K8¦228¦ ¦Independent¦Canvas Condos¦2301 Danforth AVE Toronto ON M4C 1L5¦156¦ ¦Independent¦3018 Yonge Condos¦3018 Yonge ST Toronto ON M4N 0A5¦188¦ ¦Independent¦Cranbrooke Village¦35 Saranac BLVD Toronto ON M6A 2G4¦341¦ ¦Independent¦39 Brant St¦39 Brant ST Toronto ON M5V0M8¦236¦ ¦Independent¦The Wave¦4 Elsinore PATH Toronto ON M8V 4G7¦185¦ ¦Independent¦Clock Tower Lofts¦700 King ST Toronto ON M5V 2Y6¦216¦ ¦Independent¦The Boot¦75 Dalhousie ST Toronto ON M5B 2R9¦153¦ ¦Independent¦B.Street Condos¦783 Bathurst ST Toronto ON M6G 1K1¦ ¦ ¦Independent¦85 Bloor St¦85 Bloor ST Toronto ON M4W3G9¦252¦ | FSactive, Fiberstreamagreement | [12 empty] | 0¦i3hfqv: | [7 empty] | 9.2234e+18 | [19 empty] | November 29th - Route Drawing completed. June 05/23 - Manhole survey completed. Hydro permit in progress. Aug 7/23 - Hydro permit granted. Sep 3rd 2024 - We still dont have the agreement to complete the conduit build and cable pull. Sep 4, 2024_SOW Design Details have been uploaded. Sep 10, 2024_Requires Vault Access, hoping to Schedule Friday October 4th between 10 am to 1 pm, Vault Loc Z2040 Sep 10, 2024_OSP splicing Completed. Sep 13, 2024_Booking Vault access, Vault ID: LZ2040 For Friday October 4th 10 am to 1 pm Sep 17, 2024_Vault access payment is confirmed. Confirmed appointment time with Scheduler. Oct 7, 2024 Cable pull asbuilt attached Jan 6, 2025_Meeting update- this building is being moved to March 2025 on the ON net schedule. This building requires the agreement to approved for CONST-36570 1/11/21 Ruttan. Condo 1/11/21 Ruttan is blocking 1369 Bloor from being completed. Therefore we have moved 1369 Bloor was rescheduled to March 2025. Jan 28, 2025 - Change to On Schedule- Moved from March 2025 to May 2025 due to other Condo as noted above. (Oliver has been working on this issue.) Updated change in Jira, On Net schedule, and SAP. | [6 empty] | 3 - Normal | [21 empty] | 2022-10-25 |  | 15 | 238 | Integration |  | 20490 |  |  | https://buildings.beanfield.com/buildings/view/3078 |  | 500488 | 3 - Normal | 2023-12-29 | Toronto | 7873 | 16030
Construction | CONST-39511 | 215 Lakeshore Blvd E, Toronto, Pinnacle Lakeside | 215 Lakeshore Blvd E, Toronto, Pinnacle Lakeside | Ontario | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Lorna Kurok | 2024-12-17 12:13 |  | 2025-02-04 14:01 |  |  | 2026-07-01 | 0 | 1 |  |  | CONST-39512, CONST-39514, CONST-39516, CONST-39600 |  | Newbuilds, Please launch the project for 215 Lakeshore. Attached is the approved CA form with the associated budget. This should be allocated to the FY25 Residential Construction budget. Building Type: Greenfield Choice Units: 1147 Required Date: July 2026 First Occupancy Expected: July 2026 MDU Address: [215 Lakeshore Blvd¦https://www.google.com/maps/search/215+Lakeshore+Blvd+City:+Toronto?entry=gmail&source=g] [City: Toronto¦https://www.google.com/maps/search/215+Lakeshore+Blvd+City:+Toronto?entry=gmail&source=g] Building Name - Pinnacle Lakeside # of Units: 1147 # of Floors: 49 Building First Occupancy Date or or time period of year, (eg. Mid 2026): July 2026 PM Contact Name: Anson Kwok PM Contact #: 416-925-3354 x 226 PM Email Address: [akwok@pinnacleinternational.ca¦mailto:akwok@pinnacleinternational.ca] Type of Contract (Fibre agreement or NUA & MA): Access & Marketing Building linked to other Buildings: No Bulk Related: No -- | GreenfieldChoice, PREWIRE | [12 empty] | 0¦i5enfz: | [7 empty] | 9.2234e+18 | [19 empty] | Dec 17, 2024 - Newbuilds email received. 215 Lakeshore - Residential Building Approved. Jan 9, 2025_OSP plan -no fiber capacity in CC6551 (S SIDE OF LAKESHORE BLVD E_ 20M W OF LOWER SHERBOURNE ST), Tie moved to CC6550. Jan 2025 note_ please note the Due date is based on the expected First Occupancy date of July 2026. | [6 empty] | 3 - Normal | [21 empty] | 2024-12-17 |  |  | 1147 | [5 empty] | https://buildings.beanfield.com/buildings/view/21044 |  | CONST-39511 | 3 - Normal |  | Toronto
Montreal Construction | MTLCONST-10012 | Westbury 9 - 4955/5055 Courtrai – 2 phases, 12 stories + parking, +/- 330 units | 4955/5055 Courtrai | Quebec | Condo | In Progress |  | Unresolved | Marianne Yanni | Marianne Yanni | Marianne Yanni | 2024-04-29 14:16 |  | 2025-02-11 11:18 |  |  | 2026-07-17 | 0 | 1 |  |  | MTLCONST-10016, MTLCONST-10017, MTLCONST-10713, MTLCONST-10723, MTLCONST-10724, MTLCONST-10725, MTLCONST-10726, MTLCONST-10727, MTLCONST-10728, MTLCONST-10729, MTLCONST-10730, MTLCONST-10790, MTLCONST-10799 | PUR-44209, MTLCONST-10011, MTLCONST-10013 | *For materials : WBS-MTLCONST-10012-2* bulk-internet services - residential projects being constructed by Devwah. * *_Westbury 9 - 4955/5055 Courtrai – 2 phases, 12 stories + parking, +/- 330 units_* Estimated Construction Start Date : Demolition of the existing buildings began on Monday, January 6, 2025. Estimated First Occupancy Date : August 2026 Site / Project Manager contact from Devwah : Service entrance : David Brault, dbrault@devwah.com, 514-516-2723. Building : Davide Boemio, dboemio@devwah.com, 514-651-4570. | [13 empty] | 0¦i4swqf: | [7 empty] | 9.2234e+18 | [19 empty] | 2025.01.06 Agreement is signed. 2025.01.13 Project started 2025.01.20 The basement of the 2 phases will be done at the same time, then they will build the 2 towers in 2 phases.Preliminary timelines: 1st tour: End of 2025 - Beginning of 2026, 2nd tour Summer 2026. Cable and P3000 equipment should be available in fall 2025. Design request sent to Trigenex | [6 empty] | 3 - Normal | [21 empty] | 2025-01-14 |  | 12 | 330 | Order |  | 43906.52 |  |  | https://buildings.beanfield.com/buildings/view/20187 |  | MTLCONST-10012 |  |  |  | 75243.55
Construction | CONST-35429 | 501 Yonge St / 18 Maitland Terr, Toronto - Teahouse Condos | 501 Yonge St / 18 Maitland Terr, Toronto | Ontario | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Olawale Olaniyan [X] | 2023-10-04 08:24 |  | 2025-02-11 14:56 |  |  | 2025-02-28 | 0 | 0 |  |  | CONST-35430, CONST-35431, CONST-35487, CONST-38675, CONST-38694, CONST-38695, CONST-38696, CONST-38697, CONST-38698, CONST-38699, CONST-38700, CONST-38701, CONST-38702, CONST-38703, CONST-38704, CONST-38705, CONST-38706, CONST-38774, CONST-38775, CONST-39119, CONST-39546, CONST-39570, CONST-39921 |  | Requested by Oliver Davies, Units 960 Floor 52 Can you please create a ticket for an OSP plan & site walk at the new “Teahouse Condos” at 501 Yonge St / 18 Maitland Terrace? There are 960 residential units that makeup the TSCC 2972 corporation. PM Info: *Kristie Pun* OLCM-L ¦ Condominium Manager ¦ *DUKA Property Management Inc.* As Agents for and on Behalf of T.S.C.C 2972 501 Yonge Street, Toronto, ON M4Y 0G8 Tel: 416-323-1430 ¦ Concierge: 416-929-8136 [teahouse.scm@dukamanagement.com¦mailto:teahouse.scm@dukamanagement.com] Thank you, | NUA+MA | [12 empty] | 0¦i4czrr: | [7 empty] | 9.2234e+18 | [19 empty] | Agreement signed Oct 2, 2024, 2 old budgets formates need to determine which budget should be applied? Oct 4 created task codes, Planning will begin shortly. Oct 7, 2024 Applied budget to SAP. Dec 16, 2024 - Hydro Permit note, hydro package ready to be submitted to Hydro. Dec 16, 2024 - Riser Panels - All panels installed per diagram Dec 16, 2024 - Riser Fibre Pull - Experiencing challenges roping the 501 Yonge side of the building. Dec 18, 2024 - Riser Diagram Completed January 13, 2025 Hydro Permit is granted D2024-00361 January 13, 2025 - Booking Hydro Access for January 29, 2025 January 13, 2025 - Cable pull scheduled for Jan 27 to 29, Hydro access appointment booked for January 29th 9:30 am, details in Cable Pull task code. January 14, 2025 - Conduit Build-Site walk completed, it is approx. 30m built to the existing pull box, conduit build scope completed. January 17, 2025 - Conduit Build Sketch - Troy has reached out to the pm for floor plans. January 21, 2025 - Cable Pull scheduled for Jan 27 to 29. Jan 27, 2025 - Cable pull in progress. January 21, 2025 - On Net Schedule Change, we moved this building from April to February. January 21, 2025 - conduit build sketch added. Jan 29, 2025, - OSP splicing only need cable pull to be completed, to complete OSP splicing. Jan 30th - Cable pull has been completed into building through vault. Will need to return once conduit is installed and pull to POP Feb 6, 2025 - Korey meeting with conduit manager feb 10, 2025 to discuss short conduit build in retail space. Feb 7, 2025 OSP Splicing completed, ready for testing. | [6 empty] | 3 - Normal | [21 empty] | 2024-10-02 |  | 52 | 960 | [5 empty] | https://buildings.beanfield.com/buildings/view/15219 |  | CONST-35429 | 3 - Normal |  | Toronto
Construction | CONST-26911 | 111 / 131 / 151 Upper Duke Cres, Markham - The Verdale I, II, Ⅲ | 111 / 131 / 151 Upper Duke Cres, Markham | Ontario | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Harvey Tran | 2022-02-22 12:13 |  | 2025-02-11 12:00 |  |  | 2025-07-02 | 0 | 1 |  |  | CONST-26928, CONST-26929, CONST-29794, CONST-29913, CONST-29914, CONST-29915, CONST-29916, CONST-29917, CONST-29918, CONST-29919, CONST-29920, CONST-29921, CONST-29922, CONST-29923, CONST-29924, CONST-29925, CONST-35055, CONST-37444, CONST-37541, CONST-38496, CONST-39617 | CONST-29425, CONST-26905, CONST-26906, CONST-26907, CONST-26908, CONST-26913, CONST-26914, CONST-26909, CONST-26910, CONST-31856 | *DELIO MARQUES* Property Manager, OLCM *YRSCC 1192 - The Verdale* 2645 Skymark Avenue Suite 101 ¦ Mississauga, ON L4W 4H2 Direct 905.479.3008 ¦ Cell phone 437.231.1116 Email [delio.marques@fsresidential.com¦mailto:delio.marques@fsresidential.com] | Bolton, Fiberstreamagreement, Markham | [12 empty] | 0¦i37s6v: | [7 empty] | 9.2234e+18 | [19 empty] | August 10th - Project started. Design and Permits to be in progress. Sep 14/23 - Construction scheduled to start on CONST-29425 Sep 21st Oct 12/23 - Construction started Oct 3rd on CONST-29425 May 8th, 2024 - Construction is delayed till end of Aug 2024 due to the other work is still in progress and the site is not ready for our work. Project is pushed back to end of Sep 2024. Sept 19, 2024_Email dated Sept 19, 2024, indicated this project needed to be rescheduled to July 2025, due to the City of Markham. Reference notes in the Backbone OSP Construction Sub-task Jan 6, 2025_Meeting Notes- This project is in the Construction stage. The Moratorium project is holding up this work from being completed. The city of Markham has indicated to Beanfield that the Moratorium work will be be completed April 15, 2025. Jan 15, 2025 - Splicing SOW have been completed Jan 15, 2025 - Po for Sentrex to design City permit was approved. Jan 27, 2025 - OSP splicing completed, but still waiting for cable pull to be completed. January 31, 2025 - OSP splicing is completed up to Cable pull. to return when cable pull is completed Feb 3, 2025 - OSP Splicing - Messy FOSC location, made attempt to fix it up. (this location the fosc here is very messy and difficult to work with.fixed it up as best as i could but trays have fibres that cannot be secured down and when you move the trays it cause outages) | [6 empty] | 3 - Normal | [19 empty] | Internal |  | 2022-08-10 |  | 14 | 450 |  |  | 8524 |  |  | https://buildings.beanfield.com/buildings/view/3675 |  | 500422 | 3 - Normal | 2023-10-13 | Markham | 13263 | 33385
Construction | CONST-27231 | 155 Legion Rd_Toronto_iLofts | 155 Legion Rd_Toronto_iLofts | Ontario | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Harvey Tran | 2022-03-09 14:17 |  | 2025-02-13 10:08 |  |  | 2025-05-14 | 0 | 0 | _thumb_1121752.png _thumb_1121753.png _thumb_1121754.png _thumb_1121758.png _thumb_1121759.png |  | CONST-27255, CONST-27256, CONST-30490, CONST-30491, CONST-30842, CONST-30843, CONST-30844, CONST-30845, CONST-30846, CONST-30847, CONST-30848, CONST-30849, CONST-30850, CONST-30851, CONST-30862, CONST-30863, CONST-30864, CONST-37940, CONST-39190, CONST-39324, CONST-39430, CONST-39561, CONST-39725 | CONST-27235, CONST-27237, CONST-33547, CONST-35974, CONST-38015, CONST-38017, CONST-38018, CONST-27238 | *PM information as of January 21, 2025:* Sylvia Dydyszko Condominium Manager 647-748-5757 [SDydyszko@mrcm.ca¦mailto:SDydyszko@mrcm.ca] | FSactive, Fiberstreamagreement, HumberBay | [12 empty] | 0¦i3938f: | [7 empty] | 9.2234e+18 | [19 empty] | November 11th - Project on hold. New backbone required. July 17, 2024_Project is Active and no longer on hold, New Backbone has been approved and in progress. Nov 18, 2024 - Riser Diagram completed for the 3 buildings Jan 6, 2025_Meeting Notes_ projects are moving well so we are moving these up in the schedule from July 2025 to May 2025. Feb 7, 2025 - We have been having issues with the Board at this location approving access for us to complete our work on-site. Feb 12, 2025 - OSP splicing in progress | [6 empty] | 3 - Normal | [21 empty] | 2022-09-14 |  | 27 | 254 |  |  | 51517 |  |  | https://buildings.beanfield.com/buildings/view/4020 |  | 500469 | 3 - Normal | 2025-07-31 | Etobicoke | 16683
Construction | CONST-24514 | 200 Bloor St West - Exhibit Residences | 200 Bloor St West | Ontario | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Harvey Tran | 2021-08-25 10:14 |  | 2025-02-13 10:06 |  |  | 2025-04-16 | 0 | 2 | _thumb_1124386.png |  | CONST-24515, CONST-24516, CONST-24759, CONST-24760, CONST-38258, CONST-39137, CONST-39138, CONST-39139, CONST-39140, CONST-39141, CONST-39142, CONST-39143, CONST-39144, CONST-39145, CONST-39146, CONST-39147, CONST-39148, CONST-39149, CONST-39150, CONST-39177, CONST-39571, CONST-39695 |  | Constructed in 2017 PM info: Julia Kalisperas [tscc2598admin@royalegrande.com¦mailto:tscc2598admin@royalegrande.com] 416-353-4641 BB: [https://buildings.beanfield.com/buildings/view/5608#!contacts] | NUA+MA | [12 empty] | 0¦i2vxrj: | [7 empty] | 9.2234e+18 | [19 empty] | Nov 8, 2024_Project approved, SAP Budget created, Sub task have been created. Added to the On Net schedule for April 22, 2024. Dec 17, 2024 - Riser Fiber Pull Completed Jan 8, 2025_PM would like Beanfield to set up an appointment to complete Panel prep work as well as the ISP SOW. JAN 15, 2025 - Panel Prep - All panels prepped and spliced January 17, 2025 - Hydro Permit Granted_D2024-00353 Expiry July 17, 2025 January ISP splicing in progress January 20, 2025- Progress of this building is going well, it is being moved up on the On Net schedule from April to February 2025. January 21, 2025, Vault Access appointment Confirmed from Scheduler for Feb 4, 10 am (Cable Pull details) Due to the fact, the PM will not allow us to gain access we are forced to reschedule this Vault Access appointment. January 21, 2025 - Unfortunatly, we had moved this condo up but the Condo PM, has informed Beanfield that they contractors working on the elevators until the end of March and do not want more then one contractor working in the building at the same time. Therefore we can not schedule internal work until the end of March. January 31, 2025 - OSP Splicing - Splicing completed up to the cable pull, need to return when cable pull is completed February 3, 2025 - Cable Pull is inprocess feb 3, 2025. Feb 11, 2025 - OSP Splicing Completed | [6 empty] | 3 - Normal | [21 empty] | 2024-11-08 |  | 22 | 204 | [5 empty] | https://buildings.beanfield.com/buildings/view/5608#!contacts |  | CONST-24514 | 3 - Normal |  | Toronto
Construction | CONST-5558 | 9 & 11 Bogert Ave, North York, Emerald Park Condos | 9 & 11 Bogert Ave, North York, Emerald Park Condos | Ontario | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Russell Francey | 2017-02-02 15:18 |  | 2025-02-14 08:02 |  |  | 2025-08-14 | 0 | 0 |  |  | CONST-5559, CONST-5560, CONST-5561, CONST-39820 |  | MDU Address: 9 Bogert Ave City: North York Building Name: Emerald Park # of Units: 573 # of Floors: 42 Building Constructed Year: 2015 Building First Occupancy Date or or time period of year, (eg. Mid 2026) PM Contact Name: *Karolina Mierzwa* PM Contact #: 416-730-8761 PM Email Address: [karolina.mierzwa@fsresidential.com¦mailto:karolina.mierzwa@fsresidential.com] Type of Contract (Fibre agreement or NUA & MA): A+M Building linked to other Buildings: n/a Bulk Related: no | [13 empty] | 0¦i0nxjz: | [7 empty] | 9.2234e+18 | [19 empty] | Old existing note, NA as of 2025_Never heard back from PM Jan 22, 2025_ CA Approved FTTB-00570 date Jan 21, 2025 ($25,690.47 includes $394.56 of Resto.), Agreements signed Jan 22, 2025 Jan 30, 2025 - On Net Schedule changes, James advised this could be moved from sep to aug. Feb 7, 2025 Site visit note -The current proposed tie-in point is THEP15652FA | [6 empty] | 3 - Normal | [21 empty] | 2025-01-22 |  | 40 | 573 | [5 empty] | https://buildings.beanfield.com/buildings/view/5582 |  | CONST-5558 | 3 - Normal | 2025-09-04 | North York Yonge & Eglinton (incl. North Yonge)
Construction | CONST-40044 | 10 Deerlick Crt, North York, The Ravine Condos | 10 Deerlick Crt, North York, The Ravine Condos | Ontario | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Lorna Kurok | 2025-02-12 14:37 |  | 2025-02-18 12:10 |  |  | 2025-05-28 | 0 | 0 |  |  | CONST-40045, CONST-40046, CONST-40047, CONST-40048, CONST-40049, CONST-40052, CONST-40053, CONST-40054, CONST-40055, CONST-40056, CONST-40057, CONST-40058, CONST-40059, CONST-40060, CONST-40061 | CONST-15175 | # of Units: *313* # of Floors: *29* Building Constructed Year: *2024* *PM Information as of February 12, 2025:* PM Contact Name: *Michael Liao (FS Residential)* PM Contact #: *437-246-6945* PM Email Address: [michael.liao@fsresidential.com¦mailto:michael.liao@fsresidential.com] Good Morning The below address was approved at the CAPEX meeting Wednesday, February 12th. CA with budget and Agreement attached MDU Address: *1 Deerlick Crt* City: *North York* Building Name: *The Ravine Condos* # of Units: *313* # of Floors: *29* Building Constructed Year: *2024* PM Contact Name: *Michael Liao (FS Residential)* PM Contact #: *437-246-6945* PM Email Address: [michael.liao@fsresidential.com¦mailto:michael.liao@fsresidential.com] Type of Contract (Fibre agreement or NUA & MA): *Access + Marketing* Building linked to other Buildings: *Yes - 1225 York Mills Rd (Rentals)* Bulk Related: *No* [https://buildings.beanfield.com/buildings/view/6811] | NUA+MA | [12 empty] | 0¦i5ir5j: | [7 empty] | 9.2234e+18 | [19 empty] | Feb 12, 2025_CA Approved Feb 12, 2025, FTTB-010006, Dated Feb 7, 2025. Received Marketing and Access Agreement. Feb 18, 2025 - Needed to Rename 1 Deerlick to 10 Deerlick | [6 empty] | 3 - Normal | [21 empty] | 2025-02-12 |  | 29 | 313 | [5 empty] | https://buildings.beanfield.com/buildings/view/6811 |  | CONST-40044 | 3 - Normal |  | North York
Construction | CONST-39794 | Contractor Pre-Wiring - 393 King St W, Toronto - The 393 On King | 393 King St W, Toronto | Ontario | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Lorna Kurok | 2025-01-22 15:29 |  | 2025-02-19 10:39 |  |  | 2025-04-15 | 0 | 0 |  |  | CONST-39795, CONST-39796 | CONST-35316 | Jan 22, 2025 - CA approved. *Cristina Tudor, RCM,* *OLCM* *Condominium Manager* ICC Property Management Ltd. 2875 14th Avenue, Suite 300 Markham, ON, L3R 5H8 905.940.1234 ext. 90 [ctudor@iccpropertymanagement.com¦mailto:ctudor@iccpropertymanagement.com] | PREWIRE | [12 empty] | 0¦i5h4x3: | [7 empty] | 9.2234e+18 | [19 empty] | Jan 22, 2025 - CA approved | [6 empty] | 3 - Normal | [20 empty] | 2024-12-11 | 2025-01-22 |  | 12 | 101 | [5 empty] | https://buildings.beanfield.com/buildings/view/3186 |  | CONST-39794 | 3 - Normal |  | Toronto
Construction | CONST-29127 | 85 The Donway, Toronto - Reflections Residences at Don Mills | 85 The Donway, Toronto | Ontario | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Jessica Markiewicz | 2022-07-11 07:28 |  | 2025-02-19 13:13 |  |  | 2025-03-28 | 0 | 1 |  |  | CONST-29128, CONST-29129, CONST-32535, CONST-32537, CONST-32538, CONST-32539, CONST-32540, CONST-32541, CONST-32542, CONST-32543, CONST-32544, CONST-32545, CONST-32546, CONST-32547, CONST-32548, CONST-32549, CONST-32550, CONST-35535, CONST-35536, CONST-38074, CONST-39559 | CONST-29124, CONST-38078, CONST-26996, CONST-35829 | {panel} Requested by Jay Fernandes Hi, I’ve gone through the remaining Fibrestream condos we have agreements for in the GTA and have grouped them in a way that I think makes sense for site visits and builds. There will be another list coming of buildings that don’t really fall into groups. Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. There are some current backbone (Sheppard) or NPOP (960 Lawrence) projects that will need to be completed to connect these but this will get everything into the system. Thanks! *PM: Nicole Roper* *nicole.roper@fsresidential.com* *416.444.8588* {panel} | Bolton, DonMills&Eg, FSactive, Fiberstreamagreement | [12 empty] | 0¦i3h5kf: | [7 empty] | 9.2234e+18 | [19 empty] | December 30th - Project initiated. Design and permits to be in progress. July 12/23 - City permit in progress. July 24/23 - City permit granted. Aug 15/23 - Pending City approval and schedule Sep 8/23 - Construction delay. Due dates updated. Oct 3/23 - Construction scheduled to start Oct 10th Oct 10/23 - Construction in progress Nov 23/23 - Due dates update. Waiting on building for construction approval Nov 27, 2024 - construction - Regarding Building request_(We've received a response from the corporation's solicitor with a number of requests, including having an engineer review. Josh Wignall and I will review today and provide our response to them. This project will likely need to wait until early Q1. ) Apr 03/24 - Still pending building construction approval. Due dates updated. July 23rd, 2023 - Still pending the approval from the building to start construction. Project due date is pushed back to Sep 2024. Sep 3rd, 2023 - We still dont have the approval from the building, pushing back this build to Oct 2024. Sep 9, 2024_ISP SOW Design has been revised. Oct 1, 2024 - Moved On Net schedule date to February 2025, due to 3rd party issue. Pending approval from building. Dec 3, 2024- Asbuilt notes No hard surface restoration Jan 6, 2025_Meeting Notes_Pushing 75 and 85 The Donway to March 2025 to allow more time to obtain approvals from Property Manager. Jan 28, 2025_On Net Schedule change. Moved both Donway (75 and 85) to May 2025 from March 2025. The reason is we are still waiting on permission form the Property Management. (this is with Josh Wignall) Josh has spoke again with PM, who would like to complete this by end of week Jan 31, 2025. But the challenge is with the board and the solicitor.)Updated Jira, SAP and the On Net schedule Feb 19, 2025 - Moved back to March 2025, construction is expected to be completed early march, so we believe we can complete this by the end of March. | [6 empty] | 3 - Normal | [19 empty] | Internal |  | 2022-12-30 |  | 12 | 105 | Integration |  | 14000 |  |  | https://buildings.beanfield.com/buildings/view/15598 |  | 500527 | 3 - Normal | 2023-10-27 | North York | 2420 | 14535
Construction | CONST-29124 | 75 The Donway, Toronto - Liv Lofts | 75 The Donway, Toronto | Ontario | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Jessica Markiewicz | 2022-07-11 07:26 |  | 2025-02-19 13:12 |  |  | 2025-03-28 | 0 | 1 |  |  | CONST-29125, CONST-29126, CONST-32536, CONST-32554, CONST-32555, CONST-32556, CONST-32557, CONST-32558, CONST-32559, CONST-32560, CONST-32561, CONST-38078, CONST-39558 | CONST-29127, CONST-35829, CONST-38074 | Requested by Jay Fernandes Hi, I’ve gone through the remaining Fibrestream condos we have agreements for in the GTA and have grouped them in a way that I think makes sense for site visits and builds. There will be another list coming of buildings that don’t really fall into groups. Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. There are some current backbone (Sheppard) or NPOP (960 Lawrence) projects that will need to be completed to connect these but this will get everything into the system. Thanks! *PM: Nicole Roper* *nicole.roper@fsresidential.com* *416.444.8588* | DonMills&Eg, FSactive, Fiberstreamagreement | [12 empty] | 0¦i3h5jr: | [7 empty] | 9.2234e+18 | [19 empty] | December 30th - Project initiated. Only ISP work. Will be fed from 85 The Donway. Nov 27, 2024 - construction - Regarding Building request_(We've received a response from the corporation's solicitor with a number of requests, including having an engineer review. Josh Wignall and I will review today and provide our response to them. This project will likely need to wait until early Q1. ) Nov 23/23 - Due dates update. Waiting on building for construction approval Apr 03/24 - Still pending building construction approval. Due dates updated. July 19th, 2024 - Korey has followed up with the building, they are still working out internally in order to provide us a go ahead for our work. Jul 23rd, 2023 - Still pending the approval from the building to start construction to 85 Donway. Project due date is pushed back to Sep 2024. Sep 3rd, 2023 - We still dont have the approval from the building, pushing back this build to Otc 2024. Oct 1, 2024_ pushing On Net due date to November 2024 Oct 1, 2024 - pushing 75 The Donway and 85 The Donway to February 2025, to pending property manager approval Jan 6, 2025_Meeting Notes_Pushing 75 and 85 The Donway to March 2025 to allow more time to obtain approvals from Property Manager. Jan 28, 2025_On Net Schedule change. Moved both Donway (75 and 85) to May 2025 from March 2025. The reason is we are still waiting on permission form the Property Management. (this is with Josh Wignall) Josh has spoke again with PM, who would like complete this by end of week Jan 31, 2025. But the challenge is with the board and the solicitor.) Updated Jira, SAP and the On Net schedule Feb 19, 2025 - Moved back to March 2025, construction is expected to be completed early march, so we believe we can complete this by the end of March. | [6 empty] | 3 - Normal | [21 empty] | 2022-12-30 |  | 14 | 171 | Integration |  |  |  |  | https://buildings.beanfield.com/buildings/view/15517 |  | 500528 | 3 - Normal | 2023-10-27 | Toronto | 5727
Construction | CONST-32609 | Kennedy Rd & Village Green Sq Condo Backbone | Kennedy Rd & Village Green Sq Condo Backbone | Ontario | Condo | In Progress |  | Unresolved | Brian Jackman | Denise King | David Chui | 2023-01-06 13:05 |  | 2025-02-20 11:11 |  |  | 2025-10-31 | 0 | 2 |  |  | CONST-32610, CONST-34795, CONST-40152 | CONST-26336, CONST-32622, CONST-32623, CONST-40076, CONST-40077, CONST-24038, CONST-26571 |  | Backbone | [12 empty] | 0¦i3s8w7: | [7 empty] | 9.2234e+18 | [19 empty] | Jan 9/23 - Budget sent for review & approval. Mar 20/23 - Oliver Davies is waiting for additional information relating to residential budgets before approving this budget. February 20/25 - Budget approved, SAP Project created & Capex report updated | [6 empty] | 3 - Normal | [25 empty] | Backbone |  | 365000 |  |  |  |  | CONST-32609 | 3 - Normal | 2025-10-31 | Scarborough | 7000 | 6000
Construction | CONST-36836 | Contractor Pre-Wiring - 45 Strachan Ave, Toronto | 45 Strachan Ave, Toronto | Ontario | Condo | In Progress |  | Unresolved | Unassigned | Lorna Kurok | Olawale Olaniyan [X] | 2024-03-13 14:40 |  | 2025-02-20 11:53 |  |  |  | 0 | 1 |  |  | CONST-38424, CONST-38425 | CONST-36518 | Requested by James Mowers *Updated Property Manager Information: January 22, 2025* Damon Thomas 647-660-1769 [Damon.Thomas-Anderson@bentallgreenoak.com¦mailto:Damon.Thomas-Anderson@bentallgreenoak.com] | CCS, PREWIRE | [12 empty] | 0¦i4ogyv: | [7 empty] | 9.2234e+18 | [19 empty] | January 16, 2025 First Occupancy June 2025 as per super. Occupancy schedule is attached. | [6 empty] | 3 - Normal | [32 empty] | CONST-36518(SUB) | 3 - Normal |  | Toronto
BC Construction | BCCONST-874 | 13685 102 Ave (Georgetown), Surrey BC | 13685 102 Ave (Georgetown), Surrey BC | British Columbia | Condo | New Condo |  | Unresolved | Josh Wignall | Yawn Paular | Yawn Paular | 2025-03-04 13:24 |  | 2025-03-04 16:26 |  |  | 2025-11-28 | 0 | 0 |  |  | BCCONST-877 | BCCONST-875 | 351 units 30 flrs Anthem Properties 8 phase building projects | BudgetPending | [12 empty] | 0¦i5kbnz: | [7 empty] | 9.22e+18 | [26 empty] | 3 - Normal | [24 empty] | 30 | 351 | [8 empty] | 3 - Normal |  | Surrey
BC Construction | BCCONST-875 | Whalley & Central Ave (Georgetown 2), Surrey BC | Whalley & Central Ave (Georgetown 2), Surrey BC | British Columbia | Condo | New Condo |  | Unresolved | Josh Wignall | Yawn Paular | Yawn Paular | 2025-03-04 13:26 |  | 2025-03-04 13:45 |  |  | 2025-11-28 | 0 | 0 |  |  | BCCONST-878 | BCCONST-874 | 355 units 31 Flrs Anthem Properties Occupancy Date: Late 2025 (assumption) | BudgetPending | [12 empty] | 0¦i5kbov: | [7 empty] | 9.22e+18 | [26 empty] | 3 - Normal | [13 empty] | 2025-10-01 13:24 | [10 empty] | 31 | 355 | [8 empty] | 3 - Normal |  | Surrey
BC Construction | BCCONST-873 | 13359 Old Yale Road (Holland Townline), Surrey BC | 13359 Old Yale Road (Holland Townline), Surrey BC | British Columbia | Condo | New Condo |  | Unresolved | Josh Wignall | Yawn Paular | Yawn Paular | 2025-03-04 13:20 |  | 2025-03-04 13:46 |  |  | 2025-08-29 | 0 | 0 |  |  | BCCONST-881 | BCCONST-644 | 250 units 25 flrs Close to existing FOSC at TEL MH-1078 Likely tied to 13387 Old Yale (Townline 2) | BudgetPending | [12 empty] | 0¦i5kbmv: | [7 empty] | 9.22e+18 | [26 empty] | 3 - Normal | [24 empty] | 25 | 250 | [8 empty] | 3 - Normal |  | Surrey
BC Construction | BCCONST-884 | 10581 140 St (Thrive/Domain/Dwell) | 10581 140 St (Thrive/Domain/Dwell) | British Columbia | Condo | New Condo |  | Unresolved | Josh Wignall | Yawn Paular | Yawn Paular | 2025-03-11 12:39 |  | 2025-03-18 12:50 |  |  | 2025-10-31 | 0 | 0 |  |  | BCCONST-885, BCCONST-890, BCCONST-892 |  | [10581 140 St¦https://www.google.com/maps/search/10581+140+St?entry=gmail&source=g] (Thrive) [10603 140 St¦https://www.google.com/maps/search/10603+140+St?entry=gmail&source=g] (Domain) [13963 105 Blvd¦https://www.google.com/maps/search/13963+105+Blvd?entry=gmail&source=g] (Dwell) Surrey, BC V3T 0M7 Assumption is one entrance to the property PM Contact Name: Mahyar Attar *(FS Residential)* PM Contact #: 604.683.8900 PM Email Address: _[Mahyar.Attar@fsresidential.com¦mailto:Mahyar.Attar@fsresidential.com]_ | BudgetPending | [12 empty] | 0¦i5kugn: | [7 empty] | 9.22e+18 | [26 empty] | 3 - Normal | [24 empty] | 6 | 345 | [8 empty] | 3 - Normal |  | Surrey
Construction | CONST-40460 | 327 King St W, Toronto, Empire Maverick | 327 King St W, Toronto, Empire Maverick | Ontario | Condo | Agreement |  | Unresolved | Unassigned | Lorna Kurok | Lorna Kurok | 2025-03-25 12:36 |  | 2025-03-25 13:52 |  |  |  | 0 | 0 |  |  | CONST-40461, CONST-40462, CONST-40463 |  | Condo Constructed in 2024: Units 310 Floors 49 | [13 empty] | 0¦i5m24v: | [7 empty] | 9.22e+18 | [19 empty] | March 19, 2025, CA budget approved by Beanfield board, Pending signed agreements. March 25, 2025 Ca budget created in SAP, Project added to Finance Capex tracker, Status is Agreement | [6 empty] | 3 - Normal | [24 empty] | 49 | 325 | [5 empty] | https://buildings.beanfield.com/buildings/view/20806 |  | CONST-40460 | 3 - Normal |  | Toronto
Construction | CONST-40465 | 284 King St E, Toronto, Bauhaus Condos | 284 King St E, Toronto, Bauhaus Condos | Ontario | Condo | Agreement |  | Unresolved | Unassigned | Lorna Kurok | Lorna Kurok | 2025-03-25 13:09 |  | 2025-03-28 14:51 |  |  |  | 0 | 0 |  |  | CONST-40466, CONST-40566, CONST-40567 |  | Units - 205 Floors 30 *Marcel Fatovic* ¦ Project Manager ELCIUM Construction Management LAMB Development Corp. 778 King Street West Toronto, Ontario, M5V 1N6 C – 647-862-4044 | NUA+MA | [12 empty] | 0¦i5m29j: | [7 empty] | 9.22e+18 | [19 empty] | March 25, 2025-James requested ticket, to store details pertaining to this location. March 27, 2025 - CA budget was approved at the March 26, 2025 capex meeting, project is pending agreements. March 28, 2025 - Project added to Financial Capex tracker. SAP budget Created. March 28, 2025 - Applied to the ON Net schedule for the Month of October 2025. March 28, 2025 - Design, Construction, Riser, Splicing task codes to be created when agreements are signed. | [6 empty] | 3 - Normal | [24 empty] | 30 | 205 | [5 empty] | https://buildings.beanfield.com/buildings/view/1445#!services |  | CONST-40465 | 3 - Normal |  | Toronto
Construction | CONST-40331 | 125 George Appleton Way, North York, Independence Way | 125 George Appleton Way, North York, Independence Way | Ontario | Condo | In Progress |  | Unresolved | Unassigned | Lorna Kurok | Lorna Kurok | 2025-03-14 9:24 |  | 2025-03-17 12:20 |  |  | 2025-08-21 | 0 | 0 |  |  | CONST-40338, CONST-40365 | CONST-29393, CONST-40330, CONST-40332, CONST-40333, CONST-40334, CONST-40335, CONST-40336, CONST-29402 | Building Constructed in 2014 125 George Appleton Way, units 32 Cluster combined units is 244 | FSactive, FibreStream, GeorgeAppletonCluster, Migraton | [12 empty] | 0¦i5l6en: | [7 empty] | 9.22e+18 | [19 empty] | March 11, 2025 - George Appleton Way Cluster Approved. Migration from FS to BF. March 17, 2025 - Added to On Net Schedule for Aug 21, 2025. | [6 empty] | 3 - Normal | [21 empty] | 2025-03-11 |  |  |  | 32 | Integration |  |  |  |  | https://buildings.beanfield.com/buildings/view/15582 |  | CONST-40330(sub) | 3 - Normal | 2025-08-21 | North York
Construction | CONST-40334 | 75 George Appleton Way, North York, Independence Way | 75 George Appleton Way, North York, Independence Way | Ontario | Condo | In Progress |  | Unresolved | Unassigned | Lorna Kurok | Lorna Kurok | 2025-03-14 9:57 |  | 2025-03-17 12:30 |  |  | 2025-08-21 | 0 | 0 |  |  | CONST-40368 | CONST-29393, CONST-40330, CONST-40331, CONST-40332, CONST-40333, CONST-40335, CONST-40336, CONST-29402 | Building Constructed in 2006 75 George Appleton Way units 24 Cluster units are 244 | FSactve, FibreStream, GeorgeAppletonCluster, Migraton | [12 empty] | 0¦i5l6lr: | [7 empty] | 9.22e+18 | [19 empty] | March 11, 2025 - George Appleton Way Cluster Approved. Migration from FS to BF. March 17, 2025 - Applied condo to the On net schedule for August 21, 2025. | [6 empty] | 3 - Normal | [21 empty] | 2025-03-11 |  |  |  | 24 | Integration |  |  |  |  | https://buildings.beanfield.com/buildings/view/15582 |  | CONST-40330(SUB) | 3 - Normal | 2025-08-21 | North York
Construction | CONST-40336 | 95 George Appleton Way, North York, Independence Way | 95 George Appleton Way, North York, Independence Way | Ontario | Condo | In Progress |  | Unresolved | Unassigned | Lorna Kurok | Lorna Kurok | 2025-03-14 10:11 |  | 2025-03-17 12:34 |  |  | 2025-08-21 | 0 | 0 |  |  | CONST-40370 | CONST-29393, CONST-40330, CONST-40331, CONST-40332, CONST-40333, CONST-40334, CONST-40335, CONST-29402 | Building Constructed in 2006 95 George Appleton units 32 Cluster Units are 244 | FSactve, Fibrestream, GeorgeAppletonCluster, Migration | [12 empty] | 0¦i5l6pb: | [7 empty] | 9.22e+18 | [19 empty] | March 11, 2025 - George Appleton Way Cluster Approved. Migration from FS to BF. March 17, 2025 - Applied to On Net Schedule for August 21, 2025 | [6 empty] | 3 - Normal | [21 empty] | 2025-03-11 |  |  |  | 32 | Integration |  |  |  |  | https://buildings.beanfield.com/buildings/view/15582 |  | CONST-40330(SUB) | 3 - Normal | 2025-08-21 | North York
Construction | CONST-40335 | 85 George Appleton Way, North York, Independence Way | 85 George Appleton Way, North York, Independence Way | Ontario | Condo | In Progress |  | Unresolved | Unassigned | Lorna Kurok | Lorna Kurok | 2025-03-14 10:05 |  | 2025-03-17 12:31 |  |  | 2025-08-21 | 0 | 0 |  |  | CONST-40369 | CONST-29393, CONST-40330, CONST-40331, CONST-40332, CONST-40333, CONST-40334, CONST-40336, CONST-29402 | Building Constructed in 2006 85 George Appleton Way units 24 Cluster Units 244 | FSactive, FibreStream, GeorgeAppletonCluster, Migration | [12 empty] | 0¦i5l6n3: | [7 empty] | 9.22e+18 | [19 empty] | March 11, 2025 - George Appleton Way Cluster Approved. Migration from FS to BF. March 17, 2025 - Applied condo to On net schedule for August 21, 2025 | [6 empty] | 3 - Normal | [21 empty] | 2025-03-11 |  |  |  | 24 | Integration |  |  |  |  | https://buildings.beanfield.com/buildings/view/15582 |  | CONST-40330(SUB) | 3 - Normal | 2025-08-21 | North York
Construction | CONST-40424 | 2 Aberfoyle Cres, Etobicoke, Town & Country II | 2 Aberfoyle Cres, Etobicoke, Town & Country II | Ontario | Condo | In Progress |  | Unresolved | Unassigned | Lorna Kurok | Lorna Kurok | 2025-03-21 9:34 | 2025-03-31 9:58 | 2025-03-21 13:57 |  |  | 2025-11-21 | 0 | 1 |  |  | CONST-40425, CONST-40426, CONST-40427, CONST-40428, CONST-40429, CONST-40430, CONST-40431, CONST-40432, CONST-40433, CONST-40434, CONST-40435, CONST-40436, CONST-40437, CONST-40438, CONST-40440 |  | Building Constructed Year: 2001 Aerial Feed. *+PM informations as of March 19, 2025:+* PM Contact Name: Alina Nima (FS Residential) PM Contact #: 416-233-9995 PM Email Address: [alina.nima@fsresidential.com¦mailto:alina.nima@fsresidential.com] Please see attached approved CA form and agreement. MDU Address: *2 Aberfoyle Cres* City: *Etobicoke* Building Name: *Town & Country II* # of Units: *116* # of Floors: *12* Building Constructed Year: *2001* PM Contact Name: *Alina Nima (FS Residential)* PM Contact #: *416-233-9995* PM Email Address: [alina.nima@fsresidential.com¦mailto:alina.nima@fsresidential.com] Type of Contract (Fibre agreement or NUA & MA): *Access + Marketing* Building linked to other Buildings: *1 Lomond Dr* Bulk Related: *No* [https://buildings.beanfield.com/buildings/view/16543] | NUA+MA | [12 empty] | 0¦i5ls1j: | [7 empty] | 9.22e+18 | [19 empty] | March 19, 2025 - Ca budget approved FTTB-00134, March 7, 2025, (Aerial) $40,080.00, Agreements signed March 4, 2025, Effective date March 31, 2025, Term 10 years March 19, 2025 - This Building is linked to 1 Lomond Dr, there is no existing ticket for this location.March 21, 2025 - Budget Added to SAP, Project added to Financial Capex tracker, Project is aerial, therefore there is no restoration budget, but it is listed on the Rest 2027 tracker, incase design changes. March 21, 2025 - The general sub task (Riser, Splicing, Financial) have been created because we have signed agreements and approved budget. Permit and Construction sub task will created upon the completion of the site visit. | [6 empty] | 3 - Normal | [21 empty] | 2025-03-19 |  |  | 12 | 116 | [5 empty] | https://buildings.beanfield.com/buildings/view/16543 |  | CONST-40424 | 3 - Normal | 2025-11-21 | Etobicoke
Construction | CONST-40330 | 105 George Appleton Way, North York, Independence Way | 105 George Appleton Way, North York, Independence Way | Ontario | Condo | In Progress |  | Unresolved | Unassigned | Lorna Kurok | Lorna Kurok | 2025-03-14 9:06 |  | 2025-03-17 11:07 |  |  | 2025-08-21 | 0 | 1 |  |  | CONST-40363 | CONST-29393, CONST-40331, CONST-40332, CONST-40333, CONST-40334, CONST-40335, CONST-40336 | George Appleton Cluster 105 George Appleton Way Suites 24 Cluster Units 244 Floors 21 Building Year 2013 | FSactive, FibreStream, GeorgeAppletonCluster, Migration | [12 empty] | 0¦i5l6an: | [7 empty] | 9.22e+18 | [19 empty] | March 11, 2025 - George Appleton Way Cluster Approved. Migration from FS to BF. | [6 empty] | 3 - Normal | [21 empty] | 2025-03-11 |  |  | 21 | 24 | Integration |  |  |  |  | https://buildings.beanfield.com/buildings/view/15582 |  |  | 3 - Normal | 2025-08-21 | North York
Construction | CONST-40333 | 65 George Appleton Way, North York, Independence Way | 65 George Appleton Way, North York, Independence Way | Ontario | Condo | In Progress |  | Unresolved | Unassigned | Lorna Kurok | Lorna Kurok | 2025-03-14 9:53 |  | 2025-03-17 12:25 |  |  | 2025-08-21 | 0 | 1 |  |  | CONST-40367 | CONST-29393, CONST-40330, CONST-40331, CONST-40332, CONST-40334, CONST-40335, CONST-40336, CONST-29402 | Building Constructed in 2006 65 George Appleton Way - 40 Units Cluster Units 244 | FSactive, Fibrestream, GeorgeAppletonCluster, Migration | [12 empty] | 0¦i5l6l3: | [7 empty] | 9.22e+18 | [19 empty] | March 11, 2025 - George Appleton Way Cluster Approved. Migration from FS to BF. March 17, 2025 - Applied to the On Net schedule for August 21, 2025. | [6 empty] | 3 - Normal | [21 empty] | 2025-03-11 |  |  |  | 40 | Integration |  |  |  |  | https://buildings.beanfield.com/buildings/view/15582 |  | CONST-40330(SUB) | 3 - Normal | 2025-08-21 | North York
Construction | CONST-40332 | 55 George Appleton Way, North York, Independence Way | 55 George Appleton Way, North York, Independence Way | Ontario | Condo | In Progress |  | Unresolved | Unassigned | Lorna Kurok | Lorna Kurok | 2025-03-14 9:46 |  | 2025-03-17 12:23 |  |  | 2025-08-21 | 0 | 1 |  |  | CONST-40366 | CONST-29393, CONST-40330, CONST-40331, CONST-40333, CONST-40334, CONST-40335, CONST-40336, CONST-29402 | Building Constructed in 2006 55 George Appleton Way Unit 36 Cluster Units 244 | FSactive, Fibrestream, GeorgeAppletonCluster, Migration | [12 empty] | 0¦i5l6jr: | [7 empty] | 9.22e+18 | [19 empty] | March 11, 2025 - George Appleton Way Cluster Approved. Migration from FS to BF March 17, 2025 - Applied to the On Net schedule for August 21, 2025. | [6 empty] | 3 - Normal | [21 empty] | 2025-03-11 |  |  |  | 36 | Integration |  |  |  |  | https://buildings.beanfield.com/buildings/view/15582 |  | CONST-40330(SUB) | 3 - Normal | 2025-08-21 | North York
Construction | CONST-40343 | 55 Lombard St, 80 Adelaide St E, Toronto, The Bentley (BULK) | 55 Lombard St, 80 Adelaide St E, Toronto, The Bentley (BULK) | Ontario | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Lorna Kurok | 2025-03-14 12:01 |  | 2025-03-26 13:31 |  |  | 2025-09-18 | 0 | 1 |  |  | CONST-40344, CONST-40346, CONST-40347, CONST-40348, CONST-40349, CONST-40350, CONST-40351, CONST-40352, CONST-40353, CONST-40354, CONST-40355, CONST-40356, CONST-40357, CONST-40358, CONST-40359, CONST-40372, CONST-40373, CONST-40374, CONST-40441 | CONST-35437 | MDU Address: 55 Lombard St, 80 Adelaide St E City:Toronto Building Name: *The Bentley* # of Units: *77* # of Floors: *6* Building Constructed Year: *1982* PM Contact Name:David Martins *(Brilliant)* PM Contact #: *416-363-4297* PM Email Address: *_[manager@thebentley.ca¦mailto:manager@thebentley.ca]_* Type of Contract (Fibre agreement or NUA & MA): *Access + Bulk Agreement* Building linked to other Buildings:n/a Bulk Related: *Yes* *Building Browser link:* [https://buildings.beanfield.com/buildings/view/3015] (55 Lombard St) 61 units [https://buildings.beanfield.com/buildings/view/4060] (80 Adelaide St E) 16 units | BulkDeal, NUA+Bulk, Rewire | [12 empty] | 0¦i5l7f3: | [7 empty] | 9.22e+18 | [19 empty] | March 14, 2025_Project approved. Access agreement and Bulk service agreement signed March 13, 2025 March 17, 2025- Site Notes_Budget has been added, We will first try and pull from our BFMH0065 and into the building via the vault, if this is note possible then a 25m trench will be needed. March 21, 2025 - 55 Lombard MUST ON NET OCT 1ST, 2025, the Rogers services will be disconnected On November 1st. 2025 March 26, 2025 - Rewire issued to Solutions401 | [6 empty] | 3 - Normal | [21 empty] | 2025-03-14 |  |  | 6 | 77 | [5 empty] | https://buildings.beanfield.com/buildings/view/3015 |  | CONST-40343 | 1 - Very High | 2025-09-18 | Toronto
Construction | CONST-40494 | 17 Kenaston Gardens, North York, NY Place Condos | 17 Kenaston Gardens, North York, NY Place Condos | Ontario | Condo | In Progress |  | Unresolved | Unassigned | Lorna Kurok | Lorna Kurok | 2025-03-26 11:10 |  | 2025-03-27 11:48 |  |  | 2025-06-17 | 0 | 1 |  |  | CONST-40495, CONST-40496, CONST-40497, CONST-40498, CONST-40499, CONST-40500, CONST-40501, CONST-40502, CONST-40503, CONST-40504, CONST-40505, CONST-40506, CONST-40507, CONST-40508, CONST-40509, CONST-40512, CONST-40521, CONST-40522, CONST-40523, CONST-40524 |  | *PM information as of March 26, 2025:* PM Contact Name: *Lee Boros (Performance PM)* PM Contact #: *416.645.3755 x512* PM Email Address: [lee@performancepm.com¦mailto:lee@performancepm.com] MDU Address: *17 Kenaston Gardens* City: *North York* Building Name: *NY Place Condos* # of Units: *135* # of Floors: *8* Building Constructed Year: *2012* PM Contact Name: *Lee Boros (Performance PM)* PM Contact #: *416.645.3755 x512* PM Email Address: [lee@performancepm.com¦mailto:lee@performancepm.com] Type of Contract (Fibre agreement or NUA & MA): *Access + Marketing* Building linked to other Buildings: *N/A* Bulk Related: *No* [https://buildings.beanfield.com/buildings/view/4756] | NUA+MA | [12 empty] | 0¦i5m72f: | [7 empty] | 9.22e+18 | [19 empty] | March 26, 2025 - CA Budget approved and signed agreements attached. March 26, 2025 - Ca budget added SAP, Project has been added to the Financial tracker. CA restoration budget has been added to Restoration tracker 2027. March 27, 2025 - Meeting with James, this will be a Small Short stream City Permit, therefore we moved it up from September 30, 2025 to June 17, 2025. If the project moves will, and the permit is recd, we might move it up to May. March 27, 2025 - Site visit is scheduled for April 1, 2025. | [6 empty] | 3 - Normal | [21 empty] | 2025-03-26 |  |  | 8 | 135 | [5 empty] | https://buildings.beanfield.com/buildings/view/4756 |  | CONST-40494 | 3 - Normal | 2025-09-30 | North York
Construction | CONST-40382 | 300 Balliol Street, Toronto | 300 Balliol Street, Toronto | Ontario | Condo | In Progress |  | Unresolved | Unassigned | Lorna Kurok | Lorna Kurok | 2025-03-19 15:06 |  | 2025-03-26 7:38 |  |  | 2025-11-24 | 0 | 1 |  |  | CONST-40383, CONST-40384, CONST-40385, CONST-40386, CONST-40387, CONST-40388, CONST-40389, CONST-40390, CONST-40391, CONST-40392, CONST-40393, CONST-40394, CONST-40395, CONST-40396, CONST-40397 |  | Building Year: 1999 *PM contact information as of March 19, 2025:* PM Contact Name: Diana Zarafa (Goldview) PM Contact #: [(416) 630-1234¦https://www.google.com/search?q=goldview+property+management&rlz=1C5GCEM_enCA1115CA1115&oq=goldview&gs_lcrp=EgZjaHJvbWUqCggAEAAYyQMYgAQyCggAEAAYyQMYgAQyBggBEEUYOTIKCAIQABiSAxiABDIHCAMQABiABDIHCAQQABiABDIHCAUQABiABDIHCAYQABiABDIGCAcQRRg90gEIMTM3MWowajSoAgCwAgE&sourceid=chrome&ie=UTF-8#] PM Email Address: [diane@goldview.ca¦mailto:diane@goldview.ca] Good Afternoon Please see below details and attached agreements MDU Address: 300 Balliol St City: *Toronto* Building Name: *300 Balliol St condos* # of Units: *118* # of Floors: *9* Building Constructed Year: *1999* PM Contact Name: Diana Zarafa (Goldview) PM Contact #: [(416) 630-1234¦https://www.google.com/search?q=goldview+property+management&rlz=1C5GCEM_enCA1115CA1115&oq=goldview&gs_lcrp=EgZjaHJvbWUqCggAEAAYyQMYgAQyCggAEAAYyQMYgAQyBggBEEUYOTIKCAIQABiSAxiABDIHCAMQABiABDIHCAQQABiABDIHCAUQABiABDIHCAYQABiABDIGCAcQRRg90gEIMTM3MWowajSoAgCwAgE&sourceid=chrome&ie=UTF-8#] PM Email Address: [diane@goldview.ca¦mailto:diane@goldview.ca] Type of Contract (Fibre agreement or NUA & MA): *Access + Marketing* Building linked to other Buildings:n/a Bulk Related: *No* *Building Browser link:* [https://buildings.beanfield.com/buildings/view/3801] – ¦Luke Baxter¦ ¦_Sr. Director, Strategy & Planning_¦ ¦ ¦*Office: 416.532.1555*¦ | NUA+MA, Rewire | [12 empty] | 0¦i5lm8f: | [7 empty] | 9.22e+18 | [19 empty] | March 19, 2025 - Condo approved Ca FTTB-01020, Dated March 14, 2025 and we has signed Access agreement, Dated March 11, 2025 and signed Marketing Agreement dated March 11, 2025 March 20, 2025 - Project added to Financial Capex tracker, Budget added to SAP, $40,340, Project has no restoration, but I did list it on the tracker. March 20, 2025 - Due to project having signed Agreements and approved budgets from the board, I am adding the general task tickets, (Riser, Splicing, Asbuilt), but I will add the other tickets (Permit, Construction, Conduit) when the High level budget is completed. March 20, 2025 - Approval Notes -Approval Note from Danny: This building will require a rewire due to the age of the building. We have received approval to build a new rewire team which is currently in motion. I'm sure this building will be pushed out till the end of the year, so we should have a team hired and working by then. Flag as Rewire. Changing due date from Sept 23, 2025(sep date 6months from approval date) to November 24, 2025 (November date reflection of additional work required-Rewire). March 25, 2025 - Requires Hydro Maps | [6 empty] | 3 - Normal | [24 empty] | 9 | 118 | [5 empty] | https://buildings.beanfield.com/buildings/view/3801 |  | CONST-40382 | 3 - Normal | 2025-09-23 | Toronto