## general_report
Project | JIRA_CONST_TICKET_ID | Summary | Issue Type | Status | Priority | Resolution | Assignee | Reporter | Creator | Created | Last Viewed | Updated | Resolved | Component/s | Due Date | Votes | Watchers | Images | Work Ratio | Sub-Tasks | Linked Issues | Description | Labels | Contact Attempts | Follow Up Date | Company LinkedIn | Team | Company Website | Revenue Estimate | Target start | Employee Estimate | Parent Link | Account Rep - Upsell | Original story points | Target end | Rank | Customer ID | customfield_10809 | Industry Group | Industry Segment | Sprint | End date | Epic Link | Rank (Obsolete) | Flagged | Epic/Theme | Current Phone Provider | Customer Address | Current Phone Expiry Date | BOSS_LINK | Development | SWAT_LINK | DUNS # | Building_Link | customfield_10809 | Building Name | Customer Phone Number | Date Time Contacted | Current Internet Expiry Date | Current Internet Provider | Switch Budget | Theme | customfield_10809 | Last Action | Customer Phone | Customer Email | Location Z Email | Location A Phone | Location Z Phone | Service Type | Scheduling Priority | Location A Name | Location Z Name | Location A Email | Package Link | Customer | Workstream | Customer Attention | Customer Delivery Instructions | Security Level | Planned Start | Planned End | Original Due Date | Follow-up | Scheduled Time | Past Due | Total Due | Fix Version/s | customfield_10809 | Installation Date | Work By | Building On Net | Start date | Distance (M) | Occupancy Date | # Floors | # Units | Sub-Project | Completed Date | Contractor Budget | Actual | Difference | Building Browser Link | Confluence Link | Project # | Construction Priority | Original Due Date | City | Materials Budget | Labour Budget | Installer | Work Started | Prewired | Rent or Own | Email Address | Supporting Manager | Story Link | Approved By | Rejected By | Location | Reason for Leave | Return to Work Date | Budget Type | Monthly Payment | Planning Priority | Wop Funding | Application | Class of Service
Construction | CONST-33014 | 95 McMahon Dr, North York | Condo | Restoration |  | Unresolved | Harvey Tran | Lorna Kurok | Olawale Olaniyan [X] | 2023-02-07 10:56 | 2025-03-28 09:56 | 2024-12-11 11:45 |  |  | 2024-09-30 | 0 | 1 | _thumb_922191.png _thumb_922190.png _thumb_922189.png |  | CONST-33015, CONST-33016, CONST-33061, CONST-34955, CONST-34956, CONST-34957, CONST-34958, CONST-34959, CONST-34960, CONST-34961, CONST-34962, CONST-34963, CONST-34964, CONST-34965, CONST-34966, CONST-34967, CONST-34968, CONST-34969, CONST-38030, CONST-38031, CONST-38035, CONST-38176, CONST-38570, CONST-38571 | CONST-29186, CONST-32336, CONST-32339, CONST-32342, CONST-32592, CONST-32595, CONST-32880, CONST-33876, CONST-29180, CONST-32349 | Requested by Oliver Davies: Could you kindly queue up a site walk for 5-95 McMahon Dr? This is a newly registered condo w/ 692 units that should tie in well with our existing projects on McMahon Dr & Singer Crt. *NEW PM INFO:* *_Mark Mak, OLCM, RCM_* Condominium Manager As Agents for and on behalf of TSCC 2912 *Seasons and Seasons II* ** 95 McMahon Drive, North York, Ontario M2K 0H2 Telephone: 416-224-2253 E-mail: +[waikeong.mak¦mailto:waikeong.mak@crossbridgecs.com]+ E-mail: ** [seasons@crossbridgecs.com¦mailto:seasons@crossbridgecs.com] PM info: *Ted Blomme* On Behalf of TSCC 2912 Seasons and Seasons 2 Condominiums 95 McMahon Drive, North York, ON, M2K 0H2 Telephone Management Office: 416-224-2253 Concierge Desk 24 Hours: 416-223-8496 Email: [seasons@crossbridegecs.com¦mailto:seasons@crossbridegecs.com] [edward.blomme@crossbridgecs.com¦mailto:edward.blomme@crossbridgecs.com] [www.crossbridgecondominiums.com¦http://www.crossbridgecondominiums.com/] Thanks! | NUA+MA | [12 empty] | 0¦i3umhb: | [7 empty] | 9.2234e+18 | [19 empty] | July 28/23 - Project initiated. Design and Permits in progress. There's one budget for both 95 & 85 McMahon Dr. Feb 14/24 - City permit on CONST-34335 Jul 12th 2024 - City permit is in, Construction will be a portion of the backbone build and will be scheduled later. Aug 1, 2024 - Construction is still pending schedule. Pushing this building on-net date to Sep 2024. Sept 4, 2024_OSP splicing Completed Sept 9, 2024 - ISP Splicing has been completed Sept 19, 2024- ISP Cross Connects Completed. Sept 19, 2024 - OTDR / Ruby Test Completed Sep 19, 2024 - On Net email sent. | [6 empty] | 3 - Normal | [19 empty] | External |  | 2023-07-28 | [5 empty] | 2024-09-19 | 1086 |  |  | https://buildings.beanfield.com/buildings/view/16956 |  | CONST-33014 | 3 - Normal | 2024-05-31 |  | 12560 | 26160
Construction | CONST-6205 | 99 John Street_Toronto_ PJ Condos | Condo | Restoration |  | Unresolved | Lorna Kurok | Lorna Kurok | Russell Francey | 2017-05-30 13:33 |  | 2024-12-11 11:49 |  |  | 2024-08-16 | 0 | 1 | _thumb_947869.png _thumb_948914.png |  | CONST-28672, CONST-28673, CONST-30647, CONST-31926, CONST-31927, CONST-31928, CONST-31929, CONST-31930, CONST-31931, CONST-31932, CONST-31933, CONST-31937, CONST-31954, CONST-31955, CONST-31956, CONST-31957, CONST-36129, CONST-36130, CONST-37035, CONST-37036, CONST-37799, CONST-37800, CONST-38345, CONST-38531 | CONST-25914 | Could you please proceed with creating a request for site walk at 283 Adelaide St W & 99 John St (PJ Condos), the Status can also be set to Open. JIRA: https://tickets.beanfield.com/browse/CONST-6205 BB Link: [https://buildings.beanfield.com/buildings/view/14929] +*PM Info:*+ *Alex* Condominium Manager PJ Condos 99 John Street Toronto, ON M5V 0S6 Phone: (416) 596-1954 [pjcondos.pm@delcondo.com¦mailto:pjcondos.pm@delcondo.com] (or alternatively, Andrew [pjcondos.admin@delcondo.com¦mailto:pjcondos.admin@delcondo.com]) | NUA+MA | [12 empty] | 0¦i0rchb: | [7 empty] | 9.2234e+18 | [19 empty] | January 4th - The Condo board decided that no ISP work can be initiated until May 2nd, 2023. Route drawing completed. Surveys to be scheduled. Aug 3/23 - Hydro permit not submitted yet. Due dates updated. Oct 12/23 - Hydro permit not submitted yet. Due dates updated. Jan 11/24 - Route drawing uploaded Mar 08/24 - Manhole survey in progress Mar 21/24 - Manhole survey completed Apr 09/24 - Hydro permit submitted Apr 15/24 - PO sent for Hydro permit May 31st, 2024 - City permit is granted. Locates submitted. Aug 9, 2024 - 24 FTO fibre was pulled. Unsure if building needs to be added to patch manager. Aug 9, 2024 - Cable Pull asbuilts completed. Aug 16th, 2024 - Testing is scheduled for next week. Aug 16th, 2024 - Testing completed, building is onnet. | [6 empty] | 3 - Normal | [19 empty] | External |  | 2022-11-16 | [5 empty] | 2024-08-16 | 42771 |  |  | https://buildings.beanfield.com/buildings/view/6145 |  | 500506 | 3 - Normal | 2023-06-30 | Southcore | 4948 | 14000
Construction | CONST-31357 | 357 King St W, Toronto | Condo | Restoration |  | Unresolved | Lorna Kurok | Lorna Kurok | Jessica Markiewicz | 2022-10-24 11:21 |  | 2024-12-11 11:56 |  |  | 2024-08-14 | 0 | 1 |  |  | CONST-31358, CONST-31359, CONST-31871, CONST-36585, CONST-36586, CONST-36587, CONST-36588, CONST-36589, CONST-36590, CONST-36591, CONST-36592, CONST-36593, CONST-36594, CONST-36595, CONST-36596, CONST-36597, CONST-36598, CONST-36879, CONST-36882, CONST-37237, CONST-37996, CONST-37997, CONST-38441, CONST-38442 | CONST-31527, CONST-27533 | Requested by Oliver Davies. Can you please queue up a site walk for 357 King St W? BB Link: [https://buildings.beanfield.com/buildings/view/7023] *NEW PM Info:* *Allison Baker* Condominium Manager ¦ TSCC 2963 *Agents for and on behalf of:* *357 King Street West* *Toronto, Ontario, M5V 0S7* *Phone: 416-598-3528* *Email:* +[357King.PM@Delcondo.com¦mailto:357King.PM@Delcondo.com] PM Info: In Kim 647.829.2617 [357king.pm@delcondo.com¦mailto:357king.pm@delcondo.com] This building recently began occupancy in August. Great Gulf has a bulk arrangement with Rogers for what we understand is 1x year post occupancy. I would like to get a plan in place for this location so we can prepare to launch as soon as it is viable for us. Hard hats / steel toes are required on-site currently. | NUA+MA | [12 empty] | 0¦i3nz33: | [7 empty] | 9.2234e+18 | [19 empty] | October 28th - Site Visit requested. Feb 21/24 - Project initiated. Design and Permits in progress Mar 08/24 - SS city permit application has been submitted Mar 22/24 - Redesign required. Due dates updated. Mar 25/24 - City permit granted. July 9th, 2024 - Construction completed. Cable pull is also scheduled. Aug 15th, 2024 - Testing completed. Building is onnet. Pending restoration | [6 empty] | 3 - Normal | [19 empty] | Internal |  | 2024-02-21 | [5 empty] | 2024-08-14 | 38795 |  |  | https://buildings.beanfield.com/buildings/view/7023 |  | CONST-31357 | 3 - Normal | 2024-06-28 |  | 7127 | 15455
Construction | CONST-32361 | 66 Forest Manor Rd, Toronto - Emerald City Ⅱ | Condo | Restoration |  | Unresolved | Lorna Kurok | Lorna Kurok | Jessica Markiewicz | 2022-12-14 10:55 |  | 2024-10-22 15:31 |  |  | 2024-08-30 | 0 | 3 | _thumb_931696.png _thumb_931695.png _thumb_931712.png _thumb_931711.png |  | CONST-32362, CONST-32363, CONST-33974, CONST-34924, CONST-34925, CONST-34926, CONST-34927, CONST-34928, CONST-34929, CONST-34930, CONST-34931, CONST-34932, CONST-34933, CONST-34934, CONST-34935, CONST-34936, CONST-34937, CONST-34938, CONST-35378, CONST-36763, CONST-37949, CONST-38032, CONST-38853, CONST-38854 | CONST-33772, CONST-29216, CONST-29219, CONST-29207, CONST-12142, CONST-29210 | Requested by Oliver Davies: Could you kindly create a site walk ticket for James at 66 Forest Manor Rd / Emerald City II? This is an active FibreStream building that should be included as part of the MDU group in this neighbourhood, it’s a dense pocket of condos and I believe this location was missed initially. NEW PM INFO: *Katerina Antoniadis, OLCM – LL- Condominium Manager* *Agents for and on behalf of: TSCC No. 2407* *Emerald City 2, 66 Forest Manor Road, North York M2J 0B7* *Phone:* 416-496-1772 *Fax:* 416-496-1502 *Email:* emeraldcity2.pm@DelCondo.com PM Info: ¦Property Manager¦ ¦ ¦Barbara E. Eplett¦ ¦ ¦416-496-1772¦ ¦ ¦[emeraldcity2.pm@DelCondo.com¦mailto:emeraldcity2.pm@DelCondo.com]¦ ¦ ¦[EmeraldCity2.Admin@delcondo.com¦mailto:EmeraldCity2.Admin@delcondo.com]¦ ¦ ¦ ¦ ¦ ¦ ¦ ¦ ¦Admin： Musa Pathan¦ ¦ | FSactive, Fiberstreamagreement | [12 empty] | 0¦i3r7rb: | [7 empty] | 9.2234e+18 | [19 empty] | May 01/23 - Forest Manor is under moratorium until the end of 2025. July 28/23 - Moratorium on Forest Manor will not affect this build. Project initiated. Design and Permits in progress. Mar 04/24 - Short stream city permit submitted Mar 06/24 - Short stream city permit granted Mar 14/24 - Locates completed Aug 2, 2024-ISP OSP plans for the buildings on Forest Manor Rd should be completed the week of Aug 5 to 9 2024. AUG 8, 2024 - Korey has scheduled to have a crew on site Wednesday Aug 14th to Aug 15. Aug 8, 2024 - Panel prep completed (closed) Aug 30th, 2024 - Testing completed, building is onnet. Only internal work to be required. Putting the project as "Clean up" | [6 empty] | 3 - Normal | [19 empty] | Internal |  | 2023-07-28 |  |  |  |  | Integration | 2024-08-30 | 30420 |  |  | https://buildings.beanfield.com/buildings/view/16281 |  | CONST-32361 | 3 - Normal | 2024-05-31 |  | 7646 | 16495
Construction | CONST-29210 | 52 Forest Manor Rd, Toronto - Colours of Emerald City - Phase IV | Condo | Restoration |  | Unresolved | James Mowers | Lorna Kurok | Jessica Markiewicz | 2022-07-11 15:30 |  | 2025-02-19 08:00 |  |  | 2025-02-21 | 0 | 0 |  |  | CONST-29211, CONST-29212, CONST-33976, CONST-33983, CONST-33984, CONST-33985, CONST-33986, CONST-33987, CONST-33988, CONST-33989, CONST-33990, CONST-33991, CONST-33992, CONST-33993, CONST-33994, CONST-33995, CONST-33996, CONST-33997, CONST-33998, CONST-33999, CONST-34000, CONST-37964, CONST-38091, CONST-38092, CONST-39560, CONST-39700 | CONST-33772, CONST-29216, CONST-29219, CONST-29207, CONST-12142, CONST-32361 | New Property Manager Sept 17, 2024: Maria Bramsome *Agent for and on behalf of T.S.C.C. 2654* *52 Forest Manor Road* *Toronto, Ontario M2J 0E2* *Phone:* 416-756-3323 *Fax:* 416-756-2238 *Email:* [coloursofemeraldcity.pm@delcondo.com¦mailto:coloursofemeraldcity.pm@delcondo.com] Requested by Jay Fernandes Hi, I’ve gone through the remaining Fibrestream condos we have agreements for in the GTA and have grouped them in a way that I think makes sense for site visits and builds. There will be another list coming of buildings that don’t really fall into groups. Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. There are some current backbone (Sheppard) or NPOP (960 Lawrence) projects that will need to be completed to connect these but this will get everything into the system. Thanks! *PM: Alexandrina Irini* *coloursofemeraldcity.pm@delcondo.com* | Bolton, FSactive, Fiberstreamagreement, Sheppard | [12 empty] | 0¦i3h86n: | [7 empty] | 9.2234e+18 | [19 empty] | May 01/23 - Forest Manor is under moratorium until the end of 2025. - Does not affect the build May 18/23 - Project initiated. Design & Permits in progress. July 19/23 - Hydro permit not required. Mar 04/24 - Locate completed Aug 2024_ Waiting on Concurrence letter from property manager. We Require this letter for the City Permit. Aug 20, 2024 - Riser Build Completed , all panels spliced - ISP Splicing Remains Sept 19, 024_Note from Construction (Damaged Poles in the area to be avoided. Very expensive sidewalks to be avoided. Pictures attached. Oct 1, 2024_moving 50 and 52 forest Manor to the December 2024 on the ON Net schedule. We are waiting on a permit, redesign required, due PM not agreeing to have a vault. Nov 22, 2024 moving project from December 2024 to February 27, 2025, due to pending permits. Jan 10, 2025_Redline permit attached. Jan 21, 2025 - OSP construction completed (scheduling roping an cable pull for Thursday January 23, 2025.) Jan 21, 2025- conduit build note -Core at POE has been completed. Feb 3, 2025 - Conduit Build Completed. Feb 4, 2025 - OSP Cable is being pulled on Feb 4, 2025 Feb 4, 2025 - On Net scheduled to be ON net for feb 12, 2025. Feb 12, 2025 - On net date moved to feb 13 as per noted by Kevin Sherman in the ON Net ticket. Feb 11, 2025 - City and cable pull asbuilt are attached. Feb 11, 2025 - Asbuilt notes that Hard surface restorations are required. Feb 12, 2025 - OTDR Ruby testing note: Splicing is complete, ready for testing. Feb 18, 2025 - Building is On Net. Feb 18, 2025 - Asbuilts completed, Requires Hard surface restorations, need to reconcile Finances | [6 empty] | 3 - Normal | [19 empty] | Internal | 2025-02-18 | 2023-05-18 |  |  | 13 | 245 | Integration | 2025-02-18 | 54835 |  |  | https://buildings.beanfield.com/buildings/view/6556 |  | CONST-29210 | 3 - Normal | 2024-03-29 | Toronto | 6040 | 14835
Construction | CONST-29204 | 399 Spring Garden Ave, North York - Jade Condos | Condo | Restoration |  | Unresolved | Lorna Kurok | Lorna Kurok | Jessica Markiewicz | 2022-07-11 15:23 |  | 2025-02-20 14:59 |  |  | 2024-12-19 | 0 | 2 |  |  | CONST-29205, CONST-29206, CONST-36489, CONST-36490, CONST-36491, CONST-36492, CONST-36493, CONST-36494, CONST-36495, CONST-36496, CONST-36499, CONST-36500, CONST-36501, CONST-36502, CONST-36503, CONST-36504, CONST-36505, CONST-38490, CONST-38491, CONST-38751, CONST-39612, CONST-39613 |  | Requested by Jay Fernandes Hi, I’ve gone through the remaining Fibrestream condos we have agreements for in the GTA and have grouped them in a way that I think makes sense for site visits and builds There will be another list coming of buildings that don’t really fall into groups. Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. There are some current backbone (Sheppard) or NPOP (960 Lawrence) projects that will need to be completed to connect these but this will get everything into the system. Thanks! +*NEW PM Info:*+ *Jenie Del Mundo OLCM, RCM* *Property Manager* *Y.L.Hendler Ltd.* *(416) 227-1808* [tscc2394pm@gmail.com¦mailto:tscc2394pm@gmail.com] *OLD PM: Susan Bailey* [¦https://tickets.beanfield.com/secure/AddComment!default.jspa?id=745552] *tscc2394pm@gmail.com* *416.227.1808* | Fiberstreamagreement, Sheppard | [12 empty] | 0¦i3h83j: | [7 empty] | 9.2234e+18 | [19 empty] | Feb 07/24 - Project initiated. Design and permits in progress. Apr 02/24 - SS City permit submitted. Apr 15/24 - City permit granted Apr 24/24 - Locates completed Nov 12, 2024 Project was moved to December 2024 from November 2024 on the ON Net schedule. Reason is due to the city requesting our RoDars to Start Dec 2, 2024. Changing On net date to December 30,2024. Nov 14, 2024 - Riser and Panels completed. Dec 10, 2024 - Cable Pull Asbuilt attached. Dec 19, 2024 - Building On Net Feb 3, 2025 - City asbuilt attached. Feb 20, 2025 -Asbuilt notes states that sod is needed in spring and shrubs are required. this note has been added to the restoration tracker. | [6 empty] | 3 - Normal | [19 empty] | External |  | 2024-02-07 |  |  |  | 344 |  | 2024-12-19 | 34920 |  |  | https://buildings.beanfield.com/buildings/view/4545 |  | CONST-29204 | 3 - Normal | 2024-11-29 | North York | 6886 | 14675
Construction | CONST-27867 | 12 Sudbury St, Toronto | Condo | Restoration |  | Unresolved | Harvey Tran | Olawale Olaniyan [X] | Harvey Tran | 2022-04-19 09:18 |  | 2025-02-27 09:54 |  |  | 2024-07-10 | 0 | 0 |  |  | CONST-27868, CONST-27869, CONST-28674, CONST-28675, CONST-28676, CONST-28677, CONST-28678, CONST-28679, CONST-28680, CONST-28681, CONST-28682, CONST-28683, CONST-28684, CONST-29689, CONST-31511, CONST-31517, CONST-31558, CONST-31816, CONST-35482, CONST-35483, CONST-35628, CONST-36144, CONST-36226, CONST-36227, CONST-36228, CONST-36229, CONST-38849, CONST-38850, CONST-38998 | NET-37999, CONST-3134, CONST-9777, CONST-30055 |  | Fiberstreamagreement | [12 empty] | 0¦i3bxdr: | [7 empty] | 9.2234e+18 | [19 empty] | January 4th - Hydro permit granted. City permit submitted. Apr 24/23 - City permit approved, expires Oct 20th May 17/23 - Pending locates. Aug 23/23 - Pending construction schedule. Oct 3/23 - Construction scheduled to start Nov 6th. Due dates updated. Oct 11/23 - Construction rescheduled to start Nov 13th Nov 08/23 - Construction rescheduled to start Nov 27th Jan 04/24 - Construction completed. Jan 26/24 - Cable pull completed. Jan 31/24 - Splicing in progress Feb 14/24 - SOW redesign required. Delay to splicing. Feb 16/24 - Migration needed to bring this On-Net May 9th, 2024 - Still pending SOW due to migration. Requested an update from GIS. Project due date is possibly pushed back if migration delays. May 23rd, 2024 - Migration is no more required in order to have the SOW completed for this group of building. SOW will be completed soon. Jun 20th, 2024 - Splicing completed. Testing to be scheduled soon. Jun 28th, 2024 - Project is pushed back to July as the OLT insertion needs to be completed in prior (NET-37999) Jul 10th, 2024 - Testing completed. Project is onnet. | [6 empty] | 3 - Normal | [19 empty] | Internal |  | 2022-06-06 |  |  | 34 | 180 |  | 2024-07-10 | 31876 |  |  | https://buildings.beanfield.com/buildings/view/17436 |  | 500467 | 3 - Normal |  |  | 4605 | 17880
Construction | CONST-34253 | 28 Olive Ave, North York | Condo | Restoration |  | Unresolved | Lorna Kurok | Lorna Kurok | Olawale Olaniyan [X] | 2023-06-07 08:59 |  | 2025-02-25 10:59 |  |  | 2025-02-20 | 0 | 0 | _thumb_1003322.png |  | CONST-34254, CONST-34255, CONST-34256, CONST-37129, CONST-37130, CONST-37131, CONST-37132, CONST-37133, CONST-37134, CONST-37135, CONST-37136, CONST-37137, CONST-37138, CONST-37139, CONST-37140, CONST-37141, CONST-37149, CONST-37872, CONST-38476, CONST-38477, CONST-39361, CONST-39557 | CONST-29816 | Requested by Oliver Davies. Can we get another site walk setup for 26 & 28 Olive Ave? There are two separate corporations here, the same PM manages both. PM Info: *Erlis Lleshi* Property Manager, OLCM *Agents for and on behalf of: TSCC 1506, TSCC 1515 & Princess Place Shared Facility* *Princess Place* *Phone:* 416-987-1595 *Fax:* 416-987-0063 *Email:* [princessplace@DelCondo.com¦mailto:princessplace@DelCondo.com] Note, 20 & 22 Olive Ave are part of the same series of buildings, not included on this site walk. These are all net-new and we will ultimately be seeking access to all 4x towers. Thanks for your help! | NUA+MA | [12 empty] | 0¦i4376n: | [7 empty] | 9.2234e+18 | [19 empty] | Apr 25/24 - Project initiated. Design and permits in progress Aril 19, 2024 - Agreement signed. Aug 30, 2024_Waiting for building Engineers to review our plans . Approval is a challenge with location. Jan 6, 2025_Meeting update Oliver is anticipated to have a meeting with PM for 26 and 28 Oliver. These buildings are On Net schedule but these buildings have been moved on the schedule due to the Property Managers issue. If the property management allows us to access the Condo's to work inside the building then we can meet the schedule. PM approval has been the challenge. Jan 20, 2025 - OSP splicing In progress and completed to 38 Olive BFHW, need to return when cable is pulled. Feb 11, 2025 - Riser Fibre Pull -28 olive Riser 1213ft pop 1296 83ft/26m+ 10m = 36m Feb 11, 2025 - Riser Panels - Installed 3/4 panel. 1 panel on the 9th need 3rd sheet. feb 14, 2025 - Cable pull asbuilt attached Feb 20, 2025 - Building On Net, Requires Hard surface restoration (Needs 1 Sidewalk Bay & Needs 4 Alping currant shrubs in the spring of 2025 as per pm (Glen Ecno$24.99ea), Asbuilts recd, | [6 empty] | 3 - Normal | [19 empty] | Internal | 2025-02-20 | 2024-04-25 |  |  | 16 | 176 |  | 2025-02-20 | 16242 |  |  | https://buildings.beanfield.com/buildings/view/1859 |  | 500504 | 3 - Normal | 2024-09-27 | North York | 6084 | 18970
Construction | CONST-33619 | 169 John St, Toronto | Condo | Not a candidate |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2023-04-11 14:44 |  | 2023-06-28 08:10 |  |  |  | 0 | 0 |  |  | CONST-33620, CONST-33621 |  | Requested by Oliver Davies, Can you please create a new OSP plan & request for site walk at 169 John St? This is a small building with only 44 units, however we already have fibre going to 171, 172, 179 & 180 John St and we may be able to get into the building at a low cost via BFMH-0024. PM Info: *Nikita Vasiliev* *Property Manager, OLCM-L* Tel: 416.304.0867 Email: nikita[@whitehillresidential.com¦mailto:elamcja@whitehillresidential.com] Thank you, | [13 empty] | 0¦i3yvyv: | [7 empty] | 9.2234e+18 | [19 empty] | June 28/23 - Marked as Not a Candidate due to high cost of expansion for only 44 units. As per Oliver Davies | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/2765 |  |  | 3 - Normal
Construction | CONST-33285 | 1486 Bathurst St, Toronto | Condo | Not a candidate |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2023-03-10 08:07 |  | 2023-03-13 07:12 |  |  |  | 0 | 0 |  |  | CONST-33286, CONST-33287 |  | Requested by Oliver Davies Can you please queue up a site walk for 1486 Bathurst St? This is a smaller building with only 93 units, however we should have an easy & cost-effective route pulling from CDSM13520 located immediately outside of the building. 500 St Clair Ave W & 530 St Clair Ave W are also next door - I am still awaiting an agreement from 500 so that we can initiate builds for these 2x locations. PM Info: Ingrid Kulik Property Manager TSCC 2787 – 1486 Bathurst St Toronto, ON M5P 0A5 Cell: (437) 244-9393 Concierge: (416) 651-8628 [manager@barringtoncondo.ca¦mailto:manager@barringtoncondo.ca] Thanks! | [13 empty] | 0¦i3wugv: | [7 empty] | 9.2234e+18 | [19 empty] | March 10th - Building flagged as Not a Candidate according to Oliver Davies | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/8386 |  |  | 3 - Normal
Construction | CONST-35355 | 39 Jarvis St, Toronto - The Saint James | Condo | Not a candidate |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2023-09-18 08:03 |  | 2023-10-05 14:57 |  |  |  | 0 | 0 |  |  | CONST-35356, CONST-35357 |  | Requested by Oliver Davies, Can you please create a new ticket for site walk at 39 Jarvis St? We will hope for a direct connection via the hydro-ducts at this location, otherwise it is doubtful the costs will be within our range of approval. PM Info: Gabriela Tanase , General Licence, OLCM Condominium Manager, Crossbridge Condominium Services Ltd _+Agent for and on behalf of The Saint James - MTCC 1295+_ 39 Jarvis Street, Toronto, M5E 1Z5 Office: 416-863-9035 Concierge: 416-863-1860 _+[StJamesCondominium@crossbridgecs.com¦mailto:StJamesCondominium@crossbridgecs.com]+_ _++_ Thank you, | [13 empty] | 0¦i4boxb: | [7 empty] | 9.2234e+18 | [19 empty] | Oct 5/23 - Oliver Davies " I don't think we need to proceed with this now as it seems like a messy project to take on. That said, costs here are not outlandish and it may be worthwhile to take a look at this location again in future. Olawale Olaniyan please mark as not a candidate. I will update the PM." | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/1754 |  |  | 3 - Normal
Construction | CONST-33553 | 5740 Yonge St, Toronto | Condo | Not a candidate |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2023-03-31 11:47 |  | 2023-04-25 07:54 |  |  |  | 0 | 0 |  |  | CONST-33554, CONST-33555 |  | Requested by Oliver Davies Can you please create a new OSP & Site Walk ticket for 5740 Yonge St / The Palms Residences? Nearby we have fibre running to 5775 Yonge St. We may be able to use CDSM14635 or CDSM14769 for an efficient route into this building. There are two other towers just south of here that we should also consider. The boards are difficult but I’m working on booking a site walk for them: Meridian I ([https://buildings.beanfield.com/buildings/view/13648] 416 units) & Meridian II ([https://buildings.beanfield.com/buildings/view/18155] 349 units) PM Info: *Evelina Balla* *Condominium Manager* *Agent for and on behalf of: T.S.C.C. No. 2323* *The Palm Condominium Residences* *5740 Yonge Street, Toronto, ON M2M 0B1* *Phone:* (416) 221-3628 *Fax:* (416) 221-7060 *Email:* {color:#0000ff}[thepalm.pm@delcondo.com¦mailto:thepalm.pm@delcondo.com]{color} Thank you, | [13 empty] | 0¦i3y9on: | [7 empty] | 9.2234e+18 | [19 empty] | Apr 25/23 - As per Oliver Davies "Unfortunately at $400 per unit we will need to pass on this location for now. There are 408 units being built at 5840 Yonge St that will be occupied in 2025. We may have a better shot at that time if we look at both locations. Please mark this as not a candidate". | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/2857 |  |  | 3 - Normal
Construction | CONST-33700 | 1 Grandview Ave, Thornhill | Condo | Not a candidate |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2023-04-18 12:46 | 2025-03-04 10:05 | 2023-08-11 10:43 |  |  |  | 0 | 0 |  |  | CONST-33701, CONST-33702 | CONST-27863 | Requested by Oliver Davies Could you kindly request a new OSP plan & site walk for 7089 Yonge St / 1 Grandview Ave (The Vanguard Condominiums)? This location should tie in well with the new NPOP being constructed at 7181 Yonge St via CONST-27862 I will be meeting with the board of directors on May 10th during their monthly meeting. If there is any chance of having a budget created before then it would be helpful. *PM Info:* *Ryan Erwin, OLCM++++* *Condominium Manager++++* *CMRAO No. 0031375598++++* *Forest Hill Kipling++++* Agent on Behalf of YRSCC 1469 T 416-568-6466 [vanguard.pm@fhkipling.com¦mailto:vanguard.pm@fhkipling.com] Thank you, | [13 empty] | 0¦i3zefz: | [7 empty] | 9.2234e+18 | [19 empty] | Aug 10/23 - as per Oliver Davies "we'll need to pass on this for now given the high construction costs. It's an unfortunate situation given proximity to the new NPOP and as we stubbed a conduit only 1 block away. Please mark as not a candidate." | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/5257 |  |  | 3 - Normal
Montreal Construction | MTLCONST-1779 | 700 Saint-Paul St E, Montreal | Condo | Not a candidate |  | Unresolved | Marianne Yanni | Oguz Avci [X] | Oguz Avci [X] | 2020-09-30 09:38 |  | 2022-01-31 10:04 |  |  |  | 0 | 3 |  |  | MTLCONST-1780 | MTLCONST-1781, MTLCONST-1783 | (condo; managed by Solution Condo) 136 units (phase-5) Kristopher Lalletti. kristopher@lelletti.ca | mtlcondo | [12 empty] | 0¦i26v7z: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
Montreal Construction | MTLCONST-1771 | 7000 rue Allard, Lasalle | Condo | Not a candidate |  | Unresolved | Marianne Yanni | Oguz Avci [X] | Oguz Avci [X] | 2020-09-30 09:30 |  | 2022-01-31 10:04 |  |  |  | 0 | 4 |  |  | MTLCONST-1774 |  | 7000 rue Allard Lasalle, Quebec H8N 1Y7 Contact is: Stephen Krujelskis 514-583-5052 [stephen.krujelskis@gmail.com¦mailto:stephen.krujelskis@gmail.com] | mtlcondo | [12 empty] | 0¦i26v67: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
Montreal Construction | MTLCONST-1772 | 715 William St W, Montreal | Condo | Not a candidate |  | Unresolved | Marianne Yanni | Oguz Avci [X] | Oguz Avci [X] | 2020-09-30 09:32 |  | 2022-01-31 10:05 |  |  |  | 0 | 3 |  |  | MTLCONST-1775 | MTLCONST-1773, MTLCONST-1777 | (rentals; managed by Bentall Green Oak) 125 units (phase1) - [http://www.appartementsboutique.ca¦http://www.appartementsboutique.ca/] Kristopher Lalletti. [kristopher@lelletti.ca¦mailto:kristopher@lelletti.ca] | mtlcondo | [12 empty] | 0¦i26v6f: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
Montreal Construction | MTLCONST-1773 | 705 William St W, Montreal | Condo | Not a candidate |  | Unresolved | Marianne Yanni | Oguz Avci [X] | Oguz Avci [X] | 2020-09-30 09:33 |  | 2022-01-31 10:04 |  |  |  | 0 | 3 |  |  | MTLCONST-1776 | MTLCONST-1772, MTLCONST-1777 | (condo; managed by Solution Condo) 86 units (phase-2) Kristopher Lalletti. [kristopher@lelletti.ca¦mailto:kristopher@lelletti.ca] | mtlcondo | [12 empty] | 0¦i26v6n: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
Montreal Construction | MTLCONST-1777 | 738 Saint-Paul St W, Montreal | Condo | Not a candidate |  | Unresolved | Marianne Yanni | Oguz Avci [X] | Oguz Avci [X] | 2020-09-30 09:36 |  | 2022-01-31 10:05 |  |  |  | 0 | 3 |  |  | MTLCONST-1778 | MTLCONST-1772, MTLCONST-1773 | (condo; managed by Solution Condo) 128 units (phase-1) 104 units (phase-3) Kristopher Lalletti. [kristopher@lelletti.ca¦mailto:kristopher@lelletti.ca] | mtlcondo | [12 empty] | 0¦i26v7j: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
Montreal Construction | MTLCONST-1781 | 754 Saint-Paul St E, Montreal | Condo | Not a candidate |  | Unresolved | Marianne Yanni | Oguz Avci [X] | Oguz Avci [X] | 2020-09-30 09:40 |  | 2022-01-31 10:05 |  |  |  | 0 | 3 |  |  | MTLCONST-1782 | MTLCONST-1779, MTLCONST-1783 | (condo; managed by Solution Condo) 141 units (phase-4) Kristopher Lalletti. kristopher@lelletti.ca | mtlcondo | [12 empty] | 0¦i26v8v: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
Construction | CONST-15468 | 138 St Helens Ave, Toronto | Condo | Not a candidate |  | Unresolved | Harvey Tran | Harvey Tran | Harvey Tran | 2020-10-16 11:18 |  | 2020-10-23 14:52 |  |  |  | 0 | 1 |  |  | CONST-15470 |  | +*Property Address:*+ 138 St Helen's Ave, Toronto ON M6H 4A1 +*Property Manager:*+ Warren Reid (416) 847-7231 [{color:#000000}warren.reid@fsresidential.com{color}¦mailto:warren.reid@fsresidential.com] | [13 empty] | 0¦i27ybr: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [34 empty] | 3 - Normal
Construction | CONST-15991 | 170 Galloway Rd, Scarborough | Condo | Not a candidate |  | Unresolved | Harvey Tran | Harvey Tran | Harvey Tran | 2020-11-13 12:56 |  | 2022-01-31 14:57 |  |  |  | 0 | 1 |  |  | CONST-15992 |  | +*Contact information:*+ 170 Galloway Ave Jerry Reitsma, Property Manager [annmariehill@rogers.com¦mailto:annmariehill@rogers.com] | [13 empty] | 0¦i2a5vr: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/12720#!contacts |  |  | 3 - Normal
Construction | CONST-27305 | 20 Collier St, Toronto - Twenty Collier Condos | Condo | Not a candidate |  | Unresolved | Harvey Tran | Harvey Tran | Harvey Tran | 2022-03-15 12:23 |  | 2022-04-27 14:11 |  |  |  | 0 | 0 |  |  | CONST-27306, CONST-27307 |  | Requested by Oliver Davies. The board here has expressed interest in adding Beanfield for the residents. This is a small location, though it may make sense for us as we build out fibre for the neighboring 825 Church St buildings. +*PM info:*+ Jennifer Bianco, R.C.M., O.L.C.M. Licenced Condominium Manager T. 905. 764.9166 ext. 42 e: jennifer @ tsems.com | [13 empty] | 0¦i39ijr: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/1991 |  |  | 3 - Normal
Construction | CONST-25811 | 25 Stafford St, Toronto | Condo | Not a candidate |  | Unresolved | Harvey Tran | Harvey Tran | Harvey Tran | 2021-11-19 16:22 |  | 2021-11-23 17:14 |  |  |  | 0 | 1 |  |  | CONST-25812, CONST-25813 |  | BB: [https://buildings.beanfield.com/buildings/view/1150] PM Info: Seth Freedland [seth@iconpm.ca¦mailto:seth@iconpm.ca] | [13 empty] | 0¦i31uhz: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/1150 |  |  | 3 - Normal
Construction | CONST-26371 | 750 Bay St, Toronto - The Penrose | Condo | Not a candidate |  | Unresolved | Harvey Tran | Harvey Tran | Harvey Tran | 2022-01-11 15:56 | 2025-03-04 15:10 | 2022-01-20 10:55 |  |  |  | 0 | 1 |  |  | CONST-26372, CONST-26373 |  | Requested by Katie Hodgson +*PM Info:*+ Luc Carriere 416-204-9433 management@mtcc1284.ca | [13 empty] | 0¦i34rj3: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/2224 |  |  | 3 - Normal
Construction | CONST-26496 | 160 Baldwin, Toronto | Condo | Not a candidate |  | Unresolved | Jessica Markiewicz | Jessica Markiewicz | Harvey Tran | 2022-01-25 09:23 |  | 2022-09-27 14:27 |  |  |  | 0 | 1 |  |  | CONST-26497, CONST-26498 | CONST-26499 | Requested from Katie Hodgson for a site walk for 160 Baldwin St & 21 Nassau St May I please request a site walk for 160 Baldwin St & 21 Nassau St *PM Info:* Jermaine Scarlett [kml@360cm.ca¦mailto:kml@360cm.ca] [¦https://buildings.beanfield.com/buildings/view/4530] | [13 empty] | 0¦i35o47: | [7 empty] | 9.2234e+18 | [19 empty] | PM did not provide access. | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/4530 |  |  | 3 - Normal
Construction | CONST-29136 | 70 High Park Ave, Toronto - High Park Condominiums | Condo | Not a candidate |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Jessica Markiewicz | 2022-07-11 07:39 |  | 2023-03-22 08:08 |  |  |  | 0 | 0 |  |  | CONST-29137, CONST-29138 |  | Requested by Jay Fernandes Hi, I’ve gone through the remaining Fibrestream condos we have agreements for in the GTA and have grouped them in a way that I think makes sense for site visits and builds. There will be another list coming of buildings that don’t really fall into groups. Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. There are some current backbone (Sheppard) or NPOP (960 Lawrence) projects that will need to be completed to connect these but this will get everything into the system. Thanks! *PM: Ljupco Cortanoski* *tscc1676@rogers.com* *647.351.6075* | Fiberstreamagreement, HighPark | [12 empty] | 0¦i3h5mn: | [7 empty] | 9.2234e+18 | [19 empty] | Mar 22/23 - Marked as Not a Candidate as per Oliver Davies | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/4541 |  |  | 3 - Normal
Construction | CONST-24883 | 280 Donlands Ave, East York | Condo | Not a candidate |  | Unresolved | Harvey Tran | Harvey Tran | Harvey Tran | 2021-10-01 15:32 |  | 2021-10-08 13:56 |  |  |  | 0 | 0 |  |  | CONST-24884, CONST-24885 |  | PM: Litisha Singh [eastyorker.280@gmail.com¦mailto:eastyorker.280@gmail.com] 416-466-6996 BB: [https://buildings.beanfield.com/buildings/view/5811#!contacts] | [13 empty] | 0¦i2yliv: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/5811#!contacts |  |  | 3 - Normal
Construction | CONST-24545 | 36 Howard Park, Toronto | Condo | Not a candidate |  | Unresolved | Harvey Tran | Harvey Tran | Harvey Tran | 2021-08-27 11:24 |  | 2021-08-31 08:14 |  |  |  | 0 | 1 |  |  | CONST-24546, CONST-24547 |  | PM Info: Lamali Rajab 416-630-1234 ext. 231 [lamali@goldview.ca¦mailto:lamali@goldview.ca] BB: [https://buildings.beanfield.com/buildings/view/8403] | [13 empty] | 0¦i2w5nb: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [34 empty] | 3 - Normal
Construction | CONST-17425 | 238 Albion Rd, Etobicoke | Condo | Not a candidate |  | Unresolved | Harvey Tran | Harvey Tran | Harvey Tran | 2020-12-09 14:28 |  | 2020-12-11 11:54 |  |  |  | 0 | 2 |  |  | CONST-17427 |  | I received an inquiry for building of which is interested in having us : 238 Albion Rd, located in Etobicoke - [https://buildings.beanfield.com/buildings/view/3915] +*Contact information:*+ Jelena (the J is pronounced as a Y 🙂) (416) 740-3458 [mtcc706@gmail.com¦mailto:mtcc706@gmail.com] The building is 34 years old, but he advised that they currently have Bell Fibe, and that their units are not “daisy chained” as they believe the Bell Fibre cables are run from the basement to each unit individually. | [13 empty] | 0¦i2c6zr: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/3915 |  |  | 3 - Normal
Construction | CONST-16704 | 20 Niagara St, Toronto | Condo | Not a candidate |  | Unresolved | Harvey Tran | Harvey Tran | Harvey Tran | 2020-11-30 13:45 |  | 2021-12-15 14:24 |  |  |  | 0 | 2 |  |  | CONST-16705 |  | This is a tiny condo in King West with only 22 units but a specific request to hook it up has been made as there are some movers and shakers here :) Some are excited about Shawn Mendes, I’m excited about Ken Greenberg. Haha His wife makes the most amazing cookies and their loft here is…gorgeous. Address is: 20 Niagara St. Toronto, ON M5V 3L8 BB: [https://buildings.beanfield.com/buildings/view/7992] PM - Michael Simon [michael.simon@scpl.ca¦mailto:michael.simon@scpl.ca] Board Director - Rob Coluccio [navsec@yahoo.com¦mailto:christianlovale@gmail.com] Please include both on this initial outreach. If we can set up a site walk for this week that would be great. Apparently afternoons are best. | [13 empty] | 0¦i2bdcv: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/7992 |  |  | 3 - Normal
Construction | CONST-18717 | 630 Queen St E, Toronto | Condo | Not a candidate |  | Unresolved | Harvey Tran | Harvey Tran | Harvey Tran | 2021-02-02 10:59 |  | 2021-02-16 15:10 |  |  |  | 0 | 2 |  |  | CONST-18718 |  | We have a property interested, and would need to schedule a site visit. See below for details: *Property Address:* 630 Queen St E, Toronto ON M4M 1G3 *BB Link:* [https://buildings.beanfield.com/buildings/view/1561] *Property Manager:* Colleen MacRae (416) 720-3105 {color:#000000}[manager@synccondos.com¦mailto:manager@synccondos.com] {color} | [13 empty] | 0¦i2frmv: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/1561 |  |  | 3 - Normal
Construction | CONST-18653 | 22 Southport Street, Toronto | Condo | Not a candidate |  | Unresolved | Harvey Tran | Harvey Tran | Harvey Tran | 2021-01-22 11:17 |  | 2022-01-31 15:23 |  |  |  | 0 | 1 |  |  | CONST-18654 |  | 22 Southport Street, Toronto BB: [https://buildings.beanfield.com/buildings/view/4572#!contacts] +*Contact information:*+ Ervis M Property Manager [mgtoffice@rogers.com¦mailto:mgtoffice@rogers.com] | [13 empty] | 0¦i2ezfz: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/4572#!contacts |  |  | 3 - Normal
Construction | CONST-17363 | 192 Jarvis St, Toronto | Condo | Not a candidate |  | Unresolved | Harvey Tran | Harvey Tran | Harvey Tran | 2020-12-02 14:04 |  | 2022-01-31 15:00 |  |  |  | 0 | 1 |  |  | CONST-17364 |  | We have a VERY persistent Board President at 192 Jarvis that is hoping their recently renovated 37 year old building can be compliant with our needs. He’s not really taking no for an answer, and I’d like to see if it’s possible because this would be a very easy sell, since he’s such a keener! We are working on their next door building, 186 Jarvis, therefore cable pull could be done at the same time. +*Contact information:*+ Paul Zwarts, Board President [redfred5@gmail.com¦mailto:redfred5@gmail.com] | [13 empty] | 0¦i2bon3: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/2981 |  |  | 3 - Normal
Construction | CONST-17817 | 15 Walmer Road, Toronto | Condo | Not a candidate |  | Unresolved | Harvey Tran | Harvey Tran | Harvey Tran | 2020-12-29 09:38 |  | 2021-03-29 10:23 |  |  |  | 0 | 1 |  |  | CONST-17818 | [15 empty] | 0¦i2d8q7: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [32 empty] | https://buildings.beanfield.com/buildings/view/7991#!contacts |  | 3 - Normal
Construction | CONST-19146 | 741 Sheppard West, Toronto | Condo | Not a candidate |  | Unresolved | Harvey Tran | Harvey Tran | Harvey Tran | 2021-03-02 15:38 |  | 2021-03-10 14:12 |  |  |  | 0 | 2 |  |  | CONST-19147 |  | 741 Sheppard Ave West Sylwia Bulka, Property Manager [manager@divacondo.ca¦mailto:manager@divacondo.ca] BB: [https://buildings.beanfield.com/buildings/view/14222#!contacts] | [13 empty] | 0¦i2ho3j: | [7 empty] | 9.2234e+18 | [19 empty] | March 2nd - Ticket created, Site visit to be scheduled. | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/14222#!contacts |  |  | 3 - Normal
Construction | CONST-12329 | 22 Leader Lane - King Edward Residences | Condo | Not a candidate |  | Unresolved | Harvey Tran | Oguz Avci [X] | Oguz Avci [X] | 2020-04-28 09:26 |  | 2022-01-31 14:26 |  |  |  | 0 | 2 |  |  | CONST-12330, CONST-12976, CONST-12977 |  | Bogdan: [crossbridge@kingedward.ca¦mailto:crossbridge@kingedward.ca] | [13 empty] | 0¦i1xnmf: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/1821 |  |  | 3 - Normal
Construction | CONST-12606 | Corktown District I - 569 King St East | Condo | Not a candidate |  | Unresolved | Harvey Tran | Harvey Tran | Oguz Avci [X] | 2020-06-02 14:38 |  | 2022-02-01 16:46 |  |  |  | 0 | 1 |  |  | CONST-12607, CONST-12984, CONST-12985 | CONST-12584, CONST-12608 | *+Site walk instruction:+* Please go to 510 King St. East in order to get access as they manage all of the buildings. +*Contact information:*+ Your ICON Property Management Team Icon Property Management Ltd. 510 King Street East Toronto ON M5A 0E5 Site Office Phone: 416-363-0438 ¦ Security Phone: 416-363-9392 ¦ Emergency Phone: 416 201 3887 Head Office Phone: 416-236-7979 ¦ Head Office Fax: 416-236-7977 | [13 empty] | 0¦i1z90n: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/2912 |  |  | 3 - Normal
Construction | CONST-15125 | 1100 Lansdowne Ave, Toronto - Foundry Lofts | Condo | Not a candidate |  | Unresolved | Harvey Tran | Harvey Tran | Harvey Tran | 2020-08-31 14:27 |  | 2020-09-24 12:18 |  |  |  | 0 | 2 | _thumb_253318.png |  | CONST-15126 |  | +*Building Address:*+ 1100 Lansdowne Ave, Toronto +*Property Manager:*+ Faizan Mohy u din Phone: (416) 451- 4448 Email: [Fmohyudin@mrcm.ca¦mailto:Fmohyudin@mrcm.ca] | [13 empty] | 0¦i24y33: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [34 empty] | 3 - Normal
Construction | CONST-14980 | 233 Beecroft Road, North York | Condo | Not a candidate |  | Unresolved | Harvey Tran | Harvey Tran | Harvey Tran | 2020-08-13 11:35 |  | 2020-08-25 09:03 |  |  |  | 0 | 1 |  |  | CONST-14981 |  | +*PM Contact Information:*+ Roopali Gulati *Phone:* 416-987-0014 *Fax:* 416-987-0015 *Email:* [peninsulaplace@DelCondo.com¦mailto:peninsulaplace@DelCondo.com] +*Address:*+ 233 Beecroft Rd Toronto On M2N 6Z9 | [13 empty] | 0¦i23ttj: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [34 empty] | 3 - Normal
Construction | CONST-12146 | 1001 Roselawn Ave, Toronto | Condo | Not a candidate |  | Unresolved | Harvey Tran | Oguz Avci [X] | Oguz Avci [X] | 2020-03-13 09:06 |  | 2021-07-21 10:47 |  |  |  | 0 | 1 |  |  | CONST-14937 |  | Christina Cirillo ICC Property Management email: [pm1001@rogers.com¦mailto:pm1001@rogers.com] | [13 empty] | 0¦i1vm2n: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [34 empty] | 3 - Normal
Construction | CONST-12133 | 350 Wellington St W - Soho Lofts | Condo | Not a candidate |  | Unresolved | Harvey Tran | Oguz Avci [X] | Oguz Avci [X] | 2020-03-13 08:50 |  | 2022-01-31 13:52 |  |  |  | 0 | 2 |  |  | CONST-12994, CONST-12995 |  | Pina Perone, General Licence, R.C.M. Property Manager Crossbridge Condominium Services Ltd. Tel 416-204-9900 Fax 416-204-9308 Email: [sohopm@rogers.com¦mailto:sohopm@rogers.com] | [13 empty] | 0¦i1vltb: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/1526 |  |  | 3 - Normal
Construction | CONST-12262 | 90 Niagara St | Condo | Not a candidate |  | Unresolved | Harvey Tran | Oguz Avci [X] | Oguz Avci [X] | 2020-04-07 15:42 |  | 2020-05-26 15:34 |  |  |  | 0 | 2 |  |  | CONST-12263 |  | Building Access: Abel @ 437-980-5563 SANDY SUN Property Manager 101-2645 Skymark AVE. ¦ Mississauga, ON L4W4H2 Direct 6474754027 Email [sandy.sun@fsresidential.com¦mailto:sandy.sun@fsresidential.com] *[www.fsresidential.com¦http://www.fsresidential.com/]* | cancelled | [12 empty] | 0¦i1wr7b: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [34 empty] | 3 - Normal
Construction | CONST-12051 | 205 Manning Ave - Nero Lofts | Condo | Not a candidate |  | Unresolved | Harvey Tran | Oguz Avci [X] | Oguz Avci [X] | 2020-02-21 13:02 |  | 2020-05-26 15:34 |  |  |  | 0 | 3 |  |  | CONST-12052 |  | +*Contact info:*+ Eteri Sepiashvili Property Manager Tel. 905-605-7788 Fax. 905-605-7799 Cel. 647-668-2512 E-mail. [EteriS@comfortpm.ca¦mailto:chloev@comfortpm.ca] Website. [www.comfortpm.ca¦http://www.comfortpm.ca/] | [13 empty] | 0¦i1uhcv: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/4792 |  |  | 3 - Normal
Construction | CONST-3907 | 80 Mill St | Condo | Not a candidate |  | Unresolved | Russell Francey | Jay Fernandes | Jay Fernandes | 2015-10-22 08:38 |  | 2017-10-20 09:28 |  |  |  | 0 | 1 |  |  | CONST-3908, CONST-3909, CONST-3910 | CONST-3911 | Site Visit | [13 empty] | 0¦i0d95r: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/3456 |  |  | 5 - Very Low
Construction | CONST-3911 | Lindenwood - 70 Mill St | Condo | Not a candidate |  | Unresolved | Russell Francey | Jay Fernandes | Jay Fernandes | 2015-10-22 08:42 | 2025-03-04 15:20 | 2017-10-20 09:28 |  |  |  | 0 | 2 | _thumb_56334.png _thumb_56333.png |  | CONST-3912, CONST-3913, CONST-3914 | CONST-3907 | [14 empty] | 0¦i0d96n: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/1763 |  |  | 5 - Very Low
Construction | CONST-2864 | 33 Harbour Square | Condo | Not a candidate |  | Unresolved | Russell Francey | Samantha Russell | Samantha Russell | 2014-12-03 08:53 |  | 2018-08-03 13:04 |  |  |  | 0 | 1 |  |  |  |  | Bring residential building onnet https://buildings.beanfield.com/buildings/view/1067 | Residential, WFT | [12 empty] | 0¦i053tb: | [7 empty] | 29780 | [19 empty] | Agreement with board, should be signed soon after vote. | [6 empty] | 3 - Normal | [28 empty] | 10000 | 1800 |  | https://buildings.beanfield.com/buildings/view/1067 |  | 600347 | 3 - Normal |  | Central Waterfront
Construction | CONST-3070 | 156 Portland St | Condo | Not a candidate |  | Unresolved | Russell Francey | Samantha Russell | Samantha Russell | 2015-02-25 12:35 | 2025-03-04 10:07 | 2018-04-19 15:08 |  |  |  | 0 | 1 |  |  | CONST-3071, CONST-3072, CONST-3073 |  | Bring residential building onnet https://buildings.beanfield.com/buildings/view/2870 | Residential | [12 empty] | 0¦i07qxz: | [7 empty] | 45191 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/2870 |  |  | 3 - Normal
Construction | CONST-3066 | 70 Roehampton - Republic | Condo | Not a candidate |  | Unresolved | Russell Francey | Samantha Russell | Samantha Russell | 2015-02-25 12:32 |  | 2022-08-09 11:21 |  |  |  | 0 | 2 |  |  | CONST-3067, CONST-3068, CONST-3069 | CONST-7369 | Bring Residential building onnet https://buildings.beanfield.com/buildings/view/2237 PM Ryan Funt republic2.pm@DelCondo.com 26 Floors 286 suites power in suites Pop P3 1 riser - with cross over floor to pop Backs on to Broadway but would have to build through 25 Broadway which has 160 suites | Residential | [12 empty] | 0¦i07qwv: | [7 empty] | 45186 | [19 empty] | Board meeting in 2 months | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/2237 |  |  | 3 - Normal |  | Yonge & Eglinton (incl. North Yonge)
Construction | CONST-30348 | 500 Richmond St W, Toronto - Cityscape Terrace | Condo | Not a candidate |  | Unresolved | Jessica Markiewicz | Jessica Markiewicz | Jessica Markiewicz | 2022-09-01 08:26 |  | 2022-09-27 14:22 |  |  |  | 0 | 0 |  |  | CONST-30349, CONST-30350 |  | Requested by Oliver Davies. Can you please request a site walk for 500 Richmond St W? BB Link: [https://buildings.beanfield.com/buildings/view/3377] Site Contact: Ray Landry [raymondlandry67@gmail.com¦mailto:raymondlandry67@gmail.com] 647.241.5607 + Lily Barbosa [lily@goldview.ca¦mailto:lily@goldview.ca] This location was previously investigated back in 2017 via CONST-6710. We would like to determine if the work required to bring our services online is now within reason. | [13 empty] | 0¦i3kps7: | [7 empty] | 9.2234e+18 | [19 empty] | Hight costs to build. | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/3377 |  |  | 3 - Normal
Construction | CONST-33047 | 42 Camden St, Toronto - Zen Lofts | Condo | Not a candidate |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2023-02-10 11:50 |  | 2024-02-07 10:06 |  |  |  | 0 | 0 |  |  | CONST-33048, CONST-33049 | CONST-33073 | Requested by Oliver Davies Can you please queue up an OSP plan + site walk for 42 Camden St? This is a small building with only 35 units, however we are available in most of the surrounding buildings in this neighbourhood (inc. 5, 8, 16, 20 & 21 Camden & 477 Richmond St W). 32 Camden St is immediately next door with an additional 87 units, as is 50 Camden with 65 units, both off-net - I will work on getting a site walk agreed to for these as well. The budget for 42 Camden St should give us a good indication of the overall cost to get into all 3x of these buildings. PM Info: ¦ ¦{color:#195070}*Lee Boros*{color}¦ ¦Property Manager, Performance Property Management inc.¦ ¦[416.645.3755 ¦tel:416.645.3755+ex+505] ext 512 \¦ lee[@performancepm.com¦mailto:chow@performancepm.com]¦ ¦Address: 400-901 King St. W., Toronto Ontario M5V 3H5 Website: [www.performancepm.com¦http://www.performancepm.com/]¦ ¦ Thank you, | [13 empty] | 0¦i3uvlz: | [7 empty] | 9.2234e+18 | [19 empty] | Mar 15/23 - Building marked as Not a Candidate as per Oliver Davies. | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/1427 |  |  | 3 - Normal
Construction | CONST-5694 | 32 Davenport Rd - The Yorkville | Condo | Not a candidate |  | Unresolved | Russell Francey | Russell Francey | Russell Francey | 2017-03-10 11:21 |  | 2024-02-06 13:09 |  |  |  | 0 | 1 |  |  | CONST-5695, CONST-5696, CONST-5697 |  | Kelly Jennings 647.345.6259 kelly@iconpm.ca | [13 empty] | 0¦i0p31r: | [7 empty] | 9.2234e+18 | [19 empty] | Building is a bit far from backbone, will contact once backbone is done. | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/3382 |  |  | 3 - Normal |  | Yonge & Bloor (incl. Yorkville)
Montreal Construction | MTLCONST-1783 | 693 William St E, Montreal | Condo | Not a candidate |  | Unresolved | Marianne Yanni | Oguz Avci [X] | Oguz Avci [X] | 2020-09-30 09:41 |  | 2024-02-22 10:28 |  |  |  | 0 | 4 |  |  | MTLCONST-1784 | MTLCONST-1779, MTLCONST-1781 | (rentals; managed by Bentall Green Oak) 155 units (phase-2) - http://www.appartementsboutique.ca Kristopher Lalletti. kristopher@lelletti.ca | mtlcondo | [12 empty] | 0¦i26v9b: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
Construction | CONST-36311 | 2756 Old Leslie St, North York - 2756 Old Leslie | Condo | Not a candidate |  | Unresolved | Harvey Tran | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2024-01-24 15:03 |  | 2024-05-16 10:33 |  |  |  | 0 | 0 |  |  | CONST-36312, CONST-36313 | CONST-33876 | Requested by Oliver Davies, Could you kindly proceed with creating a new OSP Plan & Site Walk ticket for 2756 Old Leslie St? The “Leslie Boutique Residences” includes 182 units. This location is at the NW corner of Esther Shiner Blvd & Old Leslie St. CDSM15981 & CDSM11824-2 are approx. 150m away on Leslie St - ideally we can pull fibre via the building ducts as construction will be expensive. We should consider this building as part of the ongoing Singer/Esther Shiner/McMahon Dr backbone expansion to the surrounding neighbourhood (https://tickets.beanfield.com/browse/CONST-33876). I have tagged this location on the attached route drawing. PM Info: {quote}*Antoniette Nardella* Condominium Manager {color:#0b5394} {color} *{color:#0b5394}Goldview Property Management Ltd.{color}* 51 Toro Road, Suite 200 Toronto, ON M3J 2A4 Phone: 416-630-1234 Facsimile: 416-630-3132 {color:#3d85c6}[www.goldview.ca¦http://www.goldview.ca/] {color} [antoniette@goldview.ca¦mailto:antoniette@goldview.ca]{quote} Thanks! | [13 empty] | 0¦i4l0v3: | [7 empty] | 9.2234e+18 | [19 empty] | May 16th, 2024 - Project is not a candidate due to high construction cost. | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/4947 |  |  | 3 - Normal
Construction | CONST-27403 | 220 Forum Dr, Mississauga - Tuscany Gate | Condo | Not a candidate |  | Unresolved | Harvey Tran | Harvey Tran | Harvey Tran | 2022-03-21 16:34 |  | 2022-07-27 10:09 |  |  |  | 0 | 0 |  |  | CONST-27404, CONST-27405 |  | +*PM Info:*+ Djordje (George) Todorovic GL, RCM, IHM Senior Property Manager [George@andrejsmanagement.com¦mailto:George@andrejsmanagement.com] Andrejs Management Inc [Tel:905.850.7750¦tel:905.850.7750] This will be a long shot, but it appears we have a BF MH in the vicinity at Hurontario & Eglinton, with plant at Matheson W/Hurontario and Robert Speck Pkwy /Hurontario. | [13 empty] | 0¦i39zzb: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/16443 |  |  | 3 - Normal
Construction | CONST-25096 | 77 Brickworks Lane, Toronto | Condo | Not a candidate |  | Unresolved | Harvey Tran | Harvey Tran | Harvey Tran | 2021-10-14 09:05 |  | 2022-01-31 17:00 |  |  |  | 0 | 1 |  |  | CONST-25097, CONST-25098 |  | BB: [https://buildings.beanfield.com/buildings/view/15247#!contacts] Property Manager Monika Gdula [{color:#000000}905-605-7788{color}¦tel:905-605-7788] {color:#777733}[monikag@comfortpm.ca¦mailto:monikag@comfortpm.ca]{color} | [13 empty] | 0¦i2zchz: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/15247#!contacts |  |  | 3 - Normal
Construction | CONST-25356 | 1630 Queen East, Toronto | Condo | Not a candidate |  | Unresolved | Harvey Tran | Harvey Tran | Harvey Tran | 2021-10-27 09:50 |  | 2022-01-31 17:01 |  |  |  | 0 | 1 |  |  | CONST-25357, CONST-25358 |  | Property Manager: Kamran Anwar [westbeach.cm@dukamanagement.com¦mailto:westbeach.cm@dukamanagement.com] 905.673.7338 BB: [https://buildings.beanfield.com/buildings/view/13652#!contacts] | [13 empty] | 0¦i305hz: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/13652#!contacts |  |  | 3 - Normal
Construction | CONST-26324 | 570 Lolita Gardens, Mississauga | Condo | Not a candidate |  | Unresolved | Harvey Tran | Harvey Tran | Harvey Tran | 2022-01-04 17:15 |  | 2022-01-05 09:20 |  |  |  | 0 | 1 |  |  | CONST-26325 |  | PM Details: Alon Meyer alon@performancepm.com 416.645.3755 ext. 509 | [13 empty] | 0¦i34akv: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/3201 |  |  | 3 - Normal
Construction | CONST-28123 | May Tower Ⅰ - 1 Lee Centre Dr, Toronto | Condo | Not a candidate |  | Unresolved | Jessica Markiewicz | Jessica Markiewicz | Harvey Tran | 2022-04-28 08:47 |  | 2023-11-02 11:39 |  |  |  | 0 | 2 |  |  | CONST-28124, CONST-28125 |  | 1 Lee Centre Dr ([https://buildings.beanfield.com/buildings/view/15791]) - Pending FS location *PM:* *Joan James* *Property Manager* *416-255-7300++++* *Mareka Properties (2000) Ltd* *[mtcc1256@marekapm.com¦mailto:mtcc1256@marekapm.com]* Nearby, 11 Lee Centre Dr and 36 Lee Centre Dr should be considered as part of an expansion to this neighbourhood. | [13 empty] | 0¦i3cl3z: | [7 empty] | 9.2234e+18 | [19 empty] | On hold as per Oliver Davis. | [6 empty] | 3 - Normal | [34 empty] | 3 - Normal
Construction | CONST-29822 | 38 Avenue Rd, Toronto | Condo | Not a candidate |  | Unresolved | Jessica Markiewicz | Jessica Markiewicz | Jessica Markiewicz | 2022-08-09 08:42 |  | 2022-11-16 07:10 |  |  |  | 0 | 0 |  |  | CONST-29823, CONST-29824 |  | Last ones for today! We are looking for another site walk at 38 Avenue Rd. and 155 St. Clair Ave W BB Link: [https://buildings.beanfield.com/buildings/view/649] PM Info: *Josefina Motton*_,_ OLCM __ Condominium Manager __ MTCC 1276 The Prince Arthur 38 Avenue Road, Toronto, Ontario M5R 2G2 Tel (437) 916-9077 ¦ Fax (416) 551-0387 Email [josie@princearthurresidence.ca¦mailto:josie@princearthurresidence.ca] Constructed in 1999 on the west side of Avenue at Yorkville Ave. | [13 empty] | 0¦i3j27r: | [7 empty] | 9.2234e+18 | [19 empty] | October 28th - Site Visit requested. | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/649 |  |  | 3 - Normal
Construction | CONST-29825 | 155 St Clair Ave W, Toronto | Condo | Not a candidate |  | Unresolved | Jessica Markiewicz | Jessica Markiewicz | Jessica Markiewicz | 2022-08-09 08:46 |  | 2022-09-27 14:23 |  |  |  | 0 | 0 |  |  | CONST-29826, CONST-29827 |  | Requested by Oliver. For 155 St Clair Ave W, this is a smaller building with only 76 units at the corner of Avenue & St. Clair Ave W. We have active network in the immediate vicinity, so it’s worth a shot! BB Link: [https://buildings.beanfield.com/buildings/view/5184] PM Info: Solmaz Akbarihamed [Theavenue.pm@delcondo.com¦mailto:Theavenue.pm@delcondo.com] 647.343.6400 | [13 empty] | 0¦i3j28v: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/5184 |  |  | 3 - Normal
Construction | CONST-23748 | 3237 Bayview Ave, North York | Condo | Not a candidate |  | Unresolved | Harvey Tran | Harvey Tran | Harvey Tran | 2021-06-23 15:36 |  | 2022-04-11 10:40 |  |  |  | 0 | 1 |  |  | CONST-23749 |  | PM: Mankee [bennettonbayview@gmail.com¦mailto:bennettonbayview@gmail.com] Thanks! | Fiberstreamagreement | [12 empty] | 0¦i2r353: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/14828#!contacts |  |  | 3 - Normal
Construction | CONST-23856 | 98 Carr St, Toronto | Condo | Not a candidate |  | Unresolved | Harvey Tran | Harvey Tran | Harvey Tran | 2021-06-29 16:25 |  | 2021-07-07 15:25 |  |  |  | 0 | 1 |  |  | CONST-23857 |  | We have a property interested, and would need to schedule a site visit. See below for details: *Property Address:* 60-98 Carr St, Toronto ON M5T 1B7 (The Gardens at Queen) *BB Link:* [https://buildings.beanfield.com/buildings/view/14244] *Property Manager:* Prakash [PHirani@percelinc.com¦mailto:PHirani@percelinc.com] Prakash is on site every Monday, Wednesday, and Friday. Site walk subtask can be set up and James can reach out. | [13 empty] | 0¦i2riwf: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/14244 |  |  | 3 - Normal
Construction | CONST-23302 | 118 The Queensway, Toronto | Condo | Not a candidate |  | Unresolved | Harvey Tran | Harvey Tran | Harvey Tran | 2021-05-06 14:56 |  | 2021-05-12 14:50 |  |  |  | 0 | 0 |  |  | CONST-23303 |  | +*118 The Queensway*+ *Property Manager:* *Shena* [NXTCondos.PM@Delcondo.com¦mailto:NXTCondos.PM@Delcondo.com] 416.255.6520 BB Link: [https://buildings.beanfield.com/buildings/view/14566] | [13 empty] | 0¦i2nlkv: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/14566 |  |  | 3 - Normal
Construction | CONST-23584 | 120 Perth Ave, Toronto | Condo | Not a candidate |  | Unresolved | Harvey Tran | Harvey Tran | Harvey Tran | 2021-06-09 14:12 |  | 2021-06-18 10:47 |  |  |  | 0 | 1 |  |  | CONST-23585 |  | Property Manager: Gabriela Ventura [gabrielaventura93@hotmail.com¦mailto:gabrielaventura93@hotmail.com] BB: [https://buildings.beanfield.com/buildings/view/14727] Thank you! | [13 empty] | 0¦i2q1d3: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/14727 |  |  | 3 - Normal
Construction | CONST-23019 | 30 Elsie Lane, Toronto - Brownstones on Wallace | Condo | Not a candidate |  | Unresolved | Harvey Tran | Harvey Tran | Harvey Tran | 2021-04-19 14:13 |  | 2021-05-12 09:18 |  |  |  | 0 | 0 |  |  | CONST-23020 |  | BB: [https://buildings.beanfield.com/buildings/view/4296#!contacts] *Michael Kurac, Property Manager* *[mkudrac@capemanagement.com¦mailto:mkudrac@capemanagement.com]* *416-704-0092* | [13 empty] | 0¦i2lxpj: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/4296#!contacts |  |  | 3 - Normal
Construction | CONST-26568 | 1375 Dupont St, Toronto - Chelsea Lofts | Condo | Not a candidate |  | Unresolved | Harvey Tran | Harvey Tran | Harvey Tran | 2022-01-28 12:56 |  | 2022-02-01 16:35 |  |  |  | 0 | 2 |  |  | CONST-26569, CONST-26570 |  | *Requested by Katie Hodgson* +*PM Info:*+ Ismail Qorri [ismail@tsems.com¦mailto:ismail@tsems.com] *Prefers next Tuesday at 1:00PM | [13 empty] | 0¦i3605j: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/5939 |  |  | 3 - Normal
Construction | CONST-26591 | 1048 Broadview Ave, Toronto | Condo | Not a candidate |  | Unresolved | Harvey Tran | Harvey Tran | Harvey Tran | 2022-01-31 13:54 |  | 2022-02-04 12:24 |  |  |  | 0 | 2 |  |  | CONST-26592, CONST-26593 |  | *Requested by Katie Hodgson* +PM Info:+ Vida Ardalan [SkyyOnBroadview.PM@delcondo.com¦mailto:SkyyOnBroadview.PM@delcondo.com] (416) 696-8963/7599 x2 | [13 empty] | 0¦i365x3: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/5282 |  |  | 3 - Normal
Construction | CONST-27051 | 2 Fieldway Rd, Etobicoke | Condo | Not a candidate |  | Unresolved | Harvey Tran | Harvey Tran | Harvey Tran | 2022-02-28 15:58 |  | 2022-04-28 10:33 |  |  |  | 0 | 2 |  |  | CONST-27052, CONST-27053 |  | Requested by Oliver Davies. Could you please create a ticket and request for a site walk at 2 Fieldway Rd? [https://buildings.beanfield.com/buildings/view/5351] PM info: *Evelyne Wong, OLCM* Regional Manager ICC Property Management Ltd. 2875 14th Avenue, Suite 300, Markham, ON, L3R 5H8 Tel: 905-940-1234 Ext. 229 [ewong@iccpropertymanagement.com¦mailto:ewong@iccpropertymanagement.com] | [13 empty] | 0¦i389tb: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/5351 |  |  | 3 - Normal
Construction | CONST-15353 | 88 Cumberland St, Toronto | Condo | Not a candidate |  | Unresolved | Harvey Tran | Harvey Tran | Harvey Tran | 2020-10-05 14:43 |  | 2022-01-31 14:52 |  |  |  | 0 | 1 |  |  | CONST-15354 |  | +*Address:*+ 88 Cumberland +*Property Manager:*+ Sandy Co Li {color:#0000ff}[yorkvillepark.pm@fhkipling.com¦mailto:yorkvillepark.pm@fhkipling.com]{color} 416.546.2798 +*Building Browser Link:*+ {color:#0068da}+[https://buildings.beanfield.com/buildings/view/13355]+{color} | [13 empty] | 0¦i2799r: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/13355 |  |  | 3 - Normal
Construction | CONST-9594 | 77 Charles St W | Condo | Not a candidate |  | Unresolved | Russell Francey | Russell Francey | Russell Francey | 2019-01-15 10:58 | 2025-03-04 14:53 | 2019-02-06 12:25 |  |  |  | 0 | 2 |  |  | CONST-9595 |  | Elaine Lee, RCM Condominium Manager elee@iccpropertymanagement.com ICC Property Management 1151 Denison St, Unit 15 Markham, ON L3R 3Y4 Tel: (905) 940 - 1234, ext 51 | [13 empty] | 0¦i1esef: | [7 empty] | 9.2234e+18 | [19 empty] | Build cost too high as of right now - Feb 6th, 2019 | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/4352 |  |  | 3 - Normal |  | Bay St Corridor
Construction | CONST-12621 | Newtowns at King Towns - 25 & 16 Laidlaw St | Condo | Not a candidate |  | Unresolved | Harvey Tran | Harvey Tran | Harvey Tran | 2020-06-08 15:50 |  | 2022-02-03 13:59 |  |  |  | 0 | 2 |  |  | CONST-12622, CONST-12970, CONST-12971 |  | *Newton at Kings Towns* *Shaz Khan* *Project Manager* Email: [[shaz@iconpm.ca¦mailto:[shaz@iconpm.ca]¦mailto:shaz@iconpm.ca] Phone: 416-887-7748 Address: 25 Laidlaw St. Toronto, ON M6K 1X3 // 16 Laidlaw St. Toronto, ON M6K 1X2 | [13 empty] | 0¦i1zlxr: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/3849 |  |  | 3 - Normal
Construction | CONST-7386 | Edge Lofts - 625 Queen St | Condo | Not a candidate |  | Unresolved | Russell Francey | Russell Francey | Russell Francey | 2018-01-24 14:28 | 2025-03-04 10:14 | 2018-08-27 15:04 |  |  |  | 0 | 0 |  |  | CONST-7387 |  | Stanley Tsang, R.C.M. Property Manager 360 Community Management Ltd. 80 Fulton Way, Unit 203 Richmond Hill, Ontario L4B 1J5 Tel: (905) 604-3602 ext: 312 Fax: (905) 604-3609 | [13 empty] | 0¦i0zqh3: | [7 empty] | 9.2234e+18 | [19 empty] | Site visit being arranged. | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/1562 |  |  | 3 - Normal |  | Carlaw (Leslieville)
Construction | CONST-5250 | 62 Wellesley - Queens Park Place | Condo | Not a candidate |  | Unresolved | Russell Francey | Russell Francey | Russell Francey | 2016-12-12 09:38 |  | 2017-08-03 10:36 |  |  |  | 0 | 0 |  |  | CONST-5251, CONST-5252, CONST-5253 |  | 102 Suites 21 Storeys Telephone room on P2 30 Year old building Zone conduits for bell on 10th floor Zoine conduits for rogers on 14th floor Daisy Chained | [13 empty] | 0¦i0mr33: | [7 empty] | 9.2234e+18 | [19 empty] | Bulk deal cancelled. | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/5283 |  |  | 3 - Normal |  | Bay St Corridor
Construction | CONST-5658 | 7 St Michael Power Pl - Port Royal Place Ⅴ | Condo | Not a candidate |  | Unresolved | Russell Francey | Russell Francey | Russell Francey | 2017-02-28 16:09 |  | 2017-04-05 14:04 |  |  |  | 0 | 0 |  |  |  |  | Dave Casha portroyalplace.pm@delcondo.ca 4166377700 Management | [13 empty] | 0¦i0olzr: | [7 empty] | 9.2234e+18 | [19 empty] | Working on project with Jay, holding for now. | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/4061 |  |  | 3 - Normal
Construction | CONST-5600 | 1121 Bay - Elev’n Residences | Condo | Not a candidate |  | Unresolved | Russell Francey | Russell Francey | Russell Francey | 2017-02-13 13:41 |  | 2021-11-30 10:23 |  |  |  | 0 | 2 | _thumb_83872.png _thumb_83874.png _thumb_83875.png |  | CONST-5601, CONST-5609, CONST-5610, CONST-5614 | CONST-25886 | Moustafa Omar elev'n21 building assistant 416-910-1143 m_1121_bay@yahoo.ca telephone room on ground floor room for us in riser conduits Bell prewired , some in bell conduits some in rogers conduits can be done but will have to be careful when we pull if were in with another fiber | [13 empty] | 0¦i0o79b: | [7 empty] | 9.2234e+18 | [19 empty] | Backbone not ready, too small to push based on cost. | [6 empty] | 3 - Normal | [28 empty] | 35000 |  |  | https://buildings.beanfield.com/buildings/view/4351 |  |  | 3 - Normal |  | Bay St Corridor | 4000 | 14000
Construction | CONST-5268 | 40 Homewood Condos - 40 Homewood Ave | Condo | Not a candidate |  | Unresolved | Russell Francey | Russell Francey | Russell Francey | 2016-12-13 10:14 |  | 2018-01-29 13:17 |  |  |  | 0 | 0 |  |  | CONST-5269, CONST-5270 |  | Customer is looking at bulk deal | [13 empty] | 0¦i0ms6f: | [7 empty] | 9.2234e+18 | [19 empty] | PM looking into bulk offer? | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/4121 |  |  | 3 - Normal |  | Church & Wellesley Village
Construction | CONST-6353 | 99 Avenue Road | Condo | Not a candidate |  | Unresolved | Russell Francey | Russell Francey | Russell Francey | 2017-06-28 10:53 |  | 2019-08-22 15:47 |  |  |  | 0 | 0 |  |  | CONST-6354 | [15 empty] | 0¦i0sa3r: | [7 empty] | 9.2234e+18 | [19 empty] | Holding off till backbone ready | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/6226#!services |  |  | 3 - Normal |  | Yonge & Bloor (incl. Yorkville)
Construction | CONST-10892 | Five Nine on Richmond - 533 Richmond St W | Condo | Not a candidate |  | Unresolved | Russell Francey | Russell Francey | Russell Francey | 2019-07-30 14:05 |  | 2019-08-27 11:43 |  |  |  | 0 | 0 |  |  | CONST-10893 |  | Lily Barbosa ¦ Senior Condominium Manager BA, RCM Goldview Property Management Ltd. 51 Toro Road, Suite 200 ¦Toronto, Ontario ¦ M3J 2A4 t: 416-630-1234 ext 249 ¦ f: 416-630-3132 e: lily@goldview.ca *Ivan* is the *superintendent* and can be reached at *647-502-3033* | [13 empty] | 0¦i1mf0v: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/4628 |  |  | 3 - Normal |  | King West
Construction | CONST-10890 | Forty Four Charles St - 44 Charles St | Condo | Not a candidate |  | Unresolved | Russell Francey | Russell Francey | Russell Francey | 2019-07-30 13:46 |  | 2019-11-05 11:13 |  |  |  | 0 | 0 |  |  | CONST-10891 |  | This is a rental building. Currently they have Rogers for bulk TV, but no bulk internet. *property managers* Michael Motz Property Director, Manulife Centre Manulife Investment Management E michael_motz@manulife.com T 416 435 1305 *Building Operator:* Mike Asfaha 416.923.6789 mike_asfaha@manulife.com They are interested in brining Beanfield into both the commercial side of the building, and the residential side. | [13 empty] | 0¦i1mexz: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/843 |  |  | 3 - Normal |  | Yonge & Bloor (incl. Yorkville)
Construction | CONST-11029 | Portland Park Village - 11 Niagara | Condo | Not a candidate |  | Unresolved | Russell Francey | Russell Francey | Russell Francey | 2019-08-29 16:22 | 2025-03-04 10:12 | 2019-11-04 10:22 |  |  |  | 0 | 0 |  |  | CONST-11030 |  | Jim Alli ppv1371@portlandpark.ca *Daisy Chained* | [13 empty] | 0¦i1no2v: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [34 empty] | 3 - Normal
Construction | CONST-9683 | 901 Queen St W - 901 Queen | Condo | Not a candidate |  | Unresolved | Russell Francey | Russell Francey | Russell Francey | 2019-01-24 11:31 |  | 2019-11-11 10:08 |  |  |  | 0 | 0 |  |  | CONST-9684 |  | Looking to see cost to bring building on-net. *Contact:* Sarah - [trinitypark.office@gmail.com¦mailto:trinitypark.office@gmail.com] ^416-603-4442^ Cost to build into the building are too high | [13 empty] | 0¦i1f6n3: | [7 empty] | 9.2234e+18 | [19 empty] | 2018: Board member has become MIA 2019: New PM, reached out, interested in Beanfield services | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/3086 |  |  | 3 - Normal |  | West Queen West
Construction | CONST-9804 | The Argyle Lofts - 183 Dovercourt Rd | Condo | Not a candidate |  | Unresolved | Russell Francey | Russell Francey | Russell Francey | 2019-02-08 09:52 |  | 2019-02-13 10:21 |  |  |  | 0 | 1 |  |  | CONST-9805, CONST-9806 |  | nicolas@conkritecapital.com Nicolas Del Valle facility manager | [13 empty] | 0¦i1fp5r: | [7 empty] | 9.2234e+18 | [19 empty] | home run is free aired from the riser across to the suite. | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/3258#!contacts |  |  | 3 - Normal
Construction | CONST-9703 | Liberty Lofts - 383 Adelaide St E | Condo | Not a candidate |  | Unresolved | Russell Francey | Russell Francey | Russell Francey | 2019-01-29 13:52 |  | 2019-02-01 09:36 |  |  |  | 0 | 0 |  |  | CONST-9704 |  | STEPHEN W. MUNENE Property Manager Direct 416.847.7225 Email stephen.munene@fsresidentail.com | [13 empty] | 0¦i1fcjb: | [7 empty] | 9.2234e+18 | [19 empty] | Condo is too small | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/4466 |  |  | 3 - Normal |  | King East
Construction | CONST-9099 | 899 Queen St E - Logan Residences | Condo | Not a candidate |  | Unresolved | Harvey Tran | Russell Francey | Russell Francey | 2018-10-29 09:08 |  | 2020-05-26 15:35 |  |  |  | 0 | 3 |  |  | CONST-8879, CONST-9100, CONST-9101 |  | Point of contact: Isaac Dutton IT Operations Manager B: 416-598-7823 idutton@danielscorp.com | [13 empty] | 0¦i1c8i7: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/7657 |  |  | 3 - Normal |  | Carlaw (Leslieville)
Construction | CONST-5680 | Tiffany Terrace - 30 Hayden St. | Condo | Not a candidate |  | Unresolved | Russell Francey | Russell Francey | Russell Francey | 2017-03-08 12:13 |  | 2021-07-12 09:24 |  |  |  | 0 | 3 | _thumb_88021.png _thumb_88023.png _thumb_88024.png _thumb_88019.png _thumb_88020.png |  | CONST-5681, CONST-5682, CONST-5683, CONST-5915 |  | Nicolle MacNeil Property Manager Shelter Canadian Properties Limited 701 King Street West, Unit 109 Toronto, Ontario, M5V 2W7 Tele: 416-703-5592 Fax: 416-504-8789 nicolle.macneil@scpl.ca Super Loretto 416-995-9226 1 Riser 14 floors + penthouse telephone room on P1 4th and 7th floor comm floors Rogers 4th , Bell 7th Daisy chained building | [13 empty] | 0¦i0p0cn: | [7 empty] | 9.2234e+18 | [19 empty] | Have to pass on building for now. | [6 empty] | 3 - Normal | [28 empty] | 22000 |  |  | https://buildings.beanfield.com/buildings/view/5755 |  |  | 3 - Normal |  | Yonge & Bloor (incl. Yorkville) | 1000 | 5000
Construction | CONST-4645 | 287 Richmond St E - Richmond Mews | Condo | Not a candidate |  | Unresolved | Jay Fernandes | Samantha Russell | Samantha Russell | 2016-07-05 09:00 |  | 2018-04-18 08:18 |  |  |  | 0 | 1 | _thumb_71091.png _thumb_71090.png |  | CONST-4646 | CONST-3402 | Bring building onnet 14 suites could not get access to risers none had a key no room in pop cables for existing suites go though a hole in the drywall and could not locate a conduit or any easy way to go up | [13 empty] | 0¦i0igkn: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [34 empty] | 3 - Normal
Construction | CONST-5107 | Harbourpoint II - 260 Queens Quay W - Bulk | Condo | Not a candidate |  | Unresolved | Russell Francey | Russell Francey | Russell Francey | 2016-11-09 08:21 |  | 2018-10-30 14:03 |  |  |  | 0 | 0 |  |  | CONST-5108, CONST-5109, CONST-5110, CONST-8573 |  | darryn@tsems.com DARRYN MARCUS, RCM T.S.E. MANAGEMENT SERVICES INC. 30 East Beaver Creek Road Suite 107 Richmond Hill, Ontario. L4B 1J2 T: (905) 764-9166 ext.42 F: (905) 882-0228 | [13 empty] | 0¦i0m15z: | [7 empty] | 9.2234e+18 | [19 empty] | Project on hold | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/3731 |  |  | 3 - Normal |  | Waterfront Central
Construction | CONST-4970 | 109 Front St - New Times Square | Condo | Not a candidate |  | Unresolved | Russell Francey | Russell Francey | Russell Francey | 2016-10-11 09:07 |  | 2017-03-13 19:59 |  |  |  | 0 | 3 | _thumb_77603.png _thumb_77602.png _thumb_77601.png |  | CONST-4971, CONST-4972, CONST-4973 |  | Daniel Bonea Property Manager Brookfield Condominium Services Ltd. As agent for and on behalf of MTCC 1280 and MTCC 1385 109 Front Street East, Toronto, ON, M5A 4P7 E-mail: managernewtimessq@rogers.com Phone: 416-504-7298 two corporations MTCC 1280 - facing front st 186 suites MTCC 1385- Facing Jarvis 193 suites Main pop in P1 beside parking spot 30 enough room for our equipment , although to get to other riser/pop located on ground floor Jarvis side ( audio Room ) conduits are congested and may not have enough room for power Multiple risers in both towers This building is daisy chained and all zone conduits lead to 6th floor telecom closet for Bell | [13 empty] | 0¦i0l57z: | [7 empty] | 9.2234e+18 | [19 empty] | No individual zhone conduits | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/1609 |  |  | 3 - Normal |  | Corktown
Construction | CONST-4512 | 50 Lombard St - The Indigo | Condo | Not a candidate |  | Unresolved | Russell Francey | Jay Fernandes | Jay Fernandes | 2016-05-22 10:06 |  | 2017-10-20 09:30 |  |  |  | 0 | 2 | _thumb_71482.png _thumb_71483.png |  | CONST-4513 |  | Condo built in 1993 - unlikely we can do it. Will be setting up a site visit in June of 2016 104 Suites Rogers and bell located on 23rd floor Conduits very tight on lower floors may not be able to accommodate firmer and power cable can enter though hydro entrance Walked in suite but could not see any telecom panels no room in current pop for us | [13 empty] | 0¦i0h3mf: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/932 |  |  | 5 - Very Low
Construction | CONST-4315 | 2 Anndale Dr - Hullmark Centre | Condo | Not a candidate |  | Unresolved | Russell Francey | Jay Fernandes | Jay Fernandes | 2016-03-16 09:07 |  | 2018-04-16 11:24 |  |  |  | 0 | 2 |  |  | CONST-4316, CONST-4317, CONST-4318 | CONST-4319 | [14 empty] | 0¦i0ft47: | [7 empty] | 9.2234e+18 | [19 empty] | Project on hold. | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/4489#!contacts |  |  | 5 - Very Low |  | North York
Construction | CONST-11047 | 140 Bathurst St - Adelaide Square | Condo | Not a candidate |  | Unresolved | Russell Francey | Russell Francey | Russell Francey | 2019-09-09 10:11 |  | 2019-10-07 11:46 |  |  |  | 0 | 0 |  |  | CONST-11048 |  | Peter Peci ¦ Condominium Manager Goldview Property Management Ltd. 51 Toro Rd, Suite 200 ¦ Toronto, Ontario ¦ M3J 2A4 ¦ t: 416-630-1234 Ext. 329 ¦ f: 416-630-3132 e: peter@goldview.ca ¦ www.goldview.ca *daisy chained conduits* | [13 empty] | 0¦i1o19r: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [34 empty] | 3 - Normal
Construction | CONST-10949 | Copperfield II - Townhouses | Condo | Not a candidate |  | Unresolved | Russell Francey | Russell Francey | Russell Francey | 2019-08-12 13:56 |  | 2019-11-05 11:10 |  |  |  | 0 | 0 |  |  | CONST-10950 | [15 empty] | 0¦i1mxzj: | [7 empty] | 9.2234e+18 | [19 empty] | Too expensive to build, will need to review in a year or two | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/8550 |  |  | 3 - Normal
Construction | CONST-10371 | 83 Redpath Residences - 83 Redpath Ave | Condo | Not a candidate |  | Unresolved | Russell Francey | Russell Francey | Russell Francey | 2019-05-03 09:04 |  | 2019-08-19 13:50 |  |  |  | 0 | 0 |  |  | CONST-10372 |  | PM: EteriS@comfortpm.ca Eteri Sepiashvili Tel. 905-605-7788 | [13 empty] | 0¦i1j08v: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/4712 |  |  | 3 - Normal |  | Yonge & Eglinton (incl. North Yonge)
Construction | CONST-10643 | 4 Avenue Rd - Park Hyatt Residences | Condo | Not a candidate |  | Unresolved | Russell Francey | Russell Francey | Russell Francey | 2019-06-10 15:09 |  | 2019-08-22 15:53 |  |  |  | 0 | 0 |  |  | CONST-10644, CONST-10649 |  | Kelvin Kwok, P.Eng ¦ Manager, Development KKwok@oxfordproperties.com | [13 empty] | 0¦i1kj0v: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/8369 |  |  | 3 - Normal |  | Yonge & Bloor (incl. Yorkville)
Construction | CONST-4107 | 500 Wellington St W | Condo | Not a candidate |  | Unresolved | Russell Francey | Jay Fernandes | Jay Fernandes | 2015-12-14 19:24 |  | 2017-05-11 15:03 |  |  |  | 0 | 1 |  |  | CONST-4108, CONST-4109, CONST-4110 | CONST-3280 | Will be able to do this building from 75 Portland | [13 empty] | 0¦i0e98n: | [7 empty] | 9.2234e+18 | [19 empty] | unable to due, since other building didn't go through | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/2230 |  |  | 5 - Very Low |  | West Queen West
Construction | CONST-7324 | Zen King West - 19 Western Battery Rd | Condo | Not a candidate |  | Unresolved | Harvey Tran | Russell Francey | Russell Francey | 2018-01-12 16:11 |  | 2020-05-26 15:35 |  |  | 2019-06-14 | 0 | 3 |  |  | CONST-9533, CONST-9755, CONST-9786, CONST-9793, CONST-9794, CONST-9795, CONST-9796, CONST-9797, CONST-9798, CONST-9799, CONST-9800, CONST-9801, CONST-9802, CONST-9803, CONST-9808 |  | Project Manager for the building is: Arash - anouraee@centrecourt.com *Bulk - Rogers* | [13 empty] | 0¦i0zcu7: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/6760 |  |  | 3 - Normal |  | Liberty Village
Construction | CONST-6171 | The High Park - 1990 Bloor St W | Condo | Not a candidate |  | Unresolved | Harvey Tran | Oguz Avci [X] | Russell Francey | 2017-05-23 10:45 |  | 2020-05-26 15:34 |  |  |  | 0 | 3 | _thumb_223917.png _thumb_223936.png |  | CONST-6172, CONST-6173, CONST-6250 |  | +*New Contact:*+ PM: Ljupco Cortanoski Direct: 416-763-5889 Email: highparkmanager@gmail.com Site Superintendent: Julio @ 647-919-5562 +*Old Contact:*+ Mosammat Jabunnesa (Jebbie), BA The High Park Property Manager Brookfield Condominium Services Ltd. Direct: 416-763-5889 Email: propertymanagement@thehighpark.com Pop on P1 near loading dock room in riser zhone conduits | [13 empty] | 0¦i0r3fz: | [7 empty] | 9.2234e+18 | [19 empty] | Backbone not ready in area, will put on hold. | [6 empty] | 3 - Normal | [28 empty] | 37000 |  |  | https://buildings.beanfield.com/buildings/view/5836 |  |  | 3 - Normal |  |  | 4000 | 16000
Construction | CONST-6650 | 801 King St - CitySphere | Condo | Not a candidate |  | Unresolved | Jessica Markiewicz | Jessica Markiewicz | Russell Francey | 2017-07-24 09:30 |  | 2022-10-28 09:10 |  |  |  | 0 | 1 |  |  | CONST-6651, CONST-9780, CONST-30648, CONST-30649 |  | Ursula Potrzebowski Property Manager MTCC 961 – Citysphere on King Toronto, ON M5V 3C9 T. 416.504.4217 ¦ F. 416.504.7983 | [13 empty] | 0¦i0t30v: | [7 empty] | 9.2234e+18 | [19 empty] | September 27th - Site revisit is needed. | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/1578 |  |  | 3 - Normal |  | West King West
Construction | CONST-4589 | 80 / 90 Sherbourne - Imperial Lofts | Condo | Not a candidate |  | Unresolved | Russell Francey | Russell Francey | Russell Francey | 2016-06-24 10:47 |  | 2021-10-18 12:11 |  |  |  | 0 | 1 | _thumb_71098.png _thumb_71097.png |  | CONST-4590, CONST-4591, CONST-4592 | CONST-3402 | [14 empty] | 0¦i0i7g7: | [7 empty] | 9.2234e+18 | [19 empty] | Condo not candidate | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/4645 |  |  | 3 - Normal |  | Downtown East
Construction | CONST-5497 | 160 The Esplanade | Condo | Not a candidate |  | Unresolved | Russell Francey | Russell Francey | Russell Francey | 2017-01-25 15:26 |  | 2018-01-29 14:35 |  |  |  | 0 | 2 | _thumb_82702.png _thumb_83980.png _thumb_83981.png _thumb_83982.png _thumb_83983.png _thumb_83984.png _thumb_83985.png _thumb_83986.png _thumb_83987.png _thumb_83988.png _thumb_83989.png _thumb_83990.png |  | CONST-5498, CONST-5499, CONST-5500, CONST-5508 |  | Bulk Deal | [13 empty] | 0¦i0nq87: | [7 empty] | 9.2234e+18 | [19 empty] | Co-op could not get votes to leave Rogers VIP package. | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/5560 |  |  | 3 - Normal |  | St. Lawrence
Construction | CONST-3402 | 311 Richmond St E - Imperial Square | Condo | Not a candidate |  | Unresolved | Russell Francey | Jay Fernandes | Jay Fernandes | 2015-05-05 08:20 |  | 2017-05-12 10:31 |  |  |  | 0 | 2 | _thumb_70723.png _thumb_70724.png _thumb_70725.png _thumb_70722.png |  | CONST-3403, CONST-3404, CONST-3405 | CONST-4629, CONST-4589, CONST-4645 | Marko Bakos, R.C.M. ¦ Senior Property Manager Goldview Property Management Ltd. 51 Toro Road, Suite 200 ¦ Toronto, Ontario ¦ M3J 2A4 t: 416-630-1234 ext. 231 ¦ f: 416-630-3132 e: marko@goldview.ca ¦ www.goldview.ca Pop P1 level outside elevator pop room small not much room for us 11 storeys - 1 riser Telephone riser on 6th floor Rogers on 7th floor Suites daisy chained Can connect 311 Richmond to 3330 Adelaide | [13 empty] | 0¦i08tn3: | [7 empty] | 51460 | [19 empty] | Not able to proceed with right now. | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/3322# |  |  | 5 - Very Low |  | Downtown East
Construction | CONST-3242 | 39 Parliament St - Parliament Square Condos | Condo | Not a candidate |  | Unresolved | Russell Francey | Jay Fernandes | Jay Fernandes | 2015-03-20 08:44 |  | 2017-10-20 09:29 |  |  |  | 0 | 2 |  |  | CONST-3243, CONST-3244, CONST-3245 |  | Possibly bring building On-Net | [13 empty] | 0¦i0835z: | [7 empty] | 47171 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/1637# |  |  | 5 - Very Low
BC Construction | BCCONST-447 | 500 Royal Ave (Dominion), New Westminster BC | Condo | Not a candidate |  | Complete | Yawn Paular | Yawn Paular | Yawn Paular | 2023-10-30 19:18 |  | 2023-12-28 13:09 | 2023-11-16 12:30 |  | 2024-01-05 | 0 | 0 |  |  | BCCONST-448, BCCONST-449, BCCONST-450, BCCONST-451, BCCONST-452, BCCONST-453, BCCONST-454 |  | 118 units BAA approved Property Manager: Harlan Kaur Site Contact: Grace Phone Number: 778-835-7791 Availability: Mon-Fri 9-1pm The building has been added to building browser: [https://buildings.beanfield.com/buildings/view/19384] Please keep me posted on installation of our network here. | Bridgenet, confirmed | [12 empty] | 0¦i4ex8v: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
BC Construction | BCCONST-326 | 7 Rialto Court, New Westminster | Condo | Not a candidate |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2023-07-10 18:37 |  | 2023-12-28 13:23 |  |  | 2023-12-01 | 0 | 0 |  |  | BCCONST-327, BCCONST-328, BCCONST-329, BCCONST-330, BCCONST-331, BCCONST-332, BCCONST-358 |  | 85 units, tie into with 10 Renaissance Sq Entrance cable located in the MTR - tie in cable from here to 10 Renaissance Sq Bridgenet in the bldg | Pre-Sales | [12 empty] | 0¦i45vjr: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [37 empty] | 4800 | 4200
BC Construction | BCCONST-489 | 13819 100 Avenue (Carriage Lanes), Surrey BC | Condo | Not a candidate |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2023-11-16 17:30 |  | 2024-05-27 13:10 |  |  | 2024-09-27 | 0 | 0 |  |  | BCCONST-691 |  | 145 units NWS2223 Bayside Property Mgmt - 604-432-7774 | [13 empty] | 0¦i4g8qf: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [26 empty] | Backbone
BC Construction | BCCONST-482 | 9868 Whalley Blvd (Balmoral Tower), Surrey BC | Condo | Not a candidate |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2023-11-16 17:16 |  | 2024-05-27 13:14 |  |  | 2024-06-28 | 0 | 0 |  |  | BCCONST-689, BCCONST-690 |  | 121 units LMS1622 Crossroads - 778-578-4445 | [13 empty] | 0¦i4g8o7: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [26 empty] | Backbone
Construction | CONST-38144 | 93 Lavinia Ave_Toronto_Swansea Town Hall Residences | Condo | Not a candidate |  | Unresolved | Lorna Kurok | Lorna Kurok | Lorna Kurok | 2024-08-15 09:51 |  | 2024-11-12 10:07 |  |  |  | 0 | 0 |  |  | CONST-38145, CONST-38146, CONST-38149 |  | _Requested By Oliver_ *68 Units for 93 Lavinia Ave* h4. {color:#0747a6}*Site Contact:*{color} Helen Davies [helend@cfdi.ca¦mailto:helend@cfdi.ca] 289-453-0588 Email Below: Could you please proceed with creating a new ticket for an OSP plan & site walk at 93 Lavinia Ave? The Swansea Town Hall Residences is a co-op with 68 units. This location is directly beside the TPL branch at 95 Lavinia Ave. ISW will be required as the building was constructed in 1993. BB Link: [https://buildings.beanfield.com/buildings/view/20701] Site Contact: Helen Davies [helend@cfdi.ca¦mailto:helend@cfdi.ca] 289-453-0588 Thank you, ¦Oliver Davies¦ | [13 empty] | 0¦i54r27: | [7 empty] | 9.2234e+18 | [19 empty] | Aug 15, 2025_Project initiated Aug 14, 2024. | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/20701 |  |  | 3 - Normal |  | Toronto
BC Construction | BCCONST-693 | 488 Furness St (Portside Townhouse Complex) New Westminster BC | Condo | Not a candidate |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2024-05-15 17:24 |  | 2024-11-08 13:49 |  |  | 2024-10-31 | 0 | 0 | _thumb_1045081.png |  | BCCONST-694, BCCONST-695, BCCONST-752, BCCONST-753, BCCONST-767, BCCONST-776 | PUR-39492 | 171 units Row housings - 8ERs *Dan Cathcart* Senior Strata Agent Rancho Management Services (B.C.) Ltd. Direct 604.331.4249 | Bridgenet, Budget_Allocated | [12 empty] | 0¦i4ubgv: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [37 empty] | 9700 | 11300
Construction | CONST-27238 | 190 Manitoba St, Toronto - The Legend at Mystic Pointe | Condo | Not a candidate |  | Unresolved | Lorna Kurok | Lorna Kurok | Harvey Tran | 2022-03-09 15:06 |  | 2024-11-19 11:36 |  |  |  | 0 | 0 |  |  | CONST-27416, CONST-27417, CONST-37975, CONST-38013 | CONST-27231, CONST-27235, CONST-27237, CONST-33547, CONST-35974, CONST-38015, CONST-38017, CONST-38018 |  | Fiberstreamagreement, HumberBay | [12 empty] | 0¦i393kv: | [7 empty] | 9.2234e+18 | [19 empty] | July 14th - This building is not candidate, since it is daisy chained. | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/4104 |  |  | 3 - Normal
BC Construction | BCCONST-794 | 2933, 3001, & 3005 Murray Street, Port Moody BC | Condo | Not a candidate |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2024-09-16 14:55 |  | 2024-12-06 19:27 |  |  | 2025-02-21 | 0 | 0 |  |  | BCCONST-795, BCCONST-796, BCCONST-797, BCCONST-798, BCCONST-799, BCCONST-800, BCCONST-801 |  | Murray Street, Port Moody - 2933, 3001, & 3005 Murray Street (207 total units) This proposal envisions a 12-storey Mass Timber building, providing for 207 rental residential units, the majority of which are designed to be dual-aspect homes with access to significant daylight and views to encourage livability. 10% of the homes will also be committed to below market rates (at Housing Income Limits rents) to ensure affordability, and resident amenities will be provided with access to extensive indoor and outdoor amenity space, including bicycle and kayak storage space, rooftop decks, children’s play area, fitness centre and rooftop urban agriculture plots. | [13 empty] | 0¦i576yf: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
BC Construction | BCCONST-638 | 13458 95 Avenue, (Galilea), Surrey BC | Condo | Not a candidate |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2024-04-04 13:43 |  | 2024-12-09 13:36 |  |  | 2025-12-26 | 0 | 0 |  |  | BCCONST-649 |  | New Bldg DES Surrey 129 Units/6 floors | DES | [12 empty] | 0¦i4q56n: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
BC Construction | BCCONST-481 | 9866 Whalley Blvd (Balmoral Court), Surrey BC | Condo | Not a candidate |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2023-11-16 17:16 |  | 2024-12-09 17:34 |  |  | 2024-11-29 | 0 | 0 |  |  |  |  | 87 units LMAS1622 Crossroads - 778-578-4445 | [13 empty] | 0¦i4g8nz: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [26 empty] | Backbone
Construction | CONST-32565 | 800 King St W - The Kings Lofts | Condo | Not a candidate |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Denise King | 2023-01-03 09:53 |  | 2024-10-10 11:56 |  |  |  | 0 | 1 |  |  | CONST-32567, CONST-32568 | CONST-4923, CONST-32606 | Requested by Oliver Davies: PM Info: Milka Matejic, RCM, OLCM PropertyWright Management Inc. MTCC 1302/MTCC 1346 208 Niagara St./800 King St. West Toronto, ON M6J 2L3/M5V 3M7 Monday, Wednesday, Thursday, Friday 8:00 am – 4:00 pm Tuesday 10:00 am – 6:00 pm Tel. (416) 362 – 9779 [Mtcc1346office@rogers.com¦mailto:Mtcc1346office@rogers.com] | [13 empty] | 0¦i3s04f: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/2030 |  |  | 3 - Normal |  | King West
BC Construction | BCCONST-548 | 618 Carnarvon St, New Westminster BC | Condo | Not a candidate |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2023-12-07 18:37 |  | 2024-10-18 18:29 |  |  | 2024-11-29 | 0 | 0 | _thumb_1045082.png |  | BCCONST-549, BCCONST-550, BCCONST-551, BCCONST-552, BCCONST-553, BCCONST-554, BCCONST-555, BCCONST-635 |  | New Bldg - occupancy date Dec 8th Property manager will reach out once they have access to the bldg 262 units 33 flrs Michael Love <Michael@quaypacific.com> - new property manager | Bridgenet, Budget_Allocated | [12 empty] | 0¦i4hutr: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [37 empty] | 14400 | 5200
Construction | CONST-12608 | Corktown District I - 52 Sumach St, Toronto | Condo | Not a candidate |  | Unresolved | Lorna Kurok | Lorna Kurok | Oguz Avci [X] | 2020-06-02 14:39 |  | 2024-12-11 09:34 |  |  |  | 0 | 2 |  |  | CONST-12609, CONST-12986, CONST-12987, CONST-39434 | CONST-12584, CONST-12606 | *+Site walk instruction:+* Please go to 510 King St. East in order to get access as they manage all of the buildings. +*Contact information:*+ Your ICON Property Management Team Icon Property Management Ltd. 510 King Street East Toronto ON M5A 0E5 Site Office Phone: 416-363-0438 ¦ Security Phone: 416-363-9392 ¦ Emergency Phone: 416 201 3887 Head Office Phone: 416-236-7979 ¦ Head Office Fax: 416-236-7977 | [13 empty] | 0¦i1z913: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 7 | 134 | [5 empty] | https://buildings.beanfield.com/buildings/view/2912 |  |  | 3 - Normal
Construction | CONST-37967 | 100 Mornelle Crt_Toronto_Centennial Hill | Condo | Not a candidate |  | Unresolved | Lorna Kurok | Lorna Kurok | Lorna Kurok | 2024-07-22 11:18 |  | 2025-01-07 08:57 |  |  |  | 0 | 1 |  |  | CONST-37968, CONST-37969, CONST-37970 |  | Constructed in 1977 Could you please create a new ticket for an OSP plan & site walk for Centennial Hill Condominiums at 100 Mornelle Crt? This condo has 209 residential units and was constructed in 1977 - ISW work will most likely be required. This location is near-net and ideally we will have minimal OSP work required to enter the building. BB Link: [https://buildings.beanfield.com/buildings/view/20591] h2. *Site Contact:* Flora Zeqiri Property Administrator Management Office York Condominium Corporation A.A. Property Management & Associates [ycc331@gmail.com¦mailto:ycc331@gmail.com] T:416-284-9769 C:647-859-8928 – ¦James Fox¦ ¦_Manager, Business Development_¦ | [13 empty] | 0¦i52rwf: | [7 empty] | 9.2234e+18 | [19 empty] | Jan 6, 2025 - Updated project to Not a Candiate. (there is No Capacity to house Beanfield equipment in the risers.) | [6 empty] | 3 - Normal | [24 empty] | 2 | 208 | [5 empty] | https://buildings.beanfield.com/buildings/view/20591 |  |  | 3 - Normal |  | Toronto
BC Construction | BCCONST-834 | 5980 Kathleen Ave (Broadview), Burnaby BC | Condo | Not a candidate |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2024-12-11 17:24 |  | 2024-12-26 12:29 |  |  | 2025-12-26 | 0 | 0 |  |  |  | BCCONST-353, BCCONST-352 | 35 flrs 295 units Condo Rental Tower | [13 empty] | 0¦i5ebk7: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 35 | 295
Construction | CONST-25898 | 352 Front St W, Toronto | Condo | Not a candidate |  | Unresolved | Unassigned | Lorna Kurok | Harvey Tran | 2021-11-29 14:51 |  | 2025-02-12 08:51 |  |  |  | 0 | 0 |  |  | CONST-25967, CONST-25968, CONST-25969, CONST-26073, CONST-26108, CONST-26109, CONST-26110, CONST-26112, CONST-26113, CONST-26114, CONST-26115, CONST-26116, CONST-26117, CONST-26118, CONST-26119, CONST-26120 | CONST-2764 |  | Fiberstreamagreement | [12 empty] | 0¦i32cvr: | [7 empty] | 9.2234e+18 | [19 empty] | Dec 6th - Project started, City permit application to be in progress. | [6 empty] | 3 - Normal | [21 empty] | 2021-12-06 |  |  | 24 | 465 | [5 empty] | https://buildings.beanfield.com/buildings/view/1775 |  | 500334 | 3 - Normal | 2022-04-15
Montreal Construction | MTLCONST-9753 | 6993 Décarie | Condo | Not a candidate |  | Unresolved | Marianne Yanni | Marianne Yanni | Marianne Yanni | 2024-02-22 10:29 |  | 2025-02-04 09:39 |  |  |  | 0 | 0 |  |  | MTLCONST-9754, MTLCONST-9755 |  | Requested by [~mamaral] We have a Residential opportunity at 6993 Décarie for a 104 unit bulk internet deal. We spoke with Mike Massie and he requires a estimate for the internal costs of deployment in order to assess the opportunity. The site contact is David 514-516-2723. | [13 empty] | 0¦i4mzjb: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/19528
Construction | CONST-17365 | 88 Queen Street East, Toronto | Condo | Condo Not Interested |  | Unresolved | Harvey Tran | Harvey Tran | Harvey Tran | 2020-12-02 14:11 |  | 2021-02-17 17:14 |  |  |  | 0 | 1 |  |  | CONST-17366 |  | This building is the development directly to the south of 77 Shuter. James passed by today and they are in the process of bring several utilities in. | [13 empty] | 0¦i2bopb: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [34 empty] | 3 - Normal
Construction | CONST-11474 | 460 Adelaide St E - Axiom Condos | Condo | Condo Not Interested |  | Unresolved | Russell Francey | Russell Francey | Russell Francey | 2019-11-28 11:06 |  | 2021-11-30 10:30 |  |  |  | 0 | 0 |  |  | CONST-11475, CONST-11675, CONST-12956, CONST-12957 | CONST-25899 | PMs info: Genta, axiomcondocm@bellnet.ca | Agreement | [12 empty] | 0¦i1r2jz: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/7479 |  |  | 3 - Normal
Construction | CONST-3202 | 90 Broadview Ave - The Ninety | Condo | Condo Not Interested |  | Unresolved | Russell Francey | Jay Fernandes | Jay Fernandes | 2015-03-12 09:35 |  | 2022-02-18 16:10 |  |  |  | 0 | 0 |  |  | CONST-3203, CONST-5079, CONST-5080 | [15 empty] | 0¦i07yrz: | [7 empty] | 46460 | [19 empty] | Condo is looking at a bulk option, should know more in the coming month | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/1569# |  |  | 5 - Very Low |  | Carlaw (Leslieville)
Construction | CONST-3019 | 170 Sudbury St - Curve Condos | Condo | Condo Not Interested |  | Unresolved | Russell Francey | Jay Fernandes | Jay Fernandes | 2015-02-25 08:20 |  | 2022-07-06 08:48 |  |  |  | 0 | 1 |  |  | CONST-3020, CONST-3021, CONST-3022 |  | Condo in WQW we hope to do after the Sheridan build is completed. PM: Elaine.Lee@fsresidential.com ELAINE LEE Direct 647.417.3102 | Residential | [12 empty] | 0¦i07qe7: | [7 empty] | 45102 | [19 empty] | Need to find out who the PM is now | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/building/view/2294 |  |  | 3 - Normal |  | West Queen West
BC Construction | BCCONST-360 | 977 Mainland Street, Vancouver (Yaletown Park 3) | Condo | Condo Not Interested |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2023-08-02 13:03 |  | 2023-12-12 12:13 |  |  | 2024-05-31 | 0 | 0 |  |  | BCCONST-369, BCCONST-370, BCCONST-371, BCCONST-372, BCCONST-373, BCCONST-374, BCCONST-375 | BCCONST-1, BCCONST-333 | 30 flrs/277 units Waiting for Michael to setup site check | [13 empty] | 0¦i47xq7: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
Construction | CONST-3488 | 120 Balliol - Balliol Park | Condo | Condo Not Interested |  | Unresolved | Russell Francey | Jay Fernandes | Jay Fernandes | 2015-06-01 20:28 | 2025-03-04 10:44 | 2018-04-16 12:02 |  |  |  | 0 | 1 |  |  | CONST-3489 |  | Developer approached Chris | [13 empty] | 0¦i098fb: | [7 empty] | 53855 | [19 empty] | Developer approached Chris | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/3447 |  |  | 5 - Very Low |  | Yonge & Eglinton (incl. North Yonge)
Construction | CONST-3490 | 45 Dunfield Ave - The Torontonian | Condo | Condo Not Interested |  | Unresolved | Russell Francey | Jay Fernandes | Jay Fernandes | 2015-06-01 20:30 |  | 2017-12-07 11:23 |  |  |  | 0 | 1 |  |  | CONST-3491 |  | Developer approached Chris regarding a bulk deal | [13 empty] | 0¦i098fr: | [7 empty] | 53857 | [19 empty] | Chris working on bulk deal - followup with Chris - May 11th | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/3448 |  |  | 5 - Very Low |  | Yonge & Eglinton (incl. North Yonge)
Construction | CONST-10539 | Park Lake Residences - 1900 Lake Shore Blvd W | Condo | Condo Not Interested |  | Unresolved | Russell Francey | Russell Francey | Russell Francey | 2019-05-23 11:47 |  | 2022-12-21 11:58 |  |  |  | 0 | 0 |  |  | CONST-10540, CONST-10541 |  | Zamira Salillari, RCM Property Manager Crossbridge Condominium Services Ltd As Agents for and on behalf of Park Lake Residences TSCC 2129 1900 Lake Shore Blvd West Toronto, ON, M6S 1A4 Tel: 647-352-1900 Fax: 647-352-1919 Email: tscc2129@gmail.com | [13 empty] | 0¦i1jq6f: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/8331 |  |  | 3 - Normal
Construction | CONST-10366 | Garden District Condos - 79 Shuter | Condo | Condo Not Interested |  | Unresolved | Russell Francey | Russell Francey | Russell Francey | 2019-05-02 09:28 |  | 2019-08-14 11:02 |  |  |  | 0 | 0 |  |  | CONST-10367, CONST-10368 |  | Chris is working with - Shakeel. shakeel@shercorp.ca Estimated Occupancy : Jan 2020 | [13 empty] | 0¦i1iy0n: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/6975 |  |  | 3 - Normal
Construction | CONST-9553 | Riva Del Lago - 110 Marine Parade Dr | Condo | Condo Not Interested |  | Unresolved | Russell Francey | Russell Francey | Russell Francey | 2019-01-08 14:58 |  | 2019-03-01 12:35 |  |  |  | 0 | 0 |  |  | CONST-9554 |  | Airish de Leon TSCC 2594 110 MARINE PARADE DRIVE Etobicoke, ON, M8V 0B6 Tel: 416-901-2436 / Fax: 416 901 2438 Concierge: 416 546 8990 Email: rivacondo.pm@gmail.com | [13 empty] | 0¦i1eiov: | [7 empty] | 9.2234e+18 | [19 empty] | PM became MIA | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/5886 |  |  | 3 - Normal |  | Etobicoke
Construction | CONST-9954 | 180 Sudbury - 180 Sudbury St | Condo | Condo Not Interested |  | Unresolved | Russell Francey | Russell Francey | Russell Francey | 2019-03-07 11:06 |  | 2019-04-23 14:36 |  |  |  | 0 | 0 |  |  | CONST-9955, CONST-9995 |  | Tina Le Property Manager 180 Sudbury Street, Toronto, ON, M6J 0A8 Email: tina@stclares.ca Phone: 416-927-1899 ext: 229 | [13 empty] | 0¦i1go5r: | [7 empty] | 9.2234e+18 | [19 empty] | PM decided not to move forward with Beanfield | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/2293 |  |  | 3 - Normal |  | Liberty Village
Construction | CONST-7409 | The Ravine - 1215 York Mills Rd | Condo | Condo Not Interested |  | Unresolved | Russell Francey | Russell Francey | Russell Francey | 2018-01-29 16:04 | 2025-03-10 14:33 | 2019-02-25 13:36 |  |  |  | 0 | 0 |  |  |  |  | Follow up if no response by October. - Jory | [13 empty] | 0¦i0zvsf: | [7 empty] | 9.2234e+18 | [19 empty] | Matt working on agreement. | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/6811 |  |  | 3 - Normal |  | North York
Construction | CONST-7223 | 59 - 71 Mutual St - Ivy Condos | Condo | Condo Not Interested |  | Unresolved | Russell Francey | Russell Francey | Samantha Russell | 2017-12-13 08:11 |  | 2019-02-25 14:38 |  |  |  | 0 | 2 |  |  |  |  | Pre Construction, Chris to advise Jory | [13 empty] | 0¦i0ydn3: | [7 empty] | 9.2234e+18 | [19 empty] | No response from developer | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/6806 |  |  | 3 - Normal |  | Church & Wellesley Village
Construction | CONST-7302 | The Summit - 701 King, 705 King, 725 King | Condo | Condo Not Interested |  | Unresolved | Russell Francey | Russell Francey | Russell Francey | 2018-01-09 14:09 | 2025-03-04 15:11 | 2018-01-25 11:18 |  |  |  | 0 | 0 |  |  | CONST-7303 | [15 empty] | 0¦i0z6hj: | [7 empty] | 9.2234e+18 | [19 empty] | Presentation sent for the 3 MTCC, will see if any of them are interested. | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/818 |  |  | 3 - Normal |  | King West
Construction | CONST-5649 | U Condominium - 65 St. Mary St | Condo | Condo Not Interested |  | Unresolved | Russell Francey | Russell Francey | Russell Francey | 2017-02-27 09:30 |  | 2022-09-28 13:54 |  |  |  | 0 | 2 | _thumb_91175.png _thumb_91177.png |  | CONST-5650, CONST-5651, CONST-5652, CONST-6204 | CONST-25883 | Mark Shaffelburg R.C.M. Property Manager T.S.C.C. 2525 - U Condominiums 65 St. Mary St./1080 Bay St. 647 346 3277 mshaffelburg@scpl.ca 65 St Mary connects to 1080 Bay both have telephone rooms and look like they are interconnected POP for 1080 Bay on P1 beside V43 tight for space POP for 65 St Mary P1 beside V7- no access on day of site visit Also has townhouse Zone conduits have space , bothBell and Rogers have fiber to suites | [13 empty] | 0¦i0oio7: | [7 empty] | 9.2234e+18 | [16 empty] | 10000 |  |  | "The Board is not moving forward with this type of project in the foreseeable future." from the PM | [6 empty] | 3 - Normal | [28 empty] | 15000 |  |  | https://buildings.beanfield.com/buildings/view/5713 |  |  | 3 - Normal |  | Bay St Corridor | 3000
Construction | CONST-5255 | 7 Broadway - Broadway Plaza | Condo | Condo Not Interested |  | Unresolved | Russell Francey | Russell Francey | Russell Francey | 2016-12-12 11:18 | 2025-03-04 15:43 | 2017-03-13 19:57 |  |  |  | 0 | 0 |  |  | CONST-5256, CONST-5257 | [15 empty] | 0¦i0mrbz: | [7 empty] | 9.2234e+18 | [19 empty] | Did not end up moving forward. | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/5204 |  |  | 3 - Normal |  | Yonge & Eglinton (incl. North Yonge)
Construction | CONST-6574 | Infinity IV - 25 Lower Simcoe | Condo | Condo Not Interested |  | Unresolved | Russell Francey | Russell Francey | Russell Francey | 2017-07-12 15:19 |  | 2021-06-22 13:29 |  |  |  | 0 | 2 |  |  | CONST-6575, CONST-6576, CONST-6745, CONST-6864, CONST-7680, CONST-8409, CONST-8410, CONST-9317, CONST-9620 | CONST-6186 | [14 empty] | 0¦i0sqvz: | [7 empty] | 9.2234e+18 | [19 empty] | Emailed PM to see if they were still interested - March 4 | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/6255 |  |  | 3 - Normal |  | Southcore
Construction | CONST-5719 | 21 Nassau St - Kensington Market Lofts | Condo | Condo Not Interested |  | Unresolved | Russell Francey | Russell Francey | Russell Francey | 2017-03-15 12:09 |  | 2018-01-29 13:22 |  |  |  | 0 | 2 |  |  | CONST-5720, CONST-5721, CONST-5722, CONST-5737 |  | Erika Belicky ebelicky@360cm.ca 647.269.2229 Code for Lock box 2031 Main telephone room in 21 Nassau in PM office to the right Interconnected to 160 Baldwin Zhone conduits for Rogers and bell in both buildings Communication room for 160 Baldwin is on 3rd floor mechanical closet | [13 empty] | 0¦i0pbnj: | [7 empty] | 9.2234e+18 | [19 empty] | To far away from backbone. | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/5814 |  |  | 3 - Normal |  | Chinatown
Construction | CONST-7735 | The Stewart Lofts - 32 Stewart St | Condo | Condo Not Interested |  | Unresolved | Russell Francey | Russell Francey | Russell Francey | 2018-03-21 14:44 |  | 2022-03-04 13:17 |  |  |  | 0 | 0 |  |  | CONST-7736, CONST-7737, CONST-7738 |  | Ljupco (Lou) Cortanoski Property Manager lou@goldview.ca Goldview Property Management Ltd. 51 Toro Road, Suite 200 Toronto ON M3J 2A4 | [13 empty] | 0¦i11uq7: | [7 empty] | 9.2234e+18 | [19 empty] | PM no longer with building, never heard back since sending agreement. | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/1970 |  |  | 3 - Normal |  | King West
Construction | CONST-4425 | 28 Ted Rogers Way - Couture | Condo | Condo Not Interested |  | Unresolved | Russell Francey | Jay Fernandes | Jay Fernandes | 2016-04-28 08:32 |  | 2017-03-13 20:27 |  |  |  | 0 | 2 |  |  | CONST-4426, CONST-4427, CONST-4428 |  | Site Administrator Diana Hirboca 416.298.1956 couturecondos@rogers.com Property Manager Peter Tanase 416-928-1956 couturemanager@rogers.com www.brookfieldcondominiums.com 476 Suites Built in 2013 2 Risers 44 Storeys Power confirmed PoP room in P1 level | [13 empty] | 0¦i0gjwv: | [7 empty] | 9.2234e+18 | [19 empty] | PM never returned any calls or email. | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/2158 |  |  | 5 - Very Low |  | Church & Wellesley Village
Construction | CONST-4319 | 5 Sheppard Ave E - Hullmark Centre II | Condo | Condo Not Interested |  | Unresolved | Russell Francey | Jay Fernandes | Jay Fernandes | 2016-03-16 09:10 |  | 2018-08-27 15:01 |  |  |  | 0 | 1 |  |  | CONST-4320, CONST-4321, CONST-4322 | CONST-4315 | Use other ticket for now. | [13 empty] | 0¦i0ft53: | [7 empty] | 9.2234e+18 | [19 empty] | Project on hold - see main ticket for updates | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/4490 |  |  | 5 - Very Low |  | North York
Construction | CONST-10512 | Ten93 Queen West Condos - 106 Dovercourt Rd | Condo | Condo Not Interested |  | Unresolved | Russell Francey | Russell Francey | Russell Francey | 2019-05-21 11:14 |  | 2019-08-20 11:55 |  |  |  | 0 | 0 |  |  | CONST-10513, CONST-10514, CONST-10515 |  | Shena Grouse Property Management TSCC 2698 647-346-1471 shena.grouse@scpl.ca | [13 empty] | 0¦i1jm9z: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/7360 |  |  | 3 - Normal |  | West Queen West
Construction | CONST-10796 | Glen Lake - 2495 Dundas St W | Condo | Condo Not Interested |  | Unresolved | Russell Francey | Russell Francey | Russell Francey | 2019-07-11 14:52 | 2025-03-04 10:05 | 2019-08-19 14:28 |  |  |  | 0 | 0 |  |  | CONST-10797 |  | Michael Kudrac glenlakemgmt@rogers.com 416-762-3443 Cost are too high for now. | [13 empty] | 0¦i1lqy7: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/8464 |  |  | 3 - Normal |  | The Junction
Construction | CONST-6668 | 20 Gothic Ave - Twenty Gothic | Condo | Condo Not Interested |  | Unresolved | Russell Francey | Russell Francey | Russell Francey | 2017-08-03 09:11 |  | 2017-12-07 11:21 |  |  |  | 0 | 0 |  |  | CONST-6669 |  | Meredith Rosenfeldt 20 Gothic Avenue Toronto, ON M6P 1T5 Phone: (416) 766-6546 Fax: (416) 766-0329 Email: TwentyGothic.PM@DelCondo.com | [13 empty] | 0¦i0tjgf: | [7 empty] | 9.2234e+18 | [19 empty] | PM checking with board about presentation | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/4247 |  |  | 3 - Normal |  | Bloor West
Construction | CONST-5344 | 18 Yonge | Condo | Condo Not Interested |  | Unresolved | Russell Francey | Russell Francey | Russell Francey | 2017-01-11 08:03 |  | 2019-02-26 18:14 |  |  |  | 0 | 1 |  |  | CONST-5345, CONST-5346, CONST-5347, CONST-6548, CONST-8340 |  | Antoneta Reci G.L.M, R.C.M Phone: 416.368.3111 Fax: 416.368.3188 Email: 18Yonge.PM@DelCondo.com 39 Storeys 2 risers zone conduits have coax and cat 5 Pop is on P1 NE corner of Parking lot beside parking space 142 P1-2 underground P3-4-5 above ground Amenities and management office on6th floor Res starts on 6th floor Fed from Yonge and Esplanade MH Breakout of cc 3266 full crossing of Yonge st trench and core into telephone room | [13 empty] | 0¦i0ne9j: | [7 empty] | 9.2234e+18 | [19 empty] | Board decided not to allow Beanfield into the building. No reason was given. | [6 empty] | 3 - Normal | [28 empty] | 26000 |  |  | https://buildings.beanfield.com/buildings/view/1650 |  |  | 3 - Normal |  | Southcore | 1000 | 2000
Construction | CONST-3280 | 75 Portland | Condo | Condo Not Interested |  | Unresolved | Russell Francey | Jay Fernandes | Jay Fernandes | 2015-03-26 07:42 | 2025-03-04 10:42 | 2018-01-15 11:56 |  |  |  | 0 | 1 | _thumb_57689.png _thumb_57690.png _thumb_57691.png |  | CONST-3281, CONST-3282, CONST-3283, CONST-4048, CONST-4063 | CONST-4107 | Possibly bring building on-net Ken Mah On-Site Manager Toronto Standard Condominium Corporation 2102 75 Portland Street ¦ Toronto, Ontario ¦ M5V 2M9 t: 647-342-4163 ¦ f: 416-591-6301 e: ken@goldview.ca pop P1 level beside stairs to portland 211 suites 10 floors + PH 2 risers floor 5, 7, 9 2 storey suites Cat 5 in suites power not confirmed | [13 empty] | 0¦i086t3: | [7 empty] | 47761 | [19 empty] | Agreements finalized, but Condo board not proceeding | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/1717 |  |  | 5 - Very Low |  | King Spadina / Garment District
Construction | CONST-38618 | 71 Charles St E, Toronto, Paxton Place | Condo | Condo Not Interested |  | Unresolved | Lorna Kurok | Lorna Kurok | Lorna Kurok | 2024-09-23 15:20 |  | 2024-11-12 10:05 |  |  |  | 0 | 0 |  |  | CONST-38619, CONST-38620, CONST-38621 |  | Requested by James Fox Sept 23, 2024. Units 101 Floors 16 Constructed 1983 Likely to require ISW workThis location is near-net and ideally we will have minimal OSP work required to enter the building. {color:#0747a6}*Site Contact:*{color} *Alberto Alonso* *Ontario Licensed Condominium Manager (OLCM)* Wilson Blanchard Management Inc. Phone: 416-642-2807 Ext. 449 Email: [Alberto.Alonso@wilsonblanchard.com¦mailto:Alberto.Alonso@wilsonblanchard.com] Open Email Below: Could you please create a new ticket for an OSP plan & site walk for Paxton Place at 71 Charles St E? This condo has 101 residential units and was constructed in 1983 - ISW work will most likely be required. This location is near-net and ideally we will have minimal OSP work required to enter the building. BB Link: [https://buildings.beanfield.com/buildings/view/5022] Site Contact: *Alberto Alonso* *Ontario Licensed Condominium Manager (OLCM)* Wilson Blanchard Management Inc. Phone: 416-642-2807 Ext. 449 Email: [Alberto.Alonso@wilsonblanchard.com¦mailto:Alberto.Alonso@wilsonblanchard.com] – | [13 empty] | 0¦i57pwf: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/5022 |  |  | 3 - Normal |  | Toronto
Construction | CONST-37784 | 395 Bloor St E, Toronto (BULK) | Condo | Condo Not Interested |  | Unresolved | Harvey Tran | Harvey Tran | Harvey Tran | 2024-06-24 11:39 |  | 2024-12-06 09:17 |  |  |  | 0 | 0 |  |  | CONST-37785, CONST-37786, CONST-37829, CONST-37878 |  | Requested by Oliver Davies. We have an opportunity to win a bulk-agreement with the TSCC 2977 corporation at 387 & 395 Bloor St E. There are 486 residential units at the "Rosedale on Bloor" condos. Rogers bulk agreement expires/renews May 2 2025 - so I'll be working to win this for Beanfield within the next 2-3 months. There is a hotel that shares an address with the condo, Canopy by Hilton Yorkville. Property manager can introduce us to the hotel if needed. Could you please queue up a new ticket for an OSP plan & Site Walk? BB Link: [https://buildings.beanfield.com/buildings/view/18020] +*PM Info:*+ *Anna Oreshyna, BES, RCM* Senior Condominium Manager _TSCC 2977- Rosedale on Bloor, 395 Bloor Street East, Toronto ON M4W 0B4_ Office: 437-880-2992/Direct: 416-546-2126 x196 [Anna.Oreshyna@Melbournepm.ca¦mailto:Anna.Oreshyna@Melbournepm.ca] | BulkDeal | [12 empty] | 0¦i4yj8n: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 55 | 486 | [5 empty] | https://buildings.beanfield.com/buildings/view/18020 |  |  | 3 - Normal |  | Toronto
Construction | CONST-33398 | 252 Parliament St, Toronto | Condo | Condo Not Interested |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2023-03-22 14:09 |  | 2024-10-11 08:48 |  |  |  | 0 | 0 |  |  | CONST-33403, CONST-38142, CONST-38150 | CONST-33394, CONST-33395, CONST-33396, CONST-33397 | Requested by Oliver Davies Can you please have OSP tickets created for Mark at the following 5x addresses? These are all planned purpose-built rental communities being constructed by Core Development Group that have yet to break ground, so no site-walk is required. We would like to get an idea of what will be required to connect these locations to the Beanfield network. 929 Queen E & 252 Parliament are likely to be the most difficult. Core is looking for an ISP partner to provide connectivity to all of the units in their upcoming rental communities. * 929 Queen St E: 68 units / July 2025 occupancy (Leslieville Pumps location - BFMH located nearby via CDSM10723) * 1233 Queen St: 142 units / June 2025 occupancy (off-net -Queen / Leslie - no fibre in the immediate vicinity) * 1111 Danforth: 208 units / June 2025 occupancy (near-net CC#6083 outside of building) * 403 Keele: 261 units / September 2025 occupancy (near-net BF-0781 outside of building, this is just below the active build at 60/61 Heintzman) * 252 Parliament: 80 units / November 2024 occupancy (off-net no fibre between Queen to Dundas on Parliament) scheduled to break ground this year Each location is expected to have a number of retail units at grade. They have provided drawings/plans for all 5x locations, I will upload them to the JIRA tickets once created. Thanks! | CoreDevelopmentGroup | [12 empty] | 0¦i3xmnb: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/18103 |  |  | 3 - Normal |  | Toronto
Construction | CONST-30161 | 701 King St W - The Summit | Condo | Condo Not Interested |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Jessica Markiewicz | 2022-08-24 10:04 |  | 2024-10-10 11:45 |  |  |  | 0 | 2 |  |  | CONST-30162, CONST-30163 |  | Requested by Oliver Davies. Can we please queue up James for a site walk at 701 King St W? [https://buildings.beanfield.com/buildings/view/818] Site Contact: Colin Owens 647-217-7740 [Colin.owens.701board@gmail.com¦mailto:Colin.owens.701board@gmail.com] We have history in working with these guys in the past. There are 3x corporations that make up the “Summit” condominiums, Colin is the board treasurer of MTCC 648 / 701 King St W which has approx. 179 units, but my understanding is that there are 3x corporations that comprise these towers for a total of 740 units. This location will require a prewire of the suites, however they have been pressing us for a bulk services proposal for their residents, and we will need an updated budget so we have a framework to base our numbers on. | [13 empty] | 0¦i3k2rj: | [7 empty] | 9.2234e+18 | [19 empty] | October 28th - Site Visit requested. | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/818 |  |  | 3 - Normal
BC Construction | BCCONST-645 | 9656/9651 King George Blvd (Rize Medical), Surrey BC | Condo | Condo Not Interested |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2024-04-04 17:14 |  | 2024-09-20 19:36 |  |  | 2025-01-31 | 0 | 0 |  |  | BCCONST-658 |  | DES Conduit Entrance Rize Medical 392 units 38 flrs (4 CRUs) Joyce Shen [j.shen@rizealliance.com¦mailto:j.shen@rizealliance.com] Jericho Velarde [j.velarde@hovercraftbuilders.ca¦mailto:j.velarde@hovercraftbuilders.ca] In Service Date Jun 1st BOSA Bldg | DES | [12 empty] | 0¦i4q6wf: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
Construction | CONST-12372 | 10 Old York Mills | Condo | Condo Not Interested |  | Unresolved | Harvey Tran | Oguz Avci [X] | Oguz Avci [X] | 2020-05-11 09:18 | 2025-03-04 17:53 | 2024-10-21 13:14 |  |  |  | 0 | 1 |  |  | CONST-12373, CONST-12430, CONST-12966, CONST-12967 | CONST-38921 | Monica Abbas, General Licence Condominium Manager, Crossbridge Condominium Services Ltd. Agents for and on Behalf of MTCC No. 1401 10 Old York Mills Rd, Toronto, ON, M2P 2G9 Tel: 416.512.0867, Email: [monica.abbas@crossbridgecs.com¦mailto:monica.abbas@crossbridgecs.com] [10OldYorkMills@crossbridgecs.com¦mailto:10OldYorkMills@crossbridgecs.com] ^NEW PM^ *{color:#000000}site contact: {color}* *{color:#000000}Elise Deschamps, OLCM{color}* {color:#000000}Senior Condominium Manager/ MTCC 1401{color} {color:#000000} {color} {color:#000000}10 Old York Mills Road, Toronto, ON M2P 2G9{color} {color:#000000}Telephone: 416-560-5988{color} {color:#000000}E-mail: [pm@mtcc1401.ca¦mailto:pm@mtcc1401.ca]{color} {color:#000000} {color} | [13 empty] | 0¦i1y6sn: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [34 empty] | 3 - Normal
BC Construction | BCCONST-696 | 128 W Cordova - Woodwards Building W43 | Condo | On Hold |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2024-05-22 11:52 |  | 2024-11-25 19:23 |  |  | 2025-06-27 | 0 | 0 |  |  | BCCONST-697, BCCONST-698, BCCONST-699, BCCONST-700, BCCONST-701, BCCONST-702, BCCONST-703, BCCONST-740, BCCONST-773 | BCCONST-424 | 365 Units 43 Floors Existing building Following up from yesterday's call re. 128 W Cordova (BCS 2458) and the pending bulk-renewal in February 2025, can you please open a JIRA ticket for this building, and proceed with building an ISP budget that includes pre-wiring all of the 365x units? | migration | [12 empty] | 0¦i4up5r: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
BC Construction | BCCONST-715 | Fiberstream Buildings Budget Phase 1 | Condo | On Hold |  | Unresolved | Michael Tsamkiranis | Yawn Paular | Yawn Paular | 2024-05-31 11:56 |  | 2024-12-06 21:50 |  |  | 2026-01-02 | 0 | 0 |  |  | BCCONST-716, BCCONST-717, BCCONST-718, BCCONST-719, BCCONST-720, BCCONST-721, BCCONST-722 |  | FS Addresses within the ring that can be fed from 1040 Hamilton, 555 W Hastings ¦969 & 989 Richards St¦ ¦1055 Richards St¦ ¦1155 & 1199 Seymour St¦ ¦535 and 565 Smithe St¦ ¦833 Seymour St¦ ¦788 Richards St¦ ¦610 Granville St¦ This ticket is for budget estimate only | [13 empty] | 0¦i4wmwf: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
BC Construction | BCCONST-611 | 288 Ungless Way (Crescendo), Port Moody BC | Condo | On Hold |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2024-02-01 17:06 |  | 2024-12-09 13:36 |  |  | 2025-12-26 | 0 | 0 |  |  | BCCONST-612, BCCONST-613, BCCONST-614, BCCONST-615, BCCONST-616, BCCONST-617 |  | 138 units | QNET, migration | [12 empty] | 0¦i4lpdj: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
BC Construction | BCCONST-563 | 958 Ridgeway Avenue (The Austin), Coquitlam BC | Condo | On Hold |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2023-12-13 12:54 |  | 2024-12-09 13:58 |  |  | 2025-12-26 | 0 | 0 |  |  | BCCONST-564, BCCONST-565, BCCONST-566, BCCONST-567, BCCONST-568, BCCONST-569, BCCONST-570 |  | 19 floors 125 units 4 townhouses Keys and Fob available in our room | QNET, migration | [12 empty] | 0¦i4i8wf: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [37 empty] | 7100 | 8500
BC Construction | BCCONST-562 | 1185 The High Street (Claremont), Coquitlam BC | Condo | On Hold |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2023-12-13 12:43 |  | 2024-12-09 13:58 |  |  | 2025-12-26 | 0 | 0 |  |  | BCCONST-585, BCCONST-586, BCCONST-587, BCCONST-588, BCCONST-589, BCCONST-590, BCCONST-591 |  | 125 units 21 floors Keys and Fobs available in the room | QNET, migration | [12 empty] | 0¦i4i8u7: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [37 empty] | 10600 | 2700
BC Construction | BCCONST-561 | 2980 Atlantic Ave (Levo), Coquitlam BC | Condo | On Hold |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2023-12-13 12:41 |  | 2024-12-09 14:15 |  |  | 2025-12-19 | 0 | 0 |  |  | BCCONST-578, BCCONST-579, BCCONST-580, BCCONST-581, BCCONST-582, BCCONST-583, BCCONST-584 |  | 257 units 37 flrs Keys and Fob available in our room | QNET, migration | [12 empty] | 0¦i4i8tz: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [37 empty] | 14000 | 2900
BC Construction | BCCONST-560 | 1155 The High Street (M1), Coquitlam BC | Condo | On Hold |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2023-12-13 12:38 |  | 2024-12-09 14:17 |  |  | 2025-12-26 | 0 | 0 |  |  | BCCONST-571, BCCONST-572, BCCONST-573, BCCONST-574, BCCONST-575, BCCONST-576, BCCONST-577 |  | 194 units 30 flrs Entrance Fob access - Call caretakers for MTR and Riser Access | QNET, migration | [12 empty] | 0¦i4i8tj: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [37 empty] | 8000 | 11000
BC Construction | BCCONST-518 | 39 6th St (Quantum), New Westminster BC | Condo | On Hold |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2023-12-05 16:21 |  | 2024-12-09 14:24 |  |  | 2025-11-28 | 0 | 0 |  |  | BCCONST-540, BCCONST-541, BCCONST-542, BCCONST-543, BCCONST-544, BCCONST-545, BCCONST-546 |  | Lubo 604-612-6323 [lubo@raidanthome.ca¦mailto:lubo@raidanthome.ca] 122 units/19 flrs | Bridgenet, migration | [12 empty] | 0¦i4hnbj: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [37 empty] | 8000 | 3000
BC Construction | BCCONST-517 | 892 Carnarvorn St (Azure 2), New Westminster BC | Condo | On Hold |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2023-12-05 16:20 |  | 2024-12-09 14:26 |  |  | 2025-12-26 | 0 | 0 |  |  | BCCONST-525, BCCONST-526, BCCONST-527, BCCONST-528, BCCONST-529, BCCONST-530, BCCONST-531 |  | Cyrille Stoelzaed [manager.azure2@quaypacific.com¦mailto:manager.azure2@quaypacific.com] Jorge/Kim Pailamilla 604-442-1435 [azure2mannager@gmail.com¦mailto:azure2mannager@gmail.com] 204 Units/32 flrs | Bridgenet, migration | [12 empty] | 0¦i4hnav: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [37 empty] | 11800 | 2900
BC Construction | BCCONST-516 | 898 Carnarvon St (Azure 1), New Westminster BC | Condo | On Hold |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2023-12-05 16:18 |  | 2024-12-09 14:31 |  |  | 2025-12-26 | 0 | 0 |  |  | BCCONST-533, BCCONST-534, BCCONST-535, BCCONST-536, BCCONST-537, BCCONST-538, BCCONST-539 |  | Ryan Walmsley 604-431-1818 [rwalmsley@ascentpm.com¦mailto:rwalmsley@ascentpm.com] Victor Aristizabal 778-223-8025 [azure1manager@gmail.com¦mailto:azure1manager@gmail.com] 204 units/32 flrs | Bridgenet, migration | [12 empty] | 0¦i4hn9b: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
BC Construction | BCCONST-325 | 1055 Richards St, Vancouver | Condo | On Hold |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2023-07-10 13:49 |  | 2024-12-09 18:02 |  |  | 2025-12-26 | 0 | 0 |  |  | BCCONST-464, BCCONST-465, BCCONST-466, BCCONST-467, BCCONST-468 | BCCONST-63 | Signed FS bldg but was never built 152 units/18 flrs | Pre-Sales | [12 empty] | 0¦i45uc7: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
BC Construction | BCCONST-72 | 1199 Seymour St, Vancouver FS - OnNet | Condo | On Hold |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2023-05-02 16:33 |  | 2024-12-09 18:29 |  |  | 2025-05-30 | 0 | 0 |  |  | BCCONST-73, BCCONST-160, BCCONST-161, BCCONST-162, BCCONST-163, BCCONST-164, BCCONST-165 | BCCONST-71, BCCONST-63 | Bldg #: 249 Units: 230 Subs: 17 Penetration: 7% Last Promo: 4/7/2021 Days Since: 432 Fliers Check: - Last Check: Comps: done Notes: Shared MER with 1155, can get away with one entrance - same building management = Brava | confirmed | [12 empty] | 0¦i40fsv: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [37 empty] | 11550 | 29600
BC Construction | BCCONST-146 | 198 Aquarius Mews, Vancouver - FS to OnNET | Condo | On Hold |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2023-05-29 13:59 |  | 2024-12-09 18:28 |  |  | 2025-12-26 | 0 | 0 |  |  |  |  | Bldg #: 307 Units: 184 Subs: 29 Penetration: 16% Last Promo: 7/24/2020 Days Since: 689 Fliers Check: 5/9/2022 Last Check: 35 Comps: In Progress Notes: | confirmed | [12 empty] | 0¦i429of: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
BC Construction | BCCONST-147 | 1372 Seymour St, Vancouver - FS to OnNet | Condo | On Hold |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2023-05-29 14:00 |  | 2024-12-09 18:28 |  |  | 2025-12-26 | 0 | 0 |  |  |  |  | Bldg #: 423 Units: 300 Subs: 10 Penetration: 3% Last Promo: 10/4/2021 Days Since: 252 Fliers Check: - Last Check: Comps: Notes: Confirm comps are complete | confirmed | [12 empty] | 0¦i429ov: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
BC Construction | BCCONST-148 | 1199 Marinaside St, Vancouver- FS to OnNET | Condo | On Hold |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2023-05-29 14:20 |  | 2024-12-09 18:28 |  |  | 2025-12-26 | 0 | 0 |  |  |  |  | Bldg #: 306 Units: 180 Subs: 21 Penetration: 12% Last Promo: 7/24/2020 Days Since: 689 Fliers Check: - Last Check: Comps: In Progress Notes: | confirmed | [12 empty] | 0¦i429x3: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
BC Construction | BCCONST-149 | 189 Davie St, Vancouver - FS to OnNET | Condo | On Hold |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2023-05-29 14:25 |  | 2024-12-09 18:27 |  |  | 2025-12-26 | 0 | 0 |  |  |  |  | Bldg #: 308 Units: 84 Subs: 6 Penetration: 7% Last Promo: 7/24/2020 Days Since: 689 Fliers Check: - Last Check: Comps: Notes: | confirmed | [12 empty] | 0¦i42a13: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
BC Construction | BCCONST-150 | 1438 Richards St, Vancouver - FS to OnNET | Condo | On Hold |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2023-05-29 14:27 |  | 2024-12-09 18:19 |  |  | 2025-12-26 | 0 | 0 |  |  |  |  | Bldg #: 461 Units: 203 Subs: Penetration: Last Promo: - Days Since: Fliers Check: - Last Check: Comps: Notes: do not commit | confirmed | [12 empty] | 0¦i42a27: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
BC Construction | BCCONST-71 | 1155 Seymour St, Vancouver - FS to OnNet | Condo | On Hold |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2023-05-02 16:31 |  | 2024-10-15 17:05 |  |  | 2025-12-19 | 0 | 0 |  |  | BCCONST-157, BCCONST-158, BCCONST-159, BCCONST-286, BCCONST-594 | BCCONST-72 | Bldg #: 282 Units: 188 Subs: 28 Penetration: 15% Last Promo: 4/7/2021 Days Since: 432 Fliers Check: 5/2/2022 Last Check: 42 | [13 empty] | 0¦i40fsf: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
BC Construction | BCCONST-180 | 833 Seymour St, Vancouver FS-Onnet | Condo | On Hold |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2023-05-29 18:33 |  | 2024-10-15 17:05 |  |  | 2025-04-25 | 0 | 0 |  |  | BCCONST-181, BCCONST-182, BCCONST-183, BCCONST-184, BCCONST-185, BCCONST-186 |  | FiberStream building 43 Floors 370 units Capitol Residences | confirmed | [12 empty] | 0¦i42bpj: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
BC Construction | BCCONST-69 | 788 Richards St, Vancouver - FS to OnNet | Condo | On Hold |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2023-05-02 13:54 |  | 2024-10-15 17:20 |  |  | 2025-12-26 | 0 | 0 |  |  | BCCONST-70, BCCONST-151, BCCONST-152, BCCONST-153, BCCONST-154, BCCONST-155, BCCONST-156, BCCONST-625 | ORDER-213015 | L'Hermitage Hotel 31 Floors 184 units MDU | confirmed | [12 empty] | 0¦i40f0f: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
Construction | CONST-29419 | 35 Saranac Blvd, Toronto - Cranbrooke Village | Condo | On Hold |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Jessica Markiewicz | 2022-07-13 13:01 |  | 2025-01-07 20:23 |  |  |  | 0 | 2 |  |  | CONST-29501, CONST-29502, CONST-31548, CONST-31551, CONST-31574, CONST-31576, CONST-31577, CONST-31578, CONST-31579, CONST-31580, CONST-31581, CONST-31582, CONST-31583, CONST-31584, CONST-31585, CONST-31586, CONST-31587, CONST-31588, CONST-31589, CONST-31590, CONST-39056, CONST-39057 |  | Constructed in 2014 Requested by Jay Fernandes Hi, These are the Fibrestream condos we have agreements for that don’t seem to fit into any groups (although I maybe wrong). Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. ¦Group¦Building Name¦Address¦suites¦ ¦Independent¦Eleven Superior¦11 Superior AVE Etobicoke ON M8V 0A7¦130¦ ¦Independent¦The James Club¦1135 Royal York RD Toronto ON M9A 4A7¦209¦ ¦Independent¦Independence Way¦115 George Appleton WAY North York ON M3M 2E9¦244¦ ¦Independent¦Danforth Village Estates¦1346 Danforth RD Toronto ON M4J1M9¦249¦ ¦Independent¦beBloor¦1369 Bloor ST Toronto ON M6P 4J3¦238¦ ¦Independent¦Ion Condos¦15 James Finlay WAY Toronto ON M3M 0B3¦200¦ ¦Independent¦Paradice at the Oasis¦1720 Eglinton AVE Toronto ON M4A2X9¦190¦ ¦Independent¦Havenon the Bluffs¦20 East Haven DR Toronto ON M1N1M2¦259¦ ¦Independent¦Kilgour Estate II¦21 Burkebrook PL Toronto ON M4G4K8¦228¦ ¦Independent¦Canvas Condos¦2301 Danforth AVE Toronto ON M4C 1L5¦156¦ ¦Independent¦3018 Yonge Condos¦3018 Yonge ST Toronto ON M4N 0A5¦188¦ ¦Independent¦Cranbrooke Village¦35 Saranac BLVD Toronto ON M6A 2G4¦341¦ ¦Independent¦39 Brant St¦39 Brant ST Toronto ON M5V0M8¦236¦ ¦Independent¦The Wave¦4 Elsinore PATH Toronto ON M8V 4G7¦185¦ ¦Independent¦Clock Tower Lofts¦700 King ST Toronto ON M5V 2Y6¦216¦ ¦Independent¦The Boot¦75 Dalhousie ST Toronto ON M5B 2R9¦153¦ ¦Independent¦B.Street Condos¦783 Bathurst ST Toronto ON M6G 1K1¦ ¦ ¦Independent¦85 Bloor St¦85 Bloor ST Toronto ON M4W3G9¦252¦ | FSactive, Fiberstreamagreement | [12 empty] | 0¦i3hg1b: | [7 empty] | 9.2234e+18 | [19 empty] | October 28th - Project initiated. Design and permits to be in progress. Mar 30/23 - As per David Chui "we will wait for the overbuild to be issued and revisit this one at that time to come from the south on Bathurst." Due dates will be updated once a concrete plan is in place. | [6 empty] | 3 - Normal | [24 empty] | 13 | 341 | Integration |  | 82526 |  |  | https://buildings.beanfield.com/buildings/view/2120 |  | 500493 | 3 - Normal |  | Toronto | 7972 | 23065
Construction | CONST-29408 | 21 Burkebrook Pl, Toronto - Kilgour Estate II | Condo | On Hold |  | Unresolved | Jessica Markiewicz | Jessica Markiewicz | Jessica Markiewicz | 2022-07-13 12:41 |  | 2025-01-07 19:55 |  |  |  | 0 | 0 |  |  | CONST-29409, CONST-29410 |  | Constructed in 2008 Requested by Jay Fernandes Hi, These are the Fibrestream condos we have agreements for that don’t seem to fit into any groups (although I maybe wrong). Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. ¦Group¦Building Name¦Address¦suites¦ ¦Independent¦Eleven Superior¦11 Superior AVE Etobicoke ON M8V 0A7¦130¦ ¦Independent¦The James Club¦1135 Royal York RD Toronto ON M9A 4A7¦209¦ ¦Independent¦Independence Way¦115 George Appleton WAY North York ON M3M 2E9¦244¦ ¦Independent¦Danforth Village Estates¦1346 Danforth RD Toronto ON M4J1M9¦249¦ ¦Independent¦beBloor¦1369 Bloor ST Toronto ON M6P 4J3¦238¦ ¦Independent¦Ion Condos¦15 James Finlay WAY Toronto ON M3M 0B3¦200¦ ¦Independent¦Paradice at the Oasis¦1720 Eglinton AVE Toronto ON M4A2X9¦190¦ ¦Independent¦Havenon the Bluffs¦20 East Haven DR Toronto ON M1N1M2¦259¦ ¦Independent¦Kilgour Estate II¦21 Burkebrook PL Toronto ON M4G4K8¦228¦ ¦Independent¦Canvas Condos¦2301 Danforth AVE Toronto ON M4C 1L5¦156¦ ¦Independent¦3018 Yonge Condos¦3018 Yonge ST Toronto ON M4N 0A5¦188¦ ¦Independent¦Cranbrooke Village¦35 Saranac BLVD Toronto ON M6A 2G4¦341¦ ¦Independent¦39 Brant St¦39 Brant ST Toronto ON M5V0M8¦236¦ ¦Independent¦The Wave¦4 Elsinore PATH Toronto ON M8V 4G7¦185¦ ¦Independent¦Clock Tower Lofts¦700 King ST Toronto ON M5V 2Y6¦216¦ ¦Independent¦The Boot¦75 Dalhousie ST Toronto ON M5B 2R9¦153¦ ¦Independent¦B.Street Condos¦783 Bathurst ST Toronto ON M6G 1K1¦ ¦ ¦Independent¦85 Bloor St¦85 Bloor ST Toronto ON M4W3G9¦252¦ | FSactive, Fiberstreamagreement | [12 empty] | 0¦i3hfx3: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 8 | 228 | Integration |  |  |  |  | https://buildings.beanfield.com/buildings/view/15541 |  |  | 3 - Normal |  | Toronto
Construction | CONST-12144 | 200 Bloor St W - Exhibit Residences | Condo | On Hold |  | Unresolved | Harvey Tran | Oguz Avci [X] | Oguz Avci [X] | 2020-03-13 09:02 |  | 2025-01-07 20:08 |  |  |  | 0 | 1 |  |  | CONST-13016, CONST-13017 |  | Constructed in 2021 [tscc2598admin@royalegrande.com¦mailto:tscc2598admin@royalegrande.com] | [13 empty] | 0¦i1vm27: | [7 empty] | 9.2234e+18 | [19 empty] | Duplicate ticket use Const-24514 Const-12144 canceled | [6 empty] | 3 - Normal | [24 empty] | 32 | 204 | [5 empty] | https://buildings.beanfield.com/buildings/view/5608 |  |  | 3 - Normal |  | Toronto
Construction | CONST-30859 | 135 East Liberty St, Toronto | Condo | On Hold |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Jessica Markiewicz | 2022-10-05 10:02 |  | 2025-01-07 20:12 |  |  |  | 0 | 2 |  |  | CONST-30860, CONST-30861, CONST-31031 |  | Constructed in 2021 Requested by Oliver Davies. Can you please request a site walk from James for 135 E Liberty St, the “Liberty Market Tower Condos”? We have already built into the commercial portion at 171 E Liberty St and 125 E Liberty St, and we would like to determine what is required to bring the residential units online. BB Link: [https://buildings.beanfield.com/buildings/view/16023] *NEW PM Info:* *Klé McKoy* Property Manager Tel. 905-605-7788 Fax. 905-605-7799 E-mail. +[klem@comfortpm.ca¦mailto:klem@comfortpm.ca] PM Info: Natalie Tomasella nataliet@comfortpm.ca | [13 empty] | 0¦i3mte7: | [7 empty] | 9.2234e+18 | [19 empty] | January 30th - building on-hold pending Rogers bulk expiry in 2026. As per Oliver Davies Jan 2023_Project on hold_The solicitor for 135 E Liberty St has confirmed the corporation is locked into a bulk agreement w/ Rogers until 2026. | [6 empty] | 3 - Normal | [24 empty] | 23 | 279 | [5 empty] | https://buildings.beanfield.com/buildings/view/16023 |  |  | 3 - Normal |  | Toronto
Construction | CONST-12287 | 8 Park Rd, Toronto | Condo | On Hold |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Oguz Avci [X] | 2020-04-16 16:09 |  | 2025-01-07 20:17 |  |  |  | 0 | 4 |  |  | CONST-12288, CONST-12978, CONST-12979, CONST-13193 |  | Sincere Liu Property Manager Elite Property Management Inc. Licensed Management Provider The Residences at 8 Park Road Tel: 416-944-8908 Fax: 416-944-9435 {color:#1f4e79}[sliu@elitepminc.com¦mailto:sliu@elitepminc.com]{color} | [13 empty] | 0¦i1x7e7: | [7 empty] | 9.2234e+18 | [19 empty] | Aug 30/23 - Marked as Not a Candidate. Please see Oliver Davies comments here CONST-13193 Feb 08/24 - Status updated to "On Hold" requested by Oliver Davies. Building is On Hold due to the demands of the Building Boards are extensive, refer to Agreement comments | [6 empty] | 3 - Normal | [24 empty] | 28 | 297 | [5 empty] | https://buildings.beanfield.com/buildings/view/4225 |  |  | 3 - Normal |  | Toronto
Construction | CONST-18719 | 411 Victoria Park, Scarborough - New Development | Condo | On Hold |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Harvey Tran | 2021-02-02 11:59 |  | 2025-01-07 20:28 |  |  |  | 0 | 1 |  |  | CONST-18720 |  | There is a new development at VP and Danforth (see attached and below). The electrical Engineer has reached out to me to see if beanfield would like to be part of the project. It seems that they are taking the lead in identifying the Telecos. Todd, this is how we got involved in Vallewoods Development. It was not through the developer (urban Capital). My question to Newbuilds is how do I proceed with this? +*Contact information:*+ Ted Gayowsky, M.A.Sc., P.Eng. (905) 827-7887 x240 RTG Systems Inc. 3518 Mainway, Suite 201 | [13 empty] | 0¦i2frxb: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2023 March 7, 2024 Placed ON I haven't made any headway with getting a developer contact that can approve our access, but I'll do some more work on this | [6 empty] | 3 - Normal | [24 empty] | 12 | 375 | [8 empty] | 3 - Normal |  | Scarborough
Construction | CONST-25892 | 181 Wynford Drive, Toronto | Condo | On Hold |  | Unresolved | Jessica Markiewicz | Jessica Markiewicz | Harvey Tran | 2021-11-29 14:43 |  | 2025-01-08 10:41 |  |  |  | 0 | 0 |  |  | CONST-25893, CONST-25894, CONST-26075, CONST-26251 | CONST-14664 | Constructed in 2009 | Fiberstreamagreement | [12 empty] | 0¦i32ctj: | [7 empty] | 9.2234e+18 | [19 empty] | Inability to access the hydro chamber outside of the building. | [6 empty] | 3 - Normal | [24 empty] | 34 | 327 | [5 empty] | https://buildings.beanfield.com/buildings/view/7250 |  |  | 3 - Normal |  | Toronto
Construction | CONST-15681 | 4 Elsinore Path, Etobicoke | Condo | On Hold |  | Unresolved | Jessica Markiewicz | Jessica Markiewicz | Harvey Tran | 2020-11-02 13:38 |  | 2025-01-08 10:37 |  |  |  | 0 | 1 |  |  | CONST-15682, CONST-29503 |  | *Constructed in 2007* +*Contact Information:*+ Andrew Saksida, Condo Manager E: [andrewsaksida@gmail.com¦mailto:Cristal.Zak@crossbridgecs.com] 416-357-8779 | [13 empty] | 0¦i29ben: | [7 empty] | 9.2234e+18 | [19 empty] | High building costs. | [6 empty] | 3 - Normal | [24 empty] | 13 | 185 | [5 empty] | https://buildings.beanfield.com/buildings/view/2935 |  |  | 3 - Normal |  | Etobicoke
Construction | CONST-7238 | 955 Queen St W- Chocolate Company Lofts | Condo | On Hold |  | Unresolved | Jessica Markiewicz | Jessica Markiewicz | Russell Francey | 2017-12-18 09:58 |  | 2025-01-08 10:50 |  |  |  | 0 | 2 |  |  | CONST-7239, CONST-10387, CONST-10388, CONST-10389, CONST-10390, CONST-10391, CONST-10392, CONST-10393, CONST-10394, CONST-10395, CONST-10396, CONST-10397, CONST-10550, CONST-10901 | CONST-4453, CONST-29550, CONST-30935 | Constructed in 2005 debbie@goldview.ca | [13 empty] | 0¦i0yihz: | [7 empty] | 9.2234e+18 | [19 empty] | November 16th - Project was revisited this year, but put on hold, until 993 Queen St and other commercial projects in the area are approved. | [6 empty] | 3 - Normal | [24 empty] | 5 | 144 |  |  | 33900 |  |  | https://buildings.beanfield.com/buildings/view/657 |  | 500201 | 3 - Normal |  | Mississauga West Queen West | 9400 | 36400
Construction | CONST-29390 | 1135 Royal York Rd, Toronto - The James Club | Condo | On Hold |  | Unresolved | Jessica Markiewicz | Jessica Markiewicz | Jessica Markiewicz | 2022-07-13 11:49 |  | 2025-01-08 10:54 |  |  |  | 0 | 0 |  |  | CONST-29391, CONST-29392 |  | Constructed in 2011 Requested by Jay Fernandes Hi, These are the Fibrestream condos we have agreements for that don’t seem to fit into any groups (although I maybe wrong). Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. ¦Group¦Building Name¦Address¦suites¦ ¦Independent¦Eleven Superior¦11 Superior AVE Etobicoke ON M8V 0A7¦130¦ ¦Independent¦The James Club¦1135 Royal York RD Toronto ON M9A 4A7¦209¦ ¦Independent¦Independence Way¦115 George Appleton WAY North York ON M3M 2E9¦244¦ ¦Independent¦Danforth Village Estates¦1346 Danforth RD Toronto ON M4J1M9¦249¦ ¦Independent¦beBloor¦1369 Bloor ST Toronto ON M6P 4J3¦238¦ ¦Independent¦Ion Condos¦15 James Finlay WAY Toronto ON M3M 0B3¦200¦ ¦Independent¦Paradice at the Oasis¦1720 Eglinton AVE Toronto ON M4A2X9¦190¦ ¦Independent¦Havenon the Bluffs¦20 East Haven DR Toronto ON M1N1M2¦259¦ ¦Independent¦Kilgour Estate II¦21 Burkebrook PL Toronto ON M4G4K8¦228¦ ¦Independent¦Canvas Condos¦2301 Danforth AVE Toronto ON M4C 1L5¦156¦ ¦Independent¦3018 Yonge Condos¦3018 Yonge ST Toronto ON M4N 0A5¦188¦ ¦Independent¦Cranbrooke Village¦35 Saranac BLVD Toronto ON M6A 2G4¦341¦ ¦Independent¦39 Brant St¦39 Brant ST Toronto ON M5V0M8¦236¦ ¦Independent¦The Wave¦4 Elsinore PATH Toronto ON M8V 4G7¦185¦ ¦Independent¦Clock Tower Lofts¦700 King ST Toronto ON M5V 2Y6¦216¦ ¦Independent¦The Boot¦75 Dalhousie ST Toronto ON M5B 2R9¦153¦ ¦Independent¦B.Street Condos¦783 Bathurst ST Toronto ON M6G 1K1¦ ¦ ¦Independent¦85 Bloor St¦85 Bloor ST Toronto ON M4W3G9¦252¦ | Fiberstreamagreement | [12 empty] | 0¦i3hfg7: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 14 | 209 | [5 empty] | https://buildings.beanfield.com/buildings/view/8167 |  |  | 3 - Normal |  | Toronto
Construction | CONST-18602 | 95 Lakeshore Blvd. East, Toronto - Sugar Wharf Condos | Condo | On Hold |  | Unresolved | Harvey Tran | Harvey Tran | Harvey Tran | 2021-01-18 17:24 |  | 2025-01-08 11:10 |  |  |  | 0 | 1 |  |  | CONST-18603 |  | These buildings are NOT part of our waterfront agreement so we’re not guaranteed access and will need to get an agreement. +*Project director*+ Geoffrey Smith Email: [Geoffrey.Smith@menkes.com¦mailto:Geoffrey.Smith@menkes.com] Menkes General number: 416-491-2222 | [13 empty] | 0¦i2ens7: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2023 Jan 31, 2022_Bulk Deal until 2026 with Rogers, project On Hold | [6 empty] | 3 - Normal | [24 empty] | 80 | 1927 | [5 empty] | https://buildings.beanfield.com/buildings/view/8606 |  |  | 3 - Normal |  | Toronto
Construction | CONST-17432 | 3391 Bloor St W, Toronto | Condo | On Hold |  | Unresolved | Harvey Tran | Harvey Tran | Harvey Tran | 2020-12-11 10:53 |  | 2025-01-08 11:16 |  |  |  | 0 | 2 |  |  | CONST-17433 |  | Constructed in 2008 *Property Address:* 3391 Bloor St W, Toronto ON M8X 1G3 *BB Link:* [https://buildings.beanfield.com/buildings/view/2349] *Property Manager:* Vito Trombino [vito@trombino.me¦mailto:vito@trombino.me] 416-854-3285 | [13 empty] | 0¦i2cbe7: | [7 empty] | 9.2234e+18 | [19 empty] | Jan 31, 2022_Placing On Hold due to discussion about Backbone. | [6 empty] | 3 - Normal | [24 empty] | 12 | 143 | [5 empty] | https://buildings.beanfield.com/buildings/view/2349 |  |  | 3 - Normal |  | Etobicoke
Construction | CONST-15403 | 8 Colborne St, Toronto | Condo | On Hold |  | Unresolved | Harvey Tran | Harvey Tran | Harvey Tran | 2020-10-06 14:28 |  | 2025-01-08 12:29 |  |  |  | 0 | 1 |  |  | CONST-15404, CONST-15555 |  | *Constructed 2005* +*Property Address:*+ 8 Colborne St Toronto ON, M5E 1E1 +*BB Link:*+ [8 Colborne St¦https://buildings.beanfield.com/buildings/view/5618] +*Property Manager:*+ Fuada Zace (416) 568-1935 [fuada.zace@¦mailto:fuada.zace@fsresidential.com][fsresidential.com¦mailto:fuada.zace@fsresidential.com] | [13 empty] | 0¦i27cif: | [7 empty] | 9.2234e+18 | [19 empty] | January 31, 2022_ Put on Hold, PM missing in action | [6 empty] | 3 - Normal | [24 empty] | 26 | 97 | [5 empty] | https://buildings.beanfield.com/buildings/view/5618 |  |  | 3 - Normal |  | Toronto
Construction | CONST-10424 | The St.Clair - 10 Delisle Ave, Toronto | Condo | On Hold |  | Unresolved | Harvey Tran | Russell Francey | Russell Francey | 2019-05-10 09:27 |  | 2025-01-08 12:34 |  |  |  | 0 | 1 |  |  | CONST-10425, CONST-10426, CONST-10427, CONST-12951, CONST-12952 |  |  | Agreement | [12 empty] | 0¦i1ja5j: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2004 | [6 empty] | 3 - Normal | [24 empty] | 15 | 226 | [5 empty] | https://buildings.beanfield.com/buildings/view/8212 |  |  | 3 - Normal |  | Toronto. Yonge & St Clair
Construction | CONST-9259 | Queens Harbour - 600 Queens Quay W, Toronto | Condo | On Hold |  | Unresolved | James Mowers | Lorna Kurok | Russell Francey | 2018-11-19 13:42 | 2025-03-04 09:31 | 2025-01-06 10:11 |  |  |  | 0 | 0 |  |  | CONST-9260, CONST-9261, CONST-9263, CONST-38378, CONST-38379, CONST-38380, CONST-39444, CONST-39445, CONST-39446, CONST-39447, CONST-39448, CONST-39449, CONST-39450, CONST-39451, CONST-39452, CONST-39453, CONST-39454, CONST-39455, CONST-39456, CONST-39457, CONST-39458, CONST-39459, CONST-39460, CONST-39461, CONST-39462 | CONST-39440 | Units 276 Floors 11 Constructed in 2000 Nadir El Achhab Property Manager P 647-704-9252 F 416-236-7977 Email: [nadir@iconpm.ca¦mailto:nadir@iconpm.ca] *Project Summary* Address: 600 Queens Quay West Opportunity Type: Brownfield - Choice (post 2000) MDU Address: *600 Queens Quay W* City: *Toronto* Building Name: *Queens Harbour* # of Units: *276* # of Floors: *11* Building Constructed Year: *2000* PM Contact Name: *Nadir El Achhab* PM Contact #: *416-362-1582* PM Email Address: *[nadir@iconpm.ca¦mailto:nadir@iconpm.ca]* Type of Contract (Fibre agreement or NUA & MA): *NUA & MA* Building linked to other Buildings: *N/A* Bulk Related: *N/A* Attachments: * Fibre Estimate Request (FER): Attached detailing cost breakdown * Agreement: Signed * any pertinent comments such as phased build / spend | FibreStream, NUA+MA | [12 empty] | 0¦i1d2h3: | [7 empty] | 9.2234e+18 | [19 empty] | Sept 6, 2024_Reopened Ticket for revisit. Sep 9, 2024_OSP plan closed Sep 10, 2024_Budget Added Dec 11, 2024- NEW RESIDENTIAL BUILDING – CA APPROVED FTTB#00900 - 600 Queens Quay West - Luke Baxter. Please reference CONST-9259 Jan 6, 2025 Project is on hold. This condo is a daisy chain and we will need to analysis the prewire requirement (NewData). The the prewire requirement was not part of the approved budget. | [6 empty] | 3 - Normal | [24 empty] | 11 | 276 | [5 empty] | https://buildings.beanfield.com/buildings/view/2146 |  |  | 3 - Normal |  | Toronto_Central Waterfront
Construction | CONST-30391 | 57 St Joseph / 1000 Bay St, Toronto - 1 Thousand Bay | Condo | On Hold |  | Unresolved | James Mowers | Lorna Kurok | Jessica Markiewicz | 2022-09-02 16:21 |  | 2025-01-20 15:48 |  |  |  | 0 | 1 |  |  | CONST-30392, CONST-30393 |  | Constructed in 2016 Requested by Oliver Davies. Last but not least, can you please request a site walk for 57 St Joseph / 1000 Bay St? This is an active FibreStream location that may have been missed in the earlier stages of migrating these buildings to Beanfield. BB Link: [https://buildings.beanfield.com/buildings/view/3468] PM: ¦Kat Ng¦ ¦[kat@legacymgt.ca¦mailto:kat@legacymgt.ca]¦ ¦(416) 928-6056¦ | FSactive, Fiberstreamagreement | [12 empty] | 0¦i3kuvb: | [7 empty] | 9.2234e+18 | [19 empty] | Jan 7, 2025_ James asked Nathan if there is a closer MH that could feed this condo, which could reduce budget cost. Jan 20, 2025 - Note in Site visit (A closer BFMH has been identified its rufly 225m away, which translates to 3k per year in Hydro fees, is this worth revisiting?)(Thanks James Mowers - this will be up to Nathan Lei's team to determine. As we are eliminating a third-party circuit at $800/mo, the new design should help make the numbers more feasible to move forward.) | [6 empty] | 3 - Normal | [24 empty] | 32 | 378 | Integration |  |  |  |  | https://buildings.beanfield.com/buildings/view/3468 |  |  | 3 - Normal |  | Toronto
Construction | CONST-17908 | 2010 Yonge St, Toronto | Condo | On Hold |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Harvey Tran | 2021-01-11 08:55 |  | 2025-01-03 15:24 |  |  |  | 0 | 2 |  |  | CONST-17909 |  | This is a also part of that batch of new developments with Sud Group. Can we please issue a site walk and also set me as a watcher on the subtask: *Lola & Glebe* 2010 – 2050 Yonge Street Toronto, ON M4S 1Z9 +*Developer:*+ Elliot Sud [elliott@sudgroup.com¦mailto:elliott@sudgroup.com] 416-820-9000 | [13 empty] | 0¦i2e0j3: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 14 | 264 | [5 empty] | https://buildings.beanfield.com/buildings/view/13999 |  |  | 3 - Normal |  | Toronto
Construction | CONST-12143 | 39 Niagara St Toronto, ON M5V 1C2 | Condo | On Hold |  | Unresolved | Harvey Tran | Oguz Avci [X] | Oguz Avci [X] | 2020-03-13 09:00 | 2025-03-05 11:15 | 2025-01-03 15:40 |  |  |  | 0 | 1 |  |  | CONST-13014, CONST-13015 |  | [39Niagara@minto.com¦mailto:39Niagara@minto.com] | [13 empty] | 0¦i1vm1r: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2019 | [6 empty] | 3 - Normal | [25 empty] | 506 | [5 empty] | https://buildings.beanfield.com/buildings/view/8474 |  |  | 3 - Normal |  | Toronto
Construction | CONST-29489 | 700 King St West, Toronto - Clock Tower Lofts | Condo | On Hold |  | Unresolved | Jessica Markiewicz | Jessica Markiewicz | Jessica Markiewicz | 2022-07-15 10:27 |  | 2025-01-06 21:16 |  |  |  | 0 | 0 |  |  | CONST-29490, CONST-29491 |  | Requested by Jay Fernandes Hi, These are the Fibrestream condos we have agreements for that don’t seem to fit into any groups (although I maybe wrong). Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. ¦Group¦Building Name¦Address¦suites¦ ¦Independent¦Eleven Superior¦11 Superior AVE Etobicoke ON M8V 0A7¦130¦ ¦Independent¦The James Club¦1135 Royal York RD Toronto ON M9A 4A7¦209¦ ¦Independent¦Independence Way¦115 George Appleton WAY North York ON M3M 2E9¦244¦ ¦Independent¦Danforth Village Estates¦1346 Danforth RD Toronto ON M4J1M9¦249¦ ¦Independent¦beBloor¦1369 Bloor ST Toronto ON M6P 4J3¦238¦ ¦Independent¦Ion Condos¦15 James Finlay WAY Toronto ON M3M 0B3¦200¦ ¦Independent¦Paradice at the Oasis¦1720 Eglinton AVE Toronto ON M4A2X9¦190¦ ¦Independent¦Havenon the Bluffs¦20 East Haven DR Toronto ON M1N1M2¦259¦ ¦Independent¦Kilgour Estate II¦21 Burkebrook PL Toronto ON M4G4K8¦228¦ ¦Independent¦Canvas Condos¦2301 Danforth AVE Toronto ON M4C 1L5¦156¦ ¦Independent¦3018 Yonge Condos¦3018 Yonge ST Toronto ON M4N 0A5¦188¦ ¦Independent¦Cranbrooke Village¦35 Saranac BLVD Toronto ON M6A 2G4¦341¦ ¦Independent¦39 Brant St¦39 Brant ST Toronto ON M5V0M8¦236¦ ¦Independent¦The Wave¦4 Elsinore PATH Toronto ON M8V 4G7¦185¦ ¦Independent¦Clock Tower Lofts¦700 King ST Toronto ON M5V 2Y6¦216¦ ¦Independent¦The Boot¦75 Dalhousie ST Toronto ON M5B 2R9¦153¦ ¦Independent¦B.Street Condos¦783 Bathurst ST Toronto ON M6G 1K1¦ ¦ ¦Independent¦85 Bloor St¦85 Bloor ST Toronto ON M4W3G9¦252¦ | FSactive, Fiberstreamagreement | [12 empty] | 0¦i3hl47: | [7 empty] | 9.2234e+18 | [19 empty] | October 28th - Site Visit in progress. | [6 empty] | 3 - Normal | [24 empty] | 14 | 216 | Integration |  |  |  |  | https://buildings.beanfield.com/buildings/view/369 |  |  | 3 - Normal |  | Toronto
Construction | CONST-36119 | 110 George St S, Toronto - Marketview Housing Co-Op (BULK) | Condo | On Hold |  | Unresolved | Harvey Tran | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2024-01-03 11:58 |  | 2025-01-07 08:05 |  |  |  | 0 | 0 |  |  | CONST-36120, CONST-36121, CONST-36514, CONST-36533 |  | Requested by Oliver Davies, Could you please queue up a site walk & OSP plan for 110 George St S? The Marketview Housing Co-Op is exploring new options for their residents as the Rogers bulk agreement is expiring later this year. This location will likely require a pre-wire of the units, but that poses less of a barrier if we are going with a bulk model. PM Info: *Raymond Favis* *Marketview Housing Co-operative Inc.* *110 George St S, Toronto, ON M5A 4P9* *Tel: 416-363-7787* Cell: 416-294-5119 [office@marketviewcoop.com¦mailto:office@marketviewcoop.com] Thank you, | BulkDeal | [12 empty] | 0¦i4jhdj: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2010 Feb 12/24 - PO sent to THES (AP) for vault access (site visit) Feb 14/24 - Invoice for vault access received June 7th, 2024 - This project is placed on hold. PM is unresponsive | [6 empty] | 3 - Normal | [24 empty] | 11 | 112 |  |  | 57280 |  |  | https://buildings.beanfield.com/buildings/view/5512 |  | CONST-36119 | 3 - Normal |  | Toronto | 15500 | 15271
Construction | CONST-27676 | 305 Roehampton Ave, Toronto | Condo | On Hold |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Harvey Tran | 2022-04-06 12:52 |  | 2025-01-07 08:09 |  |  |  | 0 | 0 |  |  | CONST-27677, CONST-27678 |  | Constructed in 2015 | Fiberstreamagreement | [12 empty] | 0¦i3b7xb: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 14 | 225 | [5 empty] | https://buildings.beanfield.com/buildings/view/4881 |  |  | 3 - Normal |  | Toronto
Construction | CONST-29550 | 993 Queen St W, Toronto - The Candy Factory Lofts | Condo | On Hold |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Jessica Markiewicz | 2022-07-19 08:20 |  | 2025-01-07 08:11 |  |  |  | 0 | 1 |  |  | CONST-29551, CONST-29552 | CONST-7238, CONST-30935 | Constructed in 1999 Requested by Jay Fernandes Can we set up a site visit and budget for the Candy Factory Lofts at 993 Queen St W where we have a Fibrestream agreement? [https://buildings.beanfield.com/buildings/view/5513] When we’re working on the budget let’s see if we can incorporate the build to get us into the Chocolate Factory Lofts at 955 Queen St W where we have an access agreement but couldn’t make the finances work due to the old poles on Queen Street. [https://buildings.beanfield.com/buildings/view/657] If we’re looking at both buildings this might make them both possible. We will likely have to engage Oliver to talk with the Chocolate Factory Lofts if this works out. Property Manager Contact: Hagai Groisman Condominium Manager Nadlan-Harris Property Management Inc. Tel: (416)915-9115 ext.33 Fax: (416)915-9114 [hagai@nadlan-harris.com¦mailto:hagai@nadlan-harris.com] | Fiberstreamagreement | [12 empty] | 0¦i3hrf3: | [7 empty] | 9.2234e+18 | [19 empty] | October 28th - Budged pending approval. Dependent on 12 Ossington. | [6 empty] | 3 - Normal | [24 empty] | 6 | 121 | [5 empty] | https://buildings.beanfield.com/buildings/view/5513 |  |  | 3 - Normal |  | Toronto
Construction | CONST-17434 | 380 Macpherson Ave, Toronto | Condo | On Hold |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Harvey Tran | 2020-12-11 10:57 |  | 2025-01-07 08:16 |  |  |  | 0 | 3 |  |  | CONST-17435, CONST-18110 | CONST-28918 | *Constructed in 2009* *Property Address:* 380 Macpherson Avenue, Toronto ON M4V 3E3 *BB Link:* [https://buildings.beanfield.com/buildings/view/1341] *Property Manager:* Carlos Branco [cbranco@iccpropertymanagement.com¦mailto:cbranco@iccpropertymanagement.com] [(905) 940-1234¦tel:(905) 940-1234] | [13 empty] | 0¦i2cben: | [7 empty] | 9.2234e+18 | [19 empty] | Apr 19/23 - As per Oliver Davies: can you please mark this one as On Hold? The board here signed a bulk agreement with Bell for the next 5 years (as of March 2023). | [6 empty] | 3 - Normal | [24 empty] | 6 | 211 | [5 empty] | https://buildings.beanfield.com/buildings/view/1341 |  |  | 3 - Normal
Construction | CONST-18699 | 8 Cumberland St, Toronto | Condo | On Hold |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Harvey Tran | 2021-01-29 14:06 |  | 2025-01-07 08:19 |  |  |  | 0 | 2 |  |  | CONST-18748, CONST-18851, CONST-19334, CONST-19335, CONST-19336, CONST-19337, CONST-23071, CONST-23072, CONST-23073, CONST-23074, CONST-23126, CONST-23647, CONST-25433, CONST-25434, CONST-28398, CONST-28959 |  | Constructed 2021 This is a brand new development being built at 8 Cumberland. *Contact:* Kevin Mckeown, Developer [kevin.mckeown@greatgulf.com¦mailto:kevin.mckeown@greatgulf.com] 416-433-4262 *BB:* [https://buildings.beanfield.com/buildings/view/14096#!contacts] | [13 empty] | 0¦i2fj9j: | [7 empty] | 9.2234e+18 | [19 empty] | June 14th - OSP cable has been pulled into the building. Pending Riser works due to 2 years Bell exclusive deal is blocking Beanfield. Aug 2/23 - Project put on hold pending expiry of Bell exclusive deal, will revisit when appropriate. | [6 empty] | 3 - Normal | [24 empty] | 51 | 371 | [5 empty] | https://buildings.beanfield.com/buildings/view/14096#!contacts |  | 500328 | 3 - Normal | 2021-12-31 |  | 4547
Construction | CONST-28212 | 1815 Yonge St, Toronto - Merton Yonge Condominiums (MYC Condos) | Condo | On Hold |  | Unresolved | Harvey Tran | Olawale Olaniyan [X] | Harvey Tran | 2022-05-04 11:30 |  | 2025-01-07 08:26 |  |  |  | 0 | 0 | _thumb_892310.png _thumb_892308.png _thumb_892309.png |  | CONST-28213, CONST-28214, CONST-32012, CONST-32013, CONST-32014, CONST-32015, CONST-32016, CONST-32017, CONST-32018, CONST-32019, CONST-32020, CONST-32021, CONST-32022, CONST-32023, CONST-32024, CONST-32025, CONST-34741, CONST-34742, CONST-34791, CONST-37835 |  |  | FSactive, Fiberstreamagreement | [12 empty] | 0¦i3czxr: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2014 November 30th - Route drawing completed. Hydro permit to be in progress. Cable Pull only. Mar 15/23 - Manhole Survey completed. Apr 19/23 - Hydro Permit conditionally granted. Apr 20/23 - Hydro Permit granted. July 20/23 - Still pending building approval for cable pull. July 26/23 - Conduit build tentatively scheduled for Aug 10th Aug 21/23 - Delay with conduit build. Due dates updated. Oct 11/23 - Delay with construction approval. Due dates updated. May 9th, 2024 - Hydro permit has been cancelled and we will need to restart the permit application process. Permit should be expected in end of Jun 2024. Pushing back the building due date to end of July 2024. Jul 5th, 2024 - Hydro permit needs to be reapplied. Survey will be redone and rescheduled. | [6 empty] | 3 - Normal | [19 empty] | N/A |  | 2022-11-22 |  |  | 28 | 205 | Integration |  | 5634 |  |  | https://buildings.beanfield.com/buildings/view/4750 |  | 500510 | 3 - Normal | 2023-11-24 | Toronto | 5935 | 21580
Construction | CONST-28817 | 88 Grangeway AVE Scarborough - Altitude Condos | Condo | On Hold |  | Unresolved | Jessica Markiewicz | Jessica Markiewicz | Harvey Tran | 2022-06-14 14:09 |  | 2025-01-07 08:32 |  |  |  | 0 | 0 |  |  | CONST-28818, CONST-28819 |  | Constructed in 2012 | FSactive, Fiberstreamagreement | [12 empty] | 0¦i3fmfb: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 26 | 222 | Integration |  |  |  |  | https://buildings.beanfield.com/buildings/view/15498 |  |  | 3 - Normal |  | Scarborough
Construction | CONST-29289 | 28 Empress Ave, North York - The Majestic | Condo | On Hold |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Jessica Markiewicz | 2022-07-12 08:53 |  | 2025-01-07 08:35 |  |  |  | 0 | 0 |  |  | CONST-29290, CONST-29291 | CONST-35958 | Constructed in 2000 Requested by Jay Fernandes Hi, I’ve gone through the remaining Fibrestream condos we have agreements for in the GTA and have grouped them in a way that I think makes sense for site visits and builds. There will be another list coming of buildings that don’t really fall into groups. Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. There are some current backbone (Sheppard) or NPOP (960 Lawrence) projects that will need to be completed to connect these but this will get everything into the system. Thanks! *PM: Justina Lee* *majestic1@delcondo.com* *416.229.4551* | FSactive, Fiberstreamagreement, Yonge&Shep | [12 empty] | 0¦i3ha7r: | [7 empty] | 9.2234e+18 | [19 empty] | July 11/23 - As per Oliver Davies "With the additional hydro costs and at $313 per unit this will be an expensive project. We'll likely move forward over the coming months, but for now Olawale Olaniyan please mark as On Hold" | [6 empty] | 3 - Normal | [24 empty] | 22 | 269 | Integration |  |  |  |  | https://buildings.beanfield.com/buildings/view/3795 |  |  | 3 - Normal |  | North York
Construction | CONST-29231 | 223 St. Clair Ave, Toronto - Zigg Condos | Condo | On Hold |  | Unresolved | Jessica Markiewicz | Jessica Markiewicz | Jessica Markiewicz | 2022-07-11 15:53 |  | 2025-01-07 08:41 |  |  |  | 0 | 0 |  |  | CONST-29232, CONST-29233 |  | Constructed in 2018 Requested by Jay Fernandes Hi, I’ve gone through the remaining Fibrestream condos we have agreements for in the GTA and have grouped them in a way that I think makes sense for site visits and builds. There will be another list coming of buildings that don’t really fall into groups. Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. There are some current backbone (Sheppard) or NPOP (960 Lawrence) projects that will need to be completed to connect these but this will get everything into the system. Thanks! *PM: Sandra Guida* *zigg.pm@delcondo.com* | FSactive, Fiberstreamagreement, StClair | [12 empty] | 0¦i3h8iv: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 11 | 164 | Integration |  |  |  |  | https://buildings.beanfield.com/buildings/view/15587 |  |  | 3 - Normal |  | Toronto
Construction | CONST-29234 | 530 St Clair Ave W, Toronto | Condo | On Hold |  | Unresolved | Jessica Markiewicz | Jessica Markiewicz | Jessica Markiewicz | 2022-07-11 15:56 |  | 2025-01-07 08:49 |  |  |  | 0 | 0 |  |  | CONST-29235, CONST-29236 | CONST-30680 | Constructed in 2013 Requested by Jay Fernandes Hi, I’ve gone through the remaining Fibrestream condos we have agreements for in the GTA and have grouped them in a way that I think makes sense for site visits and builds. There will be another list coming of buildings that don’t really fall into groups. Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. There are some current backbone (Sheppard) or NPOP (960 Lawrence) projects that will need to be completed to connect these but this will get everything into the system. Thanks! *PM: Aron Mats* *aron@iconpm.ca* | FSactive, Fiberstreamagreement, StClair | [12 empty] | 0¦i3h8jj: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 19 | 155 | Integration |  |  |  |  | https://buildings.beanfield.com/buildings/view/3329 |  |  | 3 - Normal |  | Toronto
Construction | CONST-39834 | 701 Sheppard Ave West, North York, Portrait Condos | Condo | On Hold |  | Unresolved | James Mowers | Lorna Kurok | Lorna Kurok | 2025-01-28 08:33 |  | 2025-02-11 14:28 |  |  |  | 0 | 1 |  |  | CONST-39853, CONST-39854, CONST-39855, CONST-39888 |  | Building Constructed in 2014 Requested PM information: Good Morning, The following buildings were approved for Fibrestream migration. Please let me know anything else you might require, Steve you may need to provide budgets etc. ¦Address¦Municipality ¦Units¦Build Cost¦CPU¦Passes¦Meeting Date¦Approved¦ ¦20 Thomas Riley ¦Toronto¦282¦$39,217¦$139¦Yes¦2025-01-22¦Approved¦ ¦701 Sheppard Ave W¦Toronto¦199¦$38,099¦$191¦Yes¦2025-01-22¦Approved¦ ¦16 Brookers Lane¦Etobicoke¦389¦$48,307¦$124¦Yes¦2025-01-22¦Approved¦ ¦88 Sheppard Avenue East¦Toronto¦408¦$83,483¦$205¦No¦2025-01-22¦Approved¦ | FSactive, FibreStream | [12 empty] | 0¦i5hie7: | [7 empty] | 9.2234e+18 | [19 empty] | Jan 22, 2025 - Building was approved email received Jan 22, 2025. (Fibresteam building) January 30, 2025 - On Net schedule change, advised by James January 30, 2025 - OSP Plan_701 Sheppard ave W is on the far right of this residential cluster. Every building listed in the kmz has has to tie back into Sheppard and Wilmington unless we create a new fosc somewhere along the way. January 31, 2025 - High level budget is pending, Using the approved build of $38,099 to create the SAP budget. Jan 31, 2025 - OSP Plan Notes: 701 Sheppard ave W is on the far right of this residential cluster. Every building listed in the kmz has has to tie back into Sheppard and Wilmington unless we create a new fosc somewhere along the way. February 6, 2025_Email_ Fibrestram Migration Approvals_701 Sheppard is part of Cluster Build that hasn't been approved. On Hold February 10, 2025 - Project is actually part of a Cluster, that is pending approval_ Removed project from On Net Schedule, project is ON Hold on the Capex Financial tracker, project is not in SAP. Feb 6, 2025 - Building is part of a Cluster and pending approval, per email feb 6. 2025 | [6 empty] | 3 - Normal | [21 empty] | 2025-01-22 |  |  | 8 | 201 | Integration |  |  |  |  | https://buildings.beanfield.com/buildings/view/1858 |  |  | 3 - Normal | 2025-09-02 | North York
Construction | CONST-31591 | 20 Thomas Riley Rd, Etobicoke - The Kip District | Condo | On Hold |  | Unresolved | James Mowers | Lorna Kurok | Jessica Markiewicz | 2022-10-28 14:02 |  | 2025-02-11 14:42 |  |  |  | 0 | 0 |  |  | CONST-31592, CONST-31593, CONST-39871, CONST-39944 | CONST-35910 | Constructed in 2019 Requested by Jay Fernandes. Good Afternoon, I just realized I missed one of the Fibrestream condos we have an agreement with. Can we get a project set up for a site visit and budget for this building? The Kip District - 20 Thomas Riley Rd [https://buildings.beanfield.com/buildings/view/9876] Thanks! Property manager: NOHA ELMURTADA, CMCA, AMS, PCAM Property Manager Direct 647.258.3453 ¦ Toll Free 1.855.244.8854 Email noha.elmurtada@fsresidential.com | FSactive, Fiberstreamagreement | [12 empty] | 0¦i3oehb: | [7 empty] | 9.2234e+18 | [19 empty] | November 25th - Project on hold. To be looked at as a group. January 22, 2025 - Received Condo approval email on January 22, 2025. January 29, 2025 - We should do a revisit of this site for a new High level Budget, the existing Hight level budget did not coincide with the Approved build cost. January 30, 2025 - Added On Net date to jira, Changed schedule date, James advised due date. EST Scope before design Bore 230m, Trench 15m, HydroAerial 110m February 10, 2025 - Project is part of Cluster that is pending approval, therefore this project is on ON hold, until approval. Project was removed from On Net schedule, Placed On Hold in Capex Finance tracker. There is no SAP. February 6, 2025 - We need building agreement feb 6, 2025 - this building is ON HOLD until we get secure a bulk agreement with 20TR and or secure an access agreement with Samuel Wood. | [6 empty] | 3 - Normal | [21 empty] | 2025-01-22 |  |  | 28 | 282 | Integration |  |  |  |  | https://buildings.beanfield.com/buildings/view/9876 |  |  | 3 - Normal | 2025-09-01 | Etobicoke
Construction | CONST-26574 | 275 Village Green, Toronto - Avani at Metrogate | Condo | On Hold |  | Unresolved | James Mowers | Harvey Tran | Harvey Tran | 2022-01-28 13:20 |  | 2025-02-14 10:52 |  |  |  | 0 | 1 |  |  | CONST-26575, CONST-26576 | CONST-26336, CONST-32622, CONST-32623, CONST-40076, CONST-40077, CONST-26571 | Requested by Katie Hodgson PM Info: Momir Petkovic [Avani.PM@Delcondo.com¦mailto:Avani.PM@Delcondo.com] (647)342-7641 | [13 empty] | 0¦i3608v: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2019 | [6 empty] | 3 - Normal | [24 empty] | 35 | 360 | [8 empty] | 3 - Normal |  | Scarborough
Construction | CONST-26571 | 255 Village Green, Toronto | Condo | On Hold |  | Unresolved | James Mowers | Harvey Tran | Harvey Tran | 2022-01-28 13:00 |  | 2025-02-14 10:52 |  |  |  | 0 | 1 |  |  | CONST-26572, CONST-26573 | CONST-26336, CONST-32609, CONST-32622, CONST-32623, CONST-40076, CONST-40077, CONST-26574 | Requested by Katie Hodgson PM Info: Momir Petkovic [Avani.PM@Delcondo.com¦mailto:Avani.PM@Delcondo.com] (647)342-7641 | [13 empty] | 0¦i3606f: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2016 | [6 empty] | 3 - Normal | [24 empty] | 36 | 363 | [5 empty] | https://buildings.beanfield.com/buildings/view/16175 |  |  | 3 - Normal |  | Scarborough
Construction | CONST-3336 | 36 Blue Jays Way - Soho Metropolitan | Condo | On Hold |  | Unresolved | Harvey Tran | Jay Fernandes | Jay Fernandes | 2015-04-08 12:42 |  | 2025-02-07 10:18 |  |  |  | 0 | 2 |  |  | CONST-3337, CONST-3338, CONST-3339, CONST-4355, CONST-4536, CONST-4537, CONST-4538, CONST-4539, CONST-15564, CONST-38163, CONST-38164 |  | +*New contact information:*+ ¦{color:#195070}*Lee Boros*{color}¦ ¦Property Manager, Performance Property Management inc.¦ ¦[416.645.3755 \\\¦tel:416.645.3755+ex+505] ext 512 \¦ lee[@performancepm.com¦mailto:chow@performancepm.com]¦ ¦Address: 470 Wellington St, Toronto Ontario M5V 1E3 Website: [www.performancepm.com¦http://www.performancepm.com/]¦ Condo Constructed in 2003. 6 Blue Jay way pop on P2 approx 200 suites 350 Wellington pop P1 approx 191 suites interconnect conduits b/w pops are congested Number of Units as per BBS is 203 318 Wellington St W, Toronto 348 Wellington St W, Toronto 350 Wellington St W, Toronto | [13 empty] | 0¦i08dsf: | [7 empty] | 48892 | [16 empty] | 0 |  |  | Board has gone MIA Constructed 2003 February 7, 2025 Budget CA- 03, approved budget amount. $$28,413,58, On hold for the moment, team discussion, determined that a prewire may be required so additional funds required. | [6 empty] | 3 - Normal | [24 empty] | 17 | 203 |  |  | 15000 |  |  | https://buildings.beanfield.com/buildings/view/1526 |  | 600458 | 5 - Very Low |  | Toronto. King Spadina / Garment District | 0 | 3000
BC Construction | BCCONST-457 | 161 W Georgia, Vancouver BC | Condo | On Hold |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2023-11-01 20:43 |  | 2025-03-18 13:41 |  |  | 2026-01-02 | 0 | 0 |  |  | BCCONST-458, BCCONST-459, BCCONST-460, BCCONST-461, BCCONST-462, BCCONST-463 | BCCONST-438 | 253 units 23 floors 4 4inch from MER - Risers 3 4inch from 3rd flr - Risers 3rd flr - EC 5flr - EC with space 6th - TEL with space 7th - EC with space 8th TEL with space 9th - EC with space 10th - TEL empty 11th - EC not much space 12th - TEL with space 15th - EC not much space 16th - Empty 9 units! 17th - EC 18th - TEL with little space 19th - EC with no space 20th - Empty space 21st - EC with no space 22nd - TEL with some space 23rd - EC 25th - Empty 26th 27th | [13 empty] | 0¦i4f5yf: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
BC Construction | BCCONST-515 | 888 Carnarvon St (Marinus), New Westminster, BC | Condo | On Hold |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2023-12-05 16:14 |  | 2025-03-18 13:40 |  |  | 2025-11-28 | 0 | 0 |  |  | BCCONST-519, BCCONST-520, BCCONST-521, BCCONST-522, BCCONST-523, BCCONST-524, BCCONST-532 |  | Mark Yee Fung [Mark.YeeFung@fsresidential.com¦mailto:Mark.YeeFung@fsresidential.com] Fitu 604-725-7802 [managemermarinus@gmail.com¦mailto:managemermarinus@gmail.com] 238/36 flrs | Bridgenet, migration | [12 empty] | 0¦i4hn87: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [37 empty] | 7500 | 2900
Construction | CONST-30956 | 188 Doris Ave, Toronto - The Boulevard Condos | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Jessica Markiewicz | 2022-10-06 09:17 |  | 2023-01-19 08:55 |  |  |  | 0 | 2 |  |  | CONST-30957, CONST-30958 |  | Requested by Oliver Davies. Could you kindly queue up a site walk for the following 3x locations? *188 Doris Ave (FS Agreement / Off-Net)* **This location neighbours* *21 Hillcrest Ave**, a connection may be possible between buildings* BB Link: [https://buildings.beanfield.com/buildings/view/9983] PM Info: Filomena Tescione Senior Condominium Manager GPM Property Management Inc. as agent and on behalf of Metropolitan Toronto Condominium Corporation No. 1377 188 Doris Avenue Toronto, Ontario M2N 6Z5 Office # - 416-226-5469 Email - [office@188doris.ca¦mailto:office@188doris.ca] | Fiberstreamagreement | [12 empty] | 0¦i3mwjb: | [7 empty] | 9.2234e+18 | [19 empty] | October 28th - Site Visit requested. | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/9983 |  |  | 3 - Normal
Construction | CONST-35712 | Four Springs Ave Condo Backbone, Mississauga (Part 1) | Condo | New Condo |  | Unresolved | Denise King | Denise King | Denise King | 2023-11-09 12:33 |  | 2023-12-07 11:58 |  |  |  | 0 | 3 | _thumb_779337.png |  | CONST-35713, CONST-35714 | CONST-28793, CONST-35716, CONST-35717, CONST-35718, CONST-35719, CONST-35720 | Requested by Oliver Davies: Could you please create a new ticket, linking the below addresses so we can move forward with an estimate for backbone to connect this pocket of buildings in Mississauga? We only have an agreement with the Amber Condos, the other locations will need to be negotiated once we have a plan in place. | [13 empty] | 0¦i4fp6n: | [7 empty] | 9.2234e+18 | [19 empty] | Dec 5/23 - Budget submitted for approval. Will need to wait for lateral budgets to consider together before moving forward. | [6 empty] | 3 - Normal | [26 empty] | Backbone | [7 empty] | 3 - Normal |  | Mississauga
Construction | CONST-33397 | 403 Keele St, Toronto | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2023-03-22 14:08 |  | 2023-03-30 10:54 |  |  |  | 0 | 0 |  |  | CONST-33402 | CONST-33394, CONST-33395, CONST-33396, CONST-33398 | Requested by Oliver Davies Can you please have OSP tickets created for Mark at the following 5x addresses? These are all planned purpose-built rental communities being constructed by Core Development Group that have yet to break ground, so no site-walk is required. We would like to get an idea of what will be required to connect these locations to the Beanfield network. 929 Queen E & 252 Parliament are likely to be the most difficult. Core is looking for an ISP partner to provide connectivity to all of the units in their upcoming rental communities. * 929 Queen St E: 68 units / July 2025 occupancy (Leslieville Pumps location - BFMH located nearby via CDSM10723) * 1233 Queen St: 142 units / June 2025 occupancy (off-net -Queen / Leslie - no fibre in the immediate vicinity) * 1111 Danforth: 208 units / June 2025 occupancy (near-net CC#6083 outside of building) * 403 Keele: 261 units / September 2025 occupancy (near-net BF-0781 outside of building, this is just below the active build at 60/61 Heintzman) * 252 Parliament: 80 units / November 2024 occupancy (off-net no fibre between Queen to Dundas on Parliament) scheduled to break ground this year Each location is expected to have a number of retail units at grade. They have provided drawings/plans for all 5x locations, I will upload them to the JIRA tickets once created. Thanks! | CoreDevelopmentGroup | [12 empty] | 0¦i3xmn3: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/18102 |  |  | 3 - Normal
Construction | CONST-33395 | 1233 Queen St E, Toronto | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2023-03-22 14:08 |  | 2023-03-30 10:56 |  |  |  | 0 | 0 |  |  | CONST-33400 | CONST-33394, CONST-33396, CONST-33397, CONST-33398 | Requested by Oliver Davies Can you please have OSP tickets created for Mark at the following 5x addresses? These are all planned purpose-built rental communities being constructed by Core Development Group that have yet to break ground, so no site-walk is required. We would like to get an idea of what will be required to connect these locations to the Beanfield network. 929 Queen E & 252 Parliament are likely to be the most difficult. Core is looking for an ISP partner to provide connectivity to all of the units in their upcoming rental communities. * 929 Queen St E: 68 units / July 2025 occupancy (Leslieville Pumps location - BFMH located nearby via CDSM10723) * 1233 Queen St: 142 units / June 2025 occupancy (off-net -Queen / Leslie - no fibre in the immediate vicinity) * 1111 Danforth: 208 units / June 2025 occupancy (near-net CC#6083 outside of building) * 403 Keele: 261 units / September 2025 occupancy (near-net BF-0781 outside of building, this is just below the active build at 60/61 Heintzman) * 252 Parliament: 80 units / November 2024 occupancy (off-net no fibre between Queen to Dundas on Parliament) scheduled to break ground this year Each location is expected to have a number of retail units at grade. They have provided drawings/plans for all 5x locations, I will upload them to the JIRA tickets once created. Thanks! | CoreDevelopmentGroup | [12 empty] | 0¦i3xmmn: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/18100 |  |  | 3 - Normal
Construction | CONST-33396 | 1111 Danforth Ave, Toronto | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2023-03-22 14:08 |  | 2023-03-30 10:55 |  |  |  | 0 | 0 |  |  | CONST-33401 | CONST-33394, CONST-33395, CONST-33397, CONST-33398 | Requested by Oliver Davies Can you please have OSP tickets created for Mark at the following 5x addresses? These are all planned purpose-built rental communities being constructed by Core Development Group that have yet to break ground, so no site-walk is required. We would like to get an idea of what will be required to connect these locations to the Beanfield network. 929 Queen E & 252 Parliament are likely to be the most difficult. Core is looking for an ISP partner to provide connectivity to all of the units in their upcoming rental communities. * 929 Queen St E: 68 units / July 2025 occupancy (Leslieville Pumps location - BFMH located nearby via CDSM10723) * 1233 Queen St: 142 units / June 2025 occupancy (off-net -Queen / Leslie - no fibre in the immediate vicinity) * 1111 Danforth: 208 units / June 2025 occupancy (near-net CC#6083 outside of building) * 403 Keele: 261 units / September 2025 occupancy (near-net BF-0781 outside of building, this is just below the active build at 60/61 Heintzman) * 252 Parliament: 80 units / November 2024 occupancy (off-net no fibre between Queen to Dundas on Parliament) scheduled to break ground this year Each location is expected to have a number of retail units at grade. They have provided drawings/plans for all 5x locations, I will upload them to the JIRA tickets once created. Thanks! | CoreDevelopmentGroup | [12 empty] | 0¦i3xmmv: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/18101 |  |  | 3 - Normal
Construction | CONST-27670 | 119 Merton ST Toronto - The Metro | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Harvey Tran | 2022-04-06 12:32 |  | 2024-05-28 12:00 |  |  |  | 0 | 0 |  |  | CONST-27671, CONST-27672 |  |  | Fiberstreamagreement | [12 empty] | 0¦i3b7uv: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/593 |  |  | 3 - Normal
Construction | CONST-38332 | 1684 - 1702 Queen St E, Toronto (BULK) | Condo | New Condo |  | Unresolved | Lorna Kurok | Harvey Tran | Harvey Tran | 2024-09-04 11:27 | 2025-03-02 17:03 | 2024-12-06 10:03 |  |  |  | 0 | 0 |  |  | CONST-38336, CONST-38337 | CONST-38333, CONST-38334, CONST-38335, CONST-38904 | Requested by Oliver. Units 216 Occupancy estimated for mid to end of 2026 Developer: Sud Group Greenfield MDU project Type Condo Could you please create tickets for OSP plans to connect the following 4x greenfield MDU projects to Beanfield's network? Sud Group is the developer for each location. They are interested in signing bulk-agreements with Beanfield, timeline for their decision is in the next 2-3 months. (noted on Sept 4, 2024) Estimated occupancy dates for the 3x condos is mid-end 2026. The rental project is forecasted for first occupancy early 2026. With exception to 1291 Gerrard St E, all of the sites should be near-net to Beanfield's existing network today. Architectural plans for each location will be uploaded to the JIRA ticket. James, if you could please prepare a high-level budget for each location once the OSP plans are in place that will be helpful so that a proposal for the developer can be approved and submitted. 1684 - 1702 Queen St E (Condo) / 216 residential units [https://buildings.beanfield.com/buildings/view/13998] 1291 Gerrard St E (Rental) / 289 residential units [https://buildings.beanfield.com/buildings/view/20801] 1212 - 1238 Kingston Rd (Condo) / 216 residential units [https://buildings.beanfield.com/buildings/view/20802] 2010 Yonge St (Condo) / 264 residential units [https://buildings.beanfield.com/buildings/view/13999] | BulkDeal, Sud_Group | [12 empty] | 0¦i56b9z: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 10 | 216 | [5 empty] | https://buildings.beanfield.com/buildings/view/13998 |  |  | 3 - Normal |  | Toronto
Construction | CONST-38550 | 425 Front - Site walk for building internal cat5 | Condo | New Condo |  | Unresolved | Michael Ng | Jeff Moore | Jeff Moore | 2024-09-19 09:42 |  | 2024-10-07 14:09 |  |  |  | 0 | 0 | _thumb_1023123.png _thumb_1023122.png _thumb_1023121.png _thumb_1023120.png _thumb_1023119.png _thumb_1023118.png _thumb_1023117.png _thumb_1023116.png _thumb_1023115.png _thumb_1023114.png _thumb_1023113.png _thumb_1023112.png _thumb_1023111.png _thumb_1023110.png _thumb_1023109.png _thumb_1023108.png _thumb_1023107.png _thumb_1023106.png _thumb_1023105.png |  |  | CONST-38521, SUPPORT-45027, SUPPORT-45036 | We need to arrange a meeting with Arshdeep at 425 Front. He had requested that we terminate some cat5 cables for him but it appears they have already installed a patch panel. We need to find out if these require keystone jacks and if the building is providing those or if they expect us to. | [13 empty] | 0¦i57f8v: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [34 empty] | 3 - Normal
Construction | CONST-38260 | 3880 Duke of York Blvd, Mississauga, Ovation | Condo | New Condo |  | Unresolved | Harvey Tran | Harvey Tran | Harvey Tran | 2024-08-27 14:53 |  | 2024-10-29 09:56 |  |  |  | 0 | 0 |  |  | CONST-38261, CONST-38262, CONST-38991 | CONST-37795, CONST-38259 | Requested by James Fox. Units 466 Floors 31 Constructed in 2004 Related to Square One Backbone Ovation 1_3880 Duke of York Blvd Could you please create a new ticket for an OSP plan & site walk Ovation2 at 3888 Duke of York Blvd? This condo has 471 units and was built in 2005. Ovation 1 at 3880 Duke of York Blvd. This condo has 466 units and was built in 2004 This location is part of the Mississauga Square One- Condo Backbone build: CONST-37795, ideally we will have minimal OSP work required to enter the building. BB Link: Ovation 2: [https://buildings.beanfield.com/buildings/view/6110] Ovation 1: [https://buildings.beanfield.com/buildings/view/2839] Site Contact: *Sujata Sundaram* *Condominium Manager, O.L.C.M.* *Agent for and on behalf of: PSCC 754* *Ovation Phase II* *3888 Duke of York Blvd. Mississauga, On L5B 4P5* *Phone:* 905-848-9378 *Fax:* 905-848-3800 {*}Email:{*}ovation2.pm@DelCondo.com Please also CC other PM's on site: [Ovation.SF@delcondo.com¦mailto:Ovation.SF@delcondo.com], [Ovation1.pm@delcondo.com¦mailto:Ovation1.pm@delcondo.com] | [13 empty] | 0¦i55o6v: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 31 | 466 | [5 empty] | https://buildings.beanfield.com/buildings/view/2839 |  |  | 3 - Normal |  | Mississauga
Construction | CONST-38259 | 3888 Duke of York Blvd, Mississauga, Ovation II | Condo | New Condo |  | Unresolved | Harvey Tran | Harvey Tran | Harvey Tran | 2024-08-27 14:52 |  | 2024-10-29 09:52 |  |  |  | 0 | 0 |  |  | CONST-38263, CONST-38264, CONST-38992 | CONST-37795, CONST-38260 | Requested by James Fox. Units 471 Floors 31 Constructed 2005 Ovation 2_3888 Duke of York Blvd Could you please create a new ticket for an OSP plan & site walk Ovation2 at 3888 Duke of York Blvd? This condo has 471 units and was built in 2005. Ovation 1 at 3880 Duke of York Blvd. This condo has 466 units and was built in 2004 This location is part of the Mississauga Square One- Condo Backbone build: CONST-37795, ideally we will have minimal OSP work required to enter the building. BB Link: Ovation 2: [https://buildings.beanfield.com/buildings/view/6110] Ovation 1: [https://buildings.beanfield.com/buildings/view/2839] Site Contact: *Sujata Sundaram* *Condominium Manager, O.L.C.M.* *Agent for and on behalf of: PSCC 754* *Ovation Phase II* *3888 Duke of York Blvd. Mississauga, On L5B 4P5* *Phone:* 905-848-9378 *Fax:* 905-848-3800 {*}Email:{*}ovation2.pm@DelCondo.com Please also CC other PM's on site: [Ovation.SF@delcondo.com¦mailto:Ovation.SF@delcondo.com], [Ovation1.pm@delcondo.com¦mailto:Ovation1.pm@delcondo.com] | [13 empty] | 0¦i55o67: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 31 | 471 | [5 empty] | https://buildings.beanfield.com/buildings/view/6110 |  |  | 3 - Normal |  | Mississauga
Construction | CONST-37816 | 105 Victoria St, Toronto, The Victorian | Condo | New Condo |  | Unresolved | Unassigned | Harvey Tran | Harvey Tran | 2024-06-28 08:37 |  | 2024-10-29 10:24 |  |  |  | 0 | 0 | _thumb_938549.png |  | CONST-37817, CONST-37818 |  | Requested by Oliver Davies. Units 103 Floors 14 Constructed in 1997 ISW work will likely be required. Near-net might be minimal OSP work to enter building This condo has 103 residential units and was constructed in 1997 - ISW work will most likely be required. This location is near-net and ideally we will have minimal OSP work required to enter the building. Nearest access points will be CC#3622 or CC#3253 BB Link: [https://buildings.beanfield.com/buildings/view/4360] +*Site Contact:*+ *Ali (Superintendent/Board Member) - will provide access on-site.* 416 887-1983. OR _Steven LaChapelle, OLCM_ _Property Manager_ _365 Evans Avenue, Suite 601_ _Etobicoke, ON M8Z 1K2_ E [steven@iconpm.ca¦mailto:steven@iconpm.ca] | [13 empty] | 0¦i4zrxz: | [7 empty] | 9.2234e+18 | [19 empty] | Oct 29, 2024 added units | [6 empty] | 3 - Normal | [24 empty] | 103 | 14 | [5 empty] | https://buildings.beanfield.com/buildings/view/4360 |  |  | 3 - Normal |  | Toronto
Construction | CONST-37919 | Woodbridge MDU's (Various Locations) | Condo | New Condo |  | Unresolved | Denise King | Denise King | Denise King | 2024-07-10 14:40 | 2025-03-03 10:53 | 2024-10-21 09:30 |  |  |  | 0 | 1 | _thumb_951466.png |  | CONST-37920, CONST-37921, CONST-38154 |  | Requested by Oliver Davies: Request for a backbone estimate to build Beanfield's fibre network into the various MDUs throughout Woodbridge. This project will open up 2,681 net-new units across 15 MDUs, 1 of which we have a FS agreement for already. Additionally, 1 active FS location will be migrated to Beanfield, with another 2,005 units under development that can be connected at a later date. MDU List: ¦Name¦Address¦Agreement¦Units¦Build Date¦Condo Corp.¦Notes¦Building Browser¦ ¦Ambria¦4620 Hwy 7 W¦n¦81¦2007¦YRSC-1099¦ ¦[https://buildings.beanfield.com/buildings/view/20527]¦ ¦Vista Parc Condos¦4700 Hwy 7 W¦n¦122¦2015¦YRCC-1278¦ ¦[https://buildings.beanfield.com/buildings/view/20528]¦ ¦Avenue on 7¦4800 Hwy 7 W¦fibrestream¦278¦2019¦YRCC-1405¦ ¦[https://buildings.beanfield.com/buildings/view/15639]¦ ¦La Viva Towns¦26 Bruce St¦n¦124¦2016¦YRCC-1333¦ ¦[https://buildings.beanfield.com/buildings/view/20529]¦ ¦Boutik Condos¦4908 Hwy 7 W¦n¦153¦ ¦ ¦Development. Occupancy date pending¦[https://buildings.beanfield.com/buildings/view/20530]¦ ¦Volare Condos¦7730 Kipling Ave¦n¦118¦2013¦YRCC-1223¦ ¦[https://buildings.beanfield.com/buildings/view/20531]¦ ¦Oggi Townhomes¦5279 Hwy 7 W¦n¦169¦2021¦YRCC-1467¦ ¦[https://buildings.beanfield.com/buildings/view/20532]¦ ¦Allegra¦12 Woodstream Blvd¦FS Agreement (Unactioned)¦213¦ ¦ ¦ ¦[https://buildings.beanfield.com/buildings/view/16167]¦ ¦Allegra Condos¦24 Woodstream Blvd¦n¦172¦2015¦YRCC-1284¦ ¦[https://buildings.beanfield.com/buildings/view/20533]¦ ¦Renaissance Court¦281 Woodbridge Ave¦FS Agreement (Active)¦228¦2011¦YRCC-1196¦ ¦[https://buildings.beanfield.com/buildings/view/15594]¦ ¦Highlands of Woodbridge¦8026 Kipling Ave¦n¦117¦2008¦YRCC-1115,YRSC-1141¦ ¦[https://buildings.beanfield.com/buildings/view/20535]¦ ¦Old Market Lane Condos¦177 Woodbridge Ave¦n¦85¦ ¦ ¦Development: Pre-construction¦[https://buildings.beanfield.com/buildings/view/20537]¦ ¦Grand Manor¦160 Woodbridge Ave¦n¦55¦2007¦YRCC-1105¦ ¦[https://buildings.beanfield.com/buildings/view/20538]¦ ¦The Clarence¦86 Woodbridge Ave¦n¦110¦2017¦YRCC-1352¦ ¦[https://buildings.beanfield.com/buildings/view/5881]¦ ¦Piazza Woodbridge¦53 Woodbridge Ave¦n¦105¦1999¦YRCC-916¦ ¦[https://buildings.beanfield.com/buildings/view/20539]¦ ¦8209 Islington Ave Condos¦8201 Islington Ave¦n¦149¦2006¦YRCC-1069¦ ¦[https://buildings.beanfield.com/buildings/view/20406]¦ ¦Vero Condos¦8302 Islington Ave¦n¦85¦ ¦-¦ ¦[https://buildings.beanfield.com/buildings/view/20540]¦ ¦Centro Square Condos¦3600 Hwy 7 W¦n¦783¦2018¦YRCC-1381¦ ¦[https://buildings.beanfield.com/buildings/view/20543]¦ ¦3201 Highway 7 Condos¦3201 Hwy 7¦n¦1641¦ ¦ ¦Development: Status: Pre-construction, Occupancy date pending¦[https://buildings.beanfield.com/buildings/view/20544]¦ ¦Murals Condos¦4585 Hwy 7¦n¦126¦ ¦ ¦Development: Status: Pre-construction, Occupancy date pending, selling now¦[https://buildings.beanfield.com/buildings/view/20545]¦ Aerial screenshot is attached to identify the various MDU locations to be included in our scope of work for this project. | [13 empty] | 0¦i51x3r: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [26 empty] | Backbone | [7 empty] | 3 - Normal |  | Woodbridge
Construction | CONST-39538 | 11 Yonge St, Toronto, SkyTower at Pinnacle One Yonge | Condo | New Condo |  | Unresolved | James Mowers | Lorna Kurok | Lorna Kurok | 2024-12-18 10:40 |  | 2025-01-09 14:32 |  |  | 2025-10-01 | 0 | 1 |  |  | CONST-39539, CONST-39540, CONST-39541, CONST-39599 |  | *PM information as of Dec 20, 2024:* PM Contact Name: Anson Kwok PM Contact #: 416-925-3354 x 226 PM Email Address: [akwok@pinnacleinternational.ca¦mailto:akwok@pinnacleinternational.ca] Please launch the project for 11 Yonge. Attached is the approved CA form with the associated budget. This should be allocated to the FY25 Residential Construction budget. Building Type: Greenfield Choice Units: 995 Required Date: October 2025 Oct 2025 1st Occupancy All OSP will be completed by contractors. Greenfield - ISW cost of $370/unit includs all partas and labour OSP cost of $650 reflect TOR CBD rates MDU Address: [11 Yonge St¦https://www.google.com/maps/search/11+Yonge+St+City:+Toronto?entry=gmail&source=g] [City: Toronto¦https://www.google.com/maps/search/11+Yonge+St+City:+Toronto?entry=gmail&source=g] Building Name - SkyTower at Pinnacle One Yonge # of Units: 955 # of Floors: 95 Building First Occupancy Date or or time period of year: October 2025 PM Contact Name: Anson Kwok PM Contact #: 416-925-3354 x 226 PM Email Address: [akwok@pinnacleinternational.ca¦mailto:akwok@pinnacleinternational.ca] Type of Contract (Fibre agreement or NUA & MA): Access & Marketing Building linked to other Buildings: 1 Yonge St Bulk Related: No | GreenfieldChoice, PREWIRE | [12 empty] | 0¦i5eqrj: | [7 empty] | 9.2234e+18 | [19 empty] | Dec 17, 2024 - Newbuilds email received, 11 Yonge - Residential Building Approved_Approved CA form with budget is provided. Part of the FY25 Residential Construction Budget. Jan 6, 2025_Ca Approved, Agreement Approved, requires OSP plan to confirm building feed and then site visit to actualize the budget. When the budget is actualized PC_Lorna will create appropriate task codes. Jan 9, 2025_OSP plan Npop will be 45 Front. | [6 empty] | 3 - Normal | [25 empty] | 955 | [5 empty] | https://buildings.beanfield.com/buildings/view/21045 |  |  | 3 - Normal |  | Toronto
Construction | CONST-27685 | 195 Merton St, Toronto - The Rio IV | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Harvey Tran | 2022-04-06 13:12 |  | 2024-12-31 17:09 |  |  |  | 0 | 0 |  |  | CONST-27686, CONST-27687 |  |  | Fiberstreamagreement | [12 empty] | 0¦i3b827: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed 2004 | [6 empty] | 3 - Normal | [24 empty] | 12 | 124 | [5 empty] | https://buildings.beanfield.com/buildings/view/4982 |  |  | 3 - Normal |  | Toronto
Construction | CONST-36180 | 942 Yonge St, Toronto | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2024-01-11 15:08 | 2025-03-04 09:27 | 2024-12-31 17:34 |  |  |  | 0 | 0 |  |  | CONST-36181, CONST-36182 |  | Requested by Oliver Davies, We have received a request for our services from a PM we have worked with in the past that is now managing 942 Yonge St. The condo board has asked if Beanfield can become an option for their residents. Could you please set up site walk & OSP tickets? This is an older building constructed in the 90’s - we will need to budget for wiring the suites. The condo board is aware of this requirement. If we can get into the building using CC#4698, we may be capable of bringing this community online at a reasonable cost. PM Info: *Elise Deschamps, OLCM* Senior Condominium Manager ¦ ICC Property Management Ltd. T: (905) 940-1234 F: (905) 940-3881 E: [edeschamps@iccpropertymanagement.com¦mailto:edeschamps@iccpropertymanagement.com] Thank you, | [13 empty] | 0¦i4k4av: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed 1992 | [6 empty] | 3 - Normal | [24 empty] | 13 | 268 | [5 empty] | https://buildings.beanfield.com/buildings/view/2087 |  |  | 3 - Normal |  | Toronto
Construction | CONST-36202 | 35 Brian Peck Cres, Toronto - Scenic on Eglinton | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2024-01-15 09:56 |  | 2024-12-31 17:28 |  |  |  | 0 | 0 |  |  | CONST-36203, CONST-36204 | CONST-29120 | Requested by Jay Fernandes, This was a Fibrestream Active building that was split up from its adjoining building. Can we set up a site walk ticket for James and link it to this ticket https://tickets.beanfield.com/browse/CONST-29120? Thanks, *New PM Info:* *REI SULAJ* Property Manager 2645 Skymark Ave, Suite 101 ¦ Mississauga, ON L4W 4H2 Email [rei.sulaj@fsresidential.com¦mailto:rei.sulaj@fsresidential.com] [*www.fsresidential.com*¦http://www.fsresidential.com/] {+}Previous PM{+}: ¦NORMA LEWIS, R.C.M¦ ¦Property Manager¦ ¦Direct 647.258.8218¦ ¦Email norma.lewis@fsresidential.com¦ | Fiberstreamagreement | [12 empty] | 0¦i4k9xb: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed 2013 | [6 empty] | 3 - Normal | [24 empty] | 16 | 364 | [5 empty] | https://buildings.beanfield.com/buildings/view/15462 |  |  | 3 - Normal |  | Toronto
Construction | CONST-36580 | 71-99 Foxbar Rd, Toronto - Blue Diamond at Imperial Village | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2024-02-21 08:54 |  | 2024-12-31 17:23 |  |  |  | 0 | 0 |  |  | CONST-36581, CONST-36582 |  | Requested by Oliver Davies, Can you please queue up a site walk & OSP plan for the “Blue Diamond at Imperial Village” condos at 71-99 Foxbar Rd? This condo was recently completed in 2022 and contains 258 residential units. PM Info: Anton (PM) [bluediamond.pm@fhkipling.com¦mailto:bluediamond.pm@fhkipling.com] Renalta (admin) [bluediamond.admin@fhkipling.com¦mailto:bluediamond.admin@fhkipling.com] Thanks! | [13 empty] | 0¦i4mv73: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 26 | [6 empty] | https://buildings.beanfield.com/buildings/view/16068 |  |  | 3 - Normal |  | Toronto
Construction | CONST-35910 | 30 Samuel Wood Way, Etobicoke - The Kip District 2 | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2023-12-05 13:12 |  | 2025-01-01 13:35 |  |  |  | 0 | 0 |  |  | CONST-35911, CONST-35912 | CONST-31591 | Requested by Oliver Davies, can you please queue up a site walk for 5365 Dundas St W? The Kip District 2 condos were recently registered and contain 286 residential units. The Kip District 1 is an “on-net” FibreStream building that should connect via a shared parking level. A site walk and budget was completed for Kip 1 (20 Thomas Riley Rd) last year (CONST-31593). PM Info: *NOHA ELMURTADA CMCA®, AMS®, PCAM®* Sr. Property Manager Direct 647.258.3453 [Noha.Elmurtada@fsresidential.com¦mailto:Noha.Elmurtada@fsresidential.com] This build will likely fall at about $350/unit all-in for both locations. There is a 30% pen rate with the FS customers at Kip District 1, and I think it is worthwhile to make a concerted effort to get both towers connected to Beanfield. Thank you, | [13 empty] | 0¦i4hm67: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2022 | [6 empty] | 3 - Normal | [24 empty] | 24 | 286 | [5 empty] | https://buildings.beanfield.com/buildings/view/18992 |  |  | 3 - Normal |  | Etobicoke
Construction | CONST-35391 | 18 Spring Garden Ave, North York - Platinum Towers XO | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2023-09-26 09:22 |  | 2025-01-01 17:10 |  |  |  | 0 | 0 |  |  | CONST-35392 |  | Requested by Oliver Davies, Can you please assist with creating a new ticket for an OSP Plan only at 18 Spring Garden Ave? There are 341 units here. Unfortunately, the building management is difficult and we have been unable to gain access for a site walk. This has been ongoing for a number of years despite requests from the residents and I would like to make sure we have an efficient route for bringing fibre to the building before continuing the discussion. Thank you, | [13 empty] | 0¦i4ccav: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2008. | [6 empty] | 3 - Normal | [24 empty] | 36 | 341 | [5 empty] | https://buildings.beanfield.com/buildings/view/5833 |  |  | 3 - Normal |  | North York
Construction | CONST-32212 | 238 Bonis Ave, Scarborough | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Jessica Markiewicz | 2022-12-01 09:29 |  | 2025-01-02 01:07 |  |  |  | 0 | 2 |  |  | CONST-32213, CONST-32214 |  | Requested by Oliver Davis. Can you please proceed with setting up a site walk for 238 Bonis Ave? BB Link: [https://buildings.beanfield.com/buildings/view/13429] *NEW PM info:* Marie Yang Condominium Manager OLCM Agent for and on behalf of TSCC 1889 Legends at Tam O'Shanter c/o DEL Property Management Inc. 238 Bonis Avenue, Scarborough Ontario, M1T 3W7 Phone: (416) 293-1423 [Legends.PM@delcondo.com¦mailto:Legends.PM@delcondo.com] PM Info: Aurora Rushiti Interim Condominium Manager Agent for and on behalf of TSCC 1889 Legends at Tam O'Shanter c/o DEL Property Management Inc. 238 Bonis Avenue, Scarborough Phone: (416) 293-1423 Gate House: (416) 293-6576 Email: [legends.pm@DelCondo.com¦mailto:legends.pm@DelCondo.com] Nearby, we have (unactioned) FS agreements for the following: [https://buildings.beanfield.com/buildings/view/7206] - 195 Bonis Ave [https://buildings.beanfield.com/buildings/view/15724] - 185 Bonis Ave These will be the only buildings for us to look in this neighbourhood, 138, 188 and 228 Bonis are old and will require a pre-wire. Thanks! | [13 empty] | 0¦i3qh0v: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2007 | [6 empty] | 3 - Normal | [24 empty] | 24 | 247 | [5 empty] | https://buildings.beanfield.com/buildings/view/13429 |  |  | 3 - Normal
Construction | CONST-34990 | 38 Honeycrisp Cres, Concord - Mobilio East | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2023-08-01 13:35 |  | 2025-01-01 17:44 |  |  |  | 0 | 0 |  |  | CONST-34993, CONST-34994 | CONST-34989 | Requested by Oliver Davies, Can you please create a new ticket for a sitewalk & OSP plan at the Mobilio Condos? These are new midrise condo towers & townhomes by Menkes & Quadreal that have recently registered in the Jane St / Hwy 7 area. These buildings are part of the larger masterplan community, [VMC¦https://myvmc.ca/developments/mobilio-by-menkes-and-quadreal/] (Vaughan Metropolitan Centre). Mobilio West - 550 units - 10 Honeycrisp Cres. & 55 Interchange Way Mobilio East - 462 units - 38 Honeycrisp Cres. I understand there is also a third phase that is currently under construction as part of this series of buildings. PM Info: *Nancy Lin,* OLCM, RCM, BA Senior Property Manager YRSCC 1502 - 10 Honeycrisp Cres., Vaughan, Ont. L4K 0M7 YRSCC 1508 – 38 Honeycrisp Cres., Vaughan, ON L4K 0M7 [mobiliowest@menres.com¦mailto:mobiliowest@menres.com] ¦ [mobilioeast@menres.com¦mailto:mobilioeast@menres.com] n[ancy.lin@menres.com¦mailto:ancy.lin@menres.com] I [www.menres.com¦http://www.menres.com/] Thanks! | [13 empty] | 0¦i47san: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2022 | [6 empty] | 3 - Normal | [24 empty] | 21 | 462 | [5 empty] | https://buildings.beanfield.com/buildings/view/18763 |  |  | 3 - Normal |  | Concord
Construction | CONST-35199 | 1379 Bloor St W / 30 Merchant Lane, Toronto | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2023-08-24 08:07 |  | 2025-01-01 17:32 |  |  |  | 0 | 0 |  |  | CONST-35200, CONST-35201 | CONST-29399 | Requested by Oliver Davies, Could you please schedule a site walk for the beBloor Townhomes at 1379 Bloor St W? Site Contact: Sean Karow [seankarow@sympatico.ca¦mailto:seankarow@sympatico.ca] CC’ [tscc1657@gmail.com¦mailto:tscc1657@gmail.com] 416.979.8005 We have an existing plan to bring 1369 Bloor St W (beBloor Condos) online via https://tickets.beanfield.com/browse/CONST-29401 - they share a P1 level with the townhomes. Our fibre entry point will be on the 1379 Bloor (townhome) side of P1. The tickets should be linked together. Thank you, | [13 empty] | 0¦i49nb3: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed 2005 | [6 empty] | 3 - Normal | [24 empty] | 2 | 92 | [5 empty] | https://buildings.beanfield.com/buildings/view/7583 |  |  | 3 - Normal |  | Toronto
Construction | CONST-35461 | 256 Royal York Rd & 8 Drummond St, Etobicoke - Royal Towns | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2023-10-11 08:44 |  | 2025-01-01 16:43 |  |  |  | 0 | 0 |  |  | CONST-35462, CONST-35463 |  | Requested by Oliver Davies, When you have a moment, can you please create new tickets for OSP & Site Walk for the “Royal Towns” at 256 Royal York Rd & 8 Drummond St? We have fibre running along this stretch of Royal York and we may have an efficient route into the property via BFHW-0494. PM info: Bertiana Fregjaj Condominium Manager 6205A Airport Road, Suite 301 ¦ Mississauga, ON L4V 1E1 Tel: 905.673.7338 ¦ Toll-Free: 1.888.392.DUKA (3852) ¦ Fax: 905.673.8952 [www.dukamanagement.com¦http://www.dukamanagement.com/] ¦ Email: [royaltowns@dukamanagement.com¦mailto:royaltowns@dukamanagement.com] Thank you, | [13 empty] | 0¦i4dfsn: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2017 | [6 empty] | 3 - Normal | [24 empty] | 2 | 104 | [5 empty] | https://buildings.beanfield.com/buildings/view/8510 |  |  | 3 - Normal |  | Etobicoke
Construction | CONST-35218 | 1787 St Clair Ave W, Toronto - Scout Condos | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2023-08-29 15:14 |  | 2025-01-01 16:26 |  |  |  | 0 | 0 |  |  | CONST-35219, CONST-35220 |  | Requested by Oliver Davies, Can you please set up tickets for an OSP plan & site walk for the new Scout Condos at 1787 St Clair Ave W? This will likely become a backbone build, but getting an initial plan in place will be helpful as we have limited presence along this stretch of St. Clair. With the new TTC line being built there is increased condo development happening in this area that will likely continue over the next few years. Site Contact: In Kim 647-829-2617 [scout.pm@delcondo.com¦mailto:scout.pm@delcondo.com] 1771 St. Clair Ave W is located directly across the street to the west of this location with 72 units ([https://buildings.beanfield.com/buildings/view/18982]) Opposite this building 1808 St Clair Ave W is being built with 249 residential units by Diamond Kilmer ([https://buildings.beanfield.com/buildings/view/18981]) Thank you, | [13 empty] | 0¦i4a41b: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 12 | 269 | [5 empty] | https://buildings.beanfield.com/buildings/view/18760 |  |  | 3 - Normal |  | Toronto
Construction | CONST-12141 | 188 Redpath Ave | Condo | New Condo |  | Unresolved | Harvey Tran | Oguz Avci [X] | Oguz Avci [X] | 2020-03-13 08:58 |  | 2025-01-01 16:33 |  |  |  | 0 | 1 |  |  | CONST-13010, CONST-13011 |  | [mkarimi@360cm.ca¦mailto:mkarimi@360cm.ca] | [13 empty] | 0¦i1vm1b: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2000 | [6 empty] | 3 - Normal | [24 empty] | 8 | 86 | [5 empty] | https://buildings.beanfield.com/buildings/view/9894 |  |  | 3 - Normal |  | Toronto
Construction | CONST-34989 | 10 Honeycrisp Cres & 55 Interchange Way, Concord - Mobilio West | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2023-08-01 13:34 | 2025-03-04 10:09 | 2025-01-01 17:50 |  |  |  | 0 | 0 |  |  | CONST-34991, CONST-34992 | CONST-34990 | Requested by Oliver Davies, Can you please create a new ticket for a sitewalk & OSP plan at the Mobilio Condos? These are new midrise condo towers & townhomes by Menkes & Quadreal that have recently registered in the Jane St / Hwy 7 area. These buildings are part of the larger masterplan community, [VMC¦https://myvmc.ca/developments/mobilio-by-menkes-and-quadreal/] (Vaughan Metropolitan Centre). Mobilio West - 550 units - 10 Honeycrisp Cres. & 55 Interchange Way Mobilio East - 462 units - 38 Honeycrisp Cres. I understand there is also a third phase that is currently under construction as part of this series of buildings. PM Info: *Nancy Lin,* OLCM, RCM, BA Senior Property Manager YRSCC 1502 - 10 Honeycrisp Cres., Vaughan, Ont. L4K 0M7 YRSCC 1508 – 38 Honeycrisp Cres., Vaughan, ON L4K 0M7 [mobiliowest@menres.com¦mailto:mobiliowest@menres.com] ¦ [mobilioeast@menres.com¦mailto:mobilioeast@menres.com] n[ancy.lin@menres.com¦mailto:ancy.lin@menres.com] I [www.menres.com¦http://www.menres.com/] Thanks! | [13 empty] | 0¦i47saf: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2022 | [6 empty] | 3 - Normal | [24 empty] | 21 | 550 | [5 empty] | https://buildings.beanfield.com/buildings/view/18762 |  |  | 3 - Normal |  | Concord
Construction | CONST-29114 | 120 Dallimore Cir, Toronto - Red Hot Condos | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Jessica Markiewicz | 2022-07-11 07:14 |  | 2025-01-01 17:56 |  |  |  | 0 | 0 |  |  | CONST-29115, CONST-29116 |  | Requested by Jay Fernandes Hi, I’ve gone through the remaining Fibrestream condos we have agreements for in the GTA and have grouped them in a way that I think makes sense for site visits and builds. There will be another list coming of buildings that don’t really fall into groups. Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. There are some current backbone (Sheppard) or NPOP (960 Lawrence) projects that will need to be completed to connect these but this will get everything into the system. Thanks! *PM: Tracy Everlyne* *redhotcondospm@gmail.com* *416.391.2224* | DonMills&Eg, Fiberstreamagreement | [12 empty] | 0¦i3h5h3: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2010 | [6 empty] | 3 - Normal | [24 empty] | 10 | 224 | [5 empty] | https://buildings.beanfield.com/buildings/view/15464 |  |  | 3 - Normal |  | Toronto
Construction | CONST-34828 | 35 Merton St, Toronto - The Rio Condominiums | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2023-07-20 13:30 |  | 2025-01-02 01:37 |  |  |  | 0 | 0 |  |  | CONST-34829, CONST-34830 |  | Requested by Oliver Davies, Can you please queue up a site walk & OSP plan for 35 Merton St? The *Rio Condos* contain 112 units. PM Info: *Jerry Cunningham BSc. OLCM* *Condominium Manager* Phone: 416-642-2807 Ext. 429 [Jerry.Cunningham@WILSONBLANCHARD.COM¦mailto:Jerry.Cunningham@WILSONBLANCHARD.COM] Jerry will coordinate access through their site super, Marinko Pivac. Anytime 9-5pm during the weekdays. There is a large mish mash of small condos & commercial offices down Merton St. Once the budgets are in place for this location, and the ones noted below, this should allow us to determine what other buildings we can bring on-net along the way. Also awaiting a site walk on this street: Rio IV (FibreStream Active) - 195 Merton St - 124 units CONST-27685 The Metro (FibreStream Active) - 119 Merton St - 194 units CONST-27670 We have a FBIP to the MYC Condos at 1815 Yonge St - 205 units CONST-28212 Nearby, where we do not have an agreement: Rio II - 253 Merton St - 124 units Rio III - 225 Merton St - 124 units The Domain - 319 Merton St - 239 units Beanfield is On-Net in the following: Life Condos - 68 Merton St - 156 units [https://buildings.beanfield.com/buildings/view/4725] (Commercial) Toronto Water Service Centre - 275 Merton St - [https://buildings.beanfield.com/buildings/view/13870] (Commercial) 130 Merton St [https://buildings.beanfield.com/buildings/view/1160] Thank you, | [13 empty] | 0¦i46q0v: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2000 | [6 empty] | 3 - Normal | [24 empty] | 15 | 112 | [5 empty] | https://buildings.beanfield.com/buildings/view/18554 |  |  | 3 - Normal |  | Toronto
Construction | CONST-33394 | 929 Queen St E, Toronto | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2023-03-22 14:07 |  | 2025-01-02 01:59 |  |  |  | 0 | 0 |  |  | CONST-33399 | CONST-33395, CONST-33396, CONST-33397, CONST-33398 | Requested by Oliver Davies Can you please have OSP tickets created for Mark at the following 5x addresses? These are all planned purpose-built rental communities being constructed by Core Development Group that have yet to break ground, so no site-walk is required. We would like to get an idea of what will be required to connect these locations to the Beanfield network. 929 Queen E & 252 Parliament are likely to be the most difficult. Core is looking for an ISP partner to provide connectivity to all of the units in their upcoming rental communities. * 929 Queen St E: 68 units / July 2025 occupancy (Leslieville Pumps location - BFMH located nearby via CDSM10723) * 1233 Queen St: 142 units / June 2025 occupancy (off-net -Queen / Leslie - no fibre in the immediate vicinity) * 1111 Danforth: 208 units / June 2025 occupancy (near-net CC#6083 outside of building) * 403 Keele: 261 units / September 2025 occupancy (near-net BF-0781 outside of building, this is just below the active build at 60/61 Heintzman) * 252 Parliament: 80 units / November 2024 occupancy (off-net no fibre between Queen to Dundas on Parliament) scheduled to break ground this year Each location is expected to have a number of retail units at grade. They have provided drawings/plans for all 5x locations, I will upload them to the JIRA tickets once created. Thanks! | CoreDevelopmentGroup | [12 empty] | 0¦i3xmmf: | [7 empty] | 9.2234e+18 | [19 empty] | First Occupancy July 2025. Strata indicates it was built 1979. | [6 empty] | 3 - Normal | [24 empty] | 8 | 68 | [5 empty] | https://buildings.beanfield.com/buildings/view/18099 |  |  | 3 - Normal |  | Toronto
Construction | CONST-32570 | 784 The Queensway / 7 Smith Cres | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Denise King | 2023-01-03 15:22 |  | 2025-01-02 01:49 |  |  |  | 0 | 1 |  |  | CONST-32573, CONST-32574, CONST-32575 | CONST-32576 | Requested by Oliver Davies: PM: *Ola Dychka* ([ola@iconpm.ca¦mailto:ola@iconpm.ca]) The Qube Condos at 760 The Queensway ([https://buildings.beanfield.com/buildings/view/7690]) are immediately next door, a connection here may be possible for an additional 74 units. The Curio Condos is also under construction at 801 The Queensway for another 206 units, though this is likely 2-3 years out from occupancy. As the nearest BFHW-0443 is over 400m away, we may consider adding a new HW in the vicinity to assist with expansion to these buildings. | [13 empty] | 0¦i3s1nz: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2020 | [6 empty] | 3 - Normal | [24 empty] | 9 | 170 | [5 empty] | https://buildings.beanfield.com/buildings/view/17685 |  |  | 3 - Normal |  | Etobicoke
Construction | CONST-32576 | 760 The Queensway - The Qube Condos | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Denise King | 2023-01-04 08:06 | 2025-03-04 09:28 | 2025-01-02 01:48 |  |  |  | 0 | 1 |  |  | CONST-32577, CONST-32578 | CONST-32570 | Requested by Oliver Davies: PM Info here: Kimi is admin 416.233.4100 [qube@crossbridgecs.com¦mailto:qube@crossbridgecs.com] PM: *Ola Dychka* ([ola@iconpm.ca¦mailto:ola@iconpm.ca]) The Qube Condos at 760 The Queensway ([https://buildings.beanfield.com/buildings/view/7690]) are immediately next door, a connection here may be possible for an additional 74 units. The Curio Condos is also under construction at 801 The Queensway for another 206 units, though this is likely 2-3 years out from occupancy. As the nearest BFHW-0443 is over 400m away, we may consider adding a new HW in the vicinity to assist with expansion to these buildings. | [13 empty] | 0¦i3s2lr: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2015 | [6 empty] | 3 - Normal | [24 empty] | 8 | 74 | [5 empty] | https://buildings.beanfield.com/buildings/view/7690 |  |  | 3 - Normal |  | Etobicoke
Construction | CONST-31056 | 50 Green Belt Dr, North York | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Jessica Markiewicz | 2022-10-12 12:59 | 2025-03-04 10:47 | 2025-01-02 14:36 |  |  |  | 0 | 0 |  |  | CONST-31057, CONST-31058 |  | Requested by Oliver Davies. We are looking for a budget to build fibre to a new development at 50 Green Belt Dr. Could you please create a ticket for this? Katie & Brittany Hamilton’s father, John Hamilton, is the Managing Principal at Pensio Global who has oversight on this development. [https://urbantoronto.ca/database/projects/40-moccasin-trail-50-greenbelt-drive] BB Link: [https://buildings.beanfield.com/buildings/view/17232] No Site Contact. We only require a budget for the OSP work as this project has yet to break ground. It is scheduled for completion in 2025. 1x condo building with approx. 189 units, 1x purpose built rental building with 100 units. I spoke with James about this earlier in the year, and he estimated up to $150k to build fibre from the closest MH. We should get an accurate figure in place for us to work with. FS is active nearby at 120 Dallimore Cir. ([https://buildings.beanfield.com/buildings/view/15464]), and 16 Dallimore ([https://buildings.beanfield.com/buildings/view/3655]) is also up the street. | [13 empty] | 0¦i3n9d3: | [7 empty] | 9.2234e+18 | [19 empty] | October 28th - Site Visit requested. | [6 empty] | 3 - Normal | [25 empty] | 289 | [5 empty] | https://buildings.beanfield.com/buildings/view/17232 |  |  | 3 - Normal |  | North York
Construction | CONST-30387 | 18 Valley Woods Rd, North York - Bellair Gardens | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Jessica Markiewicz | 2022-09-02 14:20 |  | 2025-01-02 14:50 |  |  |  | 0 | 0 |  |  | CONST-30388, CONST-30389 |  | Requested by Oliver Davies. Can you please schedule a site walk for 18 Valley Woods Rd? We may be able to bring fibre to this building as a result of CONST-15175 but it is a long shot. We do not require a budget if the OSP costs are already out of scope. BB Link: [https://buildings.beanfield.com/buildings/view/4045] PM: Gianina [bellairgardens@crossbridgecs.com¦mailto:bellairgardens@crossbridgecs.com] | [13 empty] | 0¦i3ku9j: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2007 October 28th - Site Visit requested. | [6 empty] | 3 - Normal | [24 empty] | 11 | 167 | [5 empty] | https://buildings.beanfield.com/buildings/view/4045 |  |  | 3 - Normal |  | North York
Construction | CONST-36330 | 1461 Lawrence Ave W, North York - 7 on the Park | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2024-01-29 11:00 |  | 2024-12-30 18:10 |  |  |  | 0 | 1 |  |  | CONST-36331, CONST-36332 |  | Requested by Oliver Davies, Could you please queue up an OSP plan & site walk for the new “7 on the Park” condos at 1461 Lawrence Ave W? There are 216 residential units here. We have a handwell located across the street from this development on Lawrence Ave W (BFHW-0924). PM Info: *Ardo Kaja OLCM - GL* *Property Manager* T.S.C.C 2940 - 7 On the Park 1461 Lawrence Ave West Toronto, Ontario M6L 0A6 E-mail: +[kajardo.kaja@crossbridgecs.com¦mailto:kajardo.kaja@crossbridgecs.com]+ Telephone: 416 - 247 - 3360 Security desk: 416 - 247 - 0047 Thank you, | [13 empty] | 0¦i4lakf: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 21 | 216 | [5 empty] | https://buildings.beanfield.com/buildings/view/19491 |  |  | 3 - Normal |  | North York
Construction | CONST-35393 | 2150 Lawrence Ave E, Scarborough - 2150 Condos Phase 2 | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2023-09-26 09:38 |  | 2024-12-30 17:59 |  |  |  | 0 | 0 |  |  | CONST-35394, CONST-35395 |  | Requested by Oliver Davies, When you have a moment, can you please queue up an OSP plan & site walk for 2150 Lawrence Ave E “2150 Condos Phase 2”. PM info: Akram Ziad Licensed Condominium Manager The Agents on Behalf of TSCC 2771 Office: (416) 551-8942 Security Line: (647) 872-1515 Email: [TSCC2771@2150condos.net¦mailto:TSCC2771@2150condos.net] {color:#3c4043} {color} {color:#3c4043}There are 3x towers that make up the “2150 Condos” community. The site walk is for 2150 Lawrence Ave E (TSCC-2771) only, though we should try to confirm that all 3x can be connected via a shared parking level.{color} {color:#3c4043} {color} {color:#3c4043}Here is a breakdown of the 3x condos here:{color} {color:#3c4043} {color} [1328 Birchmount Rd¦https://buildings.beanfield.com/buildings/view/4073]{color:#3c4043} - 2150 Condos Phase 1 - TSCC 2504 - 228 units - no ticket{color} {color:#3c4043} {color} [2150 Lawrence Ave E¦https://buildings.beanfield.com/buildings/view/18704]{color:#3c4043}- 2150 Condos Phase 2 - TSCC 2771 - 204 units - Const-35393{color} {color:#3c4043} {color} [2152 Lawrence Ave E¦https://buildings.beanfield.com/buildings/view/18706]{color:#3c4043} - 2150 Condos Phase 3 - TSCC 2796 - 132 units - no ticket{color}{color:#3c4043} {color} {color:#3c4043}Thanks!{color} | [13 empty] | 0¦i4ccev: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 16 | 204 | [5 empty] | https://buildings.beanfield.com/buildings/view/18704 |  |  | 3 - Normal |  | Scarborough
Construction | CONST-35906 | 760 Lawrence Ave, Toronto | Condo | New Condo |  | Unresolved | Harvey Tran | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2023-12-05 12:00 |  | 2024-12-30 18:06 |  |  |  | 0 | 0 |  |  | CONST-35907, CONST-35908 | CONST-29093, CONST-29099, CONST-32587 | Requested by Oliver Davies, Can you please queue up a site walk & OSP plan for the Liberty Walk Townhomes at 760 Lawrence Ave W? There are 245 residential units here and we may be able to include them in our active FBIP for the nearby Treviso buildings: # CONST-29093 # CONST-29099 # CONST-32587 PM Info: April Jackman Property Manager City Sites Property Management Inc. Tel: 416-781-0691 / Fax: 905-232-1270 Email: [tscc1513@rogers.com¦mailto:tscc1513@rogers.com] 760 Lawrence Ave West, Toronto ON M6A 3E7 {color:#201f1e}These townhomes are located approximately. 150m east of Via Bagnato on the north side of Lawrence Ave W.{color} {color:#201f1e}Thank you,{color} | [13 empty] | 0¦i4hlr3: | [7 empty] | 9.2234e+18 | [19 empty] | May 9th, 2024 - Depending on the progress of OSP work in 830 Lawrence Ave build | [6 empty] | 3 - Normal | [24 empty] | 3 | 245 | [5 empty] | https://buildings.beanfield.com/buildings/view/2978 |  |  | 3 - Normal |  | Toronto
Construction | CONST-36662 | 408 Browns Line, Etobicoke - B-Line Condos | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2024-02-28 10:02 |  | 2024-12-30 18:23 |  |  |  | 0 | 0 | _thumb_843550.png |  | CONST-36663, CONST-36664 |  | Requested by Oliver Davies, Can you please set up an OSP plan & site walk for 408 Brown’s Line? The B-Line Condos are 1 year old and include 81 residential units that makeup TSCC-2897. Danny has flagged this location as we have already completed a lot of work in the neighbourhood, and we expect this location can be connected at a very low cost by a simple cable drop from the existing FOSC outside, per the attached image. PM Info: *MILA BOTA* CONDOMINIUM MANAGER Direct: 416-546-2126 x194 Email: [Mila.Bota@Melbournepm.ca¦mailto:Mila.Bota@Melbournepm.ca] Thanks! | [13 empty] | 0¦i4ndbz: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2022 | [6 empty] | 3 - Normal | [24 empty] | 6 | 81 | [5 empty] | https://buildings.beanfield.com/buildings/view/19931 |  |  | 3 - Normal |  | Etobicoke
Construction | CONST-28791 | 208 Enfield PL Mississauga - Wide Suites | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Harvey Tran | 2022-06-14 12:56 |  | 2024-12-30 18:58 |  |  |  | 0 | 0 |  |  | CONST-28810, CONST-28811 |  |  | Fiberstreamagreement | [12 empty] | 0¦i3flsf: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2011 | [6 empty] | 3 - Normal | [24 empty] | 37 | 278 | [5 empty] | https://buildings.beanfield.com/buildings/view/15653 |  |  | 3 - Normal |  | Mississauga
Construction | CONST-35719 | 15 Watergarden Dr, Mississauga | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2023-11-09 12:41 |  | 2024-12-31 10:34 |  |  |  | 0 | 0 |  |  | CONST-35729, CONST-35730 | CONST-28793, CONST-35712, CONST-35716, CONST-35717, CONST-35718, CONST-35720 | Requested by Oliver Davies, Could you please create a new ticket, linking the below addresses so we can move forward with an estimate for backbone to connect this pocket of buildings in Mississauga? We only have an agreement with the Amber Condos, the other locations will need to be negotiated once we have a plan in place. ¦Name¦Address¦Agreement¦Units¦Status¦BB Link¦ ¦Amber Condos¦5025 & 5033 Four Springs Ave¦YES¦446¦Off-Net¦[https://buildings.beanfield.com/buildings/view/15798]¦ ¦Crystal¦55 & 75 Eglinton Ave W¦NO¦463¦Off-Net¦[https://buildings.beanfield.com/buildings/view/4007]¦ ¦Pinnacle Uptown: Watergarden¦5044 Hurontario St¦NO¦316¦Off-Net¦[https://buildings.beanfield.com/buildings/view/16767]¦ ¦Perla Towers¦35-65 Watergarden Dr¦NO¦468¦Off-Net¦[https://buildings.beanfield.com/buildings/view/19420]¦ ¦Gemma Condos¦15 Watergarden Dr¦NO¦406¦Off-Net¦[https://buildings.beanfield.com/buildings/view/19421]¦ ¦Little Creek Condos¦5020-5040 Four Springs Ave & 110-160 Little Creek Rd¦NO¦57¦Off-Net¦[https://buildings.beanfield.com/buildings/view/19422]¦ Thank you! | [13 empty] | 0¦i4fp8n: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 35 | 406 | [5 empty] | https://buildings.beanfield.com/buildings/view/19421 |  |  | 3 - Normal |  | Mississauga
Construction | CONST-35718 | 35 & 65 Watergarden Dr, Mississauga | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2023-11-09 12:41 |  | 2024-12-31 11:10 |  |  |  | 0 | 0 |  |  | CONST-35727, CONST-35728 | CONST-28793, CONST-35712, CONST-35716, CONST-35717, CONST-35719, CONST-35720 | Requested by Oliver Davies, Could you please create a new ticket, linking the below addresses so we can move forward with an estimate for backbone to connect this pocket of buildings in Mississauga? We only have an agreement with the Amber Condos, the other locations will need to be negotiated once we have a plan in place. ¦Name¦Address¦Agreement¦Units¦Status¦BB Link¦ ¦Amber Condos¦5025 & 5033 Four Springs Ave¦YES¦446¦Off-Net¦[https://buildings.beanfield.com/buildings/view/15798]¦ ¦Crystal¦55 & 75 Eglinton Ave W¦NO¦463¦Off-Net¦[https://buildings.beanfield.com/buildings/view/4007]¦ ¦Pinnacle Uptown: Watergarden¦5044 Hurontario St¦NO¦316¦Off-Net¦[https://buildings.beanfield.com/buildings/view/16767]¦ ¦Perla Towers¦35-65 Watergarden Dr¦NO¦468¦Off-Net¦[https://buildings.beanfield.com/buildings/view/19420]¦ ¦Gemma Condos¦15 Watergarden Dr¦NO¦406¦Off-Net¦[https://buildings.beanfield.com/buildings/view/19421]¦ ¦Little Creek Condos¦5020-5040 Four Springs Ave & 110-160 Little Creek Rd¦NO¦57¦Off-Net¦[https://buildings.beanfield.com/buildings/view/19422]¦ Thank you! | [13 empty] | 0¦i4fp8f: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 34 | 316 | [5 empty] | https://buildings.beanfield.com/buildings/view/19420 |  |  | 3 - Normal |  | Mississauga
Construction | CONST-35716 | 55 & 75 Eglinton Ave W, Mississauga | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2023-11-09 12:39 |  | 2024-12-31 11:06 |  |  |  | 0 | 0 |  |  | CONST-35723, CONST-35724 | CONST-28793, CONST-35712, CONST-35717, CONST-35718, CONST-35719, CONST-35720 | Requested by Oliver Davies, Could you please create a new ticket, linking the below addresses so we can move forward with an estimate for backbone to connect this pocket of buildings in Mississauga? We only have an agreement with the Amber Condos, the other locations will need to be negotiated once we have a plan in place. ¦Name¦Address¦Agreement¦Units¦Status¦BB Link¦ ¦Amber Condos¦5025 & 5033 Four Springs Ave¦YES¦446¦Off-Net¦[https://buildings.beanfield.com/buildings/view/15798]¦ ¦Crystal¦55 & 75 Eglinton Ave W¦NO¦463¦Off-Net¦[https://buildings.beanfield.com/buildings/view/4007]¦ ¦Pinnacle Uptown: Watergarden¦5044 Hurontario St¦NO¦316¦Off-Net¦[https://buildings.beanfield.com/buildings/view/16767]¦ ¦Perla Towers¦35-65 Watergarden Dr¦NO¦468¦Off-Net¦[https://buildings.beanfield.com/buildings/view/19420]¦ ¦Gemma Condos¦15 Watergarden Dr¦NO¦406¦Off-Net¦[https://buildings.beanfield.com/buildings/view/19421]¦ ¦Little Creek Condos¦5020-5040 Four Springs Ave & 110-160 Little Creek Rd¦NO¦57¦Off-Net¦[https://buildings.beanfield.com/buildings/view/19422]¦ Thank you! | [13 empty] | 0¦i4fp7r: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 28 | 463 | [5 empty] | https://buildings.beanfield.com/buildings/view/4007 |  |  | 3 - Normal |  | Mississauga
Construction | CONST-35717 | 5044 Hurontario St, Mississauga | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2023-11-09 12:40 |  | 2024-12-31 11:07 |  |  |  | 0 | 0 |  |  | CONST-35725, CONST-35726 | CONST-28793, CONST-35712, CONST-35716, CONST-35718, CONST-35719, CONST-35720 | Requested by Oliver Davies, Could you please create a new ticket, linking the below addresses so we can move forward with an estimate for backbone to connect this pocket of buildings in Mississauga? We only have an agreement with the Amber Condos, the other locations will need to be negotiated once we have a plan in place. ¦Name¦Address¦Agreement¦Units¦Status¦BB Link¦ ¦Amber Condos¦5025 & 5033 Four Springs Ave¦YES¦446¦Off-Net¦[https://buildings.beanfield.com/buildings/view/15798]¦ ¦Crystal¦55 & 75 Eglinton Ave W¦NO¦463¦Off-Net¦[https://buildings.beanfield.com/buildings/view/4007]¦ ¦Pinnacle Uptown: Watergarden¦5044 Hurontario St¦NO¦316¦Off-Net¦[https://buildings.beanfield.com/buildings/view/16767]¦ ¦Perla Towers¦35-65 Watergarden Dr¦NO¦468¦Off-Net¦[https://buildings.beanfield.com/buildings/view/19420]¦ ¦Gemma Condos¦15 Watergarden Dr¦NO¦406¦Off-Net¦[https://buildings.beanfield.com/buildings/view/19421]¦ ¦Little Creek Condos¦5020-5040 Four Springs Ave & 110-160 Little Creek Rd¦NO¦57¦Off-Net¦[https://buildings.beanfield.com/buildings/view/19422]¦ Thank you! | [13 empty] | 0¦i4fp7z: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 34 | 316 | [5 empty] | https://buildings.beanfield.com/buildings/view/16767 |  |  | 3 - Normal |  | Mississauga
Construction | CONST-35720 | 5020-5040 Four Springs Ave & 110-160 Little Creek Rd, Mississauga | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2023-11-09 12:44 |  | 2024-12-31 11:24 |  |  |  | 0 | 0 |  |  | CONST-35731, CONST-35732 | CONST-28793, CONST-35712, CONST-35716, CONST-35717, CONST-35718, CONST-35719 | Requested by Oliver Davies, Could you please create a new ticket, linking the below addresses so we can move forward with an estimate for backbone to connect this pocket of buildings in Mississauga? We only have an agreement with the Amber Condos, the other locations will need to be negotiated once we have a plan in place. ¦Name¦Address¦Agreement¦Units¦Status¦BB Link¦ ¦Amber Condos¦5025 & 5033 Four Springs Ave¦YES¦446¦Off-Net¦[https://buildings.beanfield.com/buildings/view/15798]¦ ¦Crystal¦55 & 75 Eglinton Ave W¦NO¦463¦Off-Net¦[https://buildings.beanfield.com/buildings/view/4007]¦ ¦Pinnacle Uptown: Watergarden¦5044 Hurontario St¦NO¦316¦Off-Net¦[https://buildings.beanfield.com/buildings/view/16767]¦ ¦Perla Towers¦35-65 Watergarden Dr¦NO¦468¦Off-Net¦[https://buildings.beanfield.com/buildings/view/19420]¦ ¦Gemma Condos¦15 Watergarden Dr¦NO¦406¦Off-Net¦[https://buildings.beanfield.com/buildings/view/19421]¦ ¦Little Creek Condos¦5020-5040 Four Springs Ave & 110-160 Little Creek Rd¦NO¦57¦Off-Net¦[https://buildings.beanfield.com/buildings/view/19422]¦ Thank you! | [13 empty] | 0¦i4fp8v: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 3 | 100 | [5 empty] | https://buildings.beanfield.com/buildings/view/19422 |  |  | 3 - Normal |  | Mississauga
Montreal Construction | MTLCONST-10731 | 2300 - 2320 Tupper street, Montréal | Condo | New Condo |  | Unresolved | Marianne Yanni | Marianne Yanni | Marianne Yanni | 2025-01-13 16:16 |  | 2025-01-13 16:22 |  |  |  | 0 | 0 |  |  | MTLCONST-10732, MTLCONST-10733 |  | Ce projet est créé afin d'évaluer le possibilité de faire un déploiement résidentiel pour le complexe de condo au 2300 et 2320 rue Tupper, Montréal. *Property Manager:* Caroline : [estwest@bureauplus.net¦mailto:estwest@bureauplus.net] *+Addresses:+* 2300 Tupper Street Montreal, Qc, Canada H3H0B9 And 2320 Tupper Street Montreal, Qc, Canada H3H0B8 | [13 empty] | 0¦i5gbfz: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
Construction | CONST-38068 | 3515 Kariya Dr_Mississauga_Eve Condos | Condo | New Condo |  | Unresolved | Lorna Kurok | Lorna Kurok | Lorna Kurok | 2024-08-06 09:55 |  | 2024-12-17 10:28 |  |  |  | 0 | 0 |  |  | CONST-38069, CONST-38070, CONST-38071 | CONST-37795, CONST-28071 | Units_276 h2. {color:#0747a6}Site Contact:{color} *Kyle Moore, OLCM* Associate Property Manager *As an agent for and on behalf of:* ** *PSCC No. 853 - Eve Condo* ** 3515 Kariya Dr, Mississauga, ON L5B 0C1 *On-Site Management Office:* 905-232-2374 *Concierge Desk, 24/7 :* 905-232-2631 Email: [pm@evecondo.ca¦mailto:pm@evecondo.ca] Could you please create a new ticket for an OSP plan & site walk the Eve Condos at 3515 Kariya Dr? This condo has 276 units and was built in 2009. This likely connects to Eden Park at 3504 Hurontario St ([https://buildings.beanfield.com/buildings/view/3829]) and the Elle Condos at 3525 Kariya Dr ([https://buildings.beanfield.com/buildings/view/20411]) This location is part of a bigger build, please connect with Ticket: CONST-37795 - Mississauga Square One - Condo Backbone BB Link:[https://buildings.beanfield.com/buildings/view/20410] | [13 empty] | 0¦i54193: | [7 empty] | 9.2234e+18 | [19 empty] | Aug 6, 2024_Site walk request email received Aug 6, 2024. New Condo ticket started. Aug 12, 2024_ OSP plan completed Aug 12, 2024, requires site visit | [6 empty] | 3 - Normal | [24 empty] | 32 | 276 | [5 empty] | https://buildings.beanfield.com/buildings/view/20410 |  |  | 3 - Normal |  | Mississauga
Construction | CONST-38081 | 6 Rosebank Dr_Scarborough_Markham Place ll | Condo | New Condo |  | Unresolved | Lorna Kurok | Lorna Kurok | Lorna Kurok | 2024-08-07 15:32 |  | 2024-12-17 10:30 |  |  |  | 0 | 0 |  |  | CONST-38082, CONST-38083, CONST-38084 |  | Units - 203 (BBS states 203) h2. {color:#403294}*Site Contact:*{color} *Majid Attaran,* R.C.M., B.Sc., Condominium Manager ¦ GL. 0017770186 email: [majid@gpmmanagement.com¦mailto:majid@gpmmanagement.com] *GPM Property Management Inc.* 242 Applewood Crescent ¦ Unit 5 ¦ Concord ¦ Ontario ¦ L4K 4E5 # 905.669.0222 (Monday to Friday 9AM to 5PM) *24-Hour Emergency Line:* 905.669.0222 *+www.[gpmmanagement.com¦http://www.gpmmanagement.com/]+* Could you please create a new ticket for an OSP plan & site walk at Markham Place II at 6 RoseBank dr? This condo has 202 units and was built in 2011. This connects to Markham Place at 8 Rosebank Dr ([https://buildings.beanfield.com/buildings/view/20565]) and is likely our point of entry. This location is near-net and ideally we will have minimal OSP work required to enter the building. BB Link:[https://buildings.beanfield.com/buildings/view/20566] Site Contact: *Majid Attaran,* R.C.M., B.Sc., Condominium Manager ¦ GL. 0017770186 email: [majid@gpmmanagement.com¦mailto:majid@gpmmanagement.com] *GPM Property Management Inc.* 242 Applewood Crescent ¦ Unit 5 ¦ Concord ¦ Ontario ¦ L4K 4E5 # 905.669.0222 (Monday to Friday 9AM to 5PM) *24-Hour Emergency Line:* 905.669.0222 *+www.[gpmmanagement.com¦http://www.gpmmanagement.com/]+* | [13 empty] | 0¦i546q7: | [7 empty] | 9.2234e+18 | [19 empty] | Aug 7, 2024_ Jira Parent Ticket email received Aug 7, 2024. Requested by James Fox. | [6 empty] | 3 - Normal | [24 empty] | 16 | 203 | [5 empty] | https://buildings.beanfield.com/buildings/view/20566 |  |  | 3 - Normal |  | Scarborough
Construction | CONST-38354 | 887 Bay St_Toronto_Opera Place I | Condo | New Condo |  | Unresolved | Lorna Kurok | Lorna Kurok | Lorna Kurok | 2024-09-05 09:53 |  | 2024-12-17 10:35 |  |  |  | 0 | 0 |  |  | CONST-38355, CONST-38356, CONST-38357 |  | Requested by Oliver Sept 4, 2024 Units 161 {color:#0747a6}*Site Contact:*{color} Timothy (Security Desk) {color:#0747a6}*Regional Contact:*{color} *Endri Prifti, B.A., RCM, OLCM* Regional Area Manager AA Property Management & Associates 86 Audia Court Concord, ON L4K 3N4 Tel: 905-763-0677 Fax: 905-763-0577 Email: [e¦mailto:pscc767aapm@gmail.com] [ndri@aapm.ca¦mailto:ndri@aapm.ca] Can you please assist with queueing up an OSP plan & Site Walk for the Opera Place I condos at 887 Bay St? This location was constructed in 1999 and contains 161 residential units. BB Link: [https://buildings.beanfield.com/buildings/view/4153] Site Contact: Timothy (Security Desk) James can visit the site anytime. If there are any issues please contact Endri, *Endri Prifti, B.A., RCM, OLCM* Regional Area Manager AA Property Management & Associates 86 Audia Court Concord, ON L4K 3N4 Tel: 905-763-0677 Fax: 905-763-0577 Email: [e¦mailto:pscc767aapm@gmail.com] [ndri@aapm.ca¦mailto:ndri@aapm.ca] Note, this building is connected to [Opera Place II at 889 Bay St¦https://buildings.beanfield.com/buildings/view/3715] which includes an additional 154 units. We only have permission to visit Opera Place I, but ideally it can be confirmed how the network will be distributed to both towers. | [13 empty] | 0¦i56f53: | [7 empty] | 9.2234e+18 | [19 empty] | Sept 4, 2024_Ticket Requested, ticket created Sept 5, 2024 Sept 10, 2024_OSP Plan Completed | [6 empty] | 3 - Normal | [24 empty] | 16 | 161 | [5 empty] | https://buildings.beanfield.com/buildings/view/4153 |  |  | 3 - Normal |  | Toronto
Construction | CONST-5352 | 1 Bloor St W - One Bloor | Condo | New Condo |  | Unresolved | Russell Francey | Russell Francey | Russell Francey | 2017-01-11 08:16 |  | 2024-12-17 10:54 |  |  |  | 0 | 0 |  |  | CONST-5353, CONST-5354, CONST-5355, CONST-5563, CONST-5628 | [15 empty] | 0¦i0nebb: | [7 empty] | 9.2234e+18 | [19 empty] | Chris working on deal | [6 empty] | 3 - Normal | [24 empty] | 82 | 416 | [5 empty] | https://buildings.beanfield.com/buildings/view/4354 |  |  | 3 - Normal |  | Toronto Yonge & Bloor (incl. Yorkville)
Construction | CONST-32606 | 208 Niagara Street | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Denise King | 2023-01-05 14:14 |  | 2024-12-17 11:00 |  |  |  | 0 | 3 |  |  | CONST-32607, CONST-32608 | CONST-32565 | Requested by Oliver Davies: PM Info: Milka Matejic, RCM, OLCM PropertyWright Management Inc. MTCC 1302/MTCC 1346 208 Niagara St./800 King St. West Toronto, ON M6J 2L3/M5V 3M7 Monday, Wednesday, Thursday, Friday 8:00 am – 4:00 pm Tuesday 10:00 am – 6:00 pm Tel. (416) 362 – 9779 [Mtcc1346office@rogers.com¦mailto:Mtcc1346office@rogers.com] | [13 empty] | 0¦i3s6mn: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 126 | 3 | [5 empty] | https://buildings.beanfield.com/buildings/view/2030 |  |  | 3 - Normal |  | Toronto
Construction | CONST-29145 | 185 Bonis Ave, Toronto - Love Condos | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Jessica Markiewicz | 2022-07-11 07:53 |  | 2025-01-02 11:55 |  |  |  | 0 | 0 |  |  | CONST-29524, CONST-29525 | CONST-29146 | Requested by Jay Fernandes Hi, I’ve gone through the remaining Fibrestream condos we have agreements for in the GTA and have grouped them in a way that I think makes sense for site visits and builds. There will be another list coming of buildings that don’t really fall into groups. Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. There are some current backbone (Sheppard) or NPOP (960 Lawrence) projects that will need to be completed to connect these but this will get everything into the system. Thanks! *PM: Edward Kim* *t2453lovecondos@gmail.com* *647.346.0400* | Fiberstreamagreement, Kennedy&Sheppard | [12 empty] | 0¦i3h5q7: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2015 | [6 empty] | 3 - Normal | [24 empty] | 20 | 276 | [5 empty] | https://buildings.beanfield.com/buildings/view/15724 |  |  | 3 - Normal |  | Toronto
Construction | CONST-29146 | 195 Bonis Ave, Scarborough - JOY Condos | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Jessica Markiewicz | 2022-07-11 07:54 |  | 2025-01-02 12:01 |  |  |  | 0 | 0 |  |  | CONST-29147, CONST-29148 | CONST-29145 | Requested by Jay Fernandes Hi, I’ve gone through the remaining Fibrestream condos we have agreements for in the GTA and have grouped them in a way that I think makes sense for site visits and builds. There will be another list coming of buildings that don’t really fall into groups. Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. There are some current backbone (Sheppard) or NPOP (960 Lawrence) projects that will need to be completed to connect these but this will get everything into the system. Thanks! *PM: Phoebe Ye* *joycondos@crossbridgecs.com* *416.292.2793* | Fiberstreamagreement, Kennedy&Sheppard | [12 empty] | 0¦i3h5qf: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2018 | [6 empty] | 3 - Normal | [24 empty] | 21 | 282 | [5 empty] | https://buildings.beanfield.com/buildings/view/7206 |  |  | 3 - Normal |  | Scarborough
Construction | CONST-29222 | 2 Clairtrell Rd, North York - Bayview Mansions | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Jessica Markiewicz | 2022-07-11 15:45 |  | 2025-01-02 12:49 |  |  |  | 0 | 0 |  |  | CONST-29223, CONST-29224 |  | Requested by Jay Fernandes Hi, I’ve gone through the remaining Fibrestream condos we have agreements for in the GTA and have grouped them in a way that I think makes sense for site visits and builds. There will be another list coming of buildings that don’t really fall into groups. Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. There are some current backbone (Sheppard) or NPOP (960 Lawrence) projects that will need to be completed to connect these but this will get everything into the system. Thanks! *PM: Cheng Wang* *cheng@timesproperty.ca* | Fiberstreamagreement, Sheppard | [12 empty] | 0¦i3h8e7: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2003 | [6 empty] | 3 - Normal | [24 empty] | 2 | 137 | [5 empty] | https://buildings.beanfield.com/buildings/view/3474 |  |  | 3 - Normal |  | North York
Construction | CONST-29225 | 363/ 369/ 383 Sorauren Ave, Toronto - Robert Watson Lofts | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Jessica Markiewicz | 2022-07-11 15:48 |  | 2025-01-02 12:59 |  |  |  | 0 | 0 |  |  | CONST-29226, CONST-29227 | CONST-31034 | Requested by Jay Fernandes Hi, I’ve gone through the remaining Fibrestream condos we have agreements for in the GTA and have grouped them in a way that I think makes sense for site visits and builds. There will be another list coming of buildings that don’t really fall into groups. Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. There are some current backbone (Sheppard) or NPOP (960 Lawrence) projects that will need to be completed to connect these but this will get everything into the system. Thanks! *PM: Christy Plaitis* *christy@iconpm.ca* *416.236.7979* | Fiberstreamagreement, Sorauren | [12 empty] | 0¦i3h8fr: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2007 | [6 empty] | 3 - Normal | [24 empty] | 6 | 153 | [5 empty] | https://buildings.beanfield.com/buildings/view/6518 |  |  | 3 - Normal |  | Toronto
Construction | CONST-29271 | 7 Lorraine Dr, Toronto - Sonata | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Jessica Markiewicz | 2022-07-11 16:28 |  | 2025-01-02 13:14 |  |  |  | 0 | 0 |  |  | CONST-29272, CONST-29273 |  | Requested by Jay Fernandes Hi, I’ve gone through the remaining Fibrestream condos we have agreements for in the GTA and have grouped them in a way that I think makes sense for site visits and builds. There will be another list coming of buildings that don’t really fall into groups. Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. There are some current backbone (Sheppard) or NPOP (960 Lawrence) projects that will need to be completed to connect these but this will get everything into the system. Thanks! *PM: Fuada Zace* *fuada.zace@wilsonblanchard.com* *416.512.1497* | Fiberstreamagreement, Yonge&Finch | [12 empty] | 0¦i3h92v: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2003 | [6 empty] | 3 - Normal | [24 empty] | 26 | 303 | [5 empty] | https://buildings.beanfield.com/buildings/view/2634 |  |  | 3 - Normal |  | Toronto
Construction | CONST-29228 | 383 Sorauren Ave, Toronto | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Jessica Markiewicz | 2022-07-11 15:50 |  | 2025-01-02 13:07 |  |  |  | 0 | 0 |  |  | CONST-29229, CONST-29230 |  | Requested by Jay Fernandes Hi, I’ve gone through the remaining Fibrestream condos we have agreements for in the GTA and have grouped them in a way that I think makes sense for site visits and builds. There will be another list coming of buildings that don’t really fall into groups. Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. There are some current backbone (Sheppard) or NPOP (960 Lawrence) projects that will need to be completed to connect these but this will get everything into the system. Thanks! *PM: Christy Plaitis* *christy@iconpm.ca* *416.236.7979* | Fiberstreamagreement, Sorauren | [12 empty] | 0¦i3h8hr: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2016 | [6 empty] | 3 - Normal | [24 empty] | 9 | 142 | [5 empty] | https://buildings.beanfield.com/buildings/view/5208 |  |  | 3 - Normal |  | Toronto
Construction | CONST-36044 | 330 Richmond St W, Toronto (BULK) | Condo | New Condo |  | Unresolved | James Mowers | Lorna Kurok | Olawale Olaniyan [X] | 2023-12-19 11:21 |  | 2025-01-02 13:26 |  |  |  | 0 | 0 |  |  | CONST-36045, CONST-36046 |  | Requested by Oliver Davies, The board at 330 Richmond St W has agreed to a site walk. This building has a bulk-agreement with Bell that will be expiring next year, they are now exploring new options. There are 340 units at this location. *Site Contact:* Hui-Hsien Wei, LL Site Administrator TSCC 2835 330 Richmond St. W., Ontario, M5V 0M4 Phone: 416 593 6558 Email: [Hui-Hsien.Wei@crossbridgecs.com¦mailto:Hui-Hsien.%20wei@crossbridgecs.com] Thanks! | BulkDeal | [12 empty] | 0¦i4in6v: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2019 | [6 empty] | 3 - Normal | [24 empty] | 27 | 340 | [5 empty] | https://buildings.beanfield.com/buildings/view/12826 |  |  | 3 - Normal |  | Toronto
Construction | CONST-38027 | 349 Rathburn Rd W_Mississauga_Grand Mirage | Condo | New Condo |  | Unresolved | Lorna Kurok | Lorna Kurok | Lorna Kurok | 2024-07-31 08:09 |  | 2025-01-02 13:28 |  |  |  | 0 | 0 |  |  | CONST-38028, CONST-38029 | CONST-37795 | h3. Units for 349 Rathburn Rd W only_344 Could you please create a new ticket for an OSP plan & site walk for the Grande Mirage at 349 Rathburn Rd W? This condo has 344 units and was built in 2021. Their next board meeting is *{color:#de350b}+Aug 23rd.+{color}* Could we have the site walk completed before then? I'd like to have some additional information for Grisilda to bring to the board. This likely connects to Mirage at 339 Rathburn Rd W ([https://buildings.beanfield.com/buildings/view/20424]) and Universal at 335 Rathburn Rd W ([https://buildings.beanfield.com/buildings/view/20423]) This location is part of a biggert build, please connect with Ticket: CONST-37795 - Mississauga Square One - Condo Backbone BB Link:[https://buildings.beanfield.com/buildings/view/20171] h2. {color:#403294}*Site Contact:*{color} *Grisilda Hajrullahi OLCM* Condominium Manager¦ Wilson Blanchard Management Grande Mirage Condominiums 349 Rathburn Road West Mississauga, ON, L5B 0G9 Phone: 905.232.3494 Fax: 905.232.3490 | [13 empty] | 0¦i53hkv: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2020 July 31, 2024_Next Board Meeting Aug 23rd, requesting site walk be completed prior to this date. | [6 empty] | 3 - Normal | [24 empty] | 22 | 344 | [5 empty] | https://buildings.beanfield.com/buildings/view/20171 |  |  | 3 - Normal |  | Mississauga
Construction | CONST-29396 | 1346 Danforth Rd, Toronto - Danforth Village Estates | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Jessica Markiewicz | 2022-07-13 11:58 |  | 2025-01-02 14:07 |  |  |  | 0 | 0 |  |  | CONST-29397, CONST-29398 |  | Requested by Jay Fernandes Hi, These are the Fibrestream condos we have agreements for that don’t seem to fit into any groups (although I maybe wrong). Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. ¦Group¦Building Name¦Address¦suites¦ ¦Independent¦Eleven Superior¦11 Superior AVE Etobicoke ON M8V 0A7¦130¦ ¦Independent¦The James Club¦1135 Royal York RD Toronto ON M9A 4A7¦209¦ ¦Independent¦Independence Way¦115 George Appleton WAY North York ON M3M 2E9¦244¦ ¦Independent¦Danforth Village Estates¦1346 Danforth RD Toronto ON M4J1M9¦249¦ ¦Independent¦beBloor¦1369 Bloor ST Toronto ON M6P 4J3¦238¦ ¦Independent¦Ion Condos¦15 James Finlay WAY Toronto ON M3M 0B3¦200¦ ¦Independent¦Paradice at the Oasis¦1720 Eglinton AVE Toronto ON M4A2X9¦190¦ ¦Independent¦Havenon the Bluffs¦20 East Haven DR Toronto ON M1N1M2¦259¦ ¦Independent¦Kilgour Estate II¦21 Burkebrook PL Toronto ON M4G4K8¦228¦ ¦Independent¦Canvas Condos¦2301 Danforth AVE Toronto ON M4C 1L5¦156¦ ¦Independent¦3018 Yonge Condos¦3018 Yonge ST Toronto ON M4N 0A5¦188¦ ¦Independent¦Cranbrooke Village¦35 Saranac BLVD Toronto ON M6A 2G4¦341¦ ¦Independent¦39 Brant St¦39 Brant ST Toronto ON M5V0M8¦236¦ ¦Independent¦The Wave¦4 Elsinore PATH Toronto ON M8V 4G7¦185¦ ¦Independent¦Clock Tower Lofts¦700 King ST Toronto ON M5V 2Y6¦216¦ ¦Independent¦The Boot¦75 Dalhousie ST Toronto ON M5B 2R9¦153¦ ¦Independent¦B.Street Condos¦783 Bathurst ST Toronto ON M6G 1K1¦ ¦ ¦Independent¦85 Bloor St¦85 Bloor ST Toronto ON M4W3G9¦252¦ | Fiberstreamagreement | [12 empty] | 0¦i3hfhr: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2018 | [6 empty] | 3 - Normal | [24 empty] | 16 | 249 | [5 empty] | https://buildings.beanfield.com/buildings/view/15645 |  |  | 3 - Normal |  | Scarborough
Construction | CONST-30169 | 38 Fontenay Crt, Toronto | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Jessica Markiewicz | 2022-08-24 15:02 |  | 2025-01-02 14:16 |  |  |  | 0 | 2 |  |  | CONST-30170, CONST-30171 |  | Requested by Oliver Davies. Can you kindly queue up a site walk for 38 Fontenay Crt? BB Link: [https://buildings.beanfield.com/buildings/view/3907] PM: Michelle Tietz Property Manager Brilliant Property Management Inc. [www.brilliantproperty.ca¦http://www.brilliantproperty.ca/] [michelle@brilliantproperty.ca¦mailto:michelle@brilliantproperty.ca] FYI James, [https://buildings.beanfield.com/buildings/view/6245] 25/35 Fontenay Crt is directly across the street and is a larger location with 289 units. We have interest in bringing these towers online as well. | [13 empty] | 0¦i3k4rr: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2005 October 28th - Site Visit requested. | [6 empty] | 3 - Normal | [24 empty] | 17 | 153 | [5 empty] | https://buildings.beanfield.com/buildings/view/3907 |  |  | 3 - Normal |  | Etobicoke
Construction | CONST-8493 | Pier 27 Tower - 15 Queens Quay E | Condo | New Condo |  | Unresolved | Harvey Tran | Harvey Tran | Russell Francey | 2018-08-08 10:30 |  | 2025-01-02 15:07 |  |  |  | 0 | 3 |  |  | CONST-8494, CONST-8495 |  | Bulk deal with Rogers. | [13 empty] | 0¦i18he7: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2020 Agreement signed but there are legal roadblocks preventing us from completing the site visit. July 26, 2023-they signed a bulk agreement with Bell. | [6 empty] | 3 - Normal | [24 empty] | 35 | 400 | [5 empty] | https://buildings.beanfield.com/buildings/view/8055 |  |  | 3 - Normal |  | Toronto. Central Waterfront
Construction | CONST-28528 | 33 Empress Ave, North York | Condo | New Condo |  | Unresolved | Harvey Tran | Harvey Tran | Harvey Tran | 2022-05-20 11:25 |  | 2025-01-02 15:10 |  |  |  | 0 | 0 |  |  | CONST-28529, CONST-28530 |  | *PM Info:* *Yana Mendelevich, OLCM* Property Manager 33 Empress Avenue Toronto, ON M2N 6Y7 *Tel: 416-512-1229 x22*** *Fax: 416-512-1231*** E-mail: [pm@RoyalPinnacle.ca¦mailto:pm@RoyalPinnacle.ca] | [13 empty] | 0¦i3e1i7: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed 2000 | [6 empty] | 3 - Normal | [24 empty] | 32 | 320 | [5 empty] | https://buildings.beanfield.com/buildings/view/5757 |  |  | 3 - Normal |  | North York
Construction | CONST-26499 | 21 Nassau St Toronto - Kensington Market Lofts | Condo | New Condo |  | Unresolved | Harvey Tran | Harvey Tran | Harvey Tran | 2022-01-25 09:26 |  | 2025-01-02 15:22 |  |  |  | 0 | 1 |  |  | CONST-26500, CONST-26501 | CONST-26496 | Requested from Katie Hodgson for a site walk for 160 Baldwin St & 21 Nassau St May I please request a site walk for 160 Baldwin St & 21 Nassau St *PM Info:* Jermaine Scarlett [kml@360cm.ca¦mailto:kml@360cm.ca] [https://buildings.beanfield.com/buildings/view/4530] | [13 empty] | 0¦i35o53: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2000 | [6 empty] | 3 - Normal | [24 empty] | 7 | 145 | [5 empty] | https://buildings.beanfield.com/buildings/view/5814 |  |  | 3 - Normal |  | Toronto
Construction | CONST-38392 | 109 Front St E_Toronto_New Times Square I & II | Condo | New Condo |  | Unresolved | Lorna Kurok | Lorna Kurok | Lorna Kurok | 2024-09-10 11:39 |  | 2024-12-17 11:32 |  |  |  | 0 | 0 |  |  | CONST-38393, CONST-38394, CONST-38395 |  | Requested by Oliver_ Sep 9, 2024 Units_371 Floors_12 Building Built 1999 Likely to require a Prewire of the suites. h3. *{color:#0747a6}PM Info:{color}* h2. Doug Vallery, BA OLCM Condominium Manager ¦ ¦ Agents for and on behalf of New Time Square Condos - MTCC 1280 and MTCC 1385 109 Front St E, Toronto, Ontario, M5A 4P7 Phone: 14165047298 Email: [managernewtimessq@bell.net¦mailto:managernewtimessq@bell.net] Could you kindly assist with creating new tickets for an OSP plan & Site walk for the New Times Square Condos at 109 Front St E? There are 371 units in this property. The building was constructed in 1999 and likely requires a pre-wire of the suites. BB Link: [https://buildings.beanfield.com/buildings/view/1609] PM Info: h2. Doug Vallery, BA OLCM Condominium Manager ¦ ¦ Agents for and on behalf of New Time Square Condos - MTCC 1280 and MTCC 1385 109 Front St E, Toronto, Ontario, M5A 4P7 Phone: 14165047298 Email: [managernewtimessq@bell.net¦mailto:managernewtimessq@bell.net] | [13 empty] | 0¦i56s6n: | [7 empty] | 9.2234e+18 | [19 empty] | Sept 9, 2024_Site Walk Email Request. Sept 10, 2024_OSP Plan Completed | [6 empty] | 3 - Normal | [24 empty] | 12 | 371 | [5 empty] | https://buildings.beanfield.com/buildings/view/1609 |  |  | 3 - Normal |  | Toronto
Construction | CONST-38252 | 1 & 5 Greystone Walk Dr., Toronto, Greystone Walk I | Condo | New Condo |  | Unresolved | Lorna Kurok | Lorna Kurok | Harvey Tran | 2024-08-27 09:01 |  | 2024-12-20 11:46 |  |  |  | 0 | 0 |  |  | CONST-38253, CONST-38254, CONST-38257, CONST-38637 |  | Requested by James Fox. Units 353 Constructed in 1990 Could you please create a new ticket for an OSP plan & site walk for Greystone Walk I at 5 Greystone Walk Dr? This condo has 353 residential units and was constructed in 1990 - ISW work will most likely be required. This location is near-net and ideally we will have minimal OSP work required to enter the building. It shares a complex with Greystone Walk II ([https://buildings.beanfield.com/buildings/view/13055]) and I Greystone Walk ([https://buildings.beanfield.com/buildings/view/5138]) BB Link: [https://buildings.beanfield.com/buildings/view/5531] Site Contact: Anthony Ho PM – OLCM MTCC884 5 Greystone Walk Drive, Toronto, ON Contact # 416-261-1069 x 23 My office phone is 437-423-9647 e:[mtcc884@mtcc884.ca¦mailto:mtcc884@mtcc884.ca] | [13 empty] | 0¦i55m3j: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 22 | 353 | [5 empty] | https://buildings.beanfield.com/buildings/view/5531 |  |  | 3 - Normal |  | Toronto
Construction | CONST-38238 | 55 Centre Ave, Toronto | Condo | New Condo |  | Unresolved | Harvey Tran | Lorna Kurok | Harvey Tran | 2024-08-26 09:53 |  | 2024-12-20 11:40 |  |  |  | 0 | 1 |  |  | CONST-38239, CONST-38240, CONST-38251 |  | Requested by James Fox. {color:#000000}Could you please create a new ticket for an OSP plan & site walk the Chestnut Park at {color}55 Centre Ave{color:#000000}? This condo has 138 units and was built in 1990. {color}ISW work will most likely be required.{color:#000000} {color}This location is near-net and ideally we will have minimal OSP work required to enter the building. {color:#000000} {color} {color:#000000}BB Link:{color}[https://buildings.beanfield.com/buildings/view/2825]{color:#000000} {color} +*{color:#000000}Site Contact:{color}*+ _Crystal Dion_ _Property Manager,_ _Brilliant Property Management Inc._ _on behalf of MTCC 868 - 55 Centre Ave. Toronto_ _[chestnutparkmanagement@gmail.com¦mailto:chestnutparkmanagement@gmail.com]_ _Office: 416-341-0005_ | PREWIRE | [12 empty] | 0¦i55idb: | [7 empty] | 9.2234e+18 | [19 empty] | Sept 4, 2024_Requires request for Vault access for Sept 11. Checking with Finance before inquiring the fee of $652. Prewire Sept 10, 2024 Waiting on Approval from Finance, to spend money to gain access to the Vault, to Finalize budget. | [6 empty] | 3 - Normal | [24 empty] | 22 | 137 | [5 empty] | https://buildings.beanfield.com/buildings/view/2825 |  |  | 3 - Normal |  | Toronto
Construction | CONST-38267 | 9 Northern Heights Dr, Richmond Hill, Empire Place on Yonge III | Condo | New Condo |  | Unresolved | Lorna Kurok | Lorna Kurok | Harvey Tran | 2024-08-28 10:49 |  | 2024-12-20 11:53 |  |  |  | 0 | 0 |  |  | CONST-38268, CONST-38269, CONST-38274 | CONST-37839 | Requested by James Fox. Could you please create a new ticket for an OSP plan & site walk for Empire Place on Yonge III at 9 Northern Heights Dr? This condo has 189 units and was built in 2003. This connects to Empire Place on Yonge at 29 Northern Heights Dr ([https://buildings.beanfield.com/buildings/view/20441]), and Empire Place on Yonge II at 19 Northern Heights Dr([https://buildings.beanfield.com/buildings/view/20434]) This location is a part of the Yonge Street Corridor/ Richmond Hill- Condo Backbone CONST-37839 and ideally we will have minimal OSP work required to enter the building. BB Link: [https://buildings.beanfield.com/buildings/view/20439] Site Contact: {*}Matt Kabiri{*}, BBA, R.C.M. , O.L.C.M. Condominium Manager ¦ ¦ Agents for and on behalf of Empire Place Three-YRSCC 996 9 Northern Heights Drive, Ontario, L4B4M5 Phone: 905-764-6609 Email: [empireplacethree@crossbridgecs.com¦mailto:empireplacethree@crossbridgecs.com%20or%20empireonyonge@rogers.com] | [13 empty] | 0¦i55qov: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 14 | 189 | [5 empty] | https://buildings.beanfield.com/buildings/view/20439 |  |  | 3 - Normal |  | Richmond Hill
Construction | CONST-38359 | 736 Bay St, Toronto - Conservatory Tower | Condo | New Condo |  | Unresolved | Lorna Kurok | Lorna Kurok | Lorna Kurok | 2024-09-05 10:49 |  | 2024-12-20 11:56 |  |  |  | 0 | 0 |  |  | CONST-38360, CONST-38361, CONST-38362 |  | Requested by James Fox Units 306 Built in 1995 ISW work will likely be required. This location is near- net and ideally we will have minimal OSP work required to enter the building. *Site Contact as of Sept 5, 2024* Sam Jasoor Property Manager *+MTCC No. 1085+* 736 Bay Street Toronto, ON M5G 2M4 Tel: 416-598-1916 Fax: 416-598-1954 Security Desk: 416-598-8138 Email: [propertymanagement@bellnet.ca¦mailto:propertymanagement@bellnet.ca] Could you please create a new ticket for an OSP plan & site walk for the Conservatory Tower at 736 Bay St? This condo has 306 units and was built in 1995. ISW work will most likely be required. This location is near-net and ideally we will have minimal OSP work required to enter the building. BB Link: [https://buildings.beanfield.com/buildings/view/3120] Site Contact: Sam Jasoor Property Manager *+MTCC No. 1085+* 736 Bay Street Toronto, ON M5G 2M4 Tel: 416-598-1916 Fax: 416-598-1954 Security Desk: 416-598-8138 Email: [propertymanagement@bellnet.ca¦mailto:propertymanagement@bellnet.ca] | [13 empty] | 0¦i56frz: | [7 empty] | 9.2234e+18 | [19 empty] | Sep 9, 2024_OSP Plan completed Sep 18, 2024_Budget Added | [6 empty] | 3 - Normal | [24 empty] | 30 | 306 | [5 empty] | https://buildings.beanfield.com/buildings/view/3120 |  |  | 3 - Normal |  | Toronto
Construction | CONST-38333 | 1291 Gerrard St E, Toronto (BULK) | Condo | New Condo |  | Unresolved | Lorna Kurok | Harvey Tran | Harvey Tran | 2024-09-04 11:27 |  | 2024-12-20 14:53 |  |  |  | 0 | 0 |  |  | CONST-38338, CONST-38339 | CONST-38332, CONST-38334, CONST-38335, CONST-38904 | Requested by Oliver. Units 289 Occupancy estimated for Early 2026 Developer: Sud Group Greenfield MDU project Type Rental Could you please create tickets for OSP plans to connect the following 4x greenfield MDU projects to Beanfield's network? Sud Group is the developer for each location. They are interested in signing bulk-agreements with Beanfield, timeline for their decision is in the next 2-3 months. _(noted on Sept 4, 2024, decision should be by december)_ Estimated occupancy dates for the 3x condos is mid-end 2026. The rental project is forecasted for first occupancy early 2026. With exception to 1291 Gerrard St E, all of the sites should be near-net to Beanfield's existing network today. Architectural plans for each location will be uploaded to the JIRA ticket. James, if you could please prepare a high-level budget for each location once the OSP plans are in place that will be helpful so that a proposal for the developer can be approved and submitted. 1684 - 1702 Queen St E (Condo) / 216 residential units [https://buildings.beanfield.com/buildings/view/13998] 1291 Gerrard St E (Rental) / 289 residential units [https://buildings.beanfield.com/buildings/view/20801] 1212 - 1238 Kingston Rd (Condo) / 216 residential units [https://buildings.beanfield.com/buildings/view/20802] 2010 Yonge St (Condo) / 264 residential units [https://buildings.beanfield.com/buildings/view/13999] | BulkDeal, Rental, Sud_Group | [12 empty] | 0¦i56baf: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 11 | 289 | [5 empty] | https://buildings.beanfield.com/buildings/view/20801 |  |  | 3 - Normal |  | Toronto
Construction | CONST-38904 | 26 Laing St, Toronto | Condo | New Condo |  | Unresolved | Unassigned | Lorna Kurok | Lorna Kurok | 2024-10-18 14:09 |  | 2024-12-20 14:59 |  |  |  | 0 | 0 |  |  | CONST-38905, CONST-38906, CONST-38907 | CONST-38332, CONST-38333, CONST-38334, CONST-38335 | Requested by Oliver. Units 166 Floors 14 Construction estimated to begin Late 2026 Developer: Sud Group Greenfield MDU project Type Rental Could you please create a new ticket for an OSP plan & high-level budget for bringing 26 Laing St On Net with Beanfield? This is a new greenfield rental development by Sud Group. Construction is not expected to begin until late 2026. BB Link: [https://buildings.beanfield.com/buildings/view/20957] The developer has submitted architectural drawings which I will upload to the ticket. This location can be linked to the other 4x buildings by Sud Group that James has prepared budgets for recently: A) 1684 - 1702 Queen St E (Condo) / 216 residential units. # CONST-38332 [https://buildings.beanfield.com/buildings/view/13998] B) 1291 Gerrard St E (Rental) / 289 residential units # CONST-38333 [https://buildings.beanfield.com/buildings/view/20801] C) 1212 - 1238 Kingston Rd (Condo) / 216 residential units # CONST-38334 [ https://buildings.beanfield.com/buildings/view/20802] D) 2010 Yonge St (Condo) / 264 residential units # CONST-38335 [https://buildings.beanfield.com/buildings/view/13999] Thanks! | BulkDeal, Rental, Sud_Group | [12 empty] | 0¦i59pcv: | [7 empty] | 9.2234e+18 | [19 empty] | Oct 17, 2024 - OSP Design & Budget Email Sent by Oliver Davies. | [6 empty] | 3 - Normal | [24 empty] | 14 | 166 | [5 empty] | https://buildings.beanfield.com/buildings/view/20957 |  |  | 3 - Normal |  | Toronto
Construction | CONST-38334 | 1212 - 1238 Kingston Rd, Toronto (BULK) | Condo | New Condo |  | Unresolved | Lorna Kurok | Harvey Tran | Harvey Tran | 2024-09-04 11:28 |  | 2024-12-20 15:01 |  |  |  | 0 | 0 |  |  | CONST-38340, CONST-38341 | CONST-38332, CONST-38333, CONST-38335, CONST-38904 | Requested by Oliver. Units 216 Occupancy estimated for mid to end of 2026 Developer: Sud Group Greenfield MDU project Type Condo Could you please create tickets for OSP plans to connect the following 4x greenfield MDU projects to Beanfield's network? Sud Group is the developer for each location. They are interested in signing bulk-agreements with Beanfield, timeline for their decision is in the next 2-3 months. Estimated occupancy dates for the 3x condos is mid-end 2026. The rental project is forecasted for first occupancy early 2026. With exception to 1291 Gerrard St E, all of the sites should be near-net to Beanfield's existing network today. Architectural plans for each location will be uploaded to the JIRA ticket. James, if you could please prepare a high-level budget for each location once the OSP plans are in place that will be helpful so that a proposal for the developer can be approved and submitted. 1684 - 1702 Queen St E (Condo) / 216 residential units [https://buildings.beanfield.com/buildings/view/13998] 1291 Gerrard St E (Rental) / 289 residential units [https://buildings.beanfield.com/buildings/view/20801] 1212 - 1238 Kingston Rd (Condo) / 216 residential units [https://buildings.beanfield.com/buildings/view/20802] 2010 Yonge St (Condo) / 264 residential units [https://buildings.beanfield.com/buildings/view/13999] | BulkDeal, Sud_Group | [12 empty] | 0¦i56bav: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 11 | 216 | [5 empty] | https://buildings.beanfield.com/buildings/view/20802 |  |  | 3 - Normal |  | Toronto
Construction | CONST-38335 | 2010 & 2050 Yonge St, Toronto (BULK) | Condo | New Condo |  | Unresolved | Lorna Kurok | Harvey Tran | Harvey Tran | 2024-09-04 11:30 |  | 2024-12-20 15:07 |  |  |  | 0 | 0 |  |  | CONST-38342, CONST-38343 | CONST-38332, CONST-38333, CONST-38334, CONST-38904 | Requested by Oliver. Actual Units per Architectual drawings are 264. Developer Sud Group Greenfield MDU project Occupancy estimated for mid to late 2026 Could you please create tickets for OSP plans to connect the following 4x greenfield MDU projects to Beanfield's network? Sud Group is the developer for each location. They are interested in signing bulk-agreements with Beanfield, timeline for their decision is in the next 2-3 months. (noted on Sept 4, 2024, estimating by December.) Estimated occupancy dates for the 3x condos is mid-end 2026. The rental project is forecasted for first occupancy early 2026. With exception to 1291 Gerrard St E, all of the sites should be near-net to Beanfield's existing network today. Architectural plans for each location will be uploaded to the JIRA ticket. James, if you could please prepare a high-level budget for each location once the OSP plans are in place that will be helpful so that a proposal for the developer can be approved and submitted. 1684 - 1702 Queen St E (Condo) / 216 residential units [https://buildings.beanfield.com/buildings/view/13998] 1291 Gerrard St E (Rental) / 289 residential units [https://buildings.beanfield.com/buildings/view/20801] 1212 - 1238 Kingston Rd (Condo) / 216 residential units [https://buildings.beanfield.com/buildings/view/20802] 2010 Yonge St (Condo) / 264 residential units [https://buildings.beanfield.com/buildings/view/13999] | BulkDeal, Sud_Group | [12 empty] | 0¦i56bbr: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 14 | 264 | [5 empty] | https://buildings.beanfield.com/buildings/view/13999 |  |  | 3 - Normal |  | Toronto
Construction | CONST-29213 | 55 Ann O'Reilly Rd, North York - Alto & Parkside at Atria | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Jessica Markiewicz | 2022-07-11 15:33 |  | 2024-12-24 10:37 |  |  |  | 0 | 0 |  |  | CONST-29214, CONST-29215 |  | Constructed 2017 Requested by Jay Fernandes Hi, I’ve gone through the remaining Fibrestream condos we have agreements for in the GTA and have grouped them in a way that I think makes sense for site visits and builds. There will be another list coming of buildings that don’t really fall into groups. Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. There are some current backbone (Sheppard) or NPOP (960 Lawrence) projects that will need to be completed to connect these but this will get everything into the system. Thanks! *PM: Grace Lee* *atria.pm@delcondo.com* *647.343.7560* | Fiberstreamagreement, Sheppard | [12 empty] | 0¦i3h893: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 44 | 578 | [5 empty] | https://buildings.beanfield.com/buildings/view/15811 |  |  | 3 - Normal |  | North York
Construction | CONST-28793 | 5025 & 5033 Four Springs Ave, Mississauga - Amber Condos | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Harvey Tran | 2022-06-14 12:58 |  | 2024-12-24 11:07 |  |  |  | 0 | 0 |  |  | CONST-28806, CONST-28807 | CONST-35712, CONST-35716, CONST-35717, CONST-35718, CONST-35719, CONST-35720 | Constructed in 2018 | Fiberstreamagreement | [12 empty] | 0¦i3flsv: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 26 | 446 | [5 empty] | https://buildings.beanfield.com/buildings/view/15798 |  |  | 3 - Normal |  | Mississauga
Construction | CONST-38655 | 3311 Kingston Rd, Scarborough (BULK) | Condo | New Condo |  | Unresolved | Lorna Kurok | Lorna Kurok | Lorna Kurok | 2024-10-01 13:45 |  | 2024-12-24 11:30 |  |  |  | 0 | 0 |  |  | CONST-38656, CONST-38657, CONST-38658 |  | Requested by James Fox__Priority {color:#de350b}**{*}CURRENT BULK DEALS EXPIRES JUNE 2025{*}**{color} +*BULK OPPORTUNITY WITH QUICK TIMELINE*+ Units 150 Floors 14 Built in 1991 Likely to require ISW work. Possibly minimal OSP work required to enter the building Location is Near-Net *site contact:* *Michael Luu* Condominium Manager Pro-House Management Ltd. MTCC 970 – Kingston Heights 3311 Kingston Road Scarborough, ON M1M 1R1 Phone: 416.264.3780 ¦[mluu@pro-house.ca¦mailto:mluu@pro-house.ca]¦ Could you please create a new ticket for an OSP plan & site walk for Kingston Heights at 3311 Kingston Rd, Scarborough? This condo has 150 residential units and was constructed in 1991 - ISW work will most likely be required. *This is a bulk opportunity with a quick timeline. Please make this a priority.* This location is near-net and ideally we will have minimal OSP work required to enter the building. BB Link: [https://buildings.beanfield.com/buildings/view/16017] *site contact:* *Michael Luu* Condominium Manager Pro-House Management Ltd. MTCC 970 – Kingston Heights 3311 Kingston Road Scarborough, ON M1M 1R1 Phone: 416.264.3780 | BulkDeal | [12 empty] | 0¦i58dsn: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 14 | 150 | [5 empty] | https://buildings.beanfield.com/buildings/view/16017 |  |  | 3 - Normal |  | Scarborough
Construction | CONST-32680 | 2910 Hwy 7 - Expo City II | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Denise King | 2023-01-12 12:10 | 2025-03-04 10:10 | 2024-12-24 15:00 |  |  |  | 0 | 2 |  |  | CONST-32681, CONST-32682 | CONST-37926, CONST-32717, CONST-35871, CONST-32677 | Requested by Oliver Davies: Constructed in 2017 *NEW PM Info:* Erlisa Shkreli [expocityIandII@crossbridgecs.com.¦mailto:expocityIandII@crossbridgecs.com.] PM Info Jamie-Leigh Mcarthur [jamie-leigh.mcarthur@crossbridgecs.com¦mailto:jamie-leigh.mcarthur@crossbridgecs.com] Both of the Expo City towers are active on third-party circuit via FibreStream. | FSactive, Fiberstreamagreement | [12 empty] | 0¦i3t01j: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 351 | 36 | [5 empty] | https://buildings.beanfield.com/buildings/view/6663 |  |  | 3 - Normal |  | Concord
Construction | CONST-32677 | 2900 Hwy 7 - Expo City I | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Denise King | 2023-01-12 12:03 | 2025-03-04 18:48 | 2024-12-24 15:12 |  |  |  | 0 | 0 |  |  | CONST-32678, CONST-32679 | CONST-37926, CONST-32717, CONST-35871, CONST-32680 | Requested by Oliver Davies: Constructed in 2017 *NEW PM Info:* Erlisa Shkreli [expocityIandII@crossbridgecs.com.¦mailto:expocityIandII@crossbridgecs.com.] PM Info Jamie-Leigh Mcarthur [jamie-leigh.mcarthur@crossbridgecs.com¦mailto:jamie-leigh.mcarthur@crossbridgecs.com] Both of the Expo City towers are active on third-party circuit via FibreStream. | FSactive, Fiberstreamagreement | [12 empty] | 0¦i3szzz: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 353 | 36 | [5 empty] | https://buildings.beanfield.com/buildings/view/7069 |  |  | 3 - Normal |  | Concord
Construction | CONST-38005 | 25 Times Avenue_Thornhill_Liberty Tower | Condo | New Condo |  | Unresolved | James Mowers | Lorna Kurok | Lorna Kurok | 2024-07-26 07:40 |  | 2024-12-24 15:22 |  |  |  | 0 | 0 |  |  | CONST-38006, CONST-38007 | CONST-36326 | {color:#000000}Units: 131{color} {color:#000000}Built:2003{color} {color:#000000}*Site Contact:* {color} {*}Melissa Perry{*}, BA, OLCM Condominium Manager ¦ ¦ Crossbridge Condominium Services Ltd. As Agents for and on behalf of Y.R.S.C.C. #979 Liberty Tower I Telephone: (905) 763-5770 25 Times Avenue, Thornhill, Ontario L3T 7X5 Email: [libertytower@crossbridgecs.com¦mailto:ttachdjian@crossbridgecs.com] {color:#000000}Could you please create a new ticket for an OSP plan & site walk for Liberty Tower I at 25 Times Ave? This condo has 131 units and was built in 2003. {color} {color:#000000}This likely connects to Liberty Tower II at 51 Times Ave ({color}[https://buildings.beanfield.com/buildings/view/19800]) {color:#000000} This location will be near-net once the Microsoft build is completed and ideally we will have minimal OSP work required to enter the building. Please connect the ticket to the overall backbone build ticket ({color}CONST-36326){color:#000000} BB Link:{color} [https://buildings.beanfield.com/buildings/view/19801] *Site Contact:* {*}Melissa Perry{*}, BA, OLCM Condominium Manager{*}Site Contact:{*} {*}Melissa Perry{*}, BA, OLCM Condominium Manager ¦ ¦ Crossbridge Condominium Services Ltd. As Agents for and on behalf of Y.R.S.C.C. #979 Liberty Tower I Telephone: (905) 763-5770 25 Times Avenue, Thornhill, Ontario L3T 7X5 Email: [libertytower@crossbridgecs.com¦mailto:ttachdjian@crossbridgecs.com] Thanks, ¦ ¦ Crossbridge Condominium Services Ltd. As Agents for and on behalf of Y.R.S.C.C. #979 Liberty Tower I Telephone: (905) 763-5770 25 Times Avenue, Thornhill, Ontario L3T 7X5 Email: [libertytower@crossbridgecs.com¦mailto:ttachdjian@crossbridgecs.com] Thanks, | Microsoft | [12 empty] | 0¦i5354v: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [21 empty] | 2024-07-25 |  |  | 10 | 131 | [5 empty] | https://buildings.beanfield.com/buildings/view/19801 |  |  | 3 - Normal |  | Thornhill
Construction | CONST-35846 | 2201 Kingston Rd, Scarborough | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2023-11-27 08:36 |  | 2024-12-24 15:30 |  |  |  | 0 | 0 |  |  | CONST-35847, CONST-35848, CONST-38256 |  | Requested by Oliver Davies, Can you please set up a new OSP plan & site walk for the “Merge Condos” at 2201 Kingston Rd / 90 Glen Everest Rd? This is a newly registered condo with 182 units, not far from the [Haven on the Bluffs Condos at 2229 Kingston Rd / 22 East Haven¦https://buildings.beanfield.com/buildings/view/7485] (CONST-26374) Constructed in 2022 *+New PM info:+* *Ritika Sharma* Condominium Manager ¦ *DUKA Property Management Inc.* *As Agents for and on behalf of Merge Condos- T.S.C.C. No. 2992* 90 Glen Everest Road Office Tel: 647.827.2652 ¦ Concierge Tel: 647.209.4890 Toronto, ON M1N 0C3 Email: [merge.office@dukamanagement.com¦mailto:merge.office@dukamanagement.com] [www.dukamanagement.com¦http://www.dukamanagement.com/] +*Old PM Info:*+ *Muskan Khosla* Condominium Manager ¦ *DUKA Property Management Inc.* *As Agents for and on behalf of Merge Condos- T.S.C.C. No. 2992* 90 Glen Everest Road Office Tel: 647.827.2652 ¦ Concierge Tel: 416.265.8931 Toronto, ON M1N 0C3 Email: {color:#0000ff}[merge.office@dukamanagement.com¦mailto:merge.office@dukamanagement.com]{color} Thanks! | [13 empty] | 0¦i4gw2n: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 12 | 182 | [5 empty] | https://buildings.beanfield.com/buildings/view/18700 |  |  | 3 - Normal |  | Scarborough
Construction | CONST-35958 | 18 Parkview Ave, Toronto - The Majestic II | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2023-12-11 08:11 |  | 2024-12-24 15:46 |  |  |  | 0 | 0 |  |  | CONST-35959, CONST-35960 | CONST-29289 | Requested by Oliver Davies, Could you queue up an OSP plan and site walk for 18 Parkview Ave? The Majestic II condos have 285 units. It is the sister building to Majestic I at 28 Empress Ave (CONST-29291) where we will likely have a FBIP soon. They do not share a parking level from what I can tell. Next door to 18 Parkview is 256 Doris Ave “The Imperial I” and 260 Doris Ave “The Imperial II”, both of these will require a pre-wire and are not being looked at for now. New PM Info: Mohammad Mardani Email: Mardani@manorcrest.com Telephone: 416-512-6142 Ext. 440 | [13 empty] | 0¦i4hzen: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed 2004 | [6 empty] | 3 - Normal | [24 empty] | 24 | 285 | [5 empty] | https://buildings.beanfield.com/buildings/view/2588 |  |  | 3 - Normal |  | Toronto
Construction | CONST-29151 | 9015 Leslie St, Richmond Hill - Grand Parkway Residences | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Jessica Markiewicz | 2022-07-11 09:55 | 2025-03-04 17:54 | 2024-12-24 15:54 |  |  |  | 0 | 0 |  |  | CONST-29152, CONST-29153 | CONST-29156 | Requested by Jay Fernandes Hi, I’ve gone through the remaining Fibrestream condos we have agreements for in the GTA and have grouped them in a way that I think makes sense for site visits and builds. There will be another list coming of buildings that don’t really fall into groups. Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. There are some current backbone (Sheppard) or NPOP (960 Lawrence) projects that will need to be completed to connect these but this will get everything into the system. Thanks! *PM: Wendy Kwok* *grandparkway972pm@outlook.com* *905.764.8610* | FSactive, Fiberstreamagreement, Leslie&7 | [12 empty] | 0¦i3h64n: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed 2002 | [6 empty] | 3 - Normal | [24 empty] | 213 | 13 | [5 empty] | https://buildings.beanfield.com/buildings/view/15442 |  |  | 3 - Normal |  | Richmond Hill
Construction | CONST-29156 | 9017 Leslie St, Toronto - Grand Parkway - Phase II | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Jessica Markiewicz | 2022-07-11 10:29 | 2025-03-04 17:54 | 2024-12-24 15:54 |  |  |  | 0 | 0 |  |  | CONST-29157, CONST-29159 | CONST-29151 | Requested by Jay Fernandes Hi, I’ve gone through the remaining Fibrestream condos we have agreements for in the GTA and have grouped them in a way that I think makes sense for site visits and builds. There will be another list coming of buildings that don’t really fall into groups. Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. There are some current backbone (Sheppard) or NPOP (960 Lawrence) projects that will need to be completed to connect these but this will get everything into the system. Thanks! *PM: Agnes Ching* *grandparkway.pm@delcondo.com* *905.763.0319* | FSactive, Fiberstreamagreement, Leslie&7 | [12 empty] | 0¦i3h69j: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed - 2003 | [6 empty] | 3 - Normal | [24 empty] | 13 | 220 | [5 empty] | https://buildings.beanfield.com/buildings/view/15644 |  |  | 3 - Normal |  | Richmond Hill
Construction | CONST-28720 | 8 Hillcrest Ave, Toronto | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Harvey Tran | 2022-06-08 09:39 |  | 2024-12-24 15:59 |  |  |  | 0 | 0 |  |  | CONST-28721, CONST-28722 |  | +*PM Info:*+ ¦Gloria Vlad, R.C.M.¦ ¦Property Manager¦ ¦Tel: 416-225-3770 ext 12¦ ¦[mtcc1362office@rogers.com¦mailto:mtcc1362office@rogers.com]¦ ¦ ¦ 8 Hillcrest Ave is active with FS on a 3P circuit. This is the sister tower to 33 Empress Ave who has recently requested our services in their building – they are connected via P1 and we should confirm if we have the option of connecting them on a shared circuit. Unfortunately, both towers have shared conduit w/ daisy chained suites. Cost per unit to wire the suites aside, we should determine the overall budget and planned route to expand into these towers. Please include Kris Sansom (CC’d) on this site walk as he had oversight on the original FS build at 8 HC. | FSactive, Fiberstreamagreement | [12 empty] | 0¦i3f9fr: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed - 2001 | [6 empty] | 3 - Normal | [24 empty] | 31 | 378 | [5 empty] | https://buildings.beanfield.com/buildings/view/15528 |  |  | 3 - Normal |  | North York
Construction | CONST-29120 | 160 Vanderhoof Ave, Toronto - Scenic on Eglinton III | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Jessica Markiewicz | 2022-07-11 07:20 |  | 2025-01-02 13:23 |  |  |  | 0 | 0 |  |  | CONST-29121, CONST-29122, CONST-39797, CONST-39798 | CONST-36204, CONST-36202 | Requested by Jay Fernandes Hi, I’ve gone through the remaining Fibrestream condos we have agreements for in the GTA and have grouped them in a way that I think makes sense for site visits and builds. There will be another list coming of buildings that don’t really fall into groups. Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. There are some current backbone (Sheppard) or NPOP (960 Lawrence) projects that will need to be completed to connect these but this will get everything into the system. Thanks! *PM: Shari Granade* *scenic3manager@dukamanagement.com* *416.546.5340* | DonMills&Eg, Fiberstreamagreement | [12 empty] | 0¦i3h5iv: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2017 | [6 empty] | 3 - Normal | [24 empty] | 18 | 316 | [5 empty] | https://buildings.beanfield.com/buildings/view/15615 |  |  | 3 - Normal |  | Toronto
Construction | CONST-39791 | 103 & 105 West Lodge Ave, Toronto, Hazelview Properties | Condo | New Condo |  | Unresolved | James Mowers | Lorna Kurok | Lorna Kurok | 2025-01-22 14:03 |  | 2025-01-27 11:13 |  |  |  | 0 | 1 |  |  | CONST-39792, CONST-39793 | CONST-37374, CONST-39788 | Can we please get the Jira tickets and site visits completed for the below residential buildings. These should be priced as bulk buildings. Can we also set the due date on the site visit at 5 business days. We will need time to review the construction quote and complete the business case ahead of the 10 day target mentioned below. I would also like to understand the most likely/best case construction timeline based on the scope Hey Brad and Team, We're going to move forward for a bulk internet quote (XGS) for the below 4 MDU. Can we please perform site visits and get true costing for all locations. We'd like to provide them a quote within the next two weeks if possible. Site contacts below. thx Mike ¦*Property*¦*Contact*¦ ¦123 Bellamy¦Vladimir Ciobanu - [vciobanu@hazelview.com¦mailto:vciobanu@hazelview.com]¦ ¦200 Dufferin¦Chrisitina Gialousakis - [cgialousakis@hazelview.com¦mailto:cgialousakis@hazelview.com]¦ ¦103 & 105 Westlodge¦Chrisitina Gialousakis - [cgialousakis@hazelview.com¦mailto:cgialousakis@hazelview.com]¦ | [13 empty] | 0¦i5h4iv: | [7 empty] | 9.2234e+18 | [19 empty] | Jan 22, 2025_High leve Bulk quote (As per Wikipedia the units are 720, we should confirm the units) site visit to be completed by January 29, 2025. Jan 23, 2025_ OSP Plan Notes - we need 16 fibers for these two condos. Closest agg point with capacity is Queen/Macdonell. Other option could be to head north through the railroad tracks, but it would be further. | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/5470 |  |  | 1 - Very High |  | Toronto
Construction | CONST-39788 | 123 Bellamy Rd N, Scarborough (BULK) | Condo | New Condo |  | Unresolved | James Mowers | Lorna Kurok | Lorna Kurok | 2025-01-22 13:29 |  | 2025-01-28 14:05 |  |  |  | 0 | 1 |  |  | CONST-39789, CONST-39790 | CONST-37374, CONST-39791 | Hey Brad and Team, We're going to move forward for a bulk internet quote (XGS) for the below 4 MDU. Can we please perform site visits and get true costing for all locations. We'd like to provide them a quote within the next two weeks if possible. Site contacts below. thx Mike ¦*Property*¦*Contact*¦ ¦123 Bellamy¦Vladimir Ciobanu - [vciobanu@hazelview.com¦mailto:vciobanu@hazelview.com]¦ ¦200 Dufferin¦Chrisitina Gialousakis - [cgialousakis@hazelview.com¦mailto:cgialousakis@hazelview.com]¦ ¦103 & 105 Westlodge¦Chrisitina Gialousakis - [cgialousakis@hazelview.com¦mailto:cgialousakis@hazelview.com]¦ | BulkDeal | [12 empty] | 0¦i5h4fb: | [7 empty] | 9.2234e+18 | [19 empty] | Jan 22, 2025 - Site visit is due in 5 business days | [6 empty] | 3 - Normal | [34 empty] | 1 - Very High |  | Scarborough
Construction | CONST-37374 | 200 Dufferin St, Toronto (BULK) | Condo | New Condo |  | Unresolved | James Mowers | Lorna Kurok | Harvey Tran | 2024-05-15 11:03 |  | 2025-01-28 14:08 |  |  |  | 0 | 1 |  |  | CONST-37375, CONST-37376 | CONST-35795, CONST-39788, CONST-39791 | This location will be _difficult_ due to its age (built in 1964) and we are looking at it as a case study for wiring this location, and similar old buildings in the GTA. BB Link: [https://buildings.beanfield.com/buildings/view/2561] Site Contact: Elsie Nuga [ENuga@hazelview.com¦mailto:ENuga@hazelview.com] | BulkDeal | [12 empty] | 0¦i4u907: | [7 empty] | 9.2234e+18 | [19 empty] | Jan 23, 2025_OSP Plan Note_ osp plan is still valid | [6 empty] | 3 - Normal | [24 empty] | 14 | 251 | [5 empty] | https://buildings.beanfield.com/buildings/view/2561 |  |  | 1 - Very High |  | Toronto
Construction | CONST-39856 | 1350 and 1360 York Mills Rd, North York | Condo | New Condo |  | Unresolved | Unassigned | Lorna Kurok | Lorna Kurok | 2025-01-28 12:21 |  | 2025-01-28 12:47 |  |  |  | 0 | 1 |  |  | CONST-39857, CONST-39858, CONST-39859 |  | Constructed in 1972 Units 374 +*Site Contact information as of January 28, 2025:*+ *Sonela Kola* Condominium Manager, RCM, OLCM YCC 50 1350 & 1360 York Mills Rd. North York, ON Email: [ycc50.manager@gmail.com¦mailto:ycc50.manager@gmail.com] Tel: 416-441-3355 Hi Lorna, Could you please create a new ticket for an OSP plan & site walk for 1350 York MIlls at 1350 and 1360 York Mills rd? These two condo buildings have 374 units and were built in 1972. BB Link: [https://buildings.beanfield.com/buildings/view/13297] Site Contact: *Sonela Kola* Condominium Manager, RCM, OLCM YCC 50 1350 & 1360 York Mills Rd. North York, ON Email: [ycc50.manager@gmail.com¦mailto:ycc50.manager@gmail.com] Tel: 416-441-3355 this is for Access and Marketing. Pm is unsure they have room in their conduits for another provider. | [13 empty] | 0¦i5hk3r: | [7 empty] | 9.2234e+18 | [19 empty] | Jan 28, 2025 Email received to create ticket for High level budget (Site Visit) and OSP plan. (Requires an ON site scope of the work, because the property manager is unsure if the building conduits have space for another provider.) | [6 empty] | 3 - Normal | [25 empty] | 374 | [5 empty] | https://buildings.beanfield.com/buildings/view/13297 |  |  | 3 - Normal |  | North York
Construction | CONST-26100 | 481 University Ave, Toronto | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Harvey Tran | 2021-12-06 10:03 |  | 2025-01-28 15:37 |  |  |  | 0 | 0 |  |  | CONST-26101, CONST-26102, CONST-38396 |  | Commercial Units_TBD pending the space each tenant will require. First Commercial Occupancy is Quarter 1 of 2027 Residential Units_743 First Residential Occupancy is in Quarter 1 of 2028 New Contact Info Below. *David Zeegen, C.E.T.* Director of Development ¦ _Development & Construction_ *Davpart Inc.* 4576 Yonge Street, Suite 700 Toronto, ON M2N 6N4 T: (416)-222-3010, Ext. 261 M: (416) 475-4478 E: [zeegend@davpart.com¦mailto:zeegend@davpart.com] PM Info: Marlon Lillo nillom@davpart.com 416-222-30310 ex. 260 BB Link: [https://buildings.beanfield.com/buildings/view/231#!contacts] | [13 empty] | 0¦i32w53: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 8 | 743 | [5 empty] | https://buildings.beanfield.com/buildings/view/231#!contacts |  |  | 3 - Normal |  | Toronto
Construction | CONST-36884 | 1141 Bloor St W, Toronto - Bloor & Dufferin (BULK) | Condo | New Condo |  | Unresolved | James Mowers | Lorna Kurok | Olawale Olaniyan [X] | 2024-03-22 09:09 |  | 2025-02-11 15:01 |  |  |  | 0 | 0 |  |  | CONST-36885, CONST-36886, CONST-36976 |  | Requested by Oliver Davies, Can you please create an OSP plan & site walk ticket for 1141 Bloor St W? This is a somewhat urgent request as we have an opportunity to submit a bulk-services bid for Hazelview’s 2x new rental towers being constructed at 1141 Bloor St W at the SE corner of Bloor & Dufferin. We would like have a high-level budget in place before building the proposal, which we have agreed to provide to the developer early next week. There are 844 units that comprise the 2x 37 & 34 story towers making up Block B, an additional rental tower (Block A) is being built that will share the same parking level for another 211 units as well. The foundation for this project is still being built so no on-site access is available to us yet. Occupancy is scheduled for June 2026. It was requested that Beanfield enter into this development off of Bloor St W, if possible. I suspect we would need to build from CDSM10238 and breakout from Pauline Ave & Bloor St W to create our lateral connection into the building from there. P1 electrical drawings are attached. Thanks! | BulkDeal | [12 empty] | 0¦i4p2mv: | [7 empty] | 9.2234e+18 | [19 empty] | Feb 10, 2025 - Agreement Note -This location is progressing well. If this will be a bulk agreement then we will need to mobilize sooner rather than later. Please provide us with an update. | [6 empty] | 3 - Normal | [24 empty] | 37 | 844 | [5 empty] | https://buildings.beanfield.com/buildings/view/20040 |  |  | 3 - Normal |  | Toronto
BC Construction | BCCONST-647 | 10428 Whalley Blvd, (Ascent), Surrey BC | Condo | New Condo |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2024-04-04 17:51 |  | 2025-02-19 14:52 |  |  | 2025-09-26 | 0 | 0 |  |  | BCCONST-652 | BCCONST-826, BCCONST-845 | 234 units 31 flrs DES Conduit Entrance ¦Satish Sharma [satish@mlhcan.ca¦mailto:satish@mlhcan.ca] Andrei Chutskoff [achutskoff@itc-group.com¦mailto:achutskoff@itc-group.com]¦ In Service Date Aug 1st 2024 | BudgetPending, DES | [12 empty] | 0¦i4q6zr: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 31 | 234 | [10 empty] | Surrey
BC Construction | BCCONST-642 | 10760 136A, 10767 Whalley Blvd, (Flamingo), Surrey BC | Condo | New Condo |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2024-04-04 14:49 |  | 2025-02-19 14:53 |  |  | 2025-12-26 | 0 | 0 |  |  | BCCONST-655 | BCCONST-643 | DES conduit in the building, in service date July 1st 2024 ¦Zikreia Nessari [ZNessari@itc-group.com¦mailto:ZNessari@itc-group.com] Franco Gimenez [franco@tiensher.com¦mailto:franco@tiensher.com]¦ 374 units 34 floors | DES | [12 empty] | 0¦i4q5nb: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 34 | 374 | [10 empty] | Surrey
BC Construction | BCCONST-510 | 13778 100 Avenue (Park George II), Surrey BC | Condo | New Condo |  | Unresolved | John Thomson | Yawn Paular | Yawn Paular | 2023-12-04 13:52 |  | 2025-02-19 15:07 |  |  | 2025-04-25 | 0 | 0 |  |  | BCCONST-667, BCCONST-668 | BCCONST-509 | Under Construction 337 units 38Flrs Entrance could be shared with Park George I Concord Pacific Colyvan Pacific Real Estate Management Services Ltd. info@colyvanpacific.com | BudgetPending | [12 empty] | 0¦i4hirj: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 38 | 337 | [10 empty] | Surrey
BC Construction | BCCONST-805 | 6031 Wilson Avenue (Solhouse), Burnaby BC | Condo | New Condo |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2024-09-19 16:04 |  | 2025-02-20 13:34 |  |  | 2028-01-03 | 0 | 0 |  |  | BCCONST-811, BCCONST-812, BCCONST-813, BCCONST-814 | BCCONST-353, BCCONST-352 | BOSA building 411 Units 52 flrs Occupancy Date: Q4 2028 200m required of backbone | BudgetPending | [12 empty] | 0¦i57hgv: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 52 | 411 | [10 empty] | Burnaby
Construction | CONST-40201 | 15 Greenview Ave, North York | Condo | New Condo |  | Unresolved | Unassigned | Lorna Kurok | Lorna Kurok | 2025-02-26 14:22 |  | 2025-02-26 14:22 |  |  |  | 0 | 0 |  |  |  |  | Good Morning The attached was approved at this mornings capex meeting. MDU Address: 15 and 25 Greenview Ave City: North York Building Name: Meridian I and Meridian II # of Units: 788 Units (439 and 349) # of Floors:32 and 27 Building Constructed Year: 2007 and 2008 PM Contact Name: Bal Pandeya (Del) PM Contact #: 416-637-6301 PM Email Address: [meridian.pm@DelCondo.com¦mailto:meridian.pm@DelCondo.com] Type of Contract (Fibre agreement or NUA & MA): A+M Building linked to other Buildings: Bulk Related: no -- ¦ ¦Luke Baxter¦ ¦ | [13 empty] | 0¦i5jrov: | [7 empty] | 9.2234e+18 | [19 empty] | Feb 26, 2025 - Capital Approval email received from Luke. for 15 and 25 Greenview Ave. We received the agreement it list 15 Greenview. | [6 empty] | 3 - Normal | [34 empty] | 3 - Normal
BC Construction | BCCONST-822 | 10460 Parkway, Surrey BC (Brightside Tower 1) | Condo | New Condo |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2024-10-21 11:25 |  | 2025-02-04 13:35 |  |  | 2025-10-31 | 0 | 0 |  |  | BCCONST-825, BCCONST-826 | BCCONST-845, BCCONST-646, BCCONST-823 | 418 Units 40 Flrs 1350m backbone required DES Conduit Entrance In Service Date: Dec 1st 2024 ¦Jill Wanklyn [jwanklyn@bosaproperties.com¦mailto:jwanklyn@bosaproperties.com] Mehrad Azimi [mazimi@axiombuilders.ca¦mailto:mazimi@axiombuilders.ca]¦ | BudgetPending, DES | [12 empty] | 0¦i59slj: | [7 empty] | 9.2234e+18 | [19 empty] | Jan 9 - Waiting for Mike to review budget to send for approval Jan 29 - Created backbone project for PM purposes | [6 empty] | 3 - Normal | [24 empty] | 40 | 418 | [10 empty] | Surrey
BC Construction | BCCONST-643 | 10749/10745 King George Blvd, 10750 135A St (The Grand), Surrey BC | Condo | New Condo |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2024-04-04 16:45 |  | 2025-02-04 13:37 |  |  | 2026-09-25 | 0 | 0 |  |  | BCCONST-656 | BCCONST-642 | July 1st in service date Manit Saiyadh - KCM [msaiyadh@kanin.ca¦mailto:msaiyadh@kanin.ca] DES Conduit entrance 341 units 46 flrs | DES | [12 empty] | 0¦i4q6t3: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 46 | 341 | [10 empty] | Surrey
BC Construction | BCCONST-646 | 10333 133 St, Melrose, Surrey BC | Condo | New Condo |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2024-04-04 17:39 |  | 2025-02-04 14:25 |  |  | 2025-11-28 | 0 | 0 |  |  | BCCONST-653 | BCCONST-845, BCCONST-822 | Moe Dhillon [moe@brasfield.ca¦mailto:moe@brasfield.ca] Jacqueline Huynh [jhuynh@mlemporio.ca¦mailto:jhuynh@mlemporio.ca] 223 units 26 flrs DES Entrance conduit In Service date need to be adjusted. Building was slated for Mar 1st 2025 | BudgetPending, DES | [12 empty] | 0¦i4q6yv: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 26 | 223 | [10 empty] | Surrey
Construction | CONST-37998 | 85 Oneida Crescent_Richmond Hill_YongeParc | Condo | New Condo |  | Unresolved | Lorna Kurok | Lorna Kurok | Lorna Kurok | 2024-07-24 10:42 |  | 2025-02-04 15:02 |  |  |  | 0 | 1 |  |  | CONST-37999, CONST-38000 | CONST-37839 | {color:#000000}Could you please create a new ticket for an OSP plan & site walk YongeParc2 at 85 Oneida Crescent? This condo has 232 units and was built in 2022. I will be presenting to this condo board on Aug20th. Could we have the site walk completed before then? I'd like to go over the scope of work with the board if possible. {color} {color:#000000}This likely connects to YongeParc at 75 Oneida Cres ([https://buildings.beanfield.com/buildings/view/20433]), ERA at Yonge Condos at 155 High Tech rd ([https://buildings.beanfield.com/buildings/view/20431]), and ERA2 at 95 Oneida Cres ([https://buildings.beanfield.com/buildings/view/20434]){color} {color:#000000} This location will be near-net once the Microsoft build is completed and ideally we will have minimal OSP work required to enter the building. BB Link:[https://buildings.beanfield.com/buildings/view/20427] {color} {color:#000000}Site Contact:{color} *Justin Nguyen* - OLCM-L Condominium Manager ¦ ¦ !https://ci3.googleusercontent.com/meips/ADKq_NbgHOuPR7VPKj6PVSGeR0Sb5NdzvbJMO9WdRI49kJPKo3I6FFd3QvfVlivHX7rEKlxTRpNssMWQoac00bWoIagWo2EmT5OoAcQW6e00iRHtQajSJHyDuKo=s0-d-e1-ft#https://crossbridge-email-signature-generator.netlify.app/logo.png! Agent for and or behalf of YRSCC 1488 - Yonge Parc E 85 Oneida Crescent, Richmond Hill, Ontario L4B 0H4 Mngt. Office: 905-597-1132 Concierge : 905-597-1146 Email: [YongeParcE@crossbridgecs.com¦mailto:YongeParcE@crossbridgecs.com] | Microsoft | [12 empty] | 0¦i52z1z: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 19 | 232 | [5 empty] | https://buildings.beanfield.com/buildings/view/20427 |  |  | 3 - Normal |  | Richmond Hill
BC Construction | BCCONST-823 | 13301 104 Ave, Surrey BC (Bristol Tower 1) | Condo | New Condo |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2024-10-21 11:26 |  | 2025-02-04 19:49 |  |  | 2025-10-31 | 0 | 0 |  |  | BCCONST-824 | BCCONST-845, BCCONST-822 | 440 units Up to 5 towers 2030 Q1 Occupancy Date 1750m required of backbone - to be done with Brightside Towers | BudgetPending | [12 empty] | 0¦i59slz: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [25 empty] | 440 | [10 empty] | Surrey
Construction | CONST-38919 | 10 Old York Mills Road, North York (BULK) | Condo | New Condo |  | Unresolved | Lorna Kurok | Lorna Kurok | Lorna Kurok | 2024-10-21 10:56 | 2025-03-04 17:54 | 2025-02-11 08:57 |  |  |  | 0 | 0 |  |  | CONST-38920, CONST-38921, CONST-38922 |  | Requested by james Fox {color:#de350b}*Priority for site visit*{color} Bulk Opportunity {color:#172b4d}Units 113{color} {color:#172b4d}Floors 9{color} {color:#172b4d}Constructed in 2001{color} {color:#172b4d}Location is near-net{color} {color:#172b4d}Expected minimal OSP work require to enter building{color} *{color:#000000}site contact as of Oct 21, 2024:{color}* *{color:#000000}Elise Deschamps, OLCM{color}* {color:#000000}Senior Condominium Manager/ MTCC 1401{color} {color:#000000} {color} {color:#000000}10 Old York Mills Road, Toronto, ON M2P 2G9{color} {color:#000000}Telephone: 416-560-5988{color} {color:#000000}E-mail: [pm@mtcc1401.ca¦mailto:pm@mtcc1401.ca]{color} {color:#000000}Could you please create a new ticket for an OSP plan & site walk for 10 Old York MIlls Road Condos at 10 Old York Mills Road, North York? This condo has 134 residential units and was constructed in 2001 *This is a bulk opportunity. Please make this a priority.* This location is near-net and ideally we will have minimal OSP work required to enter the building. BB Link:[https://buildings.beanfield.com/buildings/view/12004]{color} *{color:#000000} site contact:{color}* *{color:#000000}Elise Deschamps, OLCM{color}* {color:#000000}Senior Condominium Manager/ MTCC 1401{color} {color:#000000} {color} {color:#000000}10 Old York Mills Road, Toronto, ON M2P 2G9{color} {color:#000000}Telephone: 416-560-5988{color} {color:#000000}E-mail: [pm@mtcc1401.ca¦mailto:pm@mtcc1401.ca]{color} | BulkDeal, BulkOpportunity | [12 empty] | 0¦i59sfb: | [7 empty] | 9.2234e+18 | [19 empty] | Oct 21, 2024 Email Request for OSP plan and Site walk_James Fox | [6 empty] | 3 - Normal | [24 empty] | 9 | 113 | [5 empty] | https://buildings.beanfield.com/buildings/view/12004 |  |  | 3 - Normal |  | North York
Construction | CONST-39158 | 100 Leeward Glenway, Toronto (BULK) | Condo | New Condo |  | Unresolved | Lorna Kurok | Lorna Kurok | Lorna Kurok | 2024-11-14 08:44 |  | 2025-02-11 08:56 |  |  |  | 0 | 1 |  |  | CONST-39160, CONST-39161, CONST-39162 |  | Requested by Oliver Nov 13, 2024 Units: 440 Floors: 22 Year Built: 1974 Opportunity to bid on a Bulk-internet Agreement *PM Information as of Nov 14, 2024:* Marina [ ycc141manage@gmail.com¦mailto:ycc141manage@gmail.com] Hi Denise, We have an opportunity to bid on a bulk-internet agreement for the 440 units that makeup 100 Leeward Glenway. BB Link: [https://buildings.beanfield.com/buildings/view/4224] Could you please create a new JIRA ticket for a high-level OSP budget to bring Beanfield's network to this location? Once this cost is confirmed we can model our bulk proposal accordingly. Thanks! | BulkDeal, BulkOpportunity | [12 empty] | 0¦i5bsxr: | [7 empty] | 9.2234e+18 | [19 empty] | Nov 13, 2024- Jira ticket requested. | [6 empty] | 3 - Normal | [24 empty] | 22 | 440 | [5 empty] | https://buildings.beanfield.com/buildings/view/4224 |  |  | 3 - Normal |  | Toronto
BC Construction | BCCONST-833 | 13866 100 Avenue (Skyliving), Surrey BC | Condo | New Condo |  | Unresolved | John Thomson | Yawn Paular | Yawn Paular | 2024-12-10 14:00 |  | 2025-03-05 18:01 |  |  | 2026-12-26 | 0 | 0 |  |  | BCCONST-837 |  | Mar 2027 Construction Completion Date 375 units 32 floors Allure Ventures | BudgetPending | [12 empty] | 0¦i5e8h3: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [13 empty] | 2027-03-01 14:46 | [8 empty] | 680 |  | 32 | 375 | [10 empty] | Surrey | 20100 | 50000
BC Construction | BCCONST-874 | 13685 102 Ave (Georgetown), Surrey BC | Condo | New Condo |  | Unresolved | Josh Wignall | Yawn Paular | Yawn Paular | 2025-03-04 13:24 |  | 2025-03-04 16:26 |  |  | 2025-11-28 | 0 | 0 |  |  | BCCONST-877 | BCCONST-875 | 351 units 30 flrs Anthem Properties 8 phase building projects | BudgetPending | [12 empty] | 0¦i5kbnz: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 30 | 351 | [8 empty] | 3 - Normal |  | Surrey
BC Construction | BCCONST-875 | Whalley & Central Ave (Georgetown 2), Surrey BC | Condo | New Condo |  | Unresolved | Josh Wignall | Yawn Paular | Yawn Paular | 2025-03-04 13:26 |  | 2025-03-04 13:45 |  |  | 2025-11-28 | 0 | 0 |  |  | BCCONST-878 | BCCONST-874 | 355 units 31 Flrs Anthem Properties Occupancy Date: Late 2025 (assumption) | BudgetPending | [12 empty] | 0¦i5kbov: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [13 empty] | 2025-10-01 13:24 | [10 empty] | 31 | 355 | [8 empty] | 3 - Normal |  | Surrey
BC Construction | BCCONST-786 | 60 Williams & 3006-3020 Spring Street, Port Moody BC | Condo | New Condo |  | Unresolved | Josh Wignall | Yawn Paular | Yawn Paular | 2024-09-16 14:21 |  | 2025-03-04 13:52 |  |  | 2025-09-26 | 0 | 0 |  |  | BCCONST-787, BCCONST-788, BCCONST-789, BCCONST-790, BCCONST-791, BCCONST-792, BCCONST-793 |  | Moody Centre Station - Integrated Development, Port Moody - 60 Williams & 3006-3020 Spring Street (857 total units) two 39-storey purpose-built rental towers above a 2-storey commercial podium, adjacent to the Moody Center Transit Station. | BudgetPending | [12 empty] | 0¦i576pr: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 39 | 857 | [10 empty] | Port Moody
Construction | CONST-37687 | 10 York St, Toronto (BULK) | Condo | New Condo |  | Unresolved | Harvey Tran | Lorna Kurok | Harvey Tran | 2024-06-11 12:38 |  | 2025-03-04 08:46 |  |  |  | 0 | 0 |  |  | CONST-37688, CONST-37689 | CONST-9078 | Requested by Oliver. Constructed in 2019 The Ten York Condos include 725 residential units. They are locked into a bulk-contract with Rogers, but the community is unhappy, and the board is exploring their options for moving the bulk internet agreement to Beanfield. BB Link: [https://buildings.beanfield.com/buildings/view/6900] +*PM Info:*+ {color:#000000}Karolina Lesniowska, RCM, OLCM{color} {color:#000000}Condominium Manager{color} {color:#000000}TSCC 2708{color}{color:#000000}10 York Street {color}{color:#000000}Toronto, ON M5J 0E1{color}{color:#000000}Phone: 647-348-9521{color}{color:#000000}Fax: 416-551-0879{color}{color:#000000}E: [10york.pm@delcondo.com¦mailto:10york.pm@delcondo.com]{color} {color:#000000} {color} {color:#000000}We already have an old open ticket for this building: https://tickets.beanfield.com/browse/CONST-9078 James, PM has asked if you could visit the building this week. The board meets next week and would like to know what is involved for bringing Beanfield to the building.{color} | BulkDeal | [12 empty] | 0¦i4xmsf: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 65 | 725 | [5 empty] | https://buildings.beanfield.com/buildings/view/6900 |  |  | 3 - Normal
BC Construction | BCCONST-648 | 9677 King George Blvd (Belvedere), Surrey BC | Condo | New Condo |  | Unresolved | Josh Wignall | Yawn Paular | Yawn Paular | 2024-04-04 17:58 |  | 2025-03-03 18:03 |  |  | 2025-04-25 | 0 | 0 |  |  | BCCONST-657, BCCONST-844 |  | 275 units Manish Sharma [manish@squarenine.ca¦mailto:manish@squarenine.ca] In Service Date: June 1st 2024 DES Conduite Entrance | BudgetPending, DES | [12 empty] | 0¦i4q713: | [7 empty] | 9.2234e+18 | [19 empty] | Jan 23 - Provided budget for Mike/John to review | [6 empty] | 3 - Normal | [22 empty] | 500 |  |  | 275 | [10 empty] | Surrey
BC Construction | BCCONST-873 | 13359 Old Yale Road (Holland Townline), Surrey BC | Condo | New Condo |  | Unresolved | Josh Wignall | Yawn Paular | Yawn Paular | 2025-03-04 13:20 |  | 2025-03-04 13:46 |  |  | 2025-08-29 | 0 | 0 |  |  | BCCONST-881 | BCCONST-644 | 250 units 25 flrs Close to existing FOSC at TEL MH-1078 Likely tied to 13387 Old Yale (Townline 2) | BudgetPending | [12 empty] | 0¦i5kbmv: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 25 | 250 | [8 empty] | 3 - Normal |  | Surrey
Construction | CONST-35437 | 77 Lombard St, Toronto - Absolute Lofts | Condo | New Condo |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2023-10-05 08:36 |  | 2025-03-14 12:29 |  |  |  | 0 | 0 |  |  | CONST-35438, CONST-35439 | CONST-40343 | Requested by Oliver Davies, Could you kindly proceed with creating OSP & site walk tickets for 77 Lombard St? This is a small building with only 83 units, however the request came from the PM who I am also working with for another location, and we may have an efficient route into the building via BFMH-0319. PM Info: *Ana Stoneman, OLCM* Condominium Manager ¦ ICC Property Management Ltd. T: (905) 940-1234 Ext. 92 F: (905) 940-3881 E: {+}astoneman@{+}[iccpropertymanagement.com¦mailto:ngajic@iccpropertymanagement.com] ICC 24-hour Emergency Hotline: 416-346-0323 Thank you, | [13 empty] | 0¦i4d2m7: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2001 | [6 empty] | 3 - Normal | [24 empty] | 83 | 8 | [5 empty] | https://buildings.beanfield.com/buildings/view/3865 |  |  | 3 - Normal |  | Toronto
BC Construction | BCCONST-806 | 5977 Wilson Ave (CentralPark), Burnaby BC | Condo | New Condo |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2024-09-19 16:04 |  | 2025-03-18 14:25 |  |  | 2025-12-12 | 0 | 0 |  |  | BCCONST-807, BCCONST-808, BCCONST-809, BCCONST-810 | BCCONST-353, BCCONST-352 | 365 units BOSA project 200m backbone required Q2 of 2025 Occupancy Date {color:#222222}Mike Pover{color} {color:#222222}604-789-0518{color} {color:#222222}mpover@axiombuilders.ca{color} | BudgetPending | [12 empty] | 0¦i57hh3: | [7 empty] | 9.2234e+18 | [19 empty] | Site check scheduled on Jan 13 9:30 AM Look for NPOP space and do the riser audit Jan 30 - No space in MTR for a potential NPOP. Looking to see if we can inquire space in Solhouse early enough since occupancy date is not until 2028 Novus already splicing fibers during our site visit Occupancy date is set for April 2025 Diverse entrance path can be done but needs to let BOSA knows about civil plans early in the development Existing TELUS manholes also found by the poles on Wilson Ave Found other new buildings within the area: 6039 Mckay Ave = Onyx (261 units/34flrs) = Polygon 6075 Wilson Ave = Nuvo (354 units) = Anthem Properties 5985 Barker Ave = early excavation = Concord Pacific | [6 empty] | 3 - Normal | [25 empty] | 365 | [10 empty] | Burnaby
BC Construction | BCCONST-884 | 10581 140 St (Thrive/Domain/Dwell) | Condo | New Condo |  | Unresolved | Josh Wignall | Yawn Paular | Yawn Paular | 2025-03-11 12:39 |  | 2025-03-18 12:50 |  |  | 2025-10-31 | 0 | 0 |  |  | BCCONST-885, BCCONST-890, BCCONST-892 |  | [10581 140 St¦https://www.google.com/maps/search/10581+140+St?entry=gmail&source=g] (Thrive) [10603 140 St¦https://www.google.com/maps/search/10603+140+St?entry=gmail&source=g] (Domain) [13963 105 Blvd¦https://www.google.com/maps/search/13963+105+Blvd?entry=gmail&source=g] (Dwell) Surrey, BC V3T 0M7 Assumption is one entrance to the property PM Contact Name: Mahyar Attar *(FS Residential)* PM Contact #: 604.683.8900 PM Email Address: _[Mahyar.Attar@fsresidential.com¦mailto:Mahyar.Attar@fsresidential.com]_ | BudgetPending | [12 empty] | 0¦i5kugn: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 6 | 345 | [8 empty] | 3 - Normal |  | Surrey
Construction | CONST-39639 | 55 Bloor St E, Toronto, Signatures on Bloor | Condo | New Condo |  | Unresolved | James Mowers | Lorna Kurok | Lorna Kurok | 2025-01-10 12:35 |  | 2025-03-18 13:20 |  |  |  | 0 | 0 | _thumb_1124837.png |  | CONST-39640, CONST-39641, CONST-39642 |  | *NewBuilds_January 9, 2025_55 Bloor St E* This was approved at the December 18th Capex meeting. For record keeping I am sharing again with agreement. newbuilds - please see agreement attached and budget document in CA form. MDU Address:55 Bloor St E City: Toronto Building Name: Signatures on Bloor # of Units: 147 # of Floors:19 Building Constructed Year: 2000 PM Contact Name: *Elinor Bahiti* PM Contact #: 905-275-9575 ext 323 PM Email Address: [elinor.bahiti@themeritusgroup.ca¦mailto:elinor.bahiti@themeritusgroup.ca] Type of Contract (Fibre agreement or NUA & MA): A+M Building linked to other Buildings: Bulk Related: no | [13 empty] | 0¦i5g607: | [7 empty] | 9.2234e+18 | [19 empty] | January 9, 2025_55 Bloor St E, CA Budget # FTTB-00111, Dated Dec 12, 2024, Consolidated Total ($45,071.19)_New Ticket_Pending Site Visit and field Budget March 6, 2025 - Removed from On Net schedule, this is a Daisy chained building requires approval of increase budget. Will need $400 per suite plus ISP / OSP plan. Pending approval. | [6 empty] | 3 - Normal | [21 empty] | 2025-01-09 |  |  | 19 | 134 | [5 empty] | https://buildings.beanfield.com/buildings/view/4355 |  |  | 3 - Normal |  | Toronto
BC Construction | BCCONST-480 | 13693 George Jct (The Line), Surrey BC | Condo | New Condo |  | Unresolved | Josh Wignall | Yawn Paular | Yawn Paular | 2023-11-16 17:10 |  | 2025-03-20 16:39 |  |  | 2025-12-26 | 0 | 0 |  |  | BCCONST-687, BCCONST-688, BCCONST-830 | BCCONST-897 | 439 Units 34 flrs Rental Properties Warrington Residential [rentals@warringtonresidential.com¦mailto:rentals@warringtonresidential.com] 604-602-1187 | BudgetPending | [12 empty] | 0¦i4g8nj: | [7 empty] | 9.2234e+18 | [19 empty] | Jan 9 - Waiting for BAA, Budget sent for approval Feb19 - Verbal interest received in Dec. To follow up | [6 empty] | 3 - Normal | [24 empty] | 34 | 439 | Backbone | [9 empty] | Surrey | 14000 | 32800
Montreal Construction | MTLCONST-10013 | Westwalk Pointe-Claire – 360 Labrosse/988 St-Jean – 2 phases, 12 stories + parking, +/- 374units | Condo | Agreement |  | Unresolved | Marianne Yanni | Marianne Yanni | Marianne Yanni | 2024-04-29 14:17 |  | 2024-10-01 09:29 |  |  |  | 0 | 0 | _thumb_1030264.png _thumb_1030262.png _thumb_1030261.png |  | MTLCONST-10018, MTLCONST-10019 | MTLCONST-10012, MTLCONST-10011 | There is an opportunity to provide bulk-internet services to 3x new greenfield residential projects being constructed by Devmont. As these locations are still in the planning phase, no site walk can be scheduled yet. The electrical drawings from the developer will be requested. * *_Westwalk Anjou – 7400-7450 boul. Des Galéries d’Anjou – 3 phases, 15 stories + parking, +/- 500units - MTLCONST-10011_* [https://buildings.beanfield.com/buildings/view/20186] * *_Westbury 9 - 4955/5055 Courtrai – 2 phases, 12 stories + parking, +/- 330 units_* *_- MTLCONST-10012_* [https://buildings.beanfield.com/buildings/view/20187] * *_Westwalk Pointe-Claire – 360 Labrosse/988 St-Jean – 2 phases, 12 stories + parking, +/- 374units_* [https://buildings.beanfield.com/buildings/view/20188] | [13 empty] | 0¦i4swr3: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
Construction | CONST-35794 | 775 Vaughan Rd, York | Condo | Agreement |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2023-11-22 10:45 |  | 2024-12-30 17:45 |  |  |  | 0 | 0 |  |  | CONST-35796, CONST-35797, CONST-37305 |  | Requested by Oliver Davies, Can you please create new tickets for an OSP plan for the 2x locations below? There is an (early) opportunity with Shannondale Developments for a 469 unit rental building that is being constructed at 775 Vaughan Rd. Occupancy is not expected until 2026-2027, but they are discussing telcos now. Also nearby is 1603 Eglinton Ave W, we have not received permission to complete a site walk, but I would like to determine what is involved outside of the building to connect them to our network. Thank you, | [13 empty] | 0¦i4gl6v: | [7 empty] | 9.2234e+18 | [19 empty] | May 9, 2024 - Expected occupancy is actually 2028. (Not until 2028. Breaking ground Q4 this year2024.) | [6 empty] | 3 - Normal | [24 empty] | 36 | 500 | [5 empty] | https://buildings.beanfield.com/buildings/view/19434 |  |  | 3 - Normal |  | York
Construction | CONST-36539 | 81 Wellesley St E, Toronto | Condo | Agreement |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2024-02-13 11:59 |  | 2024-12-30 18:16 |  |  |  | 0 | 0 |  |  | CONST-36540, CONST-36541, CONST-36853 |  | Requested by Oliver Davies, Could you please proceed with creating new tickets for an OSP plan & site walk at 81 Wellesley St E? Eighty One Wellesley is a new condo that began occupancy in late Q3 2023. There are 179 units here. PM Info: *SERENA BAKER* Condominium Manager *Melbourne Property Management Inc.* 1244 Caledonia Road, Suite 100 Toronto, ON. M6A 2X5 Direct: 416-546-2126 x153 Email: [serena.baker@melbournepm.ca¦mailto:serena.baker@melbournepm.ca] Thanks! | [13 empty] | 0¦i4mfyf: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 28 | 179 | [5 empty] | https://buildings.beanfield.com/buildings/view/18165 |  |  | 3 - Normal |  | Toronto
Montreal Construction | MTLCONST-10011 | Westwalk Anjou – 7400-7450 boul. Des Galleries d’Anjou – 3 phases, 15 stories + parking, +/- 500units | Condo | Agreement |  | Unresolved | Marianne Yanni | Marianne Yanni | Marianne Yanni | 2024-04-29 14:15 |  | 2025-01-20 14:49 |  |  |  | 0 | 0 |  |  | MTLCONST-10014, MTLCONST-10015, MTLCONST-10742 | MTLCONST-10742, MTLCONST-10012, MTLCONST-10013 | There is an opportunity to provide bulk-internet services to 3x new greenfield residential projects being constructed by Devmont. As these locations are still in the planning phase, no site walk can be scheduled yet. The electrical drawings from the developer will be requested. * *_Westwalk Anjou – 7400-7450 boul. Des Galleries d’Anjou – 3 phases, 15 stories + parking, +/- 500units_* [https://buildings.beanfield.com/buildings/view/20186] * *_Westbury 9 - 4955/5055 Courtrai – 2 phases, 12 stories + parking, +/- 330 units - MTLCONST-10012_* [https://buildings.beanfield.com/buildings/view/20187] * *_Westwalk Pointe-Claire – 360 Labrosse/988 St-Jean – 2 phases, 12 stories + parking, +/- 374units - MTLCONST-10013_* [https://buildings.beanfield.com/buildings/view/20188] | [13 empty] | 0¦i4swpz: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
Construction | CONST-12142 | 56 Forest Manor Rd - The Park Club - Emerald City | Condo | Agreement |  | Unresolved | Harvey Tran | Olawale Olaniyan [X] | Oguz Avci [X] | 2020-03-13 08:59 |  | 2024-12-17 10:42 |  |  |  | 0 | 1 |  |  | CONST-13012, CONST-13013, CONST-33978, CONST-33979, CONST-34001 | CONST-33772, CONST-29216, CONST-29219, CONST-29207, CONST-29210, CONST-32361 | +*Site contact:*+ Mahyar Taha Property Manager Agent for and on behalf of: T.S.C.C. 2721 Phone: 416-499-3252 Fax: 416-499-8052 Email: [ParkClub.PM@DelCondo.com¦mailto:ParkClub.PM@DelCondo.com] | [13 empty] | 0¦i1vm1j: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 33 | 344 | [5 empty] | https://buildings.beanfield.com/buildings/view/16441 |  |  | 3 - Normal |  | North York
Construction | CONST-29620 | 123 Parkway Forest Dr, North York | Condo | Agreement |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Jessica Markiewicz | 2022-07-22 07:59 |  | 2025-01-02 11:43 |  |  |  | 0 | 0 |  |  | CONST-29621, CONST-29622, CONST-29797, CONST-30164 | CONST-29078 | Requested by Oliver Davis Whenever you have a moment, can we please queue up a site walk for 123 Parkway Forest Dr, North York? BB: [https://buildings.beanfield.com/buildings/view/16923] PM info: *Shayna Hails* PROPERTY MANAGER *o*. 647.849-3762*¦ e*. [shaynahails@rhapsodyliving.ca¦mailto:shaynahails@rhapsodyliving.ca] VIA123 Apartments 123 Parkway Forest Drive Toronto, ON. M2J 0G1 [via123.ca¦http://via123.ca/] This is a Rhapsody rental building with 190 condo units and approx. 10 townhomes. Note from Jay Fernandes: There is currently no fibre in this area but we are working on a permit to bring fibre there for the buildings we have agreements for. This will need to be budgeted based off that which may not be possible yet. | [13 empty] | 0¦i3i0pb: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2017 | [6 empty] | 3 - Normal | [24 empty] | 20 | 200 | [5 empty] | https://buildings.beanfield.com/buildings/view/16923 |  |  | 3 - Normal |  | North York
Construction | CONST-29791 | 50 Portland St, Toronto - Fifty On the Park | Condo | Agreement |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Jessica Markiewicz | 2022-08-04 15:34 |  | 2025-01-02 11:50 |  |  |  | 0 | 0 |  |  | CONST-29792, CONST-29793, CONST-30090, CONST-30157 |  | Requested by Oliver Davies. Could you please queue up a site walk for 50 Portland St? This can be assigned via the existing ticket https://tickets.beanfield.com/browse/CONST-5331 BB Link: [https://buildings.beanfield.com/buildings/view/1635] PM: *Niyati Patel* *Property Manager* [50 Portland Street¦https://can01.safelinks.protection.outlook.com/?url=https%3A%2F%2Fwww.google.com%2Fmaps%2Fsearch%2F50%2BPortland%2BStreet%2B%250D%250A%2BToronto%2C%2BOntario%2BM5V%2B2M7%3Fentry%3Dgmail%26source%3Dg&data=04%7C01%7CNPatel%40morguard.com%7C6f6be7f5309748b581c308d9f306e449%7C0fa3cb64564a46968f3484a254b77901%7C0%7C0%7C637808034219821330%7CUnknown%7CTWFpbGZsb3d8eyJWIjoiMC4wLjAwMDAiLCJQIjoiV2luMzIiLCJBTiI6Ik1haWwiLCJXVCI6Mn0%3D%7C0&sdata=I8Y2Tn%2BbfEk2V0LdydnT9XjAu42%2B7WhRs57RXt3%2FfTI%3D&reserved=0] [Toronto, Ontario M5V 2M7¦https://can01.safelinks.protection.outlook.com/?url=https%3A%2F%2Fwww.google.com%2Fmaps%2Fsearch%2F50%2BPortland%2BStreet%2B%250D%250A%2BToronto%2C%2BOntario%2BM5V%2B2M7%3Fentry%3Dgmail%26source%3Dg&data=04%7C01%7CNPatel%40morguard.com%7C6f6be7f5309748b581c308d9f306e449%7C0fa3cb64564a46968f3484a254b77901%7C0%7C0%7C637808034219821330%7CUnknown%7CTWFpbGZsb3d8eyJWIjoiMC4wLjAwMDAiLCJQIjoiV2luMzIiLCJBTiI6Ik1haWwiLCJXVCI6Mn0%3D%7C0&sdata=I8Y2Tn%2BbfEk2V0LdydnT9XjAu42%2B7WhRs57RXt3%2FfTI%3D&reserved=0] T 416-361-1550 F 416-361-0270 E [npatel@morguard.com¦mailto:npatel@morguard.com] [www.morguard.com¦http://www.morguard.com/] | [13 empty] | 0¦i3iv2f: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2005 | [6 empty] | 3 - Normal | [24 empty] | 10 | 232 | [5 empty] | https://buildings.beanfield.com/buildings/view/1635 |  |  | 3 - Normal |  | Toronto
Construction | CONST-23272 | 7 Grenville St, Toronto | Condo | Agreement |  | Unresolved | James Mowers | Lorna Kurok | Harvey Tran | 2021-05-05 12:50 |  | 2025-01-02 11:48 |  |  |  | 0 | 1 |  |  | CONST-23273, CONST-23396 |  | We have a property interested, and would need to schedule a site visit. See below for details: *Property Address:* 7 Grenville St, Toronto ON M4Y 0E9 *BB Link*: [https://buildings.beanfield.com/buildings/view/7966] *Property Manager:* Elaine Lee [Elaine.Lee@fsresidential.com¦mailto:Elaine.Lee@fsresidential.com] 647-292-5377 Site walk subtask can be set up and James can reach out. She said Mondays don’t work for the visit, but any other day does. | [13 empty] | 0¦i2ngyn: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2017 | [6 empty] | 3 - Normal | [24 empty] | 61 | 639 | [5 empty] | https://buildings.beanfield.com/buildings/view/7966 |  |  | 3 - Normal |  | Toronto
Construction | CONST-29578 | 591 Sheppard Ave E, Toronto | Condo | Agreement |  | Unresolved | Lorna Kurok | Lorna Kurok | Jessica Markiewicz | 2022-07-20 13:53 |  | 2025-01-02 13:57 |  |  |  | 0 | 0 |  |  | CONST-29579, CONST-29580, CONST-38042 | CONST-29195, CONST-29198, CONST-29201, CONST-32106, CONST-24117, CONST-29189, CONST-29192, CONST-30959 | h3. {color:#403294}Units 201{color} Requested by Oliver Davies Could you please queue up a site walk for 591 Sheppard Ave E? This is a net-new building with no agreement in place. BB Link: [https://buildings.beanfield.com/buildings/view/16916] +*New Site Contact Info:*+ Jim Flynn [jflynn@mrcm.ca¦mailto:jflynn@mrcm.ca] +*Old Site Contact Info:*+ Denio Gomes Assistant Property Manager CPO / Canadian Properties Operator Management Inc. Agents for and on Behalf of TSCC2762 - The Village Residences 591 Sheppard Avenue East, North York, ON, M2K 0G2 Tel: 416-901-5977 ¦ Fax: 416-901-5277 Email: [tscc2762@rogers.com¦mailto:tscc2762@rogers.com] | [13 empty] | 0¦i3hvjz: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2019 October 28th - Site visit completed. Manhole location to be confirmed. Budget pending approval. July 04/23 - As per Oliver Davies "please mark this location as Not a Candidate. " | [6 empty] | 3 - Normal | [24 empty] | 10 | 201 | [5 empty] | https://buildings.beanfield.com/buildings/view/16916 |  |  | 3 - Normal |  | Toronto
Construction | CONST-38479 | 35 Hollywood Ave, North York, The Pearl Condos | Condo | Agreement |  | Unresolved | Lorna Kurok | Lorna Kurok | Lorna Kurok | 2024-09-17 07:39 |  | 2024-12-20 12:05 |  |  |  | 0 | 0 |  |  | CONST-38480, CONST-38481, CONST-38483, CONST-38559 |  | Requested by Oliver Davies_Sept 16, 2024 Units_351 Floors_24 Constructed in 2011 *{color:#0747a6}PM Info as of Sept 16, 2024:{color}* *Erlind Hasko, OLCM* Condominium Manager As Agents for and on behalf of Pearl Condos TSCC 2172 35 Hollywood Avenue ¦ Toronto, Ontario M2N 0A9 Telephone: 416.551.3535 [PearlCondos@crossbridgecs.com¦mailto:PearlCondos@crossbridgecs.com] Can you please schedule a site walk for 35 Hollywood Ave? The Pearl Condos include 351 units. They were constructed in 2011. This condo is next door, and very likely connects via P1, to the already On Net 23 Hollywood Ave "Platinum" condos built by the same developer. BB Link: [https://buildings.beanfield.com/buildings/view/4793] PM Info: *Erlind Hasko, OLCM* Condominium Manager As Agents for and on behalf of Pearl Condos TSCC 2172 35 Hollywood Avenue ¦ Toronto, Ontario M2N 0A9 Telephone: 416.551.3535 | [13 empty] | 0¦i5780v: | [7 empty] | 9.2234e+18 | [19 empty] | Sept 16 2024_Site Walk requested Sep 17, 2024_ OSP plan closed. Sep 19, 2024_Budget Added Sep 18, 2024 | [6 empty] | 3 - Normal | [24 empty] | 24 | 351 | [5 empty] | https://buildings.beanfield.com/buildings/view/4793 |  |  | 3 - Normal |  | North York
Construction | CONST-35510 | 60 Colborne St, Toronto - SIXTY Colborne | Condo | Agreement |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2023-10-17 09:28 |  | 2024-12-24 10:20 |  |  |  | 0 | 0 |  |  | CONST-35511, CONST-35513, CONST-35746 |  | Requested by Oliver Davies, Can you please queue up a new site walk & OSP plan for 60 Colborne St? There are 252 residential units at this condo. Building Constructed 2017 PM Info: *Danielle McDonald {color:#77bb41}(Primary Contact){color}* Condominium Admin, CMRAO NO. LL 0054896530 {*}Samantha Dubois{*}, MBA, OLCM Condominium Manager, CMRAO NO. GL 0033653742 *+[sixtycolborne.admin@fhkipling.com¦mailto:sixtycolborne.admin@fhkipling.com]+* *Agents on behalf of* *T.S.C.C. No. 2701* – Sixty Colborne - Suite 207 Thank you, | [13 empty] | 0¦i4dvin: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 25 | 252 | [5 empty] | https://buildings.beanfield.com/buildings/view/2228 |  |  | 3 - Normal |  | Toronto
Construction | CONST-34668 | 28 Byng Ave, North York | Condo | Agreement |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2023-07-04 11:43 |  | 2024-12-24 10:28 |  |  |  | 0 | 0 |  |  |  | CONST-34674 | Requested by Oliver Davies Will be seeking agreement from the condo boards Floors 14 Units 142 Constructed in 2003 | [13 empty] | 0¦i45cfz: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 14 | 142 | [5 empty] | https://buildings.beanfield.com/buildings/view/13883 |  |  | 3 - Normal |  | North York
Construction | CONST-34385 | 28 Avondale Ave, North York | Condo | Agreement |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2023-06-15 08:27 |  | 2024-12-24 10:29 |  |  |  | 0 | 0 |  |  | CONST-34386, CONST-34387, CONST-34472 |  | Requested by Oliver Davies, Can you please queue up a site walk for James at 28 Avondale Ave? The Flo Condos are a smaller building with 94 units, however, we have a BFMH right outside at the intersection of Avondale & Bales Ave so it _should_ be an easy endeavour to bring them online. Constructed in 2016 Site Contact: *Malcolm R. Marcus, B. Econ., O.L.C.M., R.C.M., A.C.C.I.* *Licensed Condominium Manager* **{*}President{*} *T. 905. 764.9166 x 30* *f. 905.882.0228* *e. [malcolm@tsems.com¦mailto:malcolm@tsems.com]* ** Thank you, | [13 empty] | 0¦i43wd3: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 11 | 94 | [5 empty] | https://buildings.beanfield.com/buildings/view/3608 |  |  | 3 - Normal |  | North York
Construction | CONST-22932 | 801 Bay St, Toronto | Condo | Agreement |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Harvey Tran | 2021-04-12 13:54 |  | 2024-12-24 11:19 |  |  |  | 0 | 0 |  |  | CONST-22933, CONST-23046 |  | +*PM Contact Info:*+ Andrew Canali, Property Manager {color:#777733}[acanali@gpmmanagement.com¦mailto:acanali@gpmmanagement.com]{color} 416-997-1338 Constructed 2000 | [13 empty] | 0¦i2l41r: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 18 | 137 | [5 empty] | https://buildings.beanfield.com/buildings/view/4349 |  |  | 3 - Normal |  | Toronto
Construction | CONST-36969 | 15-25 Water Walk Dr, Unionville - Uptown Markham Riverside (BULK) | Condo | Agreement |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2024-04-04 13:09 | 2025-03-04 10:05 | 2024-12-24 11:43 |  |  |  | 0 | 0 |  |  | CONST-36970, CONST-36971, CONST-37441 | CONST-34079 | Requested by Oliver Davies, Constructed in 2018 Could you please create a new ticket for an OSP plan & site walk at 15-25 Water Walk Dr, Markham? The Uptown Markham Riverside condos include 615 units and are under a bulk agreement with Rogers that expires in 2025. They have expressed interest in moving to Beanfield for the renewal. I will be meeting with the board on May 22nd, ideally we can have the budget in place by early May. PM Info: ¦*Andrew Fong* */* Property Manager OLCM¦ *Times Property Management Inc.* *Agents for and on behalf of Y.R.S.C.C. No. 1391* *15 Water Walk Drive* {*}Markham, ON L6G 0G2{*}¦ *T : (905) 604-7150 ex. 201 Email:* +[andrew@timesproperty.ca¦mailto:andrew@timesproperty.ca]+ ** Thanks! | BulkDeal | [12 empty] | 0¦i4q4zz: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 28 | 615 | [5 empty] | https://buildings.beanfield.com/buildings/view/16349 |  |  | 3 - Normal |  | Unionville
Construction | CONST-28071 | 3504 Hurontario St, Mississauga | Condo | Agreement |  | Unresolved | Harvey Tran | Harvey Tran | Harvey Tran | 2022-04-26 07:10 |  | 2024-12-24 14:17 |  |  |  | 0 | 1 |  |  | CONST-28072, CONST-28073, CONST-29771 | CONST-37795, CONST-38068 | Constructed 2007 There is a large pocket of buildings in this neighbourhood surrounding Square One mall, it would be excellent to start getting some of them on our roadmap. PM Info: Victoria Janik Condominium Manager, O.L.C.M., R.C.M. As Agents for and on behalf of _EDEN PARK CONDOMINIUM_ P.S.C.C.# 802 3504 Hurontario Street Mississauga, Ontario, L5B 0B9 Tel: 905-276-1908 Fax: 905-276-9794 Email: {color:#0000ff}[pscc802manager@gmail.com¦mailto:pscc802manager@gmail.com]{color} | [13 empty] | 0¦i3ceef: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 33 | 300 | [5 empty] | https://buildings.beanfield.com/buildings/view/3829 |  |  | 3 - Normal |  | Mississauga
Construction | CONST-36748 | 17 Michael Power Pl, Etobicoke - Port Royal Place Ⅰ | Condo | Agreement |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2024-03-05 10:29 |  | 2024-12-24 14:21 |  |  |  | 0 | 0 |  |  | CONST-36749, CONST-36750, CONST-36751, CONST-38184 | CONST-36642, CONST-29111, CONST-36641 | Constructed 2003 Requested by Oliver Davies, Units 130 Could you create an OSP plan & site walk ticket for 17 MP? PM: Carole Ogibowski [carole.ogibowski@wilsonblanchard.com¦mailto:carole.ogibowski@wilsonblanchard.com] | [13 empty] | 0¦i4nwbj: | [7 empty] | 9.2234e+18 | [19 empty] | Aug 7, 2024- Waiting to determine if the Condo Board agrees. | [6 empty] | 3 - Normal | [24 empty] | 9 | 130 | [5 empty] | https://buildings.beanfield.com/buildings/view/4739 |  |  | 3 - Normal |  | Etobicoke
Construction | CONST-35871 | 2916 Highway 7, Concord - Nord West | Condo | Agreement |  | Unresolved | Lorna Kurok | Lorna Kurok | Olawale Olaniyan [X] | 2023-11-30 10:20 |  | 2024-12-24 14:30 |  |  |  | 0 | 0 |  |  | CONST-35872, CONST-35873, CONST-37876, CONST-37877 | CONST-37926, CONST-32717, CONST-32677, CONST-32680 | Requested by Oliver Davies: Constructed in 2020 PM Info: Erika Belicky [exponord.pm@delcondo.com¦mailto:exponord.pm@delcondo.com] | [13 empty] | 0¦i4h8br: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 48 | 430 | [5 empty] | https://buildings.beanfield.com/buildings/view/16628 |  |  | 3 - Normal |  | Concord
Construction | CONST-32717 | 2908 Highway 7, Concord - Nord East | Condo | Agreement |  | Unresolved | Lorna Kurok | Lorna Kurok | Denise King | 2023-01-12 15:06 |  | 2024-12-24 15:17 |  |  |  | 0 | 2 |  |  | CONST-32718, CONST-32719, CONST-37874, CONST-37875 | CONST-37926, CONST-35871, CONST-32677, CONST-32680 | Requested by Oliver Davies: Constructed 2020 PM Info: Erika Belicky [exponord.pm@delcondo.com¦mailto:exponord.pm@delcondo.com] | [13 empty] | 0¦i3t19z: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 430 | 38 | [5 empty] | https://buildings.beanfield.com/buildings/view/16628 |  |  | 3 - Normal |  | Concord
Construction | CONST-15248 | 311 Bay Street, Toronto - The St. Regis Residences | Condo | Agreement |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Harvey Tran | 2020-09-22 11:16 |  | 2024-12-25 19:56 |  |  |  | 0 | 1 |  |  | CONST-15249, CONST-15286 |  | New property interested Constructed 2012 +*Property Address:*+ 311 Bay Street (The St.Regis Toronto ) +*Contact information:*+ *Vanessa Van Dette* *Property Manager* Tel: (416) 637- 4405 Mobile: (416) 725-9789 Email: [Vanessa.Vandette@stregis.com¦mailto:Vanessa.Vandette@stregis.com] | [13 empty] | 0¦i26bm7: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 32 | 120 | [5 empty] | https://buildings.beanfield.com/buildings/view/13123 |  |  | 3 - Normal |  | Toronto
Construction | CONST-29808 | 25 Selby St, Toronto - The Selby | Condo | Agreement |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Jessica Markiewicz | 2022-08-08 14:53 |  | 2024-12-25 20:01 |  |  |  | 0 | 0 |  |  | CONST-29809, CONST-29810, CONST-30487 |  | Requested by Oliver Davies. Can you please queue up a site walk for 25 Selby St? This is a Tricon Residential rental property with 500 units near Bloor/Sherbourne. BB Link: [https://buildings.beanfield.com/buildings/view/8150] PM Info: *Amanda Mulligan* Resident Experience Manager THE SELBY 25 Selby Street Toronto, Ontario M4Y 0E6 [amulligan@triconresidential.com¦mailto:amulligan@triconresidential.com] 647-945-5289 | [13 empty] | 0¦i3j0yn: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2019 | [6 empty] | 3 - Normal | [24 empty] | 50 | 500 | [5 empty] | https://buildings.beanfield.com/buildings/view/8150 |  |  | 3 - Normal |  | Toronto
Construction | CONST-37291 | 310 Tweedsmuir Ave, York | Condo | Agreement |  | Unresolved | Harvey Tran | Harvey Tran | Harvey Tran | 2024-05-08 13:25 |  | 2024-12-25 20:40 |  |  |  | 0 | 0 |  |  | CONST-37293, CONST-37294, CONST-37472 | CONST-37292 | Requested by Oliver Davies. Could you please create a new ticket for an OSP plan & Site Walk at 310 & 320 Tweedsmuir Ave? The Heathview is a purpose-built rental community with 499 units, owned by Morguard. BB Link: 310 - [https://buildings.beanfield.com/buildings/view/3602] 320 - [https://buildings.beanfield.com/buildings/view/3225] Site Contact: {*}J{*}{*}ames Bond{*} *Assistant Property Manager* 310 Tweedsmuir Avenue Toronto, ON M5P 2Y2 T 647-348-3310 E [jbond@morguard.co¦mailto:jbond@morguard.com]m | [13 empty] | 0¦i4ts1z: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed 2014 | [6 empty] | 3 - Normal | [24 empty] | 30 | 249 | [5 empty] | https://buildings.beanfield.com/buildings/view/3602 |  |  | 3 - Normal |  | York
Construction | CONST-37292 | 320 Tweedsmuir Ave, York | Condo | Agreement |  | Unresolved | Harvey Tran | Harvey Tran | Harvey Tran | 2024-05-08 13:26 |  | 2024-12-25 20:43 |  |  |  | 0 | 0 |  |  | CONST-37295, CONST-37296, CONST-37471 | CONST-37291 | Requested by Oliver Davies. Could you please create a new ticket for an OSP plan & Site Walk at 310 & 320 Tweedsmuir Ave? The Heathview is a purpose-built rental community with 499 units, owned by Morguard. BB Link: 310 - [https://buildings.beanfield.com/buildings/view/3602] 320 - [https://buildings.beanfield.com/buildings/view/3225] Site Contact: {*}J{*}{*}ames Bond{*} *Assistant Property Manager* 310 Tweedsmuir Avenue Toronto, ON M5P 2Y2 T 647-348-3310 E [jbond@morguard.co¦mailto:jbond@morguard.com]m h4. | [13 empty] | 0¦i4ts2n: | [7 empty] | 9.2234e+18 | [19 empty] | constructed 2014 | [6 empty] | 3 - Normal | [25 empty] | 250 | [5 empty] | https://buildings.beanfield.com/buildings/view/3225 |  |  | 3 - Normal |  | York
Construction | CONST-36570 | 1/11/21 Ruttan St, Toronto | Condo | Agreement |  | Unresolved | James Mowers | Lorna Kurok | Olawale Olaniyan [X] | 2024-02-16 13:16 |  | 2025-02-21 09:36 |  |  |  | 0 | 0 |  |  | CONST-36571, CONST-36572, CONST-38748, CONST-39588 | CONST-31440, CONST-29399 | Requested by Oliver Davies, Units 85 Floors 2 Could you also queue up a site walk for 1-11 Ruttan St? The Brownstones on Bloor contain 85 townhomes. Per CONST-29401 we will require access to this location in order to complete a cable pull to the beBloor condos at 1369 Bloor St W. PM Info: Corinna Sepp Horizon Property Management Inc. Agent for and on behalf of TSCC No. 2174 T [416-332-4988¦tel:416-332-4988] F416-332-0554 [office@tscc2174.com¦mailto:office@tscc2174.com] Thanks! | [13 empty] | 0¦i4mp0n: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2011 | [6 empty] | 3 - Normal | [24 empty] | 2 | 85 | [5 empty] | https://buildings.beanfield.com/buildings/view/7415 |  |  | 3 - Normal |  | Toronto
BC Construction | BCCONST-742 | 13740 Fraser Hwy, Tether (Phase E PCI), Surrey BC | Condo | Agreement |  | Unresolved | Josh Wignall | Yawn Paular | Yawn Paular | 2024-06-21 19:33 |  | 2025-02-13 12:06 |  |  | 2026-01-02 | 0 | 0 |  |  | BCCONST-743, BCCONST-744, BCCONST-745, BCCONST-746, BCCONST-747, BCCONST-748, BCCONST-749, BCCONST-750 |  | 402 rental units 2 electrical parkade drawings where the main comms room located, P1 electrical parkade drawings where the DES and main electrical room is located, detailed drawing with electrical room layout, and detail drawing with comms room layout + typical comms closets locations. L1 = 10 residential units, amenity lounge, co-working space, workshop space, and building manager’s office. There is also a separated amenity building with the gym (I’m not sure if it’s relevant){+}{{+}}{+}{{+}} L2 = 10 residential units.{+}{{+}}{+}{{+}} L3, L4 = 12 residential units per floor.{+}{{+}}{+}{{+}} L5 – L39 = 10 residential units per floor{+}{{+}}{+}{{+}} L40 = 8 residential units.{+}{{+}}{+}{{+}} L41 = amenity floor with 2 dining lounges and one open amenity lounge Q4 of 2026 Occupancy Date Building Name: Tether | Budget_Allocated, DES | [12 empty] | 0¦i4ygan: | [7 empty] | 9.2234e+18 | [19 empty] | Jan 22 - With Steven B for CA creation and submission. Agreements not signed yet | [6 empty] | 3 - Normal | [25 empty] | 402 | [10 empty] | Surrey | 16500 | 33400
Construction | CONST-37431 | 6 Eva Rd, Etobicoke - West Village I | Condo | Agreement |  | Unresolved | James Mowers | Harvey Tran | Harvey Tran | 2024-05-16 13:44 |  | 2025-02-19 08:36 |  |  |  | 0 | 0 |  |  | CONST-37433, CONST-37434, CONST-37553, CONST-40075 | CONST-37432 | Requested by Oliver Davies. +*PM Contact:*+ Len Neglia, Property Manager Condominium Manager West Village I & II 6 Eva Road Etobicoke, ON M9C 0B1 Tel: 416-792-4782 Fax: 416-792-4785 [Westvillage.pm@delcondo.com¦mailto:Westvillage.pm@delcondo.com] Bell / Rogers / Coextro have a presence here. Closest BFMH appears to be CDSH13399 at Gibbs Rd & The East Mall. There is a 204 unit tower being constructed at 10 Eva Rd by Tridel. | [13 empty] | 0¦i4udmn: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2014 February 14, 2025.- CAPEX Meeting - Wednesday Feb 12, Agreement is in process. Feb 14, 2025 - On net schedule for August 14 2025 | [6 empty] | 3 - Normal | [21 empty] | 2025-02-13 |  |  | 27 | 268 | [5 empty] | https://buildings.beanfield.com/buildings/view/2177 |  | CONST-37431 | 3 - Normal | 2025-08-14 | Etobicoke
Construction | CONST-37432 | 2 Eva Rd, Etobicoke - West Village II | Condo | Agreement |  | Unresolved | James Mowers | Lorna Kurok | Harvey Tran | 2024-05-16 13:45 |  | 2025-02-19 08:37 |  |  | 2025-08-14 | 0 | 0 |  |  | CONST-37435, CONST-37436, CONST-37552, CONST-40074 | CONST-37431 | Requested by Oliver Davies. +*PM Contact:*+ Len Neglia, Property Manager Condominium Manager West Village I & II 6 Eva Road Etobicoke, ON M9C 0B1 Tel: 416-792-4782 Fax: 416-792-4785 [Westvillage.pm@delcondo.com¦mailto:Westvillage.pm@delcondo.com] Bell / Rogers / Coextro have a presence here. Closest BFMH appears to be CDSH13399 at Gibbs Rd & The East Mall. There is a 204 unit tower being constructed at 10 Eva Rd by Tridel. | [13 empty] | 0¦i4udmv: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2014 February 14, 2025.- CAPEX Meeting - Wednesday Feb 12, Agreement is in process. Feb 14, 2025 - Listed on the Financial capex tracker. Scheduled to go ON net August 15, 2025. | [6 empty] | 3 - Normal | [21 empty] | 2025-02-13 |  |  | 30 | 279 | [5 empty] | https://buildings.beanfield.com/buildings/view/3718 |  | CONST-37431(Sub) | 3 - Normal |  | Etobicoke
BC Construction | BCCONST-484 | 13696 100 Avenue (Park Avenue West), Surrey BC | Condo | Agreement |  | Unresolved | Josh Wignall | Yawn Paular | Yawn Paular | 2023-11-16 17:20 |  | 2025-02-04 12:55 |  |  | 2025-06-27 | 0 | 0 |  |  | BCCONST-502, BCCONST-503, BCCONST-504, BCCONST-505, BCCONST-664, BCCONST-820 | BCCONST-483 | 462 units 45 flrs EPS4403 Ranch Mgmt - 604-684-4508 Gus Ramirez <GRamirez@ranchogroup.com> Habil Otieno Building Supervisor - Park Avenue West 13696 100 Avenue Surrey BC V3T 0L5 Phone: 604-240-4063 | Budget_Allocated | [12 empty] | 0¦i4g8on: | [7 empty] | 9.2234e+18 | [19 empty] | Jan 9 - CA form created, Mike to add ILC and send it to Steven Jan 23 - Budget approved, Josh to reach out to Gus for BAA updates | [6 empty] | 3 - Normal | [24 empty] | 45 | 462 | [10 empty] | Surrey | 36300 | 46750
BC Construction | BCCONST-483 | 13750 100 Avenue (Park Avenue East), Surrey BC | Condo | Agreement |  | Unresolved | Josh Wignall | Yawn Paular | Yawn Paular | 2023-11-16 17:18 |  | 2025-02-04 12:59 |  |  | 2025-06-27 | 0 | 0 |  |  | BCCONST-506, BCCONST-507, BCCONST-508, BCCONST-663 | BCCONST-484 | 424 units 46 flrs EPS3859 Rancho Mgmt - 604-684-4508 Gus Ramirez <GRamirez@ranchogroup.com> | Budget_Allocated | [12 empty] | 0¦i4g8of: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 46 | 424 | [10 empty] | Surrey
BC Construction | BCCONST-485 | 9981 Whalley Blvd (Park Place II), Surrey BC | Condo | Agreement |  | Unresolved | Josh Wignall | Yawn Paular | Yawn Paular | 2023-11-16 17:23 |  | 2025-02-04 13:30 |  |  | 2025-07-25 | 0 | 0 |  |  | BCCONST-496, BCCONST-497, BCCONST-498, BCCONST-662, BCCONST-755 | BCCONST-487, BCCONST-488, BCCONST-486 | 349 units 36 flrs EPS561 Rancho Mgmt - 604-684-4508 Gus Ramirez <GRamirez@ranchogroup.com> | Budget_Allocated | [12 empty] | 0¦i4g8p3: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 36 | 349 | Backbone | [9 empty] | Surrey
BC Construction | BCCONST-486 | 13688 100 Avenue (Park Place), Surrey BC | Condo | Agreement |  | Unresolved | Josh Wignall | Yawn Paular | Yawn Paular | 2023-11-16 17:25 |  | 2025-02-04 13:30 |  |  | 2025-07-25 | 0 | 0 |  |  | BCCONST-499, BCCONST-500, BCCONST-501, BCCONST-661, BCCONST-754 | BCCONST-487, BCCONST-488, BCCONST-485 | 349 units 36 floors EPS561 Rancho Mgmt - 604-684-4508 Gus Ramirez <GRamirez@ranchogroup.com> Site Contact: Stedman Espinoza - 778 899 7950 [espinoza@rservice.ca¦mailto:espinoza@rservice.ca] | Budget_Allocated | [12 empty] | 0¦i4g8pj: | [7 empty] | 9.2234e+18 | [19 empty] | Feb 4 - Waiting for BAA. Gus likely wants to see how Park Blvd goes first before signing rest of the bldgs | [6 empty] | 3 - Normal | [24 empty] | 36 | 349 | Backbone | [9 empty] | Surrey
Construction | CONST-40077 | 2035 Kennedy Rd, Scarborough, KSquare Condos | Condo | Agreement |  | Unresolved | Unassigned | Lorna Kurok | Lorna Kurok | 2025-02-14 10:41 |  | 2025-03-11 14:40 |  |  |  | 0 | 0 |  |  | CONST-40081, CONST-40082, CONST-40083 | CONST-26336, CONST-32609, CONST-32622, CONST-32623, CONST-40076, CONST-26571, CONST-26574 | [14 empty] | 0¦i5ivw7: | [7 empty] | 9.2234e+18 | [19 empty] | Feb 14, 2025 - 2035 Kennedy is a new development, Beanfield is working on obtaining the agreement at this time. | [6 empty] | 3 - Normal | [21 empty] | 2025-02-13 |  |  | 39 | 644 | [5 empty] | https://buildings.beanfield.com/buildings/view/19405 |  |  | 3 - Normal |  | Scarborough
BC Construction | BCCONST-509 | 13768 100 Avenue (Park George I), Surrey BC | Condo | Agreement |  | Unresolved | Josh Wignall | Yawn Paular | Yawn Paular | 2023-12-04 13:52 |  | 2025-03-10 13:39 |  |  | 2025-11-28 | 0 | 0 |  |  | BCCONST-511, BCCONST-665, BCCONST-666, BCCONST-827 | BCCONST-510 | Under Construction 339 units 39Flrs Entrance could be shared with Park George II Concord Pacific Colyvan Pacific Real Estate Management Services Ltd. info@colyvanpacific.com | BudgetPending | [12 empty] | 0¦i4hir3: | [7 empty] | 9.2234e+18 | [19 empty] | Mar 10 - With Josh's team for agreements | [6 empty] | 3 - Normal | [24 empty] | 39 | 339 | [10 empty] | Surrey | 31300 | 45700
Construction | CONST-32041 | 260 Sackville St, Toronto - One Park West | Condo | Agreement |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Jessica Markiewicz | 2022-11-23 12:17 |  | 2025-03-04 10:33 |  |  |  | 0 | 1 |  |  | CONST-32042, CONST-32043, CONST-38285, CONST-38286 |  | Requested by Jay Fernandes. Good Afternoon, We missed some condos that have agreements. Can we get these added and site walks and budgets. There are some old tickets created you can reuse or just start fresh. PM Info: *Taufiq Ferdaus,* MCom., Adv. Diploma- Business Acct., General Licence Condominium Manager *Agent for and on behalf of: TSCC No. 2178* *One Park West Boutique Condominiums* *260 Sackville Street Toronto, ON M5A 0B3* *Phone:* 416-792-2714 *Email:* pm@opwcondo.ca +Site Super: Dritan (416.919.3755) | FSactive, Fiberstreamagreement | [12 empty] | 0¦i3pwy7: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2011 Jan 18/23 - As per Oliver Davies "We will need to place this on hold for now. We will get to it eventually, however at almost $400/per unit it is a low priority for us today." | [6 empty] | 3 - Normal | [24 empty] | 13 | 176 | Integration |  |  |  |  | https://buildings.beanfield.com/buildings/view/1756 |  |  | 3 - Normal |  | Toronto
BC Construction | BCCONST-478 | 13615 Fraser Highway (Hub One), Surrey BC | Condo | Agreement |  | Unresolved | Josh Wignall | Yawn Paular | Yawn Paular | 2023-11-16 16:17 |  | 2025-03-20 16:39 |  |  | 2025-07-25 | 0 | 0 |  |  | BCCONST-669, BCCONST-670, BCCONST-671, BCCONST-819 | BCCONST-897, BCCONST-479 | 434 Units 40 flrs EPS7631 Tribe Mgmt 604-343-2601 [@Karanvir Singh¦mailto:KSingh@warringtonpci.com] (604-802-4147) - For all the building access (5) | Budget_Allocated | [12 empty] | 0¦i4g8jb: | [7 empty] | 9.2234e+18 | [19 empty] | Jan 9 - Waiting for BAA, Budget approved Feb 19 - Expected to hear back end of March for BAA approval | [6 empty] | 3 - Normal | [24 empty] | 40 | 434 | Backbone | [9 empty] | Surrey | 38750 | 34550
Construction | CONST-17428 | 160 Flemington Road, North York | Condo | Agreement |  | Unresolved | Unassigned | Lorna Kurok | Harvey Tran | 2020-12-09 16:16 |  | 2025-03-25 12:48 |  |  |  | 0 | 3 |  |  | CONST-17429, CONST-40402, CONST-40457 |  | Condo Constructed: 2019 We have a property interested, and would need to schedule a site visit. See below for details: *Pm Contact as March 21, 2025:* Jasleen Kaur ¦ Condominium Manager 160 Flemington Road Toronto, Ontario, M6A 0A9 T: 647-400-2389 E: [manager.yorkdaleresidences@gmail.com¦mailto:manager.yorkdaleresidences@gmail.com] [www.goldview.ca¦http://www.goldview.ca/] Goldview Property Management Ltd. Agents for and on behalf of TSCC No. 2724 *Property Address:* 160 Flemington Rd, North York ON M6A 0A9 *BB Link:* [https://buildings.beanfield.com/buildings/view/7765] *Property Manager:* Ed Johnson (647) 400-2389 [manager.yorkdaleresidences@gmail.com¦mailto:manager.yorkdaleresidences@gmail.com] | NUA+MA | [12 empty] | 0¦i2c7rz: | [7 empty] | 9.2234e+18 | [19 empty] | March 19, 2025 - CA Budget approved FTTB-01005, dated Feb 6, 2025, pending building agreements. March 25, 2025 - Created SAP Budget, Condo portion of Ca budget is $25,955, Restoration budget on Ca is $14,575, Condo has been added to the Finance Capex tracker, the status is listed as Agreement, due to pending agreement. | [6 empty] | 3 - Normal | [24 empty] | 15 | 314 | [5 empty] | https://buildings.beanfield.com/buildings/view/7765 |  | CONST-17428 | 3 - Normal |  | North York
Construction | CONST-40454 | 935 Sheppard Ave W, Toronto, The Town Plaza Condos | Condo | Agreement |  | Unresolved | Unassigned | Lorna Kurok | Lorna Kurok | 2025-03-25 10:18 |  | 2025-03-25 12:49 |  |  |  | 0 | 0 |  |  | CONST-40455, CONST-40456, CONST-40464 |  | Building Constructed in 2006 Units: 110 Floors: 9 Hi The following buildings have been approved via CA process but do not yet have agreements. Per the new initiative of getting a head start on these buildings prior to agreement, I am sharing the approved CA forms and budgets. Josh, we will require site contact information per discussion with Brad, and want you to give the thumbs up for the team to reach out for site visits recognizing we do not yet have an agreement in place. Buildings are as follows: 1) 1 Leila/160 Flemington 2) 935 Sheppard Ave West 3) 5225 Finch Ave E 4) 28 Freeland Street 5) 327 King St West 6) 2737 Keele St 7) 15-45 Strangford 8) 1480 Bathurst/500 St Clair Thanks Luke | [13 empty] | 0¦i5m13z: | [7 empty] | 9.2234e+18 | [19 empty] | March 19, 2025 - CA is approved, but the agreement is not signed and still in process. March 25, 2025 - Created Main ticket, added CA approved budget to SAP, Project has been added to the Financial Capex tracker. It's status is listed as Agreement as we expect this agreement will be signed but it is pending at this time. | [6 empty] | 3 - Normal | [24 empty] | 9 | 110 | [5 empty] | https://buildings.beanfield.com/buildings/view/2531 |  | CONST-40454 | 3 - Normal |  | Toronto
Construction | CONST-40460 | 327 King St W, Toronto, Empire Maverick | Condo | Agreement |  | Unresolved | Unassigned | Lorna Kurok | Lorna Kurok | 2025-03-25 12:36 |  | 2025-03-25 13:52 |  |  |  | 0 | 0 |  |  | CONST-40461, CONST-40462, CONST-40463 |  | Condo Constructed in 2024: Units 310 Floors 49 | [13 empty] | 0¦i5m24v: | [7 empty] | 9.2234e+18 | [19 empty] | March 19, 2025, CA budget approved by Beanfield board, Pending signed agreements. March 25, 2025 Ca budget created in SAP, Project added to Finance Capex tracker, Status is Agreement | [6 empty] | 3 - Normal | [24 empty] | 49 | 325 | [5 empty] | https://buildings.beanfield.com/buildings/view/20806 |  | CONST-40460 | 3 - Normal |  | Toronto
Construction | CONST-30680 | 500 St Clair Ave W / 1480 Bathurst St, Toronto | Condo | Agreement |  | Unresolved | James Mowers | Lorna Kurok | Jessica Markiewicz | 2022-09-29 12:26 |  | 2025-03-25 13:53 |  |  |  | 0 | 4 |  |  | CONST-30681, CONST-30682, CONST-30938, CONST-40458 | CONST-29234 | Constructed in 2010 Requested by Oliver Davies. Can you please queue up a site walk for 500 St Clair Ave W? BB Link: [https://buildings.beanfield.com/buildings/view/4770] PM Info: Michael Comeau Property Manager The Forest Hill ¦ TSCC No. 2088 500 St. Clair West, Toronto, ON M6C 1A8 D 416 651 7176 [tscc2088@gmail.com¦mailto:tscc2088@gmail.com] 530 St Clair W ([https://buildings.beanfield.com/buildings/view/3329]) is located directly across the street, and should be considered as part of the planning for this location. | [13 empty] | 0¦i3mh2v: | [7 empty] | 9.2234e+18 | [19 empty] | Jan 10/24 - Status updated to on-hold. Board refuses to grant access. March 19, 2025 - CA Budget approved, pending signed agreements. March 25, 2025 - CA Budget is added to SAP, Project is added to Financial Capex tracker, listed as Agreement. | [6 empty] | 3 - Normal | [24 empty] | 23 | 172 | [5 empty] | https://buildings.beanfield.com/buildings/view/4770 |  | CONST-30680 | 3 - Normal |  | Toronto
Construction | CONST-36563 | 5101 Dundas St W, Toronto - Evolution Condos | Condo | Agreement |  | Unresolved | James Mowers | Lorna Kurok | Olawale Olaniyan [X] | 2024-02-16 11:55 |  | 2025-03-28 14:34 |  |  |  | 0 | 0 |  |  | CONST-36566, CONST-36567, CONST-40560, CONST-40561 |  | Requested by Oliver Davies, When you have a moment, could you please queue up a site walk & OSP plan for 5101 Dundas St W? The “Evolution Condos” were constructed in 2014 and contain 145 residential units. I met with the board here last night and they are very interested in making Beanfield an option for their residents. This location is near-net to a number of active FBIP along Michael Power Pl, per the attached image. PM Info: *Anna Muchoki* Property Manager City Sites Property Management Agents on behalf of TSCC 2353 5101 Dundas Street West, Etobicoke, ON, M9A 5G8 *Tel:* 647-344-5420 *Email:* [management@evolutioncondos.ca¦mailto:management@evolutioncondos.ca] Note there is a townhome complex of 61 units that bounds this location to the immediate south. Despite the low number of units we should consider whether this location can be included as part of our plans, as there me be a connection that makes getting into 5101 Dundas St W easier ([https://buildings.beanfield.com/buildings/view/19919]) Thank you, | NUA+MA | [12 empty] | 0¦i4mos7: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2014 March 27, 2025 - CA budget was approved in March 26, 2025 capex meeting, Condo is pending agreements. (I apply the start when both the CA budget is approved and the agreements are signed. The start date determines how long it takes OSP const to complete the project. They can only start when we have both funds and agreements. March 28, 2025 - CA budget FTTB-00926 (dated march 19, 2025) was approved at the capex meeting on March 26, 2025, Condo is pending agreements. There is no restoration budget accounted for on this Ca. Project is listed on the 2027 restoration tracker. March 28, 2025 - CA budget is applied SAP, project is logged on Financial Capex tracker. March 28, 2025 - Pending Design, Construction, Riser, Splicing task codes until agreements are signed. March 28, 2025 - Applied to the ON Net schedule for the Month of October 2025. | [6 empty] | 3 - Normal | [24 empty] | 14 | 145 | [5 empty] | https://buildings.beanfield.com/buildings/view/3016 |  | CONST-36563 | 3 - Normal |  | Toronto
Construction | CONST-40465 | 284 King St E, Toronto, Bauhaus Condos | Condo | Agreement |  | Unresolved | Unassigned | Lorna Kurok | Lorna Kurok | 2025-03-25 13:09 |  | 2025-03-28 14:51 |  |  |  | 0 | 0 |  |  | CONST-40466, CONST-40566, CONST-40567 |  | Units - 205 Floors 30 *Marcel Fatovic* ¦ Project Manager ELCIUM Construction Management LAMB Development Corp. 778 King Street West Toronto, Ontario, M5V 1N6 C – 647-862-4044 | NUA+MA | [12 empty] | 0¦i5m29j: | [7 empty] | 9.2234e+18 | [19 empty] | March 25, 2025-James requested ticket, to store details pertaining to this location. March 27, 2025 - CA budget was approved at the March 26, 2025 capex meeting, project is pending agreements. March 28, 2025 - Project added to Financial Capex tracker. SAP budget Created. March 28, 2025 - Applied to the ON Net schedule for the Month of October 2025. March 28, 2025 - Design, Construction, Riser, Splicing task codes to be created when agreements are signed. | [6 empty] | 3 - Normal | [24 empty] | 30 | 205 | [5 empty] | https://buildings.beanfield.com/buildings/view/1445#!services |  | CONST-40465 | 3 - Normal |  | Toronto
Construction | CONST-28154 | 60 Fairfax Cres, Scarborough, Wilshire on the Green | Condo | Presentation |  | Unresolved | James Mowers | Lorna Kurok | Harvey Tran | 2022-04-28 15:12 |  | 2025-02-28 10:34 |  |  | 2025-08-12 | 0 | 0 |  |  | CONST-28155, CONST-28156, CONST-39808, CONST-39809, CONST-39810, CONST-39997, CONST-39998, CONST-39999, CONST-40000, CONST-40001, CONST-40002, CONST-40003, CONST-40004, CONST-40005, CONST-40006, CONST-40007, CONST-40008, CONST-40009, CONST-40010, CONST-40011 |  | Condo Constructed in 2011 *Property Manager Contact Information as of Jan 22, 2025* PM Contact Name: Aleksia Bijelic PM Contact #: 416-752-5700 PM Email Address: [management@60fairfax.org¦mailto:management@60fairfax.org] *Newbuilds email January 22, 2025* Please see attached the signed agreements and CA/Budget form for 60 Fairfax that was approved today at CAPEX. MDU Address: 60 Fairfax Cres City: Scarborough Building Name: Wilshire on the Green # of Units:{*}198{*} # of Floors: 7 Building Constructed Year: 2011 Building First Occupancy Date or or time period of year, (eg. Mid 2026) PM Contact Name: Aleksia Bijelic PM Contact #: 416-752-5700 PM Email Address: [management@60fairfax.org¦mailto:management@60fairfax.org] Type of Contract (Fibre agreement or NUA & MA): A+M Building linked to other Buildings: n/a Bulk Related: No Comp Services on agreement: 2 internet, 2 phone lines Thank you Luke h4. +*OLD PM Info:*+ *_Laura Wiley, R.C.M., OLCM_* Property Manager Newton Trelawney [manager@60fairfax.org¦mailto:manager@60fairfax.org] TSCC 2200 60 Fairfax Cres Scarborough, ON M1L 0E1 O- 416-752-5700 | [13 empty] | 0¦i3cnen: | [7 empty] | 9.2234e+18 | [19 empty] | Jan 22, 2025_CA approved FTTB-00517_ Jan 14, 2025 $36,805.95 Jan 30, 2025 - On Net Schedule change, seat with James to go over dates, he advised that Aug would be good hypothesis. | [6 empty] | 3 - Normal | [21 empty] | 2025-01-22 |  |  | 7 | 198 | [5 empty] | https://buildings.beanfield.com/buildings/view/16650 |  | CONST-28154 | 3 - Normal | 2025-09-03 | Scarborough
Construction | CONST-25883 | 1080 Bay Street, Toronto | Condo | Clean Up |  | Unresolved | Jessica Markiewicz | Jessica Markiewicz | Harvey Tran | 2021-11-29 14:29 |  | 2022-10-20 08:08 |  |  | 2022-11-04 | 0 | 1 |  |  | CONST-25884, CONST-25885, CONST-25947, CONST-26006, CONST-26007, CONST-26008, CONST-26009, CONST-26010, CONST-26011, CONST-26012, CONST-26013, CONST-26014, CONST-26015, CONST-26016, CONST-26017, CONST-26018, CONST-26078, CONST-26323, CONST-27298, CONST-27705 | CONST-5649 |  | Fiberstreamagreement | [12 empty] | 0¦i32cq7: | [7 empty] | 9.2234e+18 | [19 empty] | October 19th - Building on-net. | [6 empty] | 3 - Normal | [21 empty] | 2021-12-02 | [6 empty] | 20321 |  |  | https://buildings.beanfield.com/buildings/view/5713 |  | 500332 | 3 - Normal | 2022-04-15 |  | 11960 | 22610
Montreal Construction | MTLCONST-344 | Zibi Block 10 - 10 Rue Jos-Montferrand, Gatineau, QC | Condo | Clean Up |  | Unresolved | Danny Da Silva | Marianne Yanni | Oguz Avci [X] | 2020-05-25 10:01 |  | 2022-03-07 11:04 |  |  |  | 0 | 3 | _thumb_434431.png _thumb_434423.png _thumb_434425.png _thumb_434428.png _thumb_434429.png _thumb_434421.png _thumb_434424.png _thumb_434426.png _thumb_434430.png _thumb_434422.png _thumb_434432.png _thumb_434427.png _thumb_421419.png |  | MTLCONST-345, MTLCONST-6515, MTLCONST-6648, MTLCONST-6649, MTLCONST-6650, MTLCONST-6651, MTLCONST-6652, MTLCONST-6653, MTLCONST-6654 | CONST-11351, CONST-17442 | Address is: 10 Rue Jos-Montferrand Gatineau, QC KRISTEN JORGENSEN Project Manager Zibi Vertical Build Team 6 Booth St (Albert Island), Ottawa, ON K1R 6K8 C 613.864.9448 E {color:#0000ff}[kristen.jorgensen@zibi.ca¦mailto:kristen.jorgensen@zibi.ca]{color} | mtlcondo | [12 empty] | 0¦i1yrzb: | [7 empty] | 9.2234e+18 | [19 empty] | 2021.11.23 Site visit completed. This agreement will be a sub-agreement to a much larger agreement for the whole project. | [6 empty] | 3 - Normal
Construction | CONST-4429 | 68 Broadview Ave - Broadview Lofts | Condo | Clean Up |  | Unresolved | Harvey Tran | Jay Fernandes | Jay Fernandes | 2016-04-28 08:36 |  | 2021-02-18 15:26 |  |  | 2020-11-30 | 0 | 3 | _thumb_115560.png _thumb_79491.png _thumb_79492.png _thumb_79493.png _thumb_228445.png |  | CONST-4430, CONST-4431, CONST-4432, CONST-5156, CONST-6824, CONST-6825, CONST-6826, CONST-6832, CONST-6842, CONST-6844, CONST-7019, CONST-7020, CONST-7114, CONST-7570, CONST-7571, CONST-9584, CONST-10337, CONST-12417, CONST-12835, CONST-12836, CONST-12871, CONST-12919, CONST-13564, CONST-15507, CONST-15508, CONST-15509 | CONST-7552, CONST-4274, CONST-7405 | [14 empty] | 0¦i0gjxr: | [7 empty] | 9.2234e+18 | [19 empty] | Project back in action as of June 3, 2020 | [6 empty] | 3 - Normal | [28 empty] | 36000 |  |  | https://buildings.beanfield.com/buildings/view/452 |  | 500120 | 3 - Normal | 2020-09-30 | Carlaw (Leslieville) | 3000 | 4000
Construction | CONST-7399 | 629 King - Thompson Residences | Condo | Clean Up |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Russell Francey | 2018-01-29 10:42 |  | 2024-07-17 08:10 |  |  | 2024-02-28 | 0 | 0 |  |  | CONST-7400, CONST-7401, CONST-7402, CONST-27702, CONST-31477, CONST-31478, CONST-31479, CONST-31480, CONST-31481, CONST-31482, CONST-31483, CONST-31484, CONST-31485, CONST-31486, CONST-31487, CONST-31488, CONST-31489, CONST-31490, CONST-31491, CONST-35241, CONST-36270, CONST-36507, CONST-36508 |  | Sureka Scarlett Property Manager Elite Property Management Inc. 629 King St West Toronto, ON M5V 0G9 & 38 Stewart St Toronto, ON M5V 0H1 sscarlett@elitepminc.com Tel: 416-366-3251 | FSactive, Fiberstreamagreement | [12 empty] | 0¦i0zuzr: | [7 empty] | 9.2234e+18 | [19 empty] | November 30th - Route Drawing completed. February 10th - Manhole Survey completed. February 27th - Hydro Permit in progress. April 18/23 - Hydro permit conditionally granted. July 12/23 - Hydro permit granted. Aug 28/23 - Cable pull only. Construction not required. Jan 18/24 - Conduit build scheduled for Jan 24th. Cable pull scheduled for Feb 5th Jan 22/24 - Conduit build PO sent Jan 25/24 - Conduit build completed. Invoice received. Jan 31/24 - Cable pull scheduled for Feb 5th Feb 05/24 - Cable pull completed. Pending SOW Feb 13/24 - Splicing scheduled for Feb 22nd - 23rd Feb 21/24 - Splicing completed Feb 28/24 - Building On-Net | [6 empty] | 3 - Normal | [19 empty] | Internal |  | 2022-10-26 |  |  |  |  | Integration | 2024-02-28 | 41475 |  |  | https://buildings.beanfield.com/buildings/view/4163 |  | 500490 | 3 - Normal | 2024-02-23 | King West | 624 | 0
Construction | CONST-9777 | King West Townhomes - 1 - 47 Sudbury | Condo | Clean Up |  | Unresolved | Harvey Tran | Olawale Olaniyan [X] | Russell Francey | 2019-02-06 12:28 |  | 2024-07-18 14:50 |  |  | 2024-07-18 | 0 | 0 | _thumb_403502.png _thumb_403890.png |  | CONST-9778, CONST-20236, CONST-24305, CONST-24306, CONST-24307, CONST-24308, CONST-24309, CONST-24310, CONST-24311, CONST-24312, CONST-24313, CONST-24314, CONST-24315, CONST-25072, CONST-25406, CONST-25984, CONST-30320, CONST-30398, CONST-36224, CONST-36225, CONST-36488 | NET-37999, CONST-3134, CONST-30055, CONST-27867 | Lily Barbosa ¦ Senior Condominium Manager BA, RCM Goldview Property Management Ltd. 51 Toro Road, Suite 200 ¦Toronto, Ontario ¦ M3J 2A4 t: 416-630-1234 ext 249 ¦ f: 416-630-3132 e: lily@goldview.ca ¦ w: goldview.ca | Fiberstreamagreement | [12 empty] | 0¦i1fmf3: | [7 empty] | 9.2234e+18 | [19 empty] | September 13th - Only ISP required. Will be fed from 8 Dovercourt and 12 Sudbury. Oct 12/23 - Due dates updated. Jan 23/24 - Due dates updated Jan 26/24 - Cable pull completed. Jan 31/23 - Splicing in progress Feb 08/24 - Transferred $1,920.00 (splicing quote) from construction budget to splicing budget. Feb 12/24 - Splicing PO sent to Litewave. Splicing in progress Feb 14/24 - SOW redesign required. Delay to splicing. Feb 16/24 - Migration required to bring building On-Net. May 9th, 2024 - Still pending SOW due to migration. Requested an update from GIS. Project due date is possibly pushed back if migration delays. Jun 28th, 2024 - Project is pushed back to July as the OLT insertion needs to be completed in prior (NET-37999) Jul 11th, 2203 - OLT insertion completed. Our team will schedule to get back to complete the cross connect. Due date is updated to July 19th Jul 18th, 2024 - Building is onnet. | [6 empty] | 3 - Normal | [19 empty] | N/A |  | 2022-09-13 | [5 empty] | 2024-07-18 | 10893 |  |  | https://buildings.beanfield.com/buildings/view/3257 |  | 500323 | 3 - Normal | 2023-11-17 | West King West | 1200
Construction | CONST-29192 | 18 Kenaston Gardens, North York - Rockefeller on Bayview | Condo | Clean Up |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Jessica Markiewicz | 2022-07-11 15:06 |  | 2023-12-22 10:12 |  |  | 2023-12-21 | 0 | 0 | _thumb_792977.png |  | CONST-29193, CONST-29194, CONST-32114, CONST-32153, CONST-32154, CONST-32155, CONST-32156, CONST-32157, CONST-32158, CONST-32159, CONST-32160, CONST-32161, CONST-32162, CONST-32163, CONST-32164, CONST-32165, CONST-32166, CONST-35782, CONST-35783, CONST-35828, CONST-38085 | CONST-29195, CONST-29198, CONST-29201, CONST-32106, CONST-24117, CONST-29189, CONST-30959, CONST-29578 | Requested by Jay Fernandes Hi, I’ve gone through the remaining Fibrestream condos we have agreements for in the GTA and have grouped them in a way that I think makes sense for site visits and builds. There will be another list coming of buildings that don’t really fall into groups. Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. There are some current backbone (Sheppard) or NPOP (960 Lawrence) projects that will need to be completed to connect these but this will get everything into the system. Thanks! *PM: Alex Cvetkovic* *acvetkovic@mrcm.ca* *416.987.8200* | Fiberstreamagreement, Sheppard | [12 empty] | 0¦i3h80n: | [7 empty] | 9.2234e+18 | [19 empty] | November 28th - Project initiated. Design and permits to be in progress. June 16/23 - City permit on backbone build CONST-32115 Oct 12/23 - Construction scheduled to start Oct 18th on CONST-32106 Nov 20/23 - Construction complete. Conduit build scheduled for Dec 1st. Cable pull scheduled for Dec 18th Nov 24/23 - Cable pull rescheduled for Dec 6th Dec 04/23 - Conduit build completed. Dec 07/23 - Cable pull completed. Dec 08/23 - Riser Build Complete all Panels spliced, ISP remaining Dec 18/23 - OSP splicing completed Dec 21/23 - Building On-Net | [6 empty] | 3 - Normal | [27 empty] | 2023-12-21 | 6269 |  |  | https://buildings.beanfield.com/buildings/view/15350 |  | 500516 | 3 - Normal | 2023-11-24 |  | 5441 | 17190
Construction | CONST-29421 | 39 Brant St, Toronto - The Brant Park | Condo | Clean Up |  | Unresolved | Harvey Tran | Olawale Olaniyan [X] | Jessica Markiewicz | 2022-07-13 13:05 |  | 2024-11-11 14:49 |  |  | 2024-06-14 | 0 | 0 |  |  | CONST-29422, CONST-29423, CONST-30579, CONST-30580, CONST-30911, CONST-30912, CONST-30913, CONST-30923, CONST-30924, CONST-30925, CONST-30926, CONST-30927, CONST-30928, CONST-30929, CONST-30930, CONST-30931, CONST-30932, CONST-30933, CONST-35101, CONST-35103, CONST-35104, CONST-35364, CONST-35776, CONST-36954, CONST-37282, CONST-37290, CONST-38833, CONST-38834 |  | Requested by Jay Fernandes Hi, These are the Fibrestream condos we have agreements for that don’t seem to fit into any groups (although I maybe wrong). Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. ¦Group¦Building Name¦Address¦suites¦ ¦Independent¦Eleven Superior¦11 Superior AVE Etobicoke ON M8V 0A7¦130¦ ¦Independent¦The James Club¦1135 Royal York RD Toronto ON M9A 4A7¦209¦ ¦Independent¦Independence Way¦115 George Appleton WAY North York ON M3M 2E9¦244¦ ¦Independent¦Danforth Village Estates¦1346 Danforth RD Toronto ON M4J1M9¦249¦ ¦Independent¦beBloor¦1369 Bloor ST Toronto ON M6P 4J3¦238¦ ¦Independent¦Ion Condos¦15 James Finlay WAY Toronto ON M3M 0B3¦200¦ ¦Independent¦Paradice at the Oasis¦1720 Eglinton AVE Toronto ON M4A2X9¦190¦ ¦Independent¦Havenon the Bluffs¦20 East Haven DR Toronto ON M1N1M2¦259¦ ¦Independent¦Kilgour Estate II¦21 Burkebrook PL Toronto ON M4G4K8¦228¦ ¦Independent¦Canvas Condos¦2301 Danforth AVE Toronto ON M4C 1L5¦156¦ ¦Independent¦3018 Yonge Condos¦3018 Yonge ST Toronto ON M4N 0A5¦188¦ ¦Independent¦Cranbrooke Village¦35 Saranac BLVD Toronto ON M6A 2G4¦341¦ ¦Independent¦39 Brant St¦39 Brant ST Toronto ON M5V0M8¦236¦ ¦Independent¦The Wave¦4 Elsinore PATH Toronto ON M8V 4G7¦185¦ ¦Independent¦Clock Tower Lofts¦700 King ST Toronto ON M5V 2Y6¦216¦ ¦Independent¦The Boot¦75 Dalhousie ST Toronto ON M5B 2R9¦153¦ ¦Independent¦B.Street Condos¦783 Bathurst ST Toronto ON M6G 1K1¦ ¦ ¦Independent¦85 Bloor St¦85 Bloor ST Toronto ON M4W3G9¦252¦ | Bolton, FSactive, Fiberstreamagreement | [12 empty] | 0¦i3hg1z: | [7 empty] | 9.2234e+18 | [19 empty] | November 30th - City and Bell permit in progress. May 16/23 - Bell Permit submitted. Aug 16/23 - Bell permit rejected. We have to go through Hydro. Due dates updated. Aug 22/23 - Route drawing completed Nov 07/23 - Manhole survey completed Dec 06/23 - Hydro permit granted Dec 12/23 - City permit approved. Mar 05/24 - Construction scheduled to start Mar 8th. PO sent to John for Sentrex Mar 13/24 - PO sent to John for Sentrex Mar 27/24 - Construction completed. Due dates updated. Apr 01/24 - Cable pull scheduled for May 17th Apr 08/24 - Conduit build PO sent Apr 23/24 - Conduit build completed Apr 25/24 - Conduit build invoice received May 7th, 2024 - Cable pull scheduled May 7th, we might be able to get this building onnet in May if SOW is provided on time, still pending SOW. May 17th, 2024 - Cable pull is in progress and should be completed today. Splicing is ready to be scheduled Jun 14th, 2024 - Testing completed. Building is onnet. | [6 empty] | 3 - Normal | [19 empty] | Internal |  | 2022-10-05 |  |  |  | 243 | Integration | 2024-06-14 | 41318 |  |  | https://buildings.beanfield.com/buildings/view/4278 |  | 500468 | 3 - Normal | 2023-08-11 | Toronto | 4116 | 12120
Construction | CONST-34238 | 2 Old Mill Dr, Etobicoke | Condo | Clean Up |  | Unresolved | Harvey Tran | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2023-06-06 13:48 |  | 2024-11-12 10:08 |  |  | 2024-07-29 | 0 | 1 |  |  | CONST-34239, CONST-34240, CONST-34241, CONST-34243, CONST-34244, CONST-34245, CONST-34246, CONST-34247, CONST-34248, CONST-34249, CONST-34250, CONST-34251, CONST-35372, CONST-36964, CONST-37831, CONST-37908, CONST-37909, CONST-38398, CONST-38523 | CONST-29130 | *NEW PM Info:* {+}Sonja Boznic Phone: 647-345-4386 Email: [twooldmill.pm@delcondo.com¦mailto:twooldmill.pm@delcondo.com]{+}** {+} *PM: Natalie Santos* *oneoldmill.pm@delcondo.com* *647.350.0851* | Bolton, Fiberstreamagreement | [12 empty] | 0¦i4345r: | [7 empty] | 9.2234e+18 | [19 empty] | June 06/23 - Budget and permits on CONST-29130 Mar 13/24 - Construction scheduled to start Apr 15th Apr 08/24 - Conduit build PO sent Apr 17/24 - Cable pull scheduled for May 7th Apr 18/24 - Construction completed Apr 24/24 - Conduit build completed Jul 2nd, 2024 - Cable pull completed. Still pending SOW for splicing testing. Jul 11th, 2024 - Splicing is tentatively scheduled Jul 12th. Jul 29th, 2024 - Testing completed. Building is onnet. | [6 empty] | 3 - Normal | [19 empty] | Internal |  | 2022-10-19 | [5 empty] | 2024-07-29 |  |  |  | https://buildings.beanfield.com/buildings/view/8822 |  | CONST-29130(sub) | 3 - Normal | 2024-01-26
Construction | CONST-33850 | 33 Helendale Ave, Toronto - Whitehaus Condos | Condo | Clean Up |  | Unresolved | Lorna Kurok | Lorna Kurok | Olawale Olaniyan [X] | 2023-05-05 12:54 |  | 2024-11-07 14:16 |  |  | 2024-10-31 | 0 | 1 |  |  | CONST-33851, CONST-33852, CONST-34009, CONST-36417, CONST-36418, CONST-36419, CONST-36420, CONST-36421, CONST-36422, CONST-36423, CONST-36424, CONST-36425, CONST-36426, CONST-36427, CONST-36428, CONST-36429, CONST-36430, CONST-37236, CONST-38204, CONST-38414, CONST-38415, CONST-39033, CONST-39034 |  | Requested by Oliver Davies, Can you please queue up a site walk for 33 Helendale Ave / the Whitehaus Condominiums? Fortunately, there has been a recent change in management here and the wheels are in motion for Beanfield’s access to be approved for the condominium units. This location shares space with the commercial units at 2360 Yonge St. Existing JIRA ticket: CONST-30317 PM Info: *Eraldo Dida* Property Manager TSCC 2851 – Whitehaus Condominium T: (416) 546-3073 [eraldo@iconpm.ca¦mailto:eraldo@iconpm.ca] + June Arnold Property Administrator [june@iconpm.ca¦mailto:june@iconpm.ca] Thank you, | NUA+MA | [12 empty] | 0¦i40ovj: | [7 empty] | 9.2234e+18 | [19 empty] | Feb 05/24 - Project initiated. Design and permits in progress. Feb 07/24 - Route drawing uploaded Aug 21st, 2024 - Cable pull scheduled for Sep 6th. Moving up project due date to Oct 2024. Sept 9, 2024 Cable pull Asbuilt completed Sept 9, 2024 - Riser Build Completed - Panels and ISP Splicing Remains Sept 11, 2024_Design Note_Asbuilt added to PM Sept 19, 2024_ All panels prepped and spliced Oct 30, 2024 - Building completed. | [6 empty] | 3 - Normal | [19 empty] | N/A |  | 2024-02-05 |  |  |  | 384 |  | 2024-10-31 | 10303 |  |  | https://buildings.beanfield.com/buildings/view/6076 |  | CONST-33850 | 3 - Normal | 2024-11-29 | Toronto | 7643 | 16370
Construction | CONST-29243 | 15 Northtown Way, North York - Triomphe-East Tower | Condo | Clean Up |  | Unresolved | Lorna Kurok | Lorna Kurok | Jessica Markiewicz | 2022-07-11 16:05 |  | 2024-11-18 08:59 |  |  | 2024-11-15 | 0 | 0 | _thumb_1001766.png |  | CONST-29244, CONST-29245, CONST-34543, CONST-34611, CONST-34612, CONST-34613, CONST-34614, CONST-34615, CONST-34616, CONST-34617, CONST-34618, CONST-36819, CONST-36984, CONST-38678, CONST-39178, CONST-39179 | CONST-32598, CONST-34674, CONST-29264, CONST-32601 | Requested by Jay Fernandes Hi, I’ve gone through the remaining Fibrestream condos we have agreements for in the GTA and have grouped them in a way that I think makes sense for site visits and builds. There will be another list coming of buildings that don’t really fall into groups. Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. There are some current backbone (Sheppard) or NPOP (960 Lawrence) projects that will need to be completed to connect these but this will get everything into the system. Thanks! *PM: Eddy Chung* *triomphe.pm@15northtownway.ca* *416.224.8388* | FSactive, Fiberstreamagreement, Yonge&Finch | [12 empty] | 0¦i3h8mv: | [7 empty] | 9.2234e+18 | [19 empty] | June 28/23 - Only ISP work required. OSP will be completed on CONST-32601 Mar 05/24 - Budget updated Sept 16th - Pm has asked us to hold off the start of our build until Oct 21st Nov 15, 2024 - Building is ON Net | [6 empty] | 3 - Normal | [19 empty] | N/A | 2024-11-15 | 2023-06-28 |  |  |  | 359 | Integration | 2024-11-15 | 5930 |  |  | https://buildings.beanfield.com/buildings/view/3820 |  | CONST-29243 | 3 - Normal | 2024-04-26 | North York | 5428 | 11400
Construction | CONST-32601 | 10 Northtown Way -Grande Triomphe | Condo | Clean Up |  | Unresolved | Lorna Kurok | Lorna Kurok | Denise King | 2023-01-05 13:46 |  | 2024-11-18 08:58 |  |  | 2024-11-15 | 0 | 3 |  |  | CONST-32602, CONST-32603, CONST-34546, CONST-34584, CONST-34585, CONST-34586, CONST-34587, CONST-34588, CONST-34589, CONST-34590, CONST-34591, CONST-34592, CONST-34593, CONST-34594, CONST-34595, CONST-34597, CONST-34598, CONST-35377, CONST-38270, CONST-38271, CONST-38689, CONST-39180, CONST-39181 | CONST-32598, CONST-34674, CONST-29243, CONST-29264 | Requested by Oliver Davies: PM Info: ¦Mussie (Moses) Siele¦ ¦416-229-1800¦ ¦[grandtriomphe.pm¦http://grandtriomphe.pm/]@delcondo.com¦ ¦Condominium Manager¦ | FSactive, Fiberstreamagreement | [12 empty] | 0¦i3s6jr: | [7 empty] | 9.2234e+18 | [19 empty] | June 28/23 - Project initiated. Design & Permit in progress. Feb 20/24 - City permit completed on CONST-35102 Mar 05/24 - Permits and OSP construction will be completed on Doris Ave Condo Backbone. Budget updated Sept 5, 2024 - Cable pull drawing required. Sept 10, 2024 - Cable Pull completed Sept 11, 2024 - Cable pull asbuilt completed Nov 15, 2024 - Building is ON Net | [6 empty] | 3 - Normal | [19 empty] | N/A | 2024-11-15 | 2023-06-28 |  |  |  | 398 | Integration | 2024-11-15 | 8720 |  |  | https://buildings.beanfield.com/buildings/view/15743 |  | CONST-32601 | 3 - Normal | 2024-10-31 | North York | 6577 | 11400
Construction | CONST-29264 | 5 Northtown Way, North York - Triomphe | Condo | Clean Up |  | Unresolved | Lorna Kurok | Lorna Kurok | Jessica Markiewicz | 2022-07-11 16:22 |  | 2024-11-18 08:59 |  |  | 2024-11-15 | 0 | 0 | _thumb_1001767.png |  | CONST-29265, CONST-29266, CONST-34544, CONST-34603, CONST-34604, CONST-34605, CONST-34606, CONST-34607, CONST-34608, CONST-34609, CONST-34610, CONST-36818, CONST-36983, CONST-38888, CONST-39182, CONST-39183 | CONST-32598, CONST-34674, CONST-29243, CONST-32601 | Requested by Jay Fernandes Hi, I’ve gone through the remaining Fibrestream condos we have agreements for in the GTA and have grouped them in a way that I think makes sense for site visits and builds. There will be another list coming of buildings that don’t really fall into groups. Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. There are some current backbone (Sheppard) or NPOP (960 Lawrence) projects that will need to be completed to connect these but this will get everything into the system. Thanks! *PM: Shekhar Nagarajan* *triomphe1.pm@delcondo.com* *416.224.8388* | FSactive, Fiberstreamagreement, Yonge&Finch | [12 empty] | 0¦i3h8yv: | [7 empty] | 9.2234e+18 | [19 empty] | June 28/23 - Only ISP work required. OSP will be completed on CONST-32601 Mar 05/24 - Budget updated Sept 16th - PM has asked that we not work on our riser build until Oct 21st Nov 15, 2024 Building is On Net. | [6 empty] | 3 - Normal | [19 empty] | N/A | 2024-11-15 | 2023-06-28 |  |  |  | 339 | Integration | 2024-11-15 | 5930 |  |  | https://buildings.beanfield.com/buildings/view/4744 |  | CONST-29264 | 3 - Normal | 2024-04-26 | North York | 5162 | 11400
Construction | CONST-34451 | 880 Grandview Way - Parkside at Northtown III | Condo | Clean Up |  | Unresolved | Lorna Kurok | Lorna Kurok | Olawale Olaniyan [X] | 2023-06-19 15:02 |  | 2024-11-21 09:13 |  |  | 2024-11-20 | 0 | 1 |  |  | CONST-34452, CONST-34453, CONST-34547, CONST-34627, CONST-34628, CONST-34629, CONST-34630, CONST-34631, CONST-34632, CONST-34633, CONST-34634, CONST-34635, CONST-34636, CONST-34637, CONST-34638, CONST-34639, CONST-34640, CONST-35370, CONST-38275, CONST-38276, CONST-38383, CONST-39279 | CONST-34674 | Requested by Oliver Davies, Units 148 Can you please create a new site walk ticket for James at 880 Grandview Way? This location is active on a third-party circuit w/ FibreStream. Note: There is another condo tower and townhomes in this complex of buildings. 880 Grandview is the only location that will not require a pre-wire. +*New PM Info:*+ Frances Tsoi [northtown1.pm@delcondo.com¦mailto:northtown1.pm@delcondo.com] ¦416-224-2373¦ +*Old PM Info:*+ ¦Adam Rapp¦ ¦[northtown1.pm@delcondo.com¦mailto:northtown1.pm@delcondo.com]¦ ¦416-224-2373¦ Thank you, | FSactive, Fiberstreamagreement | [12 empty] | 0¦i445zz: | [7 empty] | 9.2234e+18 | [19 empty] | June 28/23 - Project initiated. Design & Permit in progress. Feb 14/24 - City permit completed on CONST-35102 Mar 05/24 - Permits and OSP construction will be completed on Doris Ave Condo Backbone. Budget updated Sep 9, 2024 Sep 9, 2024_ PM has requested we do not complete any internal work until October thumbs_down.png. Cable pull will need to be pushed back until we've installed conduit. Sep 2024 - ISP splicing details attached Sep 9, 2024_ We need to move the due date of this building to November, because the Building PM does not want internal work started until October Oct 30, 2024 - Cable pull completed Nov 14, 2024 - Riser Panels - All of the panels are dressed and prepped. Nov 20, 2024 - Building ON Net Nov 20, 2024 - Lorna to reconcile SAP | [6 empty] | 3 - Normal | [19 empty] | N/A |  | 2023-06-28 |  |  |  | 148 | Integration | 2024-11-20 | 8616 |  |  | https://buildings.beanfield.com/buildings/view/3319 |  | CONST-34451 | 3 - Normal | 2024-04-26 | Toronto | 4251 | 13500
Construction | CONST-32240 | 21 Balmuto St, Toronto | Condo | Clean Up |  | Unresolved | Lorna Kurok | Lorna Kurok | Jessica Markiewicz | 2022-12-06 11:50 |  | 2024-11-25 08:50 |  |  | 2024-11-22 | 0 | 3 |  |  | CONST-32241, CONST-32242, CONST-32289, CONST-35803, CONST-35804, CONST-35805, CONST-35806, CONST-35807, CONST-35808, CONST-35809, CONST-35810, CONST-35811, CONST-35812, CONST-35813, CONST-35815, CONST-35816, CONST-35817, CONST-37934, CONST-38493, CONST-38494, CONST-39134, CONST-39135 |  | *New Pm Info:* Ahmed Kassas [ahmed.kassas@fsresidential.com¦mailto:ahmed.kassas@gmail.com] phone :[647-981-3500¦tel:647-981-3500] Old PM info: ¦*MARTIN RAMINENI* Property Manager 2645 Skymark Ave. \¦ Missisauga, ON L4W 5A4 Cell phone [437-219-4050\¦tel:437-219-4050] [martin.ramineni@fsresidential.com¦mailto:martin.ramineni@fsresidential.com]¦ PM Info: *Nik Pinku,* OLCM Property Manager 2645 Skymark Avenue, Suite 101 ¦ Mississauga, ON L4W 4H2 Direct [416.928.2258¦tel:416.928.2258] ¦ Toll-Free [1.855.244.8854¦tel:1.855.244.8854] Email [nikola.pinku@fsresidential.com¦mailto:nikola.pinku@fsresidential.com] [*www.fsresidential.com*¦http://www.fsresidential.com/] ** PM is on site Tuesdays & Thursdays, site super is available throughout the week otherwise. | NUA+MA | [12 empty] | 0¦i3qq5z: | [7 empty] | 9.2234e+18 | [19 empty] | Nov 22/23 - Project initiated. Design and Permits in progress. Feb 08/24 - Route drawing uploaded. Oct 16, 2024 Cable pull scheduled for Nov 5, 2029 Nov 6, 2024 - Cable pull Asbuilt attached Nov 8, 2024 All panels prepped and spliced Nov 2024 - OSP Splicing is assigned to Contractor Litewave due to Hydro. Nov 22, 2024 - Project is ON Net. Need to close Finances, that is why it is in cleanup | [6 empty] | 3 - Normal | [19 empty] | N/A |  | 2023-11-22 |  |  |  | 139 |  | 2024-11-22 | 21369 |  |  | https://buildings.beanfield.com/buildings/view/12836 |  | CONST-32240 | 3 - Normal | 2024-10-25 | Toronto | 3545 | 13785
Construction | CONST-30240 | 425 Front St E, Toronto - Block 10 condos (BULK) | Condo | Clean Up |  | Unresolved | Harvey Tran | Olawale Olaniyan [X] | Jessica Markiewicz | 2022-08-26 14:46 |  | 2024-11-25 12:42 |  |  | 2024-05-31 | 0 | 1 |  |  | CONST-30241, CONST-30242, CONST-30243, CONST-31752, CONST-31753, CONST-31754, CONST-31755, CONST-31756, CONST-31757, CONST-31758, CONST-31759, CONST-31760, CONST-31761, CONST-31762, CONST-31763, CONST-31764, CONST-33905, CONST-33906, CONST-37317, CONST-37708, CONST-37711, CONST-38521, CONST-38522, CONST-39428 | CONST-33754, CONST-28348 | Requested by Todd Hofley. Hey! This is a new condo that falls under the CNSA Waterfront agreement (bulk) and is being built Eliis Don. The developer is Dundee/Kilmer. Site Contact is: [ovivas@ellisdon.com¦mailto:ovivas@ellisdon.com] BB: [https://buildings.beanfield.com/buildings/view/16197] Address is: 425 Front St. East Toronto, ON M5A 1G9 Agreement is already signed so full JIRA const ticket w subtasks can be populated. | BulkDeal | [12 empty] | 0¦i3kam7: | [7 empty] | 9.2234e+18 | [19 empty] | November 22nd - City permit granted and expires May 22nd, 2023. Mar 29/23 - Cable Pull scheduled for Apr 6 Mar 30/23 - Building still under construction Apr 11/23 - Due date changed. The builder needs the building on net to get elevator lines and other base building services before occupancy. Apr 12/23 - Cable Pull scheduled for Apr 19th. Apr 19/23 - Cable Pull completed. Apr 28/23 - Pending SOW. May 24/23 - SOW updated. May 30/23 - Pending ISP SOW June 06/23 - Still pending ISP SOW, due date updated June 19/23 - Still pending ISP SOW. June 27/23 - ISP SOW can not be completed without a riser diagram or order for required service. Building has been asked to put in an order for required service. Due dates updated. July 13/23 - Building occupancy target is for first quarter of 2024. Due dates updated. May 3rd, 2024 - Riser cable pull is in progress. ISP splicing to be scheduled after the riser pull is completed. May 7th, 2024 - We are still waiting for fire rated plywood to be installed throughout the riser to finish our panel install. ISP splicing is still pending schedule. May 31st, 2024 - Testing completed. Building is onnet. Only pending pre-wiring work as the building is not ready yet. | [6 empty] | 3 - Normal | [19 empty] | External |  | 2022-11-04 |  |  | 13 | 206 |  | 2024-05-31 | 26971 |  |  | https://buildings.beanfield.com/buildings/view/16197 |  | 500501 | 3 - Normal | 2023-08-11 |  | 45861 | 14760
Construction | CONST-24117 | 7 Kenaston Gardens, Toronto | Condo | Clean Up |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Harvey Tran | 2021-07-28 11:51 |  | 2024-12-11 11:09 |  |  | 2024-02-16 | 0 | 1 |  |  | CONST-24118, CONST-24125, CONST-24126, CONST-32269, CONST-35195, CONST-36102, CONST-36104, CONST-36105, CONST-36106, CONST-36107, CONST-36108, CONST-36109, CONST-36110, CONST-36111, CONST-36112, CONST-36208, CONST-36352, CONST-36353, CONST-37166 | CONST-29195, CONST-29198, CONST-29201, CONST-32106, CONST-29189, CONST-29192, CONST-30959, CONST-29578 | *Property Address:* 7 Kenaston Gdns, Toronto ON M2K 1G7 *NEW PM Info:* *Christy* *Zong* Property Manager Times Property Management Inc Cell #: 647-971-3321 christy@timesproperty.ca *Property Manager:* Sonia Tabrizi Times Property Management Inc. 350 Hwy 7 East, Suite PH7 Richmond Hill, ON L4B 3N2 T: 647-347-2488 ¦ F: 905-882-0518 Email: [sonia@timesproperty.ca¦mailto:sonia@timesproperty.ca] | NUA+MA | [12 empty] | 0¦i2trv3: | [7 empty] | 9.2234e+18 | [19 empty] | Pending agreement. Aug 23/23 - Still pending building agreement Dec 27/23 - Building agreement received. Construction completed. Jan 15/23 - Cable pull scheduled for Jan 17th Jan 17/24 - Cable pull completed Feb 05/24 - Splicing scheduled for Feb 12th - 15th Feb 15/24 - Splicing completed Feb 16/24 - Building On-Net | [6 empty] | 3 - Normal | [27 empty] | 2024-02-16 | 1169 |  |  | https://buildings.beanfield.com/buildings/view/7261 |  | CONST-24117 | 3 - Normal | 2024-02-23 |  | 4075 | 11360
Construction | CONST-33073 | 32 Camden St, Toronto | Condo | Clean Up |  | Unresolved | Lorna Kurok | Lorna Kurok | Olawale Olaniyan [X] | 2023-02-14 08:17 |  | 2024-12-11 11:40 |  |  | 2024-09-13 | 0 | 1 | _thumb_970621.png |  | CONST-33074, CONST-33075, CONST-33341, CONST-35584, CONST-35585, CONST-35586, CONST-35587, CONST-35589, CONST-35590, CONST-35591, CONST-35592, CONST-35593, CONST-35594, CONST-35595, CONST-35596, CONST-35597, CONST-35598, CONST-37751, CONST-38044, CONST-38045, CONST-38611, CONST-38883 | PUR-39440, CONST-33047 | Requested by Oliver Davies Can you please queue up a site walk for 32 Camden St? This visit should be completed in conjunction with 42 Camden St (CONST-33047) *Bell has also submitted a proposal to implement fibre to the units in this location. if the build here is doable we have a good chance of preventing that from happening. Site Contact: *Enrique* (Site Super) 647.622.5501 (Hours 8am-3pm) OR (if required) *New PM* Bal Bal@tsems.com *Malcolm R. Marcus, B. Econ., O.L.C.M., R.C.M., A.C.C.I.* {*}Licensed Condominium Manager{*}** *President* ** *T. 905. 764.9166 x 30* *e. {color:#0000ff}[malcolm@tsems.com¦mailto:malcolm@tsems.com]{color}* Thank you, | NUA+MA | [12 empty] | 0¦i3v3pr: | [7 empty] | 9.2234e+18 | [19 empty] | Oct 25/23 - Project initiated. Design and permits in progress. Feb 08/24 - Route drawing uploaded. Aug 7, 2024 - conduit build completed. Aug 27 ,2024 - Riser Build Complete - ISP and Panels Remain to be spliced Sept 6, as-built attached to cable PMID#70063 Sept 11, 2024_Splicing Lite wave submitted Test Results & CCF As built for Kevin's review. Completed and tested by Litewave, OTDR Trace attaced. Sept 12, 2024_All panels prepped and Spliced. Sept 13, 2024_OTDR Ruby testing completed Sept 13, 2024_ On Net email sent, feed from 425 Adelaide St W - NPOP Sep 17, 2024_On Net email sent. | [6 empty] | 3 - Normal | [19 empty] | N/A |  | 2023-10-25 |  |  | 12 | 87 |  | 2024-09-13 | 10919 |  |  | https://buildings.beanfield.com/buildings/view/1430 |  | CONST-33073 | 3 - Normal | 2024-07-26 | Toronto | 2384 | 8415
Construction | CONST-36641 | 11 Michael Power Pl, Etobicoke - Port Royal Place Ⅲ | Condo | Clean Up |  | Unresolved | Lorna Kurok | Lorna Kurok | Olawale Olaniyan [X] | 2024-02-26 12:40 |  | 2024-12-11 11:53 |  |  | 2024-08-29 | 0 | 1 | _thumb_931980.png _thumb_931982.png _thumb_931981.png |  | CONST-36643, CONST-36644, CONST-36753, CONST-37492, CONST-37493, CONST-37494, CONST-37495, CONST-37496, CONST-37497, CONST-37498, CONST-37499, CONST-37500, CONST-37501, CONST-37502, CONST-37503, CONST-37504, CONST-38040, CONST-38086, CONST-38180, CONST-38536, CONST-38537 | CONST-36642, CONST-29111, CONST-36748 | Requested by Oliver Davies, The boards at TSCC 1576 are TSCC 1544 are now (finally) in the process of reviewing an addition of Beanfield for their residents. Could you kindly queue up an OSP plan & site walk for these locations? Both locations share a common parking level. 11 Michael Power Pl (Port Royal Place III) (TSCC 1576) (149 units) 15 Michael Power Pl (Port Royal Place II) (TSCC 1544) (140 units) PM Info: *Harmick Artounian OLCM* *Condominium Manager* *Phone:* 416-231-4948 *Fax:* 416-231-3264 {*}Site Office{*}: 15 Michael Power Place Toronto,Ontario M9A 5G3 *Email:* [PortRoyal.PM@delcondo.com¦https://mail.accesspad.com/owa/redir.aspx?C=7ad12da260b14ebda35cc26cfd6e2188&URL=mailto%3acmercer%40delcondo.com] *Web:* [www.DelPropertyManagement.com¦https://mail.accesspad.com/owa/redir.aspx?C=7ad12da260b14ebda35cc26cfd6e2188&URL=http%3a%2f%2fwww.delpropertymanagement.com%2f] *Agents for and on behalf of TSCC 1544 & 1576* Nearby, we should also consider [17 Michael Power Pl / Port Royal Place I (TSCC 1518)¦https://buildings.beanfield.com/buildings/view/4739]. We do not have the go-ahead for a site walk here yet, however, the above PM has noted that if construction work is required to get into 11 & 15 MP, permission from 17 MP will also be needed. Thank you, | NUA+MA | [12 empty] | 0¦i4n6u7: | [7 empty] | 9.2234e+18 | [19 empty] | June 5th, 2024 - City permit is ready, locates to be submitted. Aug 19th, 2024 - Cable pull completed. Splicing will be scheduled soon once SOW is available this week. Aiming to get this building onnet in Aug 2024. Aug 29, 2024 - On Net email notices sent. | [6 empty] | 3 - Normal | [21 empty] | 2024-05-20 | [5 empty] | 2024-08-29 | 32908 |  |  | https://buildings.beanfield.com/buildings/view/2702 |  | CONST-36641 | 3 - Normal |  | Etobicoke | 4189
Construction | CONST-30055 | 41 Dovercourt Rd, Toronto | Condo | Clean Up |  | Unresolved | Harvey Tran | Olawale Olaniyan [X] | David Chui | 2022-08-17 12:20 |  | 2024-12-11 12:04 |  |  | 2024-07-08 | 0 | 3 |  |  | CONST-30056, CONST-30057, CONST-30244, CONST-34159, CONST-34160, CONST-34161, CONST-34162, CONST-34163, CONST-34164, CONST-34165, CONST-34166, CONST-34167, CONST-34168, CONST-34169, CONST-34170, CONST-36124, CONST-36386, CONST-37556, CONST-37557, CONST-38526, CONST-38527 | NET-37999, ORDER-169101, CONST-3134, CONST-9777, CONST-27867 | Requested by: [~odavies] Can we please queue up a site walk for 41 Dovercourt Rd? BB Link: [https://buildings.beanfield.com/buildings/view/4680] *NEW PM Info:* ¦*MARTHA RIOS* Property Manager Direct 647-262-2154 [Martha.rios@fsresidential.com¦mailto:Martha.rios@fsresidential.com]¦ PM Info: Bahareh Safekourdi [Bahareh.safekourdi@fsresidential.com¦mailto:Bahareh.safekourdi@fsresidential.com] This is a condo with 74 residential units, and 5 commercial downstairs. There is a commercial lead with Jam3 that will immediately benefit from this build and it should tie in well with what we have planned in the vicinity. | NUA+MA | [12 empty] | 0¦i3jmnb: | [7 empty] | 9.2234e+18 | [19 empty] | June 01/23 - Project initiated. Jan 29/24 - Conduit build scheduled for Feb 13th. Cable pull scheduled for Feb 27th. Feb 01/24 - PO sent for conduit build. Feb 07/24 - Danny approved $1,005.90 quote from THES (vault access) to be added to budget. Feb 08/24 - Vault access PO sent to AP Feb 09/24 - Vault access (AP) invoice received. Cable pull scheduled for Feb 27th Feb 12/24 - Conduit build completed. Invoice received Feb 27/24 - Cable pull completed Mar 01/24 - Pending SOW. Mar 06/24 - Migration required, delay to splicing. Due dates updated. May 9th, 2024 - Still pending SOW due to migration. Requested an update from GIS. Project due date is possibly pushed back if migration delays. May 31st, 2024 - SOW is ready, splicing to be scheduled soon. Jun 20th, 2024 - There is an open that requires fix. Our team has scheduled a fix next week. Jun 28th, 2024 - Project is pushed back to July as the OLT insertion needs to be completed in prior (NET-37999) Jul 8th, 2024 - Project completed, building is onnet. | [6 empty] | 3 - Normal | [19 empty] | N/A |  | 2023-05-25 | [5 empty] | 2024-07-08 | 3619 |  |  | https://buildings.beanfield.com/buildings/view/4680 |  | CONST-30055 | 3 - Normal | 2024-03-29 |  | 2721 | 9995
Construction | CONST-33777 | TSCC-1972 8 Scollard St, Toronto | Condo | Clean Up |  | Unresolved | Harvey Tran | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2023-05-01 14:15 |  | 2024-12-11 12:05 |  |  | 2024-07-19 | 0 | 0 |  |  | CONST-33778, CONST-33779, CONST-34043, CONST-35672, CONST-35673, CONST-35674, CONST-35675, CONST-35677, CONST-35678, CONST-35679, CONST-35680, CONST-35681, CONST-35682, CONST-35683, CONST-35684, CONST-35685, CONST-35814, CONST-36967, CONST-37402, CONST-37403, CONST-38528, CONST-38529 |  | Requested by Oliver Davies, Could please create a new ticket for an OSP plan & site walk at the “Lotus Condos" 8 Scollard St? *PM Info:* Bruno Hertl, OLCM, RCM, ACCI Condominium Manager [bhertl@stgpm.com¦mailto:bhertl@stgpm.com] 905-881-3115 ext 256 Nearby to consider on Scollard St: 50 Scollard St “Fifty Scollard Condos" (64 units) Under Development - Lanterra 55 Scollard St “Four Seasons Private Residences” (201 units) 21 Scollard St “The Villas at 18 Yorkville” (97 units) 878 Yonge St (165 units) Under Development - Cityzen 1 Scollard St (194 units) Under Development - Cityzen Thank you, | NUA+MA | [12 empty] | 0¦i40awv: | [7 empty] | 9.2234e+18 | [19 empty] | Nov 07/23 - Project initiated. Design and permits in progress Feb 09/24 - Route drawing uploaded Mar 21/24 - Manhole survey completed Mar 26/24 - Hydro & TTC permit submitted Apr 03/24 - PO sent for Hydro permit Apr 08/24 - Hydro permit granted Jul 2, 2024 - Cable pull completed. Splicing is tentatively scheduled. July 22nd, 2024 - Testing completed. Building is onnet. | [6 empty] | 3 - Normal | [19 empty] | N/A |  | 2023-11-07 | [5 empty] | 2024-07-19 | 14613 |  |  | https://buildings.beanfield.com/buildings/view/2536 |  | CONST-33777 | 3 - Normal | 2024-10-25 |  | 4480 | 13875
Construction | CONST-34761 | 75 The Esplanade / 2A Church St, Toronto | Condo | Clean Up |  | Unresolved | Harvey Tran | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2023-07-12 11:02 |  | 2024-12-11 12:17 |  |  | 2024-06-27 | 0 | 0 |  |  | CONST-34762, CONST-34763, CONST-34872, CONST-35566, CONST-35567, CONST-35568, CONST-35569, CONST-35570, CONST-35571, CONST-35572, CONST-35573, CONST-35574, CONST-35575, CONST-35576, CONST-35577, CONST-35578, CONST-35579, CONST-36958, CONST-37662, CONST-37663, CONST-37931, CONST-38520 |  | Requested by Oliver Davies Can you please create a new ticket for an OSP plan & site walk at 75 The Esplanade / 2A Church St? There are 308 units in this condo, and the corporation has just recently been registered. Old PM info: Eduart Lako +{*}Property Manager{*}. *_O.L.C.M and R.C.M_*+ *{color:#e06666}ICON{color}* Property Management 416. 236 7979 ext 122 C/O 75 Esplanade. [75.esplanade.manager@gmail.com¦mailto:75.esplanade.manager@gmail.com] Thank you, | NUA+MA | [12 empty] | 0¦i46107: | [7 empty] | 9.2234e+18 | [19 empty] | Oct 24/23 - Project initiated. Designs and permits in progress Oct 27/23 - Route drawing uploaded. Mar 21/24 - Manhole survey completed Mar 26/24 - Hydro permit submitted Apr 01/24 - Hydro permit PO sent Jun 28th, 2024 - Building is onnet. Apr 08/24 - Hydro permit granted May 9th, 2024 - Cable pull scheduled Jun 3rd. May 31st, 2024 - Cable pull is scheduled, we are able to move up this building due date to June 2024. June 7th, 2024 - Cable pull completed. Still pending SOW. Jun 27th, 2024 - Building is onnet. | [6 empty] | 3 - Normal | [19 empty] | N/A |  | 2023-10-23 | [5 empty] | 2024-06-27 | 15603 |  |  | https://buildings.beanfield.com/buildings/view/15117 |  | CONST-34761 | 3 - Normal | 2024-07-26 | Toronto | 7178 | 15700
Construction | CONST-33335 | 458 Richmond St W, Toronto | Condo | Clean Up |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2023-03-15 10:36 |  | 2024-12-12 07:42 |  |  | 2024-03-14 | 0 | 0 |  |  | CONST-33336, CONST-33337, CONST-33844, CONST-34406, CONST-34407, CONST-34408, CONST-34409, CONST-34410, CONST-34411, CONST-34412, CONST-34413, CONST-34414, CONST-34415, CONST-34416, CONST-34417, CONST-34418, CONST-34419, CONST-34420, CONST-36534, CONST-36738, CONST-36739, CONST-37214, CONST-38801 |  | Requested by Oliver Davies, Can you please assign a new site-walk ticket for 458 Richmond St W? The Woodsworth Condos are a newly registered community with 125 residential units. We have fibre running to all of the surrounding buildings from BFMH-0013 (460 Richmond St W, 438 Richmond St W & 435 Richmond St W). PM Info: Selena Jazexhi Property Manager _​_ ICON PROPERTY MANAGEMENT Email: +[Sele¦mailto:Selena@iconpm.ca] [na@iconpm.ca¦mailto:Selena@iconpm.ca]+ Cell:416-475-9740 P 416-236-7979 Thanks! | NUA+MA | [12 empty] | 0¦i3x5nb: | [7 empty] | 9.2234e+18 | [19 empty] | June 15/23 - Project initiated. Design & Permits in progress. July 24/23 - Route drawing uploaded Aug 22/23 - Manhole survey completed. Aug 29/23 - Hydro permit submitted. Nov 03/23 - Hydro permit granted. Feb 12/24 - PO sent for conduit build. Feb 20/24 - Conduit build completed. Invoice received. Cable pull scheduled for Feb 23rd Feb 23/24 - Cable pull completed Mar 01/24 - Pending SOW. Mar 13/24 - Splicing completed. Mar 14/24 - Building On-Net. | [6 empty] | 3 - Normal | [19 empty] | N/A |  | 2023-06-15 | [5 empty] | 2024-03-14 | 19388 |  |  | https://buildings.beanfield.com/buildings/view/16551 |  | CONST-33335 | 3 - Normal | 2024-03-29 | Toronto | 3327 | 9775
Construction | CONST-31856 | 8/ 10/ 18 Rouge Valley Dr W - The York Condos | Condo | Clean Up |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Jessica Markiewicz | 2022-11-10 09:15 |  | 2024-12-12 07:45 |  |  | 2024-03-06 | 0 | 3 |  |  | CONST-31857, CONST-31858, CONST-33266, CONST-35222, CONST-35223, CONST-35224, CONST-35225, CONST-35226, CONST-35227, CONST-35228, CONST-35229, CONST-35230, CONST-35231, CONST-35232, CONST-35233, CONST-35234, CONST-35235, CONST-35236, CONST-35237, CONST-35238, CONST-35239, CONST-35310, CONST-36290, CONST-36302, CONST-36576, CONST-36577, CONST-38806, CONST-38807 | CONST-26911, CONST-29425, CONST-26906, CONST-26909, CONST-26910 | Requested by Oliver Davies. Can you please queue up a site walk for 8-18 Rouge Valley Dr W “The York Condos”? This would become part of the Markham condos group that are reliant on the Birchmount and Enterprise backbone (https://tickets.beanfield.com/browse/CONST-29425) BB Link: [https://buildings.beanfield.com/buildings/view/14671] PM Info: *Wendy Tao* *¦* *Residential Property Manager* *REM Facilities Management Inc.* 10 Rouge Valley Drive West ¦ Unionville, Ontario ¦ L6G 0G9 T: 905-604-2877 [*wtao@remfmi.com*¦mailto:wtao@remfmi.com] | Bolton, Markham, NUA+MA | [12 empty] | 0¦i3p71r: | [7 empty] | 9.2234e+18 | [19 empty] | Aug 30/23 - Project initiated. Permits and Design completed on CONST-29425 Sep 14/23 - Construction scheduled to start on CONST-29425 Sep 21st Oct 12/23 - Construction started Oct 3rd on CONST-29425 Jan 24/24 - Transferred conduit build quote ($3,095.00) from Design & Permit budget to Cable pull budget (Conduit build).PO sent Jan 31/24 - Conduit build scheduled for Feb 1st. Cable pull scheduled for Feb 21st Feb 07/24 - Conduit build completed. Conduit build invoice received. Feb 12/24 - PO sent to Conview for scan & core drill. Feb 13/24 - pending SOW Feb 21/24 - Conview invoice received. Cable pull completed. Feb 22/24 - Due date will be pushed back due to still not having SOW from GIS Dept. Feb 26/24 - Transferred $7,500.00 from construction to splicing budget. PO sent for splicing. Feb 27/24 - Delay to SOW in turn caused delay to splicing. Due dates updated. Feb 28/24 - OSP splicing completed Mar 01/24 - ISP splicing in progress Mar 06/24 - Building On-Net | [6 empty] | 3 - Normal | [19 empty] | Internal |  | 2023-08-30 | [5 empty] | 2024-03-06 | 18675 |  |  | https://buildings.beanfield.com/buildings/view/14671 |  | CONST-31856 | 3 - Normal | 2023-12-29 |  | 8955 | 18140
Construction | CONST-31676 | 11 Wellesley St W, Toronto - Wellesley on the Park | Condo | Clean Up |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Jessica Markiewicz | 2022-11-01 14:15 |  | 2023-12-22 10:09 |  |  | 2023-12-20 | 0 | 3 |  |  | CONST-31677, CONST-31678, CONST-31958, CONST-32488, CONST-32489, CONST-32490, CONST-32491, CONST-32492, CONST-32493, CONST-32494, CONST-32495, CONST-32498, CONST-32499, CONST-32500, CONST-32501, CONST-32502, CONST-32503, CONST-32504, CONST-32505, CONST-32506, CONST-35406, CONST-35407, CONST-35422, CONST-35792, CONST-38544, CONST-38545 | CONST-31820, CONST-35849 | Requested by Oliver Davies. Whenever you have a moment, can you please schedule a site walk for 11 Wellesley St W? +*NEW PM Info:*+ Fisnik Basha, OLCM ¦ Senior Condominium Manager DUKA Property Management Inc. As agents for an on behalf of TSCC2845 & TSCC2893 11 & 15 Wellesley St. West, Toronto, Ontario Tel: 416-964-0866 [wellesley.cm@dukamanagement.com¦mailto:wellesley.cm@dukamanagement.com] *AND* Gresilda Th ¦ Site Administrator¦ DUKA Property Management Inc. As Agents for and on Behalf of T.S.C.C. No. 2845 & T.S.C.C. No. 2893 11 & 15 Wellesley St. West, Toronto, ON Tel: 416-964-0866 ¦ Concierge: 416-926-0216 [wellesley.admin@dukamanagement.com¦mailto:wellesley.admin@dukamanagement.com] +*OLD PM Info:*+ *Natali Gallo* ¦ Senior Condominium Manager – OLCM ¦ *DUKA Property Management Inc.* *As Agents for and on Behalf of T.S.C.C. No. 2845 & T.S.C.C. No. 2893* 11 & 15 Wellesley St. West, Toronto, ON Tel: 416-964-0866 11 Wellesley St W: [https://buildings.beanfield.com/buildings/view/9906] 15 Wellesley St W: [https://buildings.beanfield.com/buildings/view/17407] TSCC 2845 = 11 Wellesley / 740 condo units TSCC 2893 = 15 Wellesley / 66 commercial + 2 residential units | [13 empty] | 0¦i3onpr: | [7 empty] | 9.2234e+18 | [19 empty] | December 23 - Project initiated, pending design and permits. February 9th - Manhole survey completed. July 21/23 - Hydro permit granted. Oct 3/23 - Delay with conduit build. Due dates updated. Oct 31/23 - Conduit build scheduled for Nov 7th Nov 01/23 - Cable pull scheduled for Dec 1st Nov 06/23 - Conduit build completed Nov 07/23 - Conduit build invoice received. Dec 01/23 - Cable pull completed. Dec 11/23 - Splicing completed Dec 20/23 - Building On-Net | [6 empty] | 3 - Normal | [27 empty] | 2023-12-20 | 8122 |  |  | https://buildings.beanfield.com/buildings/view/9906 |  | 500525 | 3 - Normal | 2023-10-27 |  | 12283 | 21125
Construction | CONST-29416 | 3018 Yonge St, Toronto - 3018 Yonge Condos | Condo | Clean Up |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Jessica Markiewicz | 2022-07-13 12:56 |  | 2024-02-26 15:31 |  |  | 2024-02-21 | 0 | 0 |  |  | CONST-29417, CONST-29418, CONST-29999, CONST-30095, CONST-30940, CONST-30941, CONST-30942, CONST-30943, CONST-30944, CONST-30945, CONST-30946, CONST-30947, CONST-30948, CONST-30949, CONST-30950, CONST-30951, CONST-30952, CONST-35493, CONST-35494, CONST-35952, CONST-36190, CONST-38798, CONST-38799 |  | Requested by Jay Fernandes Hi, These are the Fibrestream condos we have agreements for that don’t seem to fit into any groups (although I maybe wrong). Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. ¦Group¦Building Name¦Address¦suites¦ ¦Independent¦Eleven Superior¦11 Superior AVE Etobicoke ON M8V 0A7¦130¦ ¦Independent¦The James Club¦1135 Royal York RD Toronto ON M9A 4A7¦209¦ ¦Independent¦Independence Way¦115 George Appleton WAY North York ON M3M 2E9¦244¦ ¦Independent¦Danforth Village Estates¦1346 Danforth RD Toronto ON M4J1M9¦249¦ ¦Independent¦beBloor¦1369 Bloor ST Toronto ON M6P 4J3¦238¦ ¦Independent¦Ion Condos¦15 James Finlay WAY Toronto ON M3M 0B3¦200¦ ¦Independent¦Paradice at the Oasis¦1720 Eglinton AVE Toronto ON M4A2X9¦190¦ ¦Independent¦Havenon the Bluffs¦20 East Haven DR Toronto ON M1N1M2¦259¦ ¦Independent¦Kilgour Estate II¦21 Burkebrook PL Toronto ON M4G4K8¦228¦ ¦Independent¦Canvas Condos¦2301 Danforth AVE Toronto ON M4C 1L5¦156¦ ¦Independent¦3018 Yonge Condos¦3018 Yonge ST Toronto ON M4N 0A5¦188¦ ¦Independent¦Cranbrooke Village¦35 Saranac BLVD Toronto ON M6A 2G4¦341¦ ¦Independent¦39 Brant St¦39 Brant ST Toronto ON M5V0M8¦236¦ ¦Independent¦The Wave¦4 Elsinore PATH Toronto ON M8V 4G7¦185¦ ¦Independent¦Clock Tower Lofts¦700 King ST Toronto ON M5V 2Y6¦216¦ ¦Independent¦The Boot¦75 Dalhousie ST Toronto ON M5B 2R9¦153¦ ¦Independent¦B.Street Condos¦783 Bathurst ST Toronto ON M6G 1K1¦ ¦ ¦Independent¦85 Bloor St¦85 Bloor ST Toronto ON M4W3G9¦252¦ | FSactive, Fiberstreamagreement | [12 empty] | 0¦i3hfzb: | [7 empty] | 9.2234e+18 | [19 empty] | October 6th - Project initiated. Design and Permits to be in progress. Mar 21/23 - Manhole Survey completed. June 27/23 - Hydro permit granted. Oct 12/23 - Delay with conduit build. Due dates updated. Nov 10/23 - Hydro permit extension requested Dec 14/23 - Panels and ISP Prep completed Jan 15/24 - Conduit build completed Jan 15/24 - Updated splicing budget ($4,691.00). Approved by Oliver Davies. Cable pull completed. Splicing PO sent. Jan 30/24 - SOW redesign required, delay to splicing. Due dates updated Jan 31/24 - Splicing in progress Feb 01/23 - Splicing invoice #38512 received. Feb 07/24 - SOW redesign required again. Delay to splicing. Feb 13/24 - Splicing in progress Feb 16/24 - Splicing completed Feb 21/24 - Building On-Net Feb 26/24 - Revised splicing quote ($7,337.16) due to updates to SOW added to budget. PO sent. | [6 empty] | 3 - Normal | [26 empty] | Integration | 2024-02-21 | 18176 |  |  | https://buildings.beanfield.com/buildings/view/5143 |  | 500459 | 3 - Normal | 2023-11-17 |  | 5219 | 17740
Construction | CONST-29130 | 1 Old Mill Dr, Toronto | Condo | Clean Up |  | Unresolved | Harvey Tran | Olawale Olaniyan [X] | Jessica Markiewicz | 2022-07-11 07:32 |  | 2024-09-16 09:01 |  |  | 2024-07-30 | 0 | 0 |  |  | CONST-29131, CONST-29132, CONST-29134, CONST-29135, CONST-31122, CONST-31123, CONST-31261, CONST-31262, CONST-31263, CONST-31264, CONST-31265, CONST-31266, CONST-31267, CONST-31268, CONST-31269, CONST-31270, CONST-31271, CONST-31272, CONST-31273, CONST-31274, CONST-31275, CONST-31276, CONST-31277, CONST-31278, CONST-31279, CONST-34331, CONST-35371, CONST-36310, CONST-36831, CONST-37830, CONST-37906, CONST-37907, CONST-38837, CONST-38838 | CONST-34238 | Requested by Jay Fernandes Hi, I’ve gone through the remaining Fibrestream condos we have agreements for in the GTA and have grouped them in a way that I think makes sense for site visits and builds. There will be another list coming of buildings that don’t really fall into groups. Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. There are some current backbone (Sheppard) or NPOP (960 Lawrence) projects that will need to be completed to connect these but this will get everything into the system. Thanks! *NEW PM Info:* Anila Hysi oneoldmill.pm@delcondo.com 647.350.0851 *PM: Natalie Santos* *oneoldmill.pm@delcondo.com* *647.350.0851* | Bolton, FSactive, Fiberstreamagreement, HighPark | [12 empty] | 0¦i3h5lb: | [7 empty] | 9.2234e+18 | [19 empty] | January 9 - Route drawing completed, manhole surveys to be scheduled. October 21st - Project initiated. Design and permits to be in progress. May 15/23 - Manhole Survey completed. Oct 13/23 - Delay with permits. Due dates updated Oct 25/23 - City permit approved Nov 03/23 - Hydro permit granted Jan 24/24 - Updated budget uploaded by James (Design & Permit budget) Feb 12/24 - Aerial Hydro permit (final job estimate) PO sent. Vault access PO sent to AP (THES). Vault access invoice received. Feb 28/24 - Cable pull in progress Mar 05/24 - Aerial Hydro permit granted Mar 07/24 - Locates completed. Mar 13/24 - Manhole resurvey scheduled for Apr 4th Mar 21/24 - Manhole resurvey completed Mar 28/24 - Sentrex PO sent to John Apr 01/24 - Hydro permit granted Apr 08/24 - Conduit build PO sent Apr 15/24 - PO sent to Wendy for Readyvac Apr 16/24 - Readyvac invoice received. Apr 17/24 - Cable pull scheduled for May 8th. Vault access requested. Vault access PO sent to AP for THES. Invoice received. Apr 18/24 - Construction completed A[r 24/24 - Conduit build completed Apr 26/24 - Both conduit build (1 & 2 Old Mill Dr) invoices received. Jul 2nd, 2024 - Cable pull completed. Still pending SOW for splicing testing. Jul 11th, 2024 - Splicing is tentatively scheduled Jul 19th July 30th, 2024 - Testing completed, building is onnet. | [6 empty] | 3 - Normal | [19 empty] | Internal |  | 2022-10-19 |  |  |  |  | Integration | 2024-07-30 | 79341 |  |  | https://buildings.beanfield.com/buildings/view/15389 |  | 500482 | 3 - Normal | 2024-01-26 |  | 9725 | 30745
Construction | CONST-25828 | 7165/7167 Yonge Street, Thornhill | Condo | Clean Up |  | Unresolved | Harvey Tran | Olawale Olaniyan [X] | Harvey Tran | 2021-11-22 15:47 |  | 2024-08-01 09:14 |  |  | 2024-07-31 | 0 | 2 |  |  | CONST-25829, CONST-25830, CONST-25948, CONST-25956, CONST-25957, CONST-25958, CONST-25959, CONST-25960, CONST-25961, CONST-25962, CONST-25963, CONST-25964, CONST-25965, CONST-25966, CONST-26215, CONST-26303, CONST-35706, CONST-35707, CONST-35708, CONST-35709, CONST-36555, CONST-37887, CONST-37987, CONST-37988, CONST-38652, CONST-38653 | CONST-17917, CONST-27862, CONST-27863, PUR-14560 | Can we create a ticket to get a site walk done for this condo? We have an access agreement through Fibrestream and we’ll end up building here when we have an NPOP in the future. I just want to see what we can do for deploying our internal fibre in the building. I’d like to get James to do a site walk with Kris (new to Beanfield from Fibrestream). Kris will be able to sort out access for the visit. There is no need for an access agreement sub-task for this one as we already have it and it’s uploaded. Once we have a plan from James we can figure out how we execute. | Fiberstreamagreement | [12 empty] | 0¦i31xzb: | [7 empty] | 9.2234e+18 | [19 empty] | September 13th - Conduit build completed. Splicing is pending on the BOLT confirmed by Jason Cowan as we need to identify another set of buildings. May 3rd, 2024 - Cable pull completed. Splicing is scheduled May 17th. May 9th, 2024 - As per confirmation from GIS, this build needs to wait till the NPOP at 7181 Yonge St is done in end of June 2024. Pushing back this building due date to mid July 2024. July 11th, 2024 - Splicing is in progress. This building can be on net assuming the 7181 backbone build (Primary) is done. July 30th, 2024 - The NPOP is ready for us to turn up this building, our team is working to get the testing done for this building to bring it onnet in July Jul 1st 2024 - Testing is completed, building is onnet. | [6 empty] | 3 - Normal | [19 empty] | N/A |  | 2020-12-24 | [5 empty] | 2024-07-31 | 0 |  |  | https://buildings.beanfield.com/buildings/view/8080 |  | 500331 | 3 - Normal | 2022-02-25 |  | 7208 | 18405
Construction | CONST-28903 | 219 Dundas St E, Toronto - In.DE Condos | Condo | Clean Up |  | Unresolved | Lorna Kurok | Lorna Kurok | Harvey Tran | 2022-06-20 12:32 |  | 2024-10-25 10:17 |  |  | 2024-10-21 | 0 | 2 |  |  | CONST-28904, CONST-28905, CONST-29025, CONST-36599, CONST-36600, CONST-36601, CONST-36602, CONST-36603, CONST-36604, CONST-36605, CONST-36606, CONST-36607, CONST-36608, CONST-36609, CONST-36610, CONST-36611, CONST-36612, CONST-36613, CONST-36614, CONST-36615, CONST-37749, CONST-38147, CONST-38148, CONST-38926 |  | *Requested by Oliver Davies.* Could you please queue up a site walk for 219 Dundas St E (In.DE Condos)? BB Link: [https://buildings.beanfield.com/buildings/view/15060] *NEW PM Info:* *Myra Luthra* Senior Property Manager, OLCM MenRes Property Management Inc. As Agents for and on Behalf of TSCC 2870 219 Dundas St. E., Toronto, ON, M5A 0V1 T: 416.777.9296 [inde@menres.com¦mailto:inde@menres.com] PM info: *Monica Magdi* Senior Property Manager MenRes Property Management Inc. 219 Dundas St. E., Toronto ON M5A 0V1++++ T: 416.777.9296++++ {color:#1155cc}[inde@menres.com¦mailto:inde@menres.com]{color} | NUA+MA | [12 empty] | 0¦i3fxfz: | [7 empty] | 9.2234e+18 | [19 empty] | Feb 21/24 - Project initiated. Design and permits in progress. Feb 26/24 - Route drawing uploaded Aug 14, 2024_Cable pull is scheduled for Sept 10, 2024. Sept 4, 2024_SOW design uploaded with updated splice details Sep 8, 2024_Splicing in process, partially completed, pending cable for 2 locations Sep 16, 2024_ Condo moved up from November 2024 to October 2024. Sep 17, 2024_Riser Fiber Pull completed Sept 17, 2024_Riser Panels Completed. Sept 18, 2024_Cable in process Sept 18, 2024 Sept 18, 2024_Cable pull As-built attached. Oct 21, 2024 Building On Net | [6 empty] | 3 - Normal | [19 empty] | N/A | 2024-10-21 | 2024-02-21 |  |  |  | 222 |  | 2024-10-21 | 37719 |  |  | https://buildings.beanfield.com/buildings/view/15060 |  | CONST-28903 | 3 - Normal | 2024-11-29 | Toronto | 2642 | 12360
Construction | CONST-28918 | 377 Madison Ave, Toronto | Condo | Clean Up |  | Unresolved | Lorna Kurok | Lorna Kurok | Harvey Tran | 2022-06-21 08:32 |  | 2024-10-25 10:03 |  |  | 2024-10-31 | 0 | 2 |  |  | CONST-28919, CONST-28920, CONST-29026, CONST-30167, CONST-36891, CONST-36892, CONST-36893, CONST-36894, CONST-36895, CONST-36896, CONST-36897, CONST-36898, CONST-36899, CONST-36900, CONST-36901, CONST-36902, CONST-36903, CONST-36904, CONST-37750, CONST-38152, CONST-38246, CONST-38247, CONST-38934, CONST-38935 | CONST-17434 | Ana has reached out to investigate the possibility of adding Beanfield to the building they manage at 377 Madison Ave, Toronto ON M4V 3E1. Could you kindly create a new ticket for a site walk? BB Link: [https://buildings.beanfield.com/buildings/view/5697] *NEW PM Info:* *Leah Stephens, OLCM-L* Condominium Manager ¦ ICC Property Management Ltd. T: (905) 940-1234 Ext. 253 F: (905) 940-3881 E: [lstephens@iccpropertymanagement.com¦mailto:lstephens@iccpropertymanagement.com] PM Info: [¦https://tickets.beanfield.com/secure/AddComment!default.jspa?id=738406] *Ana Stoneman, OLCM* Condominium Manager ¦ ICC Property Management Ltd. T: (905) 940-1234 Ext. 92 F: (905) 940-3881 E: [+astoneman@+iccpropertymanagement.com¦mailto:astoneman@iccpropertymanagement.com] | NUA+MA | [12 empty] | 0¦i3fzzz: | [7 empty] | 9.2234e+18 | [19 empty] | Mar 25/24 - Project initiated. Design and permits in progress. Apr 02/24 - Route drawing uploaded. Aug 4, 2024 OSP Sow design has been uploaded Sep 2024 Conduit installation Completed. Sep 13, 2024 - Conduit build has been completed. Photos Attached. Parking space 17 will need to be blocked for cable pull. Korey has already made this request to the PM. PM has approved Sep 17, 2024_Cable pull work has been completed. Asbuilt attached Oct 7, 2024 All of the panels are installed as per Riser diagram Oct 22, 2024 This is Ready to Go OnNet. OTDR testing is complete. | [6 empty] | 3 - Normal | [19 empty] | N/A | 2024-10-22 | 2024-03-25 |  |  | 7 | 164 |  | 2024-10-22 | 11662 |  |  | https://buildings.beanfield.com/buildings/view/5697 |  | CONST-28918 | 3 - Normal | 2024-11-29 | Toronto | 4138 | 2185
Construction | CONST-37041 | 595 Yonge St / 1-3 Gloucester St, Toronto - Gloucester on Yonge | Condo | Clean Up |  | Unresolved | Lorna Kurok | Lorna Kurok | Olawale Olaniyan [X] | 2024-04-16 09:54 | 2025-03-07 10:57 | 2024-10-29 08:19 |  |  | 2024-10-28 | 0 | 1 |  |  | CONST-37042, CONST-37043, CONST-37097, CONST-37356, CONST-37357, CONST-37358, CONST-37359, CONST-37360, CONST-37361, CONST-37362, CONST-37363, CONST-37364, CONST-37365, CONST-37366, CONST-37367, CONST-37368, CONST-37369, CONST-37370, CONST-38580, CONST-38988, CONST-38989 |  | Requested by Oliver Davies, Could you please assist with creating new tickets for an OSP plan & site walk at the new The Gloucester on Yonge condominiums? This location has recently been turned over from the developer and includes 528 residential units. Site Contact: Michael Heger, OLCM Senior Property Manager ¦ ¦ Agents for and on behalf of TSCC 2941 3 Gloucester St, Ontario, M4Y OC6 Phone: 647-368-7395 Email: [gloucester@crossbridgecs.com¦mailto:gloucester@crossbridgecs.com] Thanks! | NUA+MA | [12 empty] | 0¦i4ruzr: | [7 empty] | 9.2234e+18 | [19 empty] | May 15th. 2024 - Project started. Route drawing and survey to be in progress. Sept 12, 2024 - Riser Cable pull in process, need assistance of 3rd person to pull into the pop room, anticipating for sept 13, 2024. Sept 13, 2024 - Riser Cable pull note: DID multiple attempts to pull to pop but no success, so had to pull to security room, pictures are attached. Main pop is connected to security room.) Sep 13, 2024 - Note from Riser Panel _ all of the panels are dressed Sep 16, 2024_this condo is being moved up on the ON Net Schedule from November to October. | [6 empty] | 3 - Normal | [21 empty] | 2024-05-15 |  |  |  | 528 |  | 2024-10-28 | 36204 |  |  | https://buildings.beanfield.com/buildings/view/16361 |  | CONST-37041 | 3 - Normal | 2024-11-15 | Toronto | 8927
Construction | CONST-28348 | 100 Mill St. - Block 10 Rentals, Toronto | Condo | Clean Up |  | Unresolved | Harvey Tran | Olawale Olaniyan [X] | Harvey Tran | 2022-05-11 14:18 |  | 2024-10-29 10:16 |  |  | 2024-05-31 | 0 | 0 |  |  | CONST-28382, CONST-28383, CONST-28394, CONST-35645, CONST-35646, CONST-35647, CONST-35648, CONST-35649, CONST-35650, CONST-35651, CONST-35754, CONST-37250, CONST-37318, CONST-37888, CONST-38280, CONST-38900, CONST-38983 | CONST-30240 | +*PM Contact:*+ Omar Vivas, EIT M&E Coordinator C.437.235.4183 [{color:#000000}ovivas@EllisDon.com{color}¦mailto:ovivas@EllisDon.com] | [13 empty] | 0¦i3dhc7: | [7 empty] | 9.2234e+18 | [19 empty] | Nov 03/23 - ISP only. Will be fed from 425 Front St E, Toronto May 3rd 2024 - Riser cable pull is in progress. SOW is pending. May 31st, 2024 - Testing completed. Building is onnet. Only pending pre-wiring work as the building is not ready yet. | [6 empty] | 3 - Normal | [19 empty] | N/A |  | 2023-11-03 | [5 empty] | 2024-05-31 |  |  |  | https://buildings.beanfield.com/buildings/view/16127 |  | 500501(sub) | 3 - Normal | 2024-10-25
Construction | CONST-29189 | 17 Barberry Pl, North York - Kenaston Gardens | Condo | Clean Up |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Jessica Markiewicz | 2022-07-11 15:02 |  | 2023-12-22 10:15 |  |  | 2023-12-21 | 0 | 0 |  |  | CONST-29190, CONST-29191, CONST-32113, CONST-32139, CONST-32140, CONST-32141, CONST-32142, CONST-32143, CONST-32144, CONST-32145, CONST-32146, CONST-32147, CONST-32148, CONST-32149, CONST-32150, CONST-32151, CONST-32152, CONST-35861, CONST-35862, CONST-38869, CONST-38870 | CONST-29195, CONST-29198, CONST-29201, CONST-32106, CONST-24117, CONST-29192, CONST-30959, CONST-29578 | Requested by Jay Fernandes Hi, I’ve gone through the remaining Fibrestream condos we have agreements for in the GTA and have grouped them in a way that I think makes sense for site visits and builds. There will be another list coming of buildings that don’t really fall into groups. Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. There are some current backbone (Sheppard) or NPOP (960 Lawrence) projects that will need to be completed to connect these but this will get everything into the system. Thanks! *PM: Vijitha Sureshvaran* *vijitha.sureshvaran@crossbridgecs.com* *416.987.8970* | Fiberstreamagreement, Sheppard | [12 empty] | 0¦i3h7zr: | [7 empty] | 9.2234e+18 | [19 empty] | November 28th - Project initiated. Design and permits to be in progress. June 16/23 - City permit on backbone build CONST-32115 Oct 12/23 - Construction scheduled to start Oct 18th on CONST-32106 Nov 10/23 - Construction completed. Nov 20/23 - Conduit build not required. Nov 24/23 - Cable pull scheduled for Dec 6th Dec 07/23 - Cable pull completed. Dec 08/23 - Riser Build Complete all Panels Spliced, ISP Remaining Dec 18/23 - OSP splicing completed Dec 21/23 - Building On-Net | [6 empty] | 3 - Normal | [27 empty] | 2023-12-21 | 30888 |  |  | https://buildings.beanfield.com/buildings/view/3635 |  | 500515 | 3 - Normal | 2023-11-24 |  | 7837
Construction | CONST-29180 | 115 McMahon Dr, North York - Omega and Opus | Condo | Clean Up |  | Unresolved | Lorna Kurok | Lorna Kurok | Jessica Markiewicz | 2022-07-11 14:27 |  | 2024-09-26 11:28 |  |  | 2024-09-27 | 0 | 0 | _thumb_922125.png _thumb_922122.png _thumb_973808.png _thumb_973807.png _thumb_973347.png _thumb_925460.png _thumb_973809.png _thumb_973810.png _thumb_973348.png _thumb_925463.png _thumb_973349.png _thumb_925464.png |  | CONST-29181, CONST-29182, CONST-32720, CONST-32760, CONST-32761, CONST-32762, CONST-32763, CONST-32764, CONST-32765, CONST-32766, CONST-32767, CONST-32768, CONST-32769, CONST-32770, CONST-32771, CONST-32772, CONST-32773, CONST-32774, CONST-32775, CONST-37801, CONST-37863, CONST-38167, CONST-38168, CONST-38599, CONST-38607, CONST-38880 | CONST-29186, CONST-32336, CONST-32339, CONST-32342, CONST-32592, CONST-32595, CONST-32880, CONST-33876, CONST-32349, CONST-33014 | Requested by Jay Fernandes Hi, I’ve gone through the remaining Fibrestream condos we have agreements for in the GTA and have grouped them in a way that I think makes sense for site visits and builds. There will be another list coming of buildings that don’t really fall into groups. Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. There are some current backbone (Sheppard) or NPOP (960 Lawrence) projects that will need to be completed to connect these but this will get everything into the system. Thanks! PM Info: *Sandi Plesa, OLCM, RCM, CPM* Property Manager As Agents for and on behalf of TSCC 2741 *Opus and Omega on the Park* 117 McMahon Drive, North York, Ontario M2K 0E4 Telephone: (647) 358-5560 E-mail: ** +[omegaandopus@crossbridgecs.com¦mailto:omegaandopus@crossbridgecs.com]+ | Fiberstreamagreement, Sheppard | [12 empty] | 0¦i3h7qf: | [7 empty] | 9.2234e+18 | [19 empty] | Jan 13/23 - Project initiated, pending design and permits. May 11/23 - ISP only will be fed from CONST-33876 Jun 7th, 2024 This is where we will work on the UG construction to enter the whole building group. Bolton team is working on the tentative schedule for this building. Aug 2024_ Backbone Cable pull is completed, waiting on Backbone SOW. Aug 2024_Splicing scheduled to be completed Aug 29th 30th. Sep 18, 2024_On Net email sent. ruby testing completed. | [6 empty] | 3 - Normal | [19 empty] | N/A |  | 2023-01-13 | [5 empty] | 2024-09-18 | 3862 |  |  | https://buildings.beanfield.com/buildings/view/15762 |  | CONST-29180 | 3 - Normal | 2024-02-23 | North York | 11150 | 27100
Construction | CONST-29165 | 1040 The Queensway, Etobicoke - Loggia | Condo | Clean Up |  | Unresolved | Harvey Tran | Olawale Olaniyan [X] | Jessica Markiewicz | 2022-07-11 14:02 |  | 2024-10-22 15:44 |  |  | 2024-06-25 | 0 | 3 |  |  | CONST-29166, CONST-29167, CONST-30673, CONST-30674, CONST-30760, CONST-30761, CONST-30762, CONST-30763, CONST-30764, CONST-30765, CONST-30766, CONST-30767, CONST-30768, CONST-30769, CONST-30770, CONST-30771, CONST-37241, CONST-37641, CONST-37642, CONST-38417, CONST-38421 | CONST-29168 | Requested by Jay Fernandes Hi, I’ve gone through the remaining Fibrestream condos we have agreements for in the GTA and have grouped them in a way that I think makes sense for site visits and builds. There will be another list coming of buildings that don’t really fall into groups. Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. There are some current backbone (Sheppard) or NPOP (960 Lawrence) projects that will need to be completed to connect these but this will get everything into the system. Thanks! *PM: Michael Zanon* *mike@iconpm.ca* *416.236.7979 x128* | Bolton, Fiberstreamagreement, Queensway | [12 empty] | 0¦i3h7hr: | [7 empty] | 9.2234e+18 | [19 empty] | Apr 19/23 - Project Initiated. Design and Permits in progress. Oct 13/23 - Delay with permits. Due dates updated Mar 14/24 - City permit granted Apr 24/24 - Construction scheduled to start May 6th May 9th, 2024 - Construction is in progress. Cable pull is also scheduled after construction completion. May 14th, 2024 - Construction completed, cable pull is scheduled. Jun 24th, 2024 - Splicing completed. Testing will be scheduled. Jun 25th, 2024 - Testing completed. Building is onnet. | [6 empty] | 3 - Normal | [19 empty] | Internal |  | 2023-04-19 | [5 empty] | 2024-06-25 | 49258 |  |  | https://buildings.beanfield.com/buildings/view/4166 |  | CONST-29165 | 3 - Normal | 2024-01-26 |  | 2219 | 9280
Construction | CONST-29171 | 15 - 17 Zorra St, Etobicoke - Park Towers Condominiums at IQ | Condo | Clean Up |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Jessica Markiewicz | 2022-07-11 14:10 |  | 2024-11-05 10:41 |  |  | 2024-02-07 | 0 | 0 |  |  | CONST-29172, CONST-29173, CONST-31979, CONST-31980, CONST-31981, CONST-31982, CONST-31983, CONST-31984, CONST-31985, CONST-31986, CONST-31987, CONST-31988, CONST-31989, CONST-31990, CONST-31991, CONST-31992, CONST-31993, CONST-31994, CONST-31995, CONST-31996, CONST-31997, CONST-31998, CONST-36142, CONST-36163, CONST-36185, CONST-36186, CONST-36808, CONST-38749 | CONST-27001, CONST-17747 | Requested by Jay Fernandes Hi, I’ve gone through the remaining Fibrestream condos we have agreements for in the GTA and have grouped them in a way that I think makes sense for site visits and builds. There will be another list coming of buildings that don’t really fall into groups. Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. There are some current backbone (Sheppard) or NPOP (960 Lawrence) projects that will need to be completed to connect these but this will get everything into the system. Thanks! *PM: James Docherty* *jdocherty@remingtongroupinc.com* *647.350.5881* | Fiberstreamagreement, Queensway | [12 empty] | 0¦i3h7kv: | [7 empty] | 9.2234e+18 | [19 empty] | November 18th - Project initiated. Design and permits to be in progress. May 15/23 - Hydro permit conditionally granted. Oct 11/23 - City permit approved Oct 11/23 - Construction scheduled to start Nov 13th Dec 14/23 - Construction completed Dec 22/23 - Conduit build scheduled for Jan 16th - 18th. Cable pull scheduled for Jan 24th Jan 16/24 - Conduit build completed Jan 17/24 - GIS updated SOW to show splicing will be blocked by CONST-27001. Due dates updated. Jan 17/24 - GIS found a workaround to bring this condo On-Net. Due dates updated. Jan 24/24 - Cable pull completed. Jan 31/24 - Delay with SOW and splicing. Due dates updated. Feb 05/24 - OSP splicing completed Feb 07/24 - Building On-Net | [6 empty] | 3 - Normal | [19 empty] | Internal | [7 empty] | 2024-02-07 | 90046 |  |  | https://buildings.beanfield.com/buildings/view/6725 |  | 500509 | 3 - Normal | 2023-06-16 |  | 12217 | 1120
Construction | CONST-32349 | 72 Esther Shiner Blvd - Tango 2 | Condo | Clean Up |  | Unresolved | Lorna Kurok | Lorna Kurok | Jessica Markiewicz | 2022-12-13 13:03 |  | 2024-11-05 13:31 |  |  | 2024-09-20 | 0 | 1 |  |  | CONST-32350, CONST-32351, CONST-32655, CONST-32701, CONST-32702, CONST-32703, CONST-32704, CONST-32705, CONST-32706, CONST-32707, CONST-32708, CONST-32709, CONST-32710, CONST-32711, CONST-32712, CONST-32713, CONST-32714, CONST-32715, CONST-32716, CONST-37802, CONST-37869, CONST-38093, CONST-38094, CONST-38602, CONST-38610, CONST-38636 | CONST-29186, CONST-32336, CONST-32339, CONST-32342, CONST-32592, CONST-32595, CONST-32880, CONST-33876, CONST-29180, CONST-33014 | Requested by James Mowers: +*New Contact Info:*+ Nick Palantzas Property Manager - TSCC 2486 Email: [TANGOII@crossbridgecs.com¦mailto:TANGOII@crossbridgecs.com] Phone: 647-344-8297 Can we get a site visit ticket for 72 Esther Shiner Blvd.? This will be built in conjunction with the buildings at Singer Court. | FSactive, Fiberstreamagreement | [12 empty] | 0¦i3r5s7: | [7 empty] | 9.2234e+18 | [19 empty] | Jan 13/23 - Project initiated, pending design and permits. May 11/23 - ISP only will be fed from CONST-33876 Jun 11th, 2024 - Construction is required. Aug 7, 2024_Cable pull scheduled for Aug 13th Sept 4, 2024_OSP Splicing is completed Sept 20, 2024_OTDR Ruby Testing completed Sept 20, 2024_Building in ON Net. | [6 empty] | 3 - Normal | [19 empty] | N/A |  | 2023-01-13 |  |  |  |  | Integration | 2024-09-20 | 2625 |  |  | https://buildings.beanfield.com/buildings/view/5365 |  | CONST-32349 | 3 - Normal | 2024-02-23 |  | 5760 | 10435
Construction | CONST-29255 | 28 Sommerset Way, North York - Northtown Casitas Ⅱ | Condo | Clean Up |  | Unresolved | Lorna Kurok | Lorna Kurok | Jessica Markiewicz | 2022-07-11 16:16 |  | 2024-12-18 08:20 |  |  | 2024-12-17 | 0 | 1 |  |  | CONST-29256, CONST-29257, CONST-34542, CONST-34549, CONST-34550, CONST-34551, CONST-34552, CONST-34553, CONST-34554, CONST-34556, CONST-34557, CONST-34558, CONST-34559, CONST-34560, CONST-34561, CONST-34562, CONST-34563, CONST-34564, CONST-36816, CONST-38124, CONST-38446, CONST-38894, CONST-39394, CONST-39660, CONST-39661 | CONST-34674, CONST-29249 | Requested by Jay Fernandes Hi, I’ve gone through the remaining Fibrestream condos we have agreements for in the GTA and have grouped them in a way that I think makes sense for site visits and builds. There will be another list coming of buildings that don’t really fall into groups. Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. There are some current backbone (Sheppard) or NPOP (960 Lawrence) projects that will need to be completed to connect these but this will get everything into the system. Thanks! *PM: Elaine Waller* *northtown2@delcondo.com* *416.225.3966* | FSactive, Fiberstreamagreement, Yonge&Finch | [12 empty] | 0¦i3h8t3: | [7 empty] | 9.2234e+18 | [19 empty] | June 27/23 - Project initiated. Design & Permit in progress. Feb 14/24 - City permit completed on CONST-35102 Mar 05/24 - Permits and OSP construction will be completed on Doris Ave Condo Backbone. Budget updated Sept 11, 2024 Riser Fibre Pull, issues with Block 1300, Block 1100 and Block 1000 Sept 12, 2024 - Riser Fibre Pull Note - (We attempt to rope remaining twh riser however the fish keep getting stuck in all the conduit. continue trying several times fish it, kept getting stuck in several spots. We try to find other options to get the rope the riser but it was unsuccessful.) Sept 16th - This build is contingent on the conduit build as only 1/6 of the existing conduits from the Town house comm rooms are able to be used , all others are too congested to even fish and rope . Dec 17, 2024 Building is On Net | [6 empty] | 3 - Normal | [19 empty] | N/A |  | 2023-06-27 |  |  | 17 | 179 | Integration | 2024-12-17 | 5930 |  |  | https://buildings.beanfield.com/buildings/view/4234 |  | CONST-29255 | 3 - Normal | 2024-04-26 | North York | 4724 | 9120
Construction | CONST-35096 | 3220 Sheppard Ave E, Scarborough | Condo | Clean Up |  | Unresolved | Lorna Kurok | Lorna Kurok | Olawale Olaniyan [X] | 2023-08-15 12:36 |  | 2024-12-03 11:21 |  |  | 2024-11-29 | 0 | 1 | _thumb_978599.png _thumb_978607.png _thumb_978601.png |  | CONST-35097, CONST-35098, CONST-35390, CONST-37198, CONST-37199, CONST-37200, CONST-37201, CONST-37202, CONST-37203, CONST-37204, CONST-37205, CONST-37206, CONST-37207, CONST-37208, CONST-37209, CONST-37210, CONST-37211, CONST-37212, CONST-37213, CONST-38482, CONST-38530, CONST-38908, CONST-39662, CONST-39663 |  | Requested by Oliver Davies, Could you please create a new ticket for an OSP plan & site walk at 3220 Sheppard Ave E? The East 3220 Condos recently registered and include 234 residential units near Pharmacy & Sheppard Ave E. ** *NEW PM INFO* Kay (PM) [kay@naldan-harris.com¦mailto:kay@naldan-harris.com] [tscc2914manager@gmail.com¦mailto:tscc2914manager@gmail.com] 1-416-819-2373 Marlen (Super) 1-416-887-4843 {color:#de350b}Old PM Info:{color} {color:#de350b}Jorgjeta Caci{color} {color:#de350b}[jorgjeta@nadlan-harris.com¦mailto:jorgjeta@nadlan-harris.com]{color} Directly across the street, 3260 Sheppard Ave E ([https://buildings.beanfield.com/buildings/view/18857]) is being built by Pinnacle International and will include 796 units. Ideally we can create a plan that will allow ease of access to this building in future. Thank you, | NUA+MA | [12 empty] | 0¦i48xbr: | [7 empty] | 9.2234e+18 | [19 empty] | Apr 29, 2024 - Project started. Hydro permit and City permit will be in progress soon. Project SAP is created and allocated with the original budget.] Jun 5th, 2024 - City permit is still pending approval. Locates completed. Jun 24th, 2024 - City permit is in. Locates is completed. Our team will schedule construction soon. Sept 2024 Writing Noting Construction is closed. Nov 14, 2024 - All panels prepped and spliced Nov 21, 2024 - Cable Pul asbuilt attached. Nov 29, 2024 - On Net date | [6 empty] | 3 - Normal | [21 empty] | 2024-04-29 |  |  |  | 234 |  | 2024-11-29 | 85309 |  |  | https://buildings.beanfield.com/buildings/view/18701 |  | CONST-35096 | 3 - Normal |  | Scarborough | 5123 | 13700
Construction | CONST-34175 | 2335 Sheppard Ave W, Toronto | Condo | Clean Up |  | Unresolved | Lorna Kurok | Lorna Kurok | Olawale Olaniyan [X] | 2023-06-01 13:56 |  | 2024-12-16 07:58 |  |  | 2024-12-13 | 0 | 0 |  |  | CONST-34176, CONST-34177, CONST-35413, CONST-38151, CONST-38161, CONST-38188, CONST-38189, CONST-38190, CONST-38191, CONST-38192, CONST-38193, CONST-38194, CONST-38195, CONST-38196, CONST-38197, CONST-38198, CONST-38199, CONST-38200, CONST-38707, CONST-39188, CONST-39359 |  | Please update PM info in Description to the following: *Miranda John, _Property Manager_* *685 Sheppard Avenue East, Suite 505* *North York, ON M2K 1B6* *Cell: 437 219 9144* *416-640-6730 EXT 216* ¦ [www.comfield.ca¦http://www.comfield.ca/] *[mirandaj@cfdi.ca¦mailto:mirandaj@cfdi.ca]* Floors 2 Units 152 Requested by Oliver Davies, Can you please queue up a site walk for 2355 Sheppard Ave W? There are 240 town home units here that we may be capable of bringing on-net. PM Info: *Sandy Majerle, Property Manager* 685 Sheppard Ave. E., Suite 505 North York, ON M2K 1B6 416-640-6730 Ext 137 ¦ ++ [www.comfield.ca¦http://www.comfield.ca/] [sandym@cfdi.ca¦mailto:sandym@cfdi.ca] Thank you, | FibreStream | [12 empty] | 0¦i42pbz: | [7 empty] | 9.2234e+18 | [19 empty] | Aug 20th, 2024 - Project started. City permit application is in progress. Sep 13, 2024 - City Permit Note: Short stream permit is ready to be submitted to the City of Toronto for Approval. Nov 18, 2024 - UG Construction Completed. Nov 26, 2024 - This building is being moved up from January 2025 to December 2024 to replace 58 Orchard view. We are trying to keep our Condo On Net target for the 2024. DEC 13, 2024 - Building Ready to Go On net. Dec 13, 2024 - City Asbuilt notes there are No Hard surface restorations. | [6 empty] | 3 - Normal | [21 empty] | 2024-08-15 |  |  | 2 | 152 |  | 2024-12-13 |  |  |  | https://buildings.beanfield.com/buildings/view/18458 |  | CONST-34175 | 3 - Normal |  | Toronto
Construction | CONST-29246 | 18 Holmes Ave, Toronto - Mona Lisa Residences | Condo | Clean Up |  | Unresolved | Lorna Kurok | Lorna Kurok | Jessica Markiewicz | 2022-07-11 16:07 |  | 2024-12-17 08:11 |  |  | 2024-12-16 | 0 | 1 |  |  | CONST-29247, CONST-29248, CONST-34902, CONST-34903, CONST-34904, CONST-34905, CONST-34906, CONST-34907, CONST-34908, CONST-34909, CONST-34910, CONST-34911, CONST-34912, CONST-34913, CONST-34914, CONST-34915, CONST-34916, CONST-34917, CONST-36817, CONST-37965, CONST-37966, CONST-38116 | CONST-34674 | Requested by Jay Fernandes Hi, I’ve gone through the remaining Fibrestream condos we have agreements for in the GTA and have grouped them in a way that I think makes sense for site visits and builds. There will be another list coming of buildings that don’t really fall into groups. Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. There are some current backbone (Sheppard) or NPOP (960 Lawrence) projects that will need to be completed to connect these but this will get everything into the system. Thanks! +*New PM Information:*+ Diana: [tscc2107manager@comfortpm.ca¦mailto:tscc2107manager@comfortpm.ca] Ioannis: [tscc2107admin@comfortpm.ca¦mailto:tscc2107admin@comfortpm.ca] +*Old PM Information:*+ PM: Kathy Laska monalisaresidences@gmail.com 647.847.2060 | Fiberstreamagreement, Yonge&Finch | [12 empty] | 0¦i3h8o7: | [7 empty] | 9.2234e+18 | [19 empty] | July 27/23 - Project initiated. Design and Permits in progress. Mar 05/24 - Permits and OSP construction will be completed on Doris Ave Condo Backbone. Budget updated September 5, 2024_Conduit has been completed Sept 4, 2024_ SOW Design has been uploaded Sept 9, 2024 - Riser Build Completed - Panels and ISP splicing Remain Sep 9, 2024_Cable Pull Completed, Asbuilt uploaded. Sep 10, 2024_Asbuilt added to PM (Design) Sept 13, 2024_all panels preped and spliced. Oct 15, 2024 Construction has been completed Nov 19, 2024 Project moved into December as it is connected with 60 Byne Ave Dec 16, 2024 - Building ON Net. | [6 empty] | 3 - Normal | [19 empty] | N/A |  | 2023-07-27 |  |  |  | 384 |  | 2024-12-16 | 8679 |  |  | https://buildings.beanfield.com/buildings/view/702 |  | CONST-29246 | 3 - Normal | 2024-05-31 | Toronto | 6854 | 14400
Construction | CONST-29249 | 18 Sommerset Way, North York - Sommerset at Northtown | Condo | Clean Up |  | Unresolved | Lorna Kurok | Lorna Kurok | Jessica Markiewicz | 2022-07-11 16:10 |  | 2024-12-18 08:10 |  |  | 2024-12-17 | 0 | 1 | _thumb_977064.png _thumb_977067.png _thumb_977065.png _thumb_977066.png |  | CONST-29250, CONST-29251, CONST-34541, CONST-34566, CONST-34567, CONST-34568, CONST-34569, CONST-34570, CONST-34571, CONST-34572, CONST-34573, CONST-36815, CONST-37989, CONST-38282, CONST-38283, CONST-38447, CONST-38474, CONST-39080, CONST-39081, CONST-39323 | CONST-34674, CONST-29255 | Requested by Jay Fernandes Hi, I’ve gone through the remaining Fibrestream condos we have agreements for in the GTA and have grouped them in a way that I think makes sense for site visits and builds. There will be another list coming of buildings that don’t really fall into groups. Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. There are some current backbone (Sheppard) or NPOP (960 Lawrence) projects that will need to be completed to connect these but this will get everything into the system. Thanks! *PM: Elaine Waller* *northtown2@delcondo.com* *416.225.3966* | FSactive, Fiberstreamagreement, Yonge&Finch | [12 empty] | 0¦i3h8ov: | [7 empty] | 9.2234e+18 | [19 empty] | June 27/23 - Only ISP work required. OSP will be completed on CONST-29255 Sep 12, Riser Fibre Pull_issue with running fibre from noth the east and west risers, encountered obstacles between floors 18 and 16. Plastic conduit was already filled with cables from other providers. Made several attempts using different conduits, but unable to get the fish through. Sep 13, 2024_Riser Fibre note: In progress - West cable pulled to pop. Sept 17, Riser Panels completed. Riser Fibre Pull completed Nov 15, 2024 Expecting to complete Conduit build by the end of Tuesday Nov 19, 2024 | [6 empty] | 3 - Normal | [19 empty] | N/A |  | 2023-06-27 |  |  | 21 | 283 | Integration | 2024-12-17 |  |  |  | https://buildings.beanfield.com/buildings/view/15617 |  | CONST-29249 | 3 - Normal | 2024-04-26 | North York | 3683 | 10665
Construction | CONST-26910 | 8081 Birchmount Rd, Markham - The Signature Condominium | Condo | Clean Up |  | Unresolved | Lorna Kurok | Lorna Kurok | Harvey Tran | 2022-02-22 12:12 |  | 2024-12-12 15:04 |  |  | 2024-11-27 | 0 | 1 |  |  | CONST-26926, CONST-26927, CONST-29956, CONST-30000, CONST-30001, CONST-30002, CONST-30003, CONST-30004, CONST-30005, CONST-30006, CONST-30007, CONST-30008, CONST-30009, CONST-30010, CONST-30011, CONST-30012, CONST-30296, CONST-37654, CONST-37936, CONST-37937 | CONST-26911, CONST-29425, CONST-26905, CONST-26906, CONST-26907, CONST-26908, CONST-26913, CONST-26914, CONST-26909, CONST-31856 |  | Bolton, FSactive, Fiberstreamagreement, Markham | [12 empty] | 0¦i37s6n: | [7 empty] | 9.2234e+18 | [19 empty] | August 11th - Project started. Design and Permits to be in progress. Sep 14/23 - Construction scheduled to start on CONST-29425 Sep 21st Oct 12/23 - Construction started Oct 3rd on CONST-29425 Jan 16/24 - Delay with construction schedule. Due dates updated. Apr 03/24 - Delay with construction schedule. Due dates updated. May 6th, 2024 - Project pushed back to mid Sep 2024 as we are not allowed to work in the area until mid Aug 2024. Oct 17, 2024 - Core completed, need to build the conduit hoping to plan for Friday Oct 25. Nov 8, 2024 - Cable pull Asbuilt attached Nov 18, 2024 - When reaching out to this building Connect with the followingwhen you want to visit this building you will need to reach out to the following: P1 POP - Justin Chow @ jchow@remfmi.commail_small.gif Residential Panels - Ryan Chen @ ryan.chen@remfmi.commail_small.gif Copy the following as well Andrew Ho - aho@remfmi.commail_small.gif Richard Chen - rchen@remfmi.commail_small.gif Nov 27, 2024 Building is On Net. In clean up so lorna can reconcile finance | [6 empty] | 3 - Normal | [19 empty] | Internal |  | 2022-08-11 |  |  |  | 300 | Integration | 2024-11-27 | 8749 |  |  | https://buildings.beanfield.com/buildings/view/6955 |  | 500428 | 3 - Normal | 2023-10-13 |  | 4400 | 12665
Construction | CONST-12153 | 200 Dundas St E - Dundas Square Gardens | Condo | Clean Up |  | Unresolved | Harvey Tran | Oguz Avci [X] | Oguz Avci [X] | 2020-03-13 09:13 |  | 2025-01-02 15:18 |  |  |  | 0 | 2 |  |  | CONST-13032, CONST-13033 |  | HENRY HERNANDEZ Assistant Property Manager Direct 416.666.9786 Email [henry.g.hernandez@fsresidential.com¦mailto:henry.g.hernandez@fsresidential.com] [www.fsresidential.com¦http://www.fsresidential.com/] | [13 empty] | 0¦i1vm47: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in Nov 29, 2023 Building is ON Net according to BB. | [6 empty] | 3 - Normal | [27 empty] | 2023-11-29 |  |  |  | https://buildings.beanfield.com/buildings/view/9920 |  |  | 3 - Normal |  | Toronto
Construction | CONST-34773 | 8 Trent Ave, Toronto | Condo | Clean Up |  | Unresolved | Lorna Kurok | Lorna Kurok | Olawale Olaniyan [X] | 2023-07-13 10:30 |  | 2025-01-06 15:14 |  |  | 2024-10-29 | 0 | 0 |  |  | CONST-34774, CONST-34775, CONST-35260, CONST-37150, CONST-37151, CONST-37152, CONST-37153, CONST-37154, CONST-37155, CONST-37156, CONST-37157, CONST-37158, CONST-37159, CONST-37160, CONST-37161, CONST-37162, CONST-37354, CONST-37355, CONST-37616, CONST-38019, CONST-38020, CONST-38999, CONST-39000 |  | Requested by Oliver Davies, A site walk is required for 8 Trent Ave. “The Village by Main Station” condos are located near Main St / Danforth Ave and include 277 units. PM Info: ¦*JIMMY CELA* Property Manager Cell: 647-242-0394 Direct 416-691-8093 [manager@villagebymainstation.com¦mailto:manager@villagebymainstation.com]¦ *Agent for and on behalf of:* *T.S.C.C. #2714 -* *Village by Main Station* *[8 Trent Avenue, Toronto, ON. M4C 0A6¦https://www.google.com/maps/search/8+Trent+Avenue,+Toronto,+ON.+M4C%0D%0A+0A6?entry=gmail&source=g]* ** Thank you, | NUA+MA | [12 empty] | 0¦i464m7: | [7 empty] | 9.2234e+18 | [19 empty] | Apr 25/24 - Project initiated. Design and permits in progress. May 15th, 2024 - Construction is required. City permit application is in progress. May 28/24 - Pm has requested no work to be conducted on-site in September as he is away Aug 28, 2024 - Riser Build Completed - Panels and ISP Remaining - OSP cable pull not completed Oct 10, 2024 Conduit Build Completed Oct 15, 2024 Splicing expected to be completed Oct 25.2024 | [6 empty] | 3 - Normal | [19 empty] | N/A |  | 2024-04-25 |  |  | 12 | 277 |  | 2024-10-29 | 20215 |  |  | https://buildings.beanfield.com/buildings/view/8382 |  | CONST-34773 | 3 - Normal | 2024-10-25 | Toronto | 7091 | 14655
Construction | CONST-29728 | 158 Front St E, Toronto - St. Lawrence Condominiums (BULK) | Condo | Clean Up |  | Unresolved | Harvey Tran | Olawale Olaniyan [X] | Jessica Markiewicz | 2022-07-29 16:05 |  | 2024-06-20 12:11 |  |  | 2024-05-31 | 0 | 1 |  |  | CONST-29729, CONST-29730, CONST-36240, CONST-36444, CONST-36445, CONST-36446, CONST-36447, CONST-36448, CONST-36449, CONST-36450, CONST-36451, CONST-36452, CONST-36453, CONST-36454, CONST-36455, CONST-36456, CONST-36457, CONST-36458, CONST-36757, CONST-36822, CONST-37077, CONST-37078, CONST-37082, CONST-37083, CONST-37098, CONST-37665, CONST-37666, CONST-37667, CONST-39547 | ACCT-128108 | Requested by Oliver Davies 158 Front St E is a Cityzen development that has recently began occupancy. It looks like they have some type of bulk agreement with Rogers. However, we also have a signed agreement here and given its location and the number of units I think it is worthwhile to get a lay of the land. Could you please queue up a site walk? BB Link: [https://buildings.beanfield.com/buildings/view/7423] +*New PM Info:*+ Admin – Alek Garbin Email - [stlawrencecondo.admin@fhkipling.com¦mailto:stlawrencecondo.admin@fhkipling.com] New PM info: ¦*Sean Taylor, MBA, CMCA®* _Senior Condominium Manager_ TSCC 2945 – St. Lawrence Condos 158 Front Street East Toronto, ON M5A 0K9 CMRAO No. 0024495538-GL¦ PM Office: 416.551.6603 Concierge: 416.551.6613 [stlawrencecondo.pm@fhkipling.com¦mailto:stlawrencecondo.pm@fhkipling.com]¦ *+Old PM Info:+* *St. Lawrence Condos – TSCC 2945* Vijay Ahuja, OLCM Senior Condominium Manager Forest Hill Kipling – Kipling Residential Management Inc. PM Office: 416.551.6603 ¦ [stlawrencecondo.pm@fhkipling.com¦mailto:stlawrencecondo.pm@fhkipling.com] PM Info: Hind Matar Condominium Manager [158front.cm@dukamanagement.com¦mailto:158front.cm@dukamanagement.com] Hind is aware of the visit and asked that we send a quick note ahead of time so they can let the concierge know. | BulkDeal | [12 empty] | 0¦i3ijxr: | [7 empty] | 9.2234e+18 | [19 empty] | September 19th - On hold due to existing bulk agreement with Rogers. Feb 06/24 - Project initiated. Design and permits in progress. Feb 07/24 - Route drawing completed. Feb 08/24 - Manhole survey completed Feb 09/24 - Hydro permit in progress Feb 21/24 - PO sent for Hydro permit (construction verification) Feb 28/24 - Hydro permit granted. Due dates updated. Feb 29/24 - Conduit build scheduled for Mar 13th. Cable pull scheduled for Mar 25th. Mar 01/24 - Vault access requested. Mar 06/24 - Conduit build PO sent Mar 12/24 - Budget updated with pre-wire & extra materials quote. Pre-wire PO sent to James for Sentrex Mar 13/24 - Conduit build completed. Invoice received. Mar 25/24 - Cable pull completed. Apr 25/24 - Updated budget uploaded. Budget updated on SAP May 3rd, 2024 - Splicing is scheduled. May 17th, 2024 - Splicing is in progress. June 3rd, 2024 - Building is currently on-net however our team is still working on the pre-wire as the building was not ready for us. However the building is on-net. Putting the status as clean up. | [6 empty] | 3 - Normal | [19 empty] | N/A |  | 2024-02-06 | [5 empty] | 2024-05-31 | 114880 |  |  | https://buildings.beanfield.com/buildings/view/7423 |  | CONST-29728 | 3 - Normal | 2024-06-28 |  | 58153.32 | 15243
Construction | CONST-17793 | 1 Florence Wyle Lane, Toronto (BULK) | Condo | Clean Up |  | Unresolved | Lorna Kurok | Lorna Kurok | Harvey Tran | 2020-12-21 16:52 |  | 2025-01-27 10:00 |  |  | 2024-10-22 | 0 | 3 |  |  | CONST-17794, CONST-33202, CONST-35145, CONST-35178, CONST-37385, CONST-37386, CONST-37387, CONST-37388, CONST-37389, CONST-37390, CONST-37391, CONST-37392, CONST-37393, CONST-37394, CONST-37395, CONST-37396, CONST-37397, CONST-37398, CONST-37399, CONST-37400, CONST-37401, CONST-38001, CONST-38370, CONST-38371, CONST-38901, CONST-38947, CONST-38948 |  | *New PM info:* *Michael Nyznyk* *Property Manager* *416-886-6469* T.: 905-275-9575 ext 329 125 Norfinch, Suite 203 North York, ON M3N 1W8 E: [michael.nyznyk@themeritusgroup.ca¦mailto:elinor.bahiti@themeritusgroup.ca] W: [www.themeritusgroup.ca¦http://www.themeritusgroup.ca/] *Old PM Info:* *Elinor Bahiti, RCM* *(he/him)* *Condominium Manager* T.: 905-275-9575 ext 323 125 Norfinch, Suite 203 North York, ON M3N 1W8 E: [elinor.bahiti@themeritusgroup.ca¦mailto:elinor.bahiti@themeritusgroup.ca] *OLD Info* *9 Doris Anderson Court* Property Manager: Anthony Gussin [anthony.gussin@rogers.com¦mailto:anthony.gussin@rogers.com] *BB:* [https://buildings.beanfield.com/buildings/view/13950#!contacts] | BulkDeal, Cybertec, PREWIRE | [12 empty] | 0¦i2cycf: | [7 empty] | 9.2234e+18 | [19 empty] | May 15th, 2024 - Project started. Route drawing and Survey to be scheduled. City permit application is also in progress Aug 7, 2024- Construction is expected to be completed for August 19, Conduit and Cable pull should be scheduled after august 19. Aug 27th, 2024 - Construction is tentatively scheduled Sep 14th. Moving project up to end of Oct 2024 Aug 28th, 2024 - Construction and cable pull scheduled. Building is aimed to be on net in Sep 2024 Sept 11, 2024_Hoping to reschedule Const to Sept 16, pending approval from the City work zone coordinator. SEPT 13, 2024_Conduit Build- Conduit for tie cable has been completed. Photos attached. Sept 13, 2024_ Note on SP Sow/Splicing (cable pull for building scheduled for tues sept 17th will return to complete cable entry.) Sept 17, 2024 Cable pulled and coiled awaiting for construction to be complete. Pending cable pull into building dependent upon construction work. Sept 19, 2024 - Construction expecting to be completed by the end of Sept 27th. Sept 23, 2024 - Panel Prep - all panels prepped and spliced Oct 22, 2024 Building Ready to Go OnNet | [6 empty] | 3 - Normal | [21 empty] | 2024-05-15 |  |  | 3 | 187 |  | 2024-10-22 | 139930 |  |  | https://buildings.beanfield.com/buildings/view/13950 |  | CONST-17793 | 1 - Very High | 2024-12-31 | Toronto | 26404 | 14175
Construction | CONST-19082 | 155 Merchants' Wharf - Aqualuna, Toronto (BULK) | Condo | Clean Up |  | Unresolved | Harvey Tran | Harvey Tran | Harvey Tran | 2021-02-26 11:57 |  | 2025-01-30 09:55 |  |  | 2024-05-08 | 0 | 2 |  |  | CONST-19083, CONST-19084, CONST-33251, CONST-33268, CONST-33269, CONST-33270, CONST-33271, CONST-33272, CONST-33273, CONST-33274, CONST-33275, CONST-33276, CONST-33277, CONST-33278, CONST-33279, CONST-33280, CONST-35943, CONST-37072, CONST-37073, CONST-37782, CONST-37783, CONST-38096, CONST-38162, CONST-38416, CONST-38808 | CONST-36323, CONST-39908, ORDER-192030, CONST-10170 |  | BulkDeal, PREWIRE | [12 empty] | 0¦i2hdjz: | [7 empty] | 9.2234e+18 | [19 empty] | Mar 09/23 - Project initiated. Pending permit & Design Aug 1/23 - City permit required. Due dates updated. Aug 11/23 - City permit approved. Aug 15/23 - Locate submitted. Oct 3/23 - Locates completed Oct 12/23 - Delay with construction schedule. Due dates updated. Nov 16/23 - PO sent to Sentrex Dec 07/23 - Construction completed. Cable has been pulled from our hand well to just inside the building. We will need to return to complete the cable pull once the internal conduit has been completed by builder. Due dates updated. Feb 07/24 - Quote from Cybertec approved under CONST-36323. Feb 08/24 - Transferred $7,500.00 from CONST-19082 (restoration budget) to CONST-36323 (design and permits budget) May 8th, 2024 - Project completed. Building is ready to be onnet. Restoration is pending till 2025. Aug 16th, 2024 - Additional cable and splitters build is required to accommodate the bulk deal. Jan 17, 2025 -1st occupancy inspection is now scheduled for Feb. 18, with the building inspectors, for all below-grade levels, ground floor, and residential floors from L2 to L7 with life-safety on L8, and mechanical penthouses. | [6 empty] | 3 - Normal | [19 empty] | External |  | 2023-03-09 |  |  | 16 | 225 |  | 2024-05-08 | 16505 |  |  | https://buildings.beanfield.com/buildings/view/13366 |  | CONST-19082 | 3 - Normal | 2023-09-15 | Toronto | 51188
Construction | CONST-29261 | 35 Finch Ave, North York - Chicago Residences | Condo | Clean Up |  | Unresolved | Lorna Kurok | Lorna Kurok | Jessica Markiewicz | 2022-07-11 16:20 |  | 2025-02-21 10:34 |  |  | 2024-11-20 | 0 | 1 |  |  | CONST-29262, CONST-29263, CONST-34867, CONST-34881, CONST-34882, CONST-34883, CONST-34884, CONST-34885, CONST-34886, CONST-34887, CONST-34888, CONST-34889, CONST-34890, CONST-34891, CONST-34892, CONST-34893, CONST-34894, CONST-34895, CONST-38123, CONST-38277, CONST-38278, CONST-39277, CONST-39278 |  | Updated PM as of July 30, 2024 Below is the updated PM info: *Project Management Contact information:* Ilirjana Asani Property Manager [thechicago@mrcm.ca¦mailto:thechicago@mrcm.ca] *Maple Ridge Community Management – An Associa® Company* O: 905-507-6726 extension 507 *Below is the initial project information:* Requested by Jay Fernandes Hi, I’ve gone through the remaining Fibrestream condos we have agreements for in the GTA and have grouped them in a way that I think makes sense for site visits and builds. There will be another list coming of buildings that don’t really fall into groups. Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. There are some current backbone (Sheppard) or NPOP (960 Lawrence) projects that will need to be completed to connect these but this will get everything into the system. Thanks! *PM: Sergio Besir* *thechicago@mrcm.ca* *905.507.6726 x311* | FSactive, Fiberstreamagreement, Yonge&Finch | [12 empty] | 0¦i3h8xb: | [7 empty] | 9.2234e+18 | [19 empty] | July 27/23 - Project initiated. Design & Permit in progress. Feb 23/24 - City permit granted Aug 27th, 2024 - Locates are in, construction will be scheduled soon. Sept 5, 2024 Cable pull scheduled for Oct 3rd, need conduit built Sept 9, 2024 - Riser Build Completed - Panels and ISP splicing remain Sept 12, 2024 - conduit Build _ waiting of PM to receive approval from Board. Floor plans required. Sept 13, 2024_ Asbuilt sent to the city of Toronto Oct 15, 2024 - Construction to return to site on Oct 17th to connect building. Oct 16, 2024 No restoration required October 2, 2024 -Note - Pm has approved conduit work Nov 20, 2024 - Building On Net Nov 20, 2024 Clean Up Lorna to reconcile Sap Feb 20, 2025 - Reconciled SAP, Project closed no outstanding pos. No Hard surface restorations required. Asbuilts completed | [6 empty] | 3 - Normal | [19 empty] | Internal |  | 2023-07-27 |  |  |  | 233 | Integration | 2024-11-20 | 19584 |  |  | https://buildings.beanfield.com/buildings/view/15447 |  | CONST-29261 | 3 - Normal | 2024-04-26 |  | 5483 | 15455
Construction | CONST-29207 | 50 Forest Manor Rd, Toronto - Fifth on the Park | Condo | Clean Up |  | Unresolved | James Mowers | Lorna Kurok | Jessica Markiewicz | 2022-07-11 15:27 |  | 2025-02-19 08:01 |  |  | 2025-02-21 | 0 | 1 |  |  | CONST-29208, CONST-29209, CONST-33977, CONST-34002, CONST-34003, CONST-34004, CONST-34005, CONST-34006, CONST-34007, CONST-34008, CONST-38120 | CONST-33772, CONST-29078, CONST-29216, CONST-29219, CONST-12142, CONST-29210, CONST-32361 | Requested by Jay Fernandes Hi, I’ve gone through the remaining Fibrestream condos we have agreements for in the GTA and have grouped them in a way that I think makes sense for site visits and builds. There will be another list coming of buildings that don’t really fall into groups. Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. There are some current backbone (Sheppard) or NPOP (960 Lawrence) projects that will need to be completed to connect these but this will get everything into the system. Thanks! *PM: Andrew Lo* *fifthonthepark.pm@delcondo.com* *416.493.8349* | FSactive, Fiberstreamagreement, Sheppard | [12 empty] | 0¦i3h85j: | [7 empty] | 9.2234e+18 | [19 empty] | May 01/23 - Forest Manor is under moratorium until the end of 2025. - Does not affect build May 18/23 - ISP only. Will be fed from CONST-29210 Aug 15, 2024 - Riser Build Completed all panels have been Spliced ISP is in 52 Forest Manor Oct 1, 2024_moving 50 and 52 forest Manor to the December 2024 on the ON Net schedule. We are waiting on a permit, redesign required, due PM not agreeing to have a vault. Nov 22, 2024 - moving this building to February 27 2025, still pending permits. Feb 12, 2025 - OTDR Ruby testing note: Splicing is complete, ready for testing. Feb 18, 2025- Building is On Net. Email sent. Feb 18, 2025 - Need to Reconcile finances, asbuilts completed, no restorations required. | [6 empty] | 3 - Normal | [19 empty] | N/A |  | 2023-05-18 |  |  | 24 | 262 | Integration | 2025-02-18 |  |  |  | https://buildings.beanfield.com/buildings/view/15569 |  | CONST-29207 | 3 - Normal | 2024-03-29 | Toronto | 4289
Construction | CONST-26909 | 8110 Birchmount Rd, Markham - Nexus North | Condo | Clean Up |  | Unresolved | Lorna Kurok | Lorna Kurok | Harvey Tran | 2022-02-22 12:10 |  | 2025-02-11 12:48 |  |  | 2024-11-26 | 0 | 1 |  |  | CONST-26924, CONST-26925, CONST-29957, CONST-30013, CONST-30014, CONST-30015, CONST-30016, CONST-30017, CONST-30018, CONST-30019, CONST-30020, CONST-30021, CONST-30022, CONST-30023, CONST-30024, CONST-30025, CONST-30295, CONST-36810, CONST-37167, CONST-37168, CONST-37283, CONST-39395, CONST-39396 | CONST-26911, CONST-29425, CONST-26905, CONST-26906, CONST-26907, CONST-26908, CONST-26913, CONST-26914, CONST-26910, CONST-31856 | PM Contact: Richard Chen <[rchen@remfmi.com¦mailto:rchen@remfmi.com]> District Manager for the Building / Area | Fiberstreamagreement, Markham | [12 empty] | 0¦i37s47: | [7 empty] | 9.2234e+18 | [19 empty] | August 11th - Project started. Design and Permits to be in progress. Sep 14/23 - Construction scheduled to start on CONST-29425 Sep 21st Sep 27/23 - City permit granted Oct 12/23 - Construction started Oct 3rd on CONST-29425 Nov 02/23 - Due to not having construction approval at this time. Due dates updated. Jan 16/24 - Delay with construction schedule. Due dates updated. Apr 29th, 2024 - Cable pull is scheduled May 3rd. Still pending SOW for splicing. May 1st, 2024 - Construction to be scheduled soon. Cable pull is also scheduled after construction completion. May 2nd, 2024 - Construction is being pushed back due to the work of 3rd party. Temporarily pushing back this building to July 2024. May 8th, 2024 - Construction is delayed till end of Aug 2024 due to the other work is still in progress and the site is not ready for our work. Project is pushed back to end of Sep 2024. Aug 2, 2024_Municipal permit approved, requires a pre and post construction inspection. Aug 8, 2024_ Construction Portion_This is affected by CIK. The city will not allow CIK to construct until the end of August. Sept 4, 2024_SOW design Details Uploaded Oct 16, 2024_CIK should be completed there portion by the end of the week Oct 18th Nov 7, 2024- CIK has completed work, just waiting on Cable pull Nov 26, 2024 - Building is ON Net. Feb 4, 2025 - The city asbuilt was submitted under the Enterprise Backbone project. | [6 empty] | 3 - Normal | [19 empty] | Internal |  | 2022-08-11 |  |  | 14 | 378 |  | 2024-11-26 | 8083 |  |  | https://buildings.beanfield.com/buildings/view/3074 |  | 500429 | 3 - Normal | 2023-10-13 | Markham | 6387 | 16540
Construction | CONST-29283 | 17 Anndale Dr, North York - Savvy | Condo | Clean Up |  | Unresolved | James Mowers | Lorna Kurok | Jessica Markiewicz | 2022-07-12 08:48 |  | 2025-02-11 13:31 |  |  | 2025-01-14 | 0 | 0 | _thumb_1056524.png _thumb_1056519.png _thumb_1069244.png _thumb_1069243.png _thumb_1056521.png _thumb_1056520.png |  | CONST-29284, CONST-29285, CONST-36668, CONST-36674, CONST-36675, CONST-36676, CONST-36677, CONST-36678, CONST-36679, CONST-36680, CONST-36681, CONST-36682, CONST-36683, CONST-36684, CONST-36685, CONST-36686, CONST-36687, CONST-39007, CONST-39011, CONST-39073, CONST-39360 | CONST-28166 | Requested by Jay Fernandes Hi, I’ve gone through the remaining Fibrestream condos we have agreements for in the GTA and have grouped them in a way that I think makes sense for site visits and builds. There will be another list coming of buildings that don’t really fall into groups. Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. There are some current backbone (Sheppard) or NPOP (960 Lawrence) projects that will need to be completed to connect these but this will get everything into the system. Thanks! *PM: Adriana Bacila* *savvycondominiums@crossbridgecs.com* *416.221.2999* | FSactive, Fiberstreamagreement, Yonge&Shep | [12 empty] | 0¦i3ha5j: | [7 empty] | 9.2234e+18 | [19 empty] | Feb 29/24 - Project initiated. Design and permits in progress. Apr 30th, 2024 - Project on-hold as per requested by building's internal stakeholders. As this building has a high pen % rate with FibreStream. May 3, 2024 - Project is placed on hold as per Oliver Davies in May 1st. Oct 30, 2024 - Project is active, Construction is hoping to schedule for Nov 18. Depending on PM approval Oct 30, 2024 - this on the ON Net schedule for January 17, 2025 Nov 18, 2024 - Construction Start Date as per City is Nov 25, 2024 Dec 6, cable pull asbuild attached. Dec 10, 2024 - Riser Panels - All of the panels are installed as per riser diagram Jan 13, 2025 - Expected On Net date is January 15, 2025 Jan 14, 205 - Building On Net date is actually Jan 14, 2025 Feb 4, 2025 - Asbuilts completed | [6 empty] | 3 - Normal | [19 empty] | Internal |  | 2024-02-29 |  |  | 22 | 311 | Integration | 2025-01-14 | 52017 |  |  | https://buildings.beanfield.com/buildings/view/15454 |  | CONST-29283 | 3 - Normal | 2024-08-30 | North York | 6368 | 14670
Construction | CONST-35429 | 501 Yonge St / 18 Maitland Terr, Toronto - Teahouse Condos | Condo | Clean Up |  | Unresolved | James Mowers | Lorna Kurok | Olawale Olaniyan [X] | 2023-10-04 08:24 |  | 2025-02-26 08:34 |  |  | 2025-02-25 | 0 | 0 |  |  | CONST-35430, CONST-35431, CONST-35487, CONST-38675, CONST-38694, CONST-38695, CONST-38696, CONST-38697, CONST-38698, CONST-38699, CONST-38700, CONST-38701, CONST-38702, CONST-38703, CONST-38704, CONST-38705, CONST-38706, CONST-38774, CONST-38775, CONST-39119, CONST-39546, CONST-39570, CONST-39921, CONST-40185 |  | Requested by Oliver Davies, Units 960 Floor 52 Can you please create a ticket for an OSP plan & site walk at the new “Teahouse Condos” at 501 Yonge St / 18 Maitland Terrace? There are 960 residential units that makeup the TSCC 2972 corporation. PM Info: *Kristie Pun* OLCM-L ¦ Condominium Manager ¦ *DUKA Property Management Inc.* As Agents for and on Behalf of T.S.C.C 2972 501 Yonge Street, Toronto, ON M4Y 0G8 Tel: 416-323-1430 ¦ Concierge: 416-929-8136 [teahouse.scm@dukamanagement.com¦mailto:teahouse.scm@dukamanagement.com] Thank you, | NUA+MA | [12 empty] | 0¦i4czrr: | [7 empty] | 9.2234e+18 | [19 empty] | Agreement signed Oct 2, 2024, 2 old budgets formates need to determine which budget should be applied? Oct 4 created task codes, Planning will begin shortly. Oct 7, 2024 Applied budget to SAP. Dec 16, 2024 - Hydro Permit note, hydro package ready to be submitted to Hydro. Dec 16, 2024 - Riser Panels - All panels installed per diagram Dec 16, 2024 - Riser Fibre Pull - Experiencing challenges roping the 501 Yonge side of the building. Dec 18, 2024 - Riser Diagram Completed January 13, 2025 Hydro Permit is granted D2024-00361 January 13, 2025 - Booking Hydro Access for January 29, 2025 January 13, 2025 - Cable pull scheduled for Jan 27 to 29, Hydro access appointment booked for January 29th 9:30 am, details in Cable Pull task code. January 14, 2025 - Conduit Build-Site walk completed, it is approx. 30m built to the existing pull box, conduit build scope completed. January 17, 2025 - Conduit Build Sketch - Troy has reached out to the pm for floor plans. January 21, 2025 - Cable Pull scheduled for Jan 27 to 29. Jan 27, 2025 - Cable pull in progress. January 21, 2025 - On Net Schedule Change, we moved this building from April to February. January 21, 2025 - conduit build sketch added. Jan 29, 2025, - OSP splicing only need cable pull to be completed, to complete OSP splicing. Jan 30th - Cable pull has been completed into building through vault. Will need to return once conduit is installed and pull to POP Feb 6, 2025 - Korey meeting with conduit manager feb 10, 2025 to discuss short conduit build in retail space. Feb 7, 2025 OSP Splicing completed, ready for testing. Feb 21, 2025 - Isp splicing completed Feb 25, 2025 - Building is ON net. | [6 empty] | 3 - Normal | [20 empty] | 2025-02-25 | 2024-10-02 |  |  | 52 | 960 |  | 2025-02-25 |  |  |  | https://buildings.beanfield.com/buildings/view/15219 |  | CONST-35429 | 3 - Normal | 2025-04-17 | Toronto
Construction | CONST-32674 | 7895 Jane Street - The Met | Condo | Clean Up |  | Unresolved | Harvey Tran | Olawale Olaniyan [X] | Denise King | 2023-01-12 11:56 |  | 2024-10-22 15:41 |  |  | 2024-05-24 | 0 | 0 |  |  | CONST-32675, CONST-32676, CONST-33490, CONST-33508, CONST-33509, CONST-33510, CONST-33511, CONST-33512, CONST-33513, CONST-33514, CONST-33515, CONST-33517, CONST-33518, CONST-33519, CONST-33520, CONST-33521, CONST-33522, CONST-33523, CONST-35376, CONST-36809, CONST-37104, CONST-37105, CONST-38821, CONST-38822, CONST-40243 |  | *+New PM Contact:+* John Wannamaker Regional Director for Berkley PM [jwannamaker@berkleypm.ca¦mailto:jwannamaker@berkleypm.ca] +*Old PM Contact:*+ ¦Jennifer Morales, HBA, OLCM¦ ¦ ¦ ¦ ¦ ¦Property Manager¦ ¦ ¦ ¦ ¦ ¦Berkley Property Management Inc.¦ ¦ ¦ ¦ ¦ ¦_____________________________________¦ ¦ ¦ ¦ ¦ ¦Agents for and on behalf of:¦ ¦ ¦ ¦ ¦ ¦York Region Standard Condominium Coporation No. 1447¦ ¦ ¦ ¦ ¦ ¦7895 Jane Street¦ ¦ ¦ ¦ ¦ ¦Concord, Ontario¦ ¦ ¦ ¦ ¦ ¦L4K 0K2¦ ¦ ¦ ¦ ¦ ¦Direct: (289) 843-3087¦ ¦ ¦ ¦ ¦ ¦Office: (905) 597-0549¦ ¦ ¦ ¦ ¦ ¦Fax: (905) 597-0564¦ ¦ ¦ ¦ ¦ ¦[E-mail: ¦mailto:stilak@berkleypm.ca] [jmorales@berkleypm.ca¦mailto:stilak@berkleypm.ca]¦ ¦ ¦ ¦ ¦ We have a FibreStream agreement for this location (never launched). | Fiberstreamagreement | [12 empty] | 0¦i3szz3: | [7 empty] | 9.2234e+18 | [19 empty] | Mar 30/23 - Project initiated, Design and Permits in progress. July 19/23 - Hydro permit not required. Jan 16/24 - City permit granted. Jan 26/24 - Construction scheduled to start Feb 5th Feb 09/24 - Construction completed. Mar 21/24 - Cable pull scheduled for Apr 8th Apr 01/24 - Cable pull scheduled for Apr 17th Apr 17/24 - Cable pull completed. May 3rd, 2024 - Splicing is scheduled for May 7th. May 17th 2024 - Fixing will be required. Our team is on site to work on this. Pushing back the building due date to May 24th. | [6 empty] | 3 - Normal | [19 empty] | Internal |  | 2023-05-30 | [5 empty] | 2024-05-24 | 36358 |  |  | https://buildings.beanfield.com/buildings/view/12916 |  | CONST-32674 | 3 - Normal | 2024-02-09 |  | 8494 | 18120
Construction | CONST-36205 | 30 Meadowglen Pl, Scarborough, ME Living | Condo | Clean Up |  | Unresolved | James Mowers | Lorna Kurok | Olawale Olaniyan [X] | 2024-01-15 13:09 |  | 2025-02-24 09:17 |  |  | 2025-02-12 | 0 | 0 | _thumb_1114010.png |  | CONST-36206, CONST-36207, CONST-38347, CONST-38358, CONST-38500, CONST-38501, CONST-38502, CONST-38503, CONST-38504, CONST-38505, CONST-38506, CONST-38507, CONST-38508, CONST-38509, CONST-38510, CONST-38511, CONST-38512, CONST-38513, CONST-38891, CONST-38951, CONST-39554, CONST-39827, CONST-40019 |  | Units 327 Floors 28 Approx year of build 2021 Updated As of September 4, 2024_please update PM info to the following: {*}Goutam Sikder{*}{*}, MBA , OLCM , RCM{*} *Condominium Manager* *Agent for and on behalf of: T.S.C.C. 2808* *Me Living I* *30 Meadowglen Pl* *Toronto, Ontario* *M1G 0A6* *Phone:* (416) 438-6221 *Email:* +[Meliving1.pm@delcondo.com¦mailto:Meliving1.pm@delcondo.com]+ Requested by Oliver Davies, When you have a moment can you please create a new site walk & OSP ticket for 30 Meadowglen Pl? The “ME Living” condos are about 3 years old and include 327 residential units. CDSH10700 is located immediately across the street from this building on the west side of Markham Rd just south of Lawrence Ave E. @James, I will be meeting with the board here next Wednesday (24th) evening to discuss Beanfield’s access, if possible, having the budget in place will be a big help. PM Info: *CAROL WANG* Senior Condominium Manager *MTCC 886 ¦ TSCC 2808* 2645 Skymark Avenue, Suite 101 ¦ Mississauga, ON L4W 4H2 Direct 647.258.8203 ¦ Property Fax: 416.293.5904 [carol.wang@fsresidential.com¦mailto:carol.wang@fsresidential.com] | NUA+MA | [12 empty] | 0¦i4kb67: | [7 empty] | 9.2234e+18 | [19 empty] | Sept 18, 2024_Signed Agreements are in place and we can initiate this Condo, as of Sep 17, 2024. Sept 18, 2024_Estimating Due Date for Condo Feb 14, 2025. Sept 23, 2024_ Troy Browne (Design) has noted that quote is required from a consultant. Oct 16, 2024 Permit has been circulated Nov 11, 2024 - Project has been submitted to the city DFX Nov 15, 2024 City Permit has been sent to the Utility Review dept for Review. Nov 22, 2024 - Submitting for locates Nov 26, 2024 - Approved city of markham permit attached Jan 7, 2025 - Locates Submitted Jan 16, 2025 - No conduit sketch required. We are intercepting the building ducts. Jan 21, 2025 - Internal work completed Jan 21, 2025 - Locates Completed. Jan 21, 2025 - UG construction is in progrss began Jan 20. Expected to be completed next tuesday Jan 28, 2025. Feb 3, 2025 - OSP Construction is completed and roped. Cable pull is completed. Feb 7, 2025 - Cable pull completed. Feb 10, 2025 - ISP splicing is completed. Feb 4, 2025 - Scheduled to go ON Net for February 14, 2025 Feb 11, 2025 - OSP splicing completed Feb 12, 2025 - Building is On Net. City Asbuilts attached and need to close Finance. unknown restoration situation. Feb 24, 2025 - City Asbuilt recd. There are no Hardsurface restorations, but it does require soft surface seed and sod restorations. Waiting on Noramco Invoice, materials were recd. Restoration funds included on Rest. tracker 2026. | [6 empty] | 3 - Normal | [21 empty] | 2024-09-17 |  |  | 28 | 327 |  | 2025-02-12 |  |  |  | https://buildings.beanfield.com/buildings/view/8701 |  | CONST-36205 | 3 - Normal |  | Scarborough
Construction | CONST-32051 | 75 St Nicholas St, Toronto - Nicholas Residences | Condo | Clean Up |  | Unresolved | James Mowers | Lorna Kurok | Jessica Markiewicz | 2022-11-23 12:30 |  | 2025-02-24 09:52 |  |  | 2025-01-03 | 0 | 3 |  |  | CONST-32053, CONST-32054, CONST-32288, CONST-32292, CONST-32293, CONST-32294, CONST-32295, CONST-32296, CONST-32297, CONST-32298, CONST-32299, CONST-32300, CONST-32301, CONST-32302, CONST-32303, CONST-32304, CONST-32305, CONST-32306, CONST-32307, CONST-32308, CONST-36249, CONST-36658, CONST-37297, CONST-37306, CONST-39656, CONST-39657 | CONST-4782, CONST-33354 | _Updated Property Manager August 21, 2024:_ *Meredith Rosenfeldt* Condominium Manager TSCC 2444 75 St. Nicholas Street Toronto, ON 416 944 3517 - Site Office [MRosenfeldt@mrcm.ca¦mailto:MRosenfeldt@mrcm.ca] Requested by Jay Fernandes. Good Afternoon, We missed some condos that have agreements. Can we get these added and site walks and budgets. There are some old tickets created you can reuse or just start fresh. +*New Property Contact:*+ Jill Mark tscc2444@fsresidential.com +*Old Property Manager:*+ JULIA POWER FirstService Residential 2645 Skymark Avenue, Suite 101 ¦ Mississauga, ON L4W 4H2 Direct 416.568.1935 ¦ Toll Free 1.855.244.8854 Email julia.power@fsresidential.com www.fsresidential.com 35 Storeys Pop located in side of hydro room on p1 near ramp 1 riser Panels start on 3 rd floor | FSactive, Fiberstreamagreement | [12 empty] | 0¦i3px27: | [7 empty] | 9.2234e+18 | [19 empty] | December 9th - Project initiated. Design and Permits to be in progress. Jan 18/24 - OSP construction scheduled to be completed earlier than planned. Due dates update. PO sent to Sentrex Mar 13/24 - Construction in progress Mar 22/24 - Conduit build scheduled for Apr 9th. Cable pull scheduled for Apr 18th Mar 28/24 - Building management scheduled construction approval meeting for Apr 24th. Due dates updated. May 7th, 2024 - Our team is still waiting for the building approval to start construction. May 17th, 2024 - Still pending approval for construction. Followed up. June 5th, 2024 - Still no luck with the construction approval. Pushing back the due date to August 2024 August 21, 2024 Updated property manager August 30, 2024_Once Troy Browne has completed a scope of work that can be submitted to the building, Hopefully they will approve so we can move forward. This task is being completed under the Cable pull Drawing subtask Oct 29, 2024, Due date change to from December 2024 to January 2025. Permits expired due to hold up on Approvals from buildings board. We need to resubmit permits and obtain locates. James M. has communicated with the PM to make them aware this can not completed until January of 2025. Nov 13, 2024 City Permit approved short stream 1000321001 Dec 10, Conduit Build started Dec 12, 2024 - Conduit Completed pictures uploaded. Dec 16, 2024 - Cable pull asbuilt attached. Jan 3, 2025 - Building is On Net ready. Pending city Asbuilt and close out of finances. Jan 8, 2025 Asbuilt added to Patch Manager. Feb 21, 2025 - City asbuilt attached and recd from sentrex. But it does not provide Restoration notes. | [6 empty] | 3 - Normal | [19 empty] | External |  | 2022-12-09 |  |  | 35 | 307 | Integration | 2025-01-03 | 23226 |  |  | https://buildings.beanfield.com/buildings/view/2380 |  | 500520 | 3 - Normal | 2024-01-26 | Toronto | 4719 | 14910
Construction | CONST-34496 | 39 Roehampton Ave, Toronto - E2 Condos | Condo | Clean Up |  | Unresolved | Lorna Kurok | Lorna Kurok | Olawale Olaniyan [X] | 2023-06-22 15:25 |  | 2025-02-24 11:21 |  |  | 2024-08-09 | 0 | 1 |  |  | CONST-34497, CONST-34498, CONST-35137, CONST-36937, CONST-36938, CONST-36939, CONST-36940, CONST-36941, CONST-36942, CONST-36943, CONST-36944, CONST-36945, CONST-36946, CONST-36947, CONST-36948, CONST-36949, CONST-36950, CONST-36951, CONST-36952, CONST-36953, CONST-37564, CONST-37604, CONST-38003, CONST-38534, CONST-38535 |  | Requested by Oliver Davies, Can you please queue up a site walk for the E2 Condos at 39 Roehampton Ave? This is the new sister building to the [E Condos at 8 Eglinton Ave E¦https://buildings.beanfield.com/buildings/view/8827]. Site Contacts: [michael.horth@melbournepm.ca¦mailto:michael.horth@melbournepm.ca] [taylor.franco@melbournepm.ca¦mailto:taylor.franco@melbournepm.ca] OR JENNA *LAWSON* DIRECTOR OF CONDOMINIUM MANAGEMENT 1244 Caledonia Road, Suite 100 Toronto, ON. M6A 2X5 Direct: 416-546-2126 x160 Email: [jenna.lawson@melbournepm.ca¦mailto:jenna.lawson@melbournepm.ca] Thank you, | NUA+MA | [12 empty] | 0¦i44hu7: | [7 empty] | 9.2234e+18 | [19 empty] | Mar 28/24 - Project initiated. Design and permits in progress Apr 01/24 - Route drawing uploaded Apr 09/24 - Manhole survey completed May 31st, 2024 - Hydro permit is granted. Cable pull schedule is possible to move up. Project due date will be updated once our team can confirm the new schedule. June 3rd, 2024 - Cable pull is tentatively scheduled to be completed by late July. Aug 6, 2024 - Schedule to be completed On Net for the month of August Aug 9, 2024 - Building is ON Net. August 9, 2024 Feb 24, 2025 - No city permit required, therefore no ug work, Toronto hydro permit and asbuilt submitted to THES. THES po recd. | [6 empty] | 3 - Normal | [19 empty] | External |  | 2024-03-28 | [5 empty] | 2024-08-09 | 41629 |  |  | https://buildings.beanfield.com/buildings/view/17876 |  | CONST-34496 | 3 - Normal | 2024-12-27 | Toronto | 7502 | 12120
Construction | CONST-35056 | 20 Edward St, Toronto - Panda Condo (BULK) | Condo | Clean Up |  | Unresolved | Lorna Kurok | Lorna Kurok | Olawale Olaniyan [X] | 2023-08-08 17:45 |  | 2025-02-24 14:43 |  |  | 2024-06-20 | 0 | 2 |  |  | CONST-35057, CONST-35058, CONST-35444, CONST-36388, CONST-36389, CONST-36390, CONST-36391, CONST-36392, CONST-36393, CONST-36394, CONST-36395, CONST-36396, CONST-36397, CONST-36398, CONST-36399, CONST-36400, CONST-36401, CONST-36402, CONST-36756, CONST-36821, CONST-36990, CONST-36991, CONST-37668, CONST-37669, CONST-37670, CONST-38939 |  | Requested by Oliver Davies, Can you please queue up a site walk and OSP plan for 20 Edward St? This location was built by Lifetime Developments and is under a bulk-services agreement with Rogers. The bulk-services agreement will expire in July 2024 and the board is reviewing their options. PM info: *Tiffany Artinian, OLCM* Property Manager Tel. 905-605-7788 Fax. 905-605-7799 Cel. 647-628-5103 E-mail. [tiffanya@comfortpm.ca¦mailto:tiffanya@comfortpm.ca] Thank you, | BulkDeal | [12 empty] | 0¦i48ef3: | [7 empty] | 9.2234e+18 | [19 empty] | Feb 01/24 - Agreement received. Project initiated, design and permits in progress. Feb 02/24 - Route drawing uploaded. Feb 05/24 - Manhole survey completed Feb 14/24 - Hydro permit in progress Feb 21/24 - Hydro permit PO sent (construction verification) Feb 23/24 - Conduit build scheduled for Mar 14th Feb 26/24 - Conduit build PO sent Feb 28/24 - Hydro permit granted. Due dates updated Feb 29/24 - Cable pull scheduled for Mar 26th Mar 01/24 - Vault access requested Mar 05/24 - Conduit build scheduled for Mar 14th. Cable pull scheduled for Mar 26th Mar 06/24 - PO sent to AP for vault access (cable pull) Mar 12/24 - Budget updated with pre-wire & extra materials quote. Pre-wire PO sent to James for Sentrex Mar 13/24 - Invoice for vault access received. Mar 14/24 - Conduit build rescheduled for Mar 25th Mar 25/24 - Conduit build completed. Mar 26/24 - Conduit build invoice received. Cable pull completed. May 3rd, 2024 - Splicing completed. Testing will be scheduled soon. May 10th, 2024 - Prewire task is in progress. Completed invoiced sept 2024 March 28, 2024 - THES Asbuilt sent to Toronto Hydro, 1 outstanding purchase order for Toronto Hydro Construction Verification, there is no city drawings/permit, no hard surface restorations required. Feb 24, 2025 -Reconciled SAP. Still outstanding purchase order. | [6 empty] | 3 - Normal | [19 empty] | N/A |  | 2024-02-01 |  |  | 30 | 560 |  | 2024-06-20 | 118999.4 |  |  | https://buildings.beanfield.com/buildings/view/6077 |  | CONST-35056 | 3 - Normal | 2024-07-19 |  | 74057.8 | 15130
Construction | CONST-36518 | 45 Strachan Ave, Toronto | Condo | Clean Up |  | Unresolved | James Mowers | Lorna Kurok | Olawale Olaniyan [X] | 2024-02-09 13:09 |  | 2025-02-03 07:57 |  |  | 2025-01-17 | 0 | 0 |  |  | CONST-36519, CONST-36520, CONST-36652, CONST-37719, CONST-37720, CONST-37721, CONST-37722, CONST-37723, CONST-37724, CONST-37725, CONST-37726, CONST-37727, CONST-37729, CONST-37730, CONST-37758, CONST-37766, CONST-37767, CONST-37951, CONST-37953, CONST-37954, CONST-38778, CONST-39357, CONST-39742 | CONST-36836 | *Updated Property Manager Information: January 22, 2025* Damon Thomas 647-660-1769 [Damon.Thomas-Anderson@bentallgreenoak.com¦mailto:Damon.Thomas-Anderson@bentallgreenoak.com] Requested by Oliver Davies, Could you please proceed with creating an OSP plan & site walk ticket for 45 Strachan Ave? This is a new rental tower being constructed by BGO, directly north of the On Net [Ordnance St¦https://buildings.beanfield.com/buildings?q=ordnance] MDUs. There will be 433 residential units in this tower, and occupancy is slated for Fall 2025. *NEW PM Info:* _Alberto Robles_ Superintendent, Operations (Residential) ¦C: 647.403.6846 E: [arobles@ellisdon.com¦mailto:arobles@ellisdon.com] 45 Strachan Development 45 Strachan Ave, Toronto, ON M6K 3SR +[www.ellisdon.com¦http://www.ellisdon.com/]+¦ Site Contact: *Pegah Moghani* Project Manager *EllisDon Corporation* 1004 Middlegate Road Mississauga, ON, L4Y 1M4 M: 416-409-4861 E: [pmoghani@ellisdon.com¦mailto:pmoghani@ellisdon.com] Thank you, | NUA+MA, PREWIRE | [12 empty] | 0¦i4m8en: | [7 empty] | 9.2234e+18 | [19 empty] | Jan 18th, 2024 - Project started, Design and city permit in progress. August 16, 2024_Permissions to construct associated with this permit extend through to FEBRUARY 16th, 2025 (6 months from the Permit’s Granted date). Sept 3, 2024_Cable pull scheduled for Oct 2, 2024 Sept 12, 2024_Noting_This is a new build. Union Electricians will build our conduit here. Sept 12, 2024_Conduit build completed Sep 18, 2024 Riser Cable Pull Note: Risers are built up to 27. Sept 20, 2024_Cable pull planned for Oct 2, 2024 Jan 6, 2025_ meeting Notes this building can be put listed On Net January but the building Construction is still in Progress. Jan 8, 2025_ Panel prep is completed Jan 10, 2025- Prewire portion still in progress.Contractor has completed pulling suites upto the 22nd floor. Occupancy is anticipated for Fall of 2025. Jan 13, 2025- Internal splicing has been completed and is ready for testing. Jan 16, 2025 - First Occupancy is June 2025 as per superintendent. Occupancy plan is attached. Jan 17, 2025 _ OTDR / Ruby Testing Completed. Jan 17, 2025 - Building is ready to go On Net. Note Prewire In Progress First Occupancy is scheduled for June 2025 Jan 22, 2025 - Updated Condo PM information. Jan 31, 2025 - Complimentary Services - Called PM Damon to discuss the complimentary services - building is still fully under construction and slated for occupancy in October 2025 - for now we have agreed that best to hold off on any site walks until early September so as to ensure construction is complete and we can ensure a full scope of work is developed for the successful install. | [6 empty] | 3 - Normal | [21 empty] | 2024-06-18 |  |  | 39 | 433 |  | 2025-01-17 |  |  |  | https://buildings.beanfield.com/buildings/view/18861 |  | CONST-36518 | 3 - Normal |  | Toronto
Construction | CONST-28198 | 2221 Yonge St, Toronto | Condo | Clean Up |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Harvey Tran | 2022-05-03 10:53 |  | 2025-02-06 10:31 |  |  | 2024-02-27 | 0 | 2 |  |  | CONST-28199, CONST-28200, CONST-28581, CONST-28606, CONST-28607, CONST-28608, CONST-28609, CONST-28610, CONST-28611, CONST-28612, CONST-28613, CONST-28614, CONST-28615, CONST-28616, CONST-28617, CONST-33709, CONST-36154, CONST-36407, CONST-36408, CONST-38388, CONST-38800 |  | +*PM:*+ John Wannamaker [jwannamaker@berkleypm.ca¦mailto:jwannamaker@berkleypm.ca] 437-833-6377 x3 | [13 empty] | 0¦i3cx1z: | [7 empty] | 9.2234e+18 | [19 empty] | August 10th - Pending Agreement Apr 19/23 - Project Initiated. Design and Permit in progress. Apr 25/23 - Hydro Permit in progress. May 15/23 - Manhole Survey completed. July 21/23 - Hydro permit granted. Jan 23/24 - Conduit build completed. Invoice received. Jan 31/24 - Cable pull scheduled for Feb 2nd Feb 02/24 - Cable pull completed. Pending SOW Feb 13/24 - Splicing scheduled for Feb 20th & 21st Feb 15/24 - Splicing completed Feb 27/24 - Building On-Net | [6 empty] | 3 - Normal | [19 empty] | N/A |  | 2022-05-26 |  |  | 58 | 604 |  | 2024-02-27 | 11128 |  |  | https://buildings.beanfield.com/buildings/view/780 |  | 601265 | 3 - Normal | 2024-01-26 | Toronto | 7879 | 17480
Construction | CONST-27533 | 115/125 Blue Jays Way, Toronto - King Blue | Condo | Clean Up |  | Unresolved | Harvey Tran | Olawale Olaniyan [X] | Harvey Tran | 2022-03-31 11:56 |  | 2025-02-10 11:04 |  |  | 2024-07-30 | 0 | 1 |  |  | CONST-27534, CONST-27535, CONST-28703, CONST-28704, CONST-28705, CONST-28706, CONST-28707, CONST-28708, CONST-28709, CONST-28710, CONST-28711, CONST-28712, CONST-28713, CONST-28714, CONST-28715, CONST-28716, CONST-28717, CONST-31859, CONST-31860, CONST-31861, CONST-31862, CONST-35455, CONST-35456, CONST-35468, CONST-36959, CONST-38549, CONST-38789, CONST-38790 | CONST-31527, CONST-31357 | Condo constructed in 2028. Requested by Oliver. +*PM Updated Information Sept 24, 2024*+ John Wilson, OLCM, RCM Regional Manager ¦ ICC Property Management Ltd. [jwilson@iccpropertymanagement.com¦mailto:jwilson@iccpropertymanagement.com] Could you kindly request a site walk from James for 115-125 Blue Jays Way + 355 King St W (King Blue). [https://buildings.beanfield.com/buildings/view/12016] Agreement subtask can be created immediately as we have an executed FibreStream agreement. +*PM info:*+ Katherine Newman RCM, OLCM Senior Property Manager King Blue 115/125 Blue Jays Way ¦ Toronto, ON M5V 0N5 Direct 416.901.6445 Email [katherine.newman@fsresidential.com¦mailto:katherine.newman@fsresidential.com] | Bolton, Fibrestream | [12 empty] | 0¦i3asgn: | [7 empty] | 9.2234e+18 | [19 empty] | December 20th - Hydro permit granted. City permit in progress. March 10th - City Permit granted, expires September 10th. Apr 17/23 - There is active construction at this intersection. City will not approve our construction, asked to follow up again in August. Aug 18/23 - City permit extension requested Aug 21/23 - Locates Submitted. Hydro permit extension requested Aug 23/23 - City & Hydro permit extension approved Sep 18/23 - Locates completed. Pending construction schedule Oct 12/23 - Construction tentatively scheduled to start Dec 4th. Due dates updated. Dec 11/23 - Delay with construction schedule. Due dates updated. Mar 22/24 - Redesign required. Due dates updated. Mar 26/24 - Revised Hydro permit submitted Apr 01/24 - Hydro permit PO sent May 28th, 2024 - Construction is scheduled for June 10th, cable pull will be done after that. We are able to move up the project due date to July 2024. Jul 2nd, 2024 - Construction is completed. Cable pull is scheduled. Jul 15th, 2024 - Cable pull is completed. Splicing is tentatively scheduled. July 30th, 2024 - Splicing completed, we are working on the testing. July 30th, 2024 - Testing completed, building is onnet. | [6 empty] | 3 - Normal | [19 empty] | Internal |  | 2022-06-07 |  |  | 48 | 911 |  | 2024-07-30 | 71171 |  |  | https://buildings.beanfield.com/buildings/view/12016 |  | 500444 | 3 - Normal | 2023-06-09 | Toronto | 11999 | 24745
Construction | CONST-26946 | 5 St. Joseph St, Toronto - Five Condos | Condo | Clean Up |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Harvey Tran | 2022-02-22 13:19 |  | 2025-02-10 14:14 |  |  | 2024-04-12 | 0 | 1 |  |  | CONST-26964, CONST-26965, CONST-27506, CONST-27507, CONST-27508, CONST-27509, CONST-27510, CONST-27511, CONST-27512, CONST-27513, CONST-27514, CONST-27515, CONST-27541, CONST-27542, CONST-27543, CONST-27544, CONST-30293, CONST-31830, CONST-36309, CONST-36865, CONST-36866, CONST-39967 | ORDER-222944, CONST-26939, CONST-26940, CONST-26942, CONST-26943, CONST-26944, CONST-26945, CONST-26947, CONST-26948, CONST-26950, CONST-27431, CONST-37578 |  | Bolton, FSactive, Fiberstreamagreement | [12 empty] | 0¦i37slb: | [7 empty] | 9.2234e+18 | [19 empty] | January 16th - Surveys expired and resurvey required. Hydro and City permit to be in progress. Aug 1/23 - Still pending hydro permit, city permit not submitted yet. Due dates updated. Aug 2/23 - Hydro permit granted. Aug 14/23 - City permit approved. Aug 25/23 - Locate submitted Sep 18/23 - Locates completed. Pending construction schedule Jan 24/24 - PO sent to Sentrex (Wendy) Jan 29/24 - PO sent to Readyvac Inc (Wendy) Feb 07/24 - Construction completed. Cable pull scheduled for Mar 14th & 15th Feb 22/24 - Readyvac invoice received. Sentrex invoice received. Mar 01/24 - Pending SOW. Mar 15/24 - Cable pull completed. Still pending SOW Mar 20/24 - SOW uploaded. Splicing scheduled. Mar 21/24 - Transferred $5,000 from cable pull budget to splicing budget. PO sent to Litewave for splicing. Mar 22/24 - ISP splicing scheduled for Mar 27th. Due to delay from GIS for SOW and unavailability of XGS line cards. Due dates updated. Apr 03/24 - OSP splicing completed Apr 12/24 - Building On-Net FEBRUARY 10, 2025 - TORONTO HYDRO PO STILL PENDING | [6 empty] | 3 - Normal | [19 empty] | Internal |  | 2022-03-31 |  |  | 45 | 493 | Integration | 2024-04-12 | 49178 |  |  | https://buildings.beanfield.com/buildings/view/3949 |  | 500366 | 3 - Normal |  | Toronto | 6309 | 14840
Construction | CONST-29240 | 58 Orchard View Blvd, Toronto - Neon Condos | Condo | Clean Up |  | Unresolved | James Mowers | Lorna Kurok | Jessica Markiewicz | 2022-07-11 16:03 |  | 2025-03-11 14:06 |  |  | 2025-03-20 | 0 | 1 |  |  | CONST-29241, CONST-29242, CONST-37617, CONST-37618, CONST-37619, CONST-37620, CONST-37621, CONST-37622, CONST-37623, CONST-37624, CONST-37625, CONST-37626, CONST-37627, CONST-37628, CONST-37629, CONST-37630, CONST-37631, CONST-38641, CONST-38642, CONST-38759, CONST-40153 | CONST-33154 | Requested by Jay Fernandes Hi, I’ve gone through the remaining Fibrestream condos we have agreements for in the GTA and have grouped them in a way that I think makes sense for site visits and builds. There will be another list coming of buildings that don’t really fall into groups. Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. There are some current backbone (Sheppard) or NPOP (960 Lawrence) projects that will need to be completed to connect these but this will get everything into the system. Thanks! *NEW PM Info:* *Terrie-Anne Brown, OLCM* *Condominium Manager* ICC Property Management Ltd. 2875 14th Avenue, Suite 300 Markham, Ontario L3R 5H8 Tel: (905) 940-1234, ext. 52 Fax: (905) 940-3881 Added Management office number Jan 21, 2025: 647-343-9402 | FSactive, Fiberstreamagreement, Yonge&Egl | [12 empty] | 0¦i3h8m7: | [7 empty] | 9.2234e+18 | [19 empty] | Jun 4th, 2024 - Route drawing and survey to be in progress. Sept 20, 2024 Hydro Permit granted_Cable pull is scheduled for October 10. Oct 9, 2024 - Project pushed out on the On Net schedule, we are waiting for the Building Pm to grant access and this will not occur until after the Board meeting happening at the end of October. November 26, 2024 - We are still waiting for confirmation from the Condo Board of Directors. This building has been moved tentatively rescheduled to January 2025. November 28, 2024 - Condo Board of Directors has giving Beanfield approval to work Dec 20, 2024 - Cable Pull Asbuild attached Jan 2, 2025_PM has been a challenge. Emails have been sent to notify Pm of the work date. Pm was off during Christmas and Shawn already has contacts with her, he is expected to speak with her January 3, 2025. Hoping to Full confirmation to begin internal work January 6, 2024. Jan 6, 2025_The pm has still not confirmed with Shawn as of Jan 6, 2025. We are hoping they will give Shawn's team authorization so he can properly plan his work by Jan 10, 2025 Jan 8, 2025 Asbuilts sent to Hydro Jan 9_ On Net date changed from January 24, 2025 to February 20, 2025, blocked by another project. Jan 10, 2025 - Once the new splicing SOW is received, we will need to request a quote from Litewave. Jan 22- PM not responding to repeated emails and Phone calls regarding scheduling the internal riser work Jan 24, 2025_OSP Splicing (I realized some of my fibres on ca5379 were already designated for another circuit as told by Geoffrey Winniski. I could not find any available fibres on this cable that i could use and was told that we may need to take a new path. Please review Geoffrey Winniski Kevin Boodram and let us know if we should continue splicing or hold off until further notice) (Trace File V2 uploaded - in order to minimize manhole access, 58 Orchard Ave, P1 Level, POP Room, FPP1.T1.F5-6 will come out at 4711 Yonge St, Parking Level 1, NPOP-Electrical Room, Fiber Panel.FPP7.F81-82. Please let me know if anything else is needed) Jan 30, 2025 - OSP Splicing Note: New Trace file and KMZ uploaded (V3), +2 fibres for commercial use have slightly altered path due to capacity issues at Pole 1901-7 February 6, 2025 - On Net Schedule change, project moved from February 2025 to March 2025, the PM will not authorize Beanfield to work in the building until Feb 28, 2025. Feb 4, 2025 - ISP SOW (the ISP SOW for 58 Orchard View Blvd can be found in CONST-38641 and has already been completed and assigned out. This ticket can be closed.) March 11, 2025 - this build was put ON Net March 10, 2025. Project is in clean up because of the outstanding THES po for the construction verification project. please note THES asbuilt was sent Jan 6, 2025. No hard surface restorations required | [6 empty] | 3 - Normal | [20 empty] | 2025-03-10 | 2024-06-04 |  |  | 20 | 218 | Integration | 2025-03-10 | 18942 |  |  | https://buildings.beanfield.com/buildings/view/15463 |  | CONST-29240 | 3 - Normal | 2024-11-29 | Toronto | 4882
Construction | CONST-33745 | 3 Marine Parade Dr, Etobicoke | Condo | Clean Up |  | Unresolved | Lorna Kurok | Lorna Kurok | Olawale Olaniyan [X] | 2023-04-25 13:53 |  | 2025-03-07 17:29 |  |  | 2024-08-30 | 0 | 1 | _thumb_937424.png _thumb_931850.png _thumb_931852.png _thumb_970686.png _thumb_970685.png |  | CONST-33746, CONST-33747, CONST-33842, CONST-37176, CONST-37177, CONST-37178, CONST-37179, CONST-37180, CONST-37181, CONST-37182, CONST-37183, CONST-37184, CONST-37185, CONST-37186, CONST-37187, CONST-37188, CONST-37189, CONST-38064, CONST-38185, CONST-38532, CONST-38533 | CONST-27459, CONST-25612, CONST-27170, CONST-27183, CONST-27184 | Requested by Oliver Davies, Can you please queue up a site walk for 3 Marine Parade Dr? This should be linked to 5 Marine Parade via CONST-27170 *PM Info:* *GRAHAM MCLEAN* Property Manager 3 Marine Parade Drive TSCC 2078 ¦ Toronto, ON M8V 3Z5 Direct 416-259-3275 Email [graham.mclean@fsresidential.com¦mailto:graham.mclean@fsresidential.com] Thank you, | NUA+MA | [12 empty] | 0¦i3zvgv: | [7 empty] | 9.2234e+18 | [19 empty] | Apr 26th, 2024 - Project started. Hydro Permit and City permit application start. May 13th, 2024 - Project is approved to continue, our team is restarting the city permit application and locates resubmission. May 22nd, 2024 - City permit is in, our team has restarted the locate. Aug 6th, 2024 - Cable pull completed, pending SOW for splicing, moving up this building onnet date to Aug 2024. Aug 30th, 2024 - Testing completed, building is onnet. | [6 empty] | 3 - Normal | [21 empty] | 2024-04-26 | [5 empty] | 2024-08-30 | 41950 |  |  | https://buildings.beanfield.com/buildings/view/17754 |  | CONST-33745 | 3 - Normal |  |  | 2605 | 10385
Construction | CONST-30959 | 18 Rean Dr, North York - NY2 Condos | Condo | Clean Up |  | Unresolved | James Mowers | Lorna Kurok | Jessica Markiewicz | 2022-10-06 09:22 |  | 2025-03-06 11:20 |  |  | 2025-05-06 | 0 | 2 | _thumb_1076174.png |  | CONST-30960, CONST-30961, CONST-32110, CONST-35469, CONST-35470, CONST-35471, CONST-35472, CONST-35473, CONST-35474, CONST-35475, CONST-35476, CONST-35477, CONST-35478, CONST-35479, CONST-35480, CONST-38126, CONST-38351, CONST-38368, CONST-38918, CONST-38977, CONST-39651, CONST-39652, CONST-40212 | CONST-29195, CONST-29198, CONST-29201, CONST-32106, CONST-24117, CONST-29189, CONST-29192, CONST-29578 | Requested by Oliver Davies. *18 Rean Dr (No Agreement / Off-Net)* **This location neighbours 591 Sheppard Ave E (*CONST-29580*)* *if we look at both locations this may help to justify our cost of expansion.* BB Link: [https://buildings.beanfield.com/buildings/view/14282] PM Info: Kishani Wijesiriwardana Condominium Manager I.C.C. Property Management Ltd As agents for and on behalf of TSCC 2377 18 Rean Drive, Management Office Toronto, ON M2K 0C7 Office: 416-519-0805 kw@iccpropertymanagement.com | NUA+MA | [12 empty] | 0¦i3mwlr: | [7 empty] | 9.2234e+18 | [19 empty] | October 28th - Site Visit requested. Oct 11/23 - Project initiated. Design, permits will be completed on backbone build CONST-32115 Oct 12/23 - Construction scheduled to start Oct 18th on CONST-32106 Oct 16/23 - Oliver Davies - "Can you please place this location On Hold? We will need to await internal board approval before proceeding" July 15, 2024_Revised budget added. This budget is dependant on us being able to bore, if trenching is called for than this budget will increase. Aug 12, 2024_Oliver indicates project is good to go. As long as we stay within the budget. Sept 23 , 2024_ In house Permits in process. Oct 18, 2024 - Locates Submitted Nov 28, 2024 - Construction worked scheduled for Dec 5, 2025 with the Building PM. Dec 9, 2024 - Permit received Dec 16, 2024 - UG construction Completed Dec 18, 2024 - Cable Pull Asbuilt attached Jan 2, 2025 - All panels prepped and spliced Jan 2, 2025 - Moved Due date from february 2025 to Jan 9, 2025. Jan 3, 2025 - Building On net Jan 9, 2024 - clean up due to pending asbuilt and financial closeout Feb 3, 2025 - received asbuilt, no hard surface restoration, but requires sod replacement in the spring of 2025, Feb 4, 2025 Asbuilt sent to city. | [6 empty] | 3 - Normal | [21 empty] | 2024-09-05 |  |  | 7 | 140 |  | 2025-01-03 | 30401 |  |  | https://buildings.beanfield.com/buildings/view/14282 |  | CONST-30959 | 3 - Normal | 2023-12-22 | North York | 3820 | 15195
Construction | CONST-29402 | 15 James Finlay Way, Toronto - Ion Condos | Condo | Clean Up |  | Unresolved | Lorna Kurok | Lorna Kurok | Jessica Markiewicz | 2022-07-13 12:23 |  | 2025-03-14 10:16 |  |  | 2024-12-04 | 0 | 1 | _thumb_1042763.png _thumb_1042752.png |  | CONST-29403, CONST-29404, CONST-37322, CONST-37323, CONST-37324, CONST-37325, CONST-37326, CONST-37327, CONST-37328, CONST-37329, CONST-37330, CONST-37331, CONST-37332, CONST-37333, CONST-37336, CONST-37339, CONST-38661, CONST-38927, CONST-39187, CONST-39968, CONST-39978 | CONST-29393, CONST-40331, CONST-40332, CONST-40333, CONST-40334, CONST-40335, CONST-40336, CONST-29395 | Requested by Jay Fernandes {color:#0747a6}*Adding Property Manager:*{color} Davor Tomljanovic ¦ Property Manager ZORAN PROPERTIES INC. 75 International Blvd. – Suite 400 Toronto, ON M9W 6L9 T ¦ 416-633-7562 ¦ [davor@zoranproperties.com¦mailto:davor@zoranproperties.com] Hi, These are the Fibrestream condos we have agreements for that don’t seem to fit into any groups (although I maybe wrong). Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. ¦Group¦Building Name¦Address¦suites¦ ¦Independent¦Eleven Superior¦11 Superior AVE Etobicoke ON M8V 0A7¦130¦ ¦Independent¦The James Club¦1135 Royal York RD Toronto ON M9A 4A7¦209¦ ¦Independent¦Independence Way¦115 George Appleton WAY North York ON M3M 2E9¦244¦ ¦Independent¦Danforth Village Estates¦1346 Danforth RD Toronto ON M4J1M9¦249¦ ¦Independent¦beBloor¦1369 Bloor ST Toronto ON M6P 4J3¦238¦ ¦Independent¦Ion Condos¦15 James Finlay WAY Toronto ON M3M 0B3¦200¦ ¦Independent¦Paradice at the Oasis¦1720 Eglinton AVE Toronto ON M4A2X9¦190¦ ¦Independent¦Havenon the Bluffs¦20 East Haven DR Toronto ON M1N1M2¦259¦ ¦Independent¦Kilgour Estate II¦21 Burkebrook PL Toronto ON M4G4K8¦228¦ ¦Independent¦Canvas Condos¦2301 Danforth AVE Toronto ON M4C 1L5¦156¦ ¦Independent¦3018 Yonge Condos¦3018 Yonge ST Toronto ON M4N 0A5¦188¦ ¦Independent¦Cranbrooke Village¦35 Saranac BLVD Toronto ON M6A 2G4¦341¦ ¦Independent¦39 Brant St¦39 Brant ST Toronto ON M5V0M8¦236¦ ¦Independent¦The Wave¦4 Elsinore PATH Toronto ON M8V 4G7¦185¦ ¦Independent¦Clock Tower Lofts¦700 King ST Toronto ON M5V 2Y6¦216¦ ¦Independent¦The Boot¦75 Dalhousie ST Toronto ON M5B 2R9¦153¦ ¦Independent¦B.Street Condos¦783 Bathurst ST Toronto ON M6G 1K1¦ ¦ ¦Independent¦85 Bloor St¦85 Bloor ST Toronto ON M4W3G9¦252¦ | Fiberstreamagreement | [12 empty] | 0¦i3hfrr: | [7 empty] | 9.2234e+18 | [19 empty] | Jan 26/23 - As per Oliver Davies "at $372/unit our costs here are quite high. This is a net-new building and I do suspect we would have a good penetration rate, however, we'll need to place it on hold for now. A final decision can be made once we have details regarding the pedestrian tunnel on JFW and as-builts." May 13th, 2024 - Project progress starts, City permit application will be in progress. Aug 30, 2024 - Full stream Permit has been applied for. City permits are approved. Nov 13, 1014 - Construction expected to be completed Tuesday Nov 19, 2024 Nov 15, 2024 - All panels prepped and spliced Nov 27, 2024 - Cable pull completed, Cable pull Asbuilt attached. Feb 20, 2025 - Updating SAP. closing finances for project. Pending City Asbuilts (UG) March 12, 2025 - it is noted in the Asbuilts, that there are 2 sidewalk locations requiring restorations. | [6 empty] | 3 - Normal | [21 empty] | 2024-05-13 |  |  |  | 200 |  | 2024-12-04 | 71728 |  |  | https://buildings.beanfield.com/buildings/view/5948 |  | CONST-29402 | 3 - Normal |  | Toronto | 2729 | 11720
Construction | CONST-29111 | 7 & 9 Michael Power PL - Port Royal Place Ⅳ | Condo | Clean Up |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Jessica Markiewicz | 2022-07-08 14:59 |  | 2025-03-13 10:51 |  |  | 2024-04-10 | 0 | 3 |  |  | CONST-29112, CONST-29113, CONST-30440, CONST-30441, CONST-30442, CONST-30744, CONST-30745, CONST-30746, CONST-30747, CONST-30748, CONST-30749, CONST-30750, CONST-30751, CONST-30752, CONST-30753, CONST-30754, CONST-30755, CONST-30756, CONST-30757, CONST-30758, CONST-30759, CONST-33887, CONST-36322, CONST-36838, CONST-36839, CONST-38815, CONST-38816 | CONST-29102, CONST-29105, CONST-36642, CONST-36641, CONST-36748 | Requested by Jay Fernandes Hi, I’ve gone through the remaining Fibrestream condos we have agreements for in the GTA and have grouped them in a way that I think makes sense for site visits and builds. There will be another list coming of buildings that don’t really fall into groups. Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. There are some current backbone (Sheppard) or NPOP (960 Lawrence) projects that will need to be completed to connect these but this will get everything into the system. Thanks! *PM: Mark Bartoloni* | Bloor&Isl, Bolton, FSactive, Fiberstreamagreement | [12 empty] | 0¦i3h2dz: | [7 empty] | 9.2234e+18 | [19 empty] | October 4th - Project initiated. Design and Permits to be in progress. February 27th - Still waiting for the city permit. May 17/23 - Still pending city permit, due date updated. June 06/23 - Conduit Build scheduled for June 12th. July 04/23 - City permit still with Utility Review. July 17/23 - City permit taking longer than anticipated. Due dates updated. Aug 29/23 - City permit approved Sep 14/23 - Delay with construction schedule. Due dates updated. Jan 26/24 - Construction scheduled to start Feb 5th. Feb 07/24 - Short stream city permit submitted for replacement of GLB. Feb 08/24 - PO sent to ReadyVac (Wendy). SS permit granted. Feb 14/25 - Construction completed. Conduit build in progress. Cable pull scheduled for Feb 29th. Mobilization PO sent for conduit build. Feb 15/24 - Conduit build completed. Feb 22/24 - Readyvac invoice received. Feb 29/24 - Cable pull completed Mar 01/24 - Pending SOW. Mar 15/24 - SOW uploaded. Splicing scheduled for Mar 19th - 21st Mar 22/24 - Due to delay from GIS for SOW and unavailability of XGS line cards. Due dates updated. Mar 27/24 - OSP splicing completed Apr 05/24 - Troubleshooting required. ISP cables incorrectly spliced. Apr 10/24 - Building On-Net | [6 empty] | 3 - Normal | [19 empty] | Internal |  | 2022-10-04 |  |  | 12 | 149 | Integration | 2024-04-10 | 50102 |  |  | https://buildings.beanfield.com/buildings/view/3420 |  | 500450 | 3 - Normal | 2023-07-07 | Etobicoke | 5211 | 11210
Construction | CONST-34172 | 503 Beecroft Rd, North York | Condo | Clean Up |  | Unresolved | Harvey Tran | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2023-06-01 12:27 |  | 2025-03-14 15:04 |  |  | 2024-05-31 | 0 | 0 | _thumb_688606.png |  | CONST-34173, CONST-34174, CONST-34236, CONST-34259, CONST-34260, CONST-34261, CONST-34262, CONST-34263, CONST-34264, CONST-34265, CONST-34266, CONST-34267, CONST-34268, CONST-34269, CONST-34270, CONST-34271, CONST-34272, CONST-34273, CONST-34274, CONST-34275, CONST-34276, CONST-34377, CONST-35373, CONST-36647, CONST-36768, CONST-36823, CONST-36824, CONST-36972, CONST-36973, CONST-37240, CONST-38827, CONST-38828 | CONST-33954 | Requested by James Mowers ¦Frank Dodich¦ ¦Property Manager¦ ¦(416) 223-8367¦ ¦continental.pm@delcondo.com¦ | Bolton, FSactive, Fiberstreamagreement | [12 empty] | 0¦i42ouv: | [7 empty] | 9.2234e+18 | [19 empty] | June 07/23 - Project initiated. Design & Permits in progress. Feb 08/24 - City permit granted. Mar 05/24 - Conduit build scheduled for Mar 20th. Cable pull scheduled for Apr 17th Mar 26/24 - Construction tentatively scheduled to start Apr 8th Apr 08/24 - Construction rescheduled to start Apr 15th. Due dates updated Apr 29, 2024 - Construction is in progress and should be done Apr 30th. Cable pull is also scheduled. May 27th, 2024 - Splicing is required to be redone due to change in SOW, we are still trying to get the building onnet by end of May 2024. May 31st, 2024 - Testing completed. Project is onnet. Pending restoration in 2025 | [6 empty] | 3 - Normal | [19 empty] | Internal |  | 2023-06-07 |  |  | 21 | 242 | Integration | 2024-05-31 | 56918 |  |  | https://buildings.beanfield.com/buildings/view/5270 |  | CONST-34172 | 3 - Normal | 2024-03-29 | North York | 5792 | 12555
Construction | CONST-29504 | 75 Dalhousie St/ 76 Shutter St, Toronto - The Boot | Condo | Clean Up |  | Unresolved | Harvey Tran | Olawale Olaniyan [X] | Jessica Markiewicz | 2022-07-15 14:49 |  | 2025-03-14 15:05 |  |  | 2024-06-27 | 0 | 1 |  |  | CONST-29505, CONST-29506, CONST-30727, CONST-30728, CONST-31724, CONST-31726, CONST-33292, CONST-33293, CONST-33294, CONST-33295, CONST-33296, CONST-33297, CONST-33298, CONST-33299, CONST-33300, CONST-33301, CONST-33302, CONST-33303, CONST-33304, CONST-33305, CONST-35379, CONST-35580, CONST-35581, CONST-35950, CONST-36034, CONST-38835, CONST-38836 | CONST-30726 | Requested by Jay Fernandes Hi, These are the Fibrestream condos we have agreements for that don’t seem to fit into any groups (although I maybe wrong). Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. ¦Group¦Building Name¦Address¦suites¦ ¦Independent¦Eleven Superior¦11 Superior AVE Etobicoke ON M8V 0A7¦130¦ ¦Independent¦The James Club¦1135 Royal York RD Toronto ON M9A 4A7¦209¦ ¦Independent¦Independence Way¦115 George Appleton WAY North York ON M3M 2E9¦244¦ ¦Independent¦Danforth Village Estates¦1346 Danforth RD Toronto ON M4J1M9¦249¦ ¦Independent¦beBloor¦1369 Bloor ST Toronto ON M6P 4J3¦238¦ ¦Independent¦Ion Condos¦15 James Finlay WAY Toronto ON M3M 0B3¦200¦ ¦Independent¦Paradice at the Oasis¦1720 Eglinton AVE Toronto ON M4A2X9¦190¦ ¦Independent¦Havenon the Bluffs¦20 East Haven DR Toronto ON M1N1M2¦259¦ ¦Independent¦Kilgour Estate II¦21 Burkebrook PL Toronto ON M4G4K8¦228¦ ¦Independent¦Canvas Condos¦2301 Danforth AVE Toronto ON M4C 1L5¦156¦ ¦Independent¦3018 Yonge Condos¦3018 Yonge ST Toronto ON M4N 0A5¦188¦ ¦Independent¦Cranbrooke Village¦35 Saranac BLVD Toronto ON M6A 2G4¦341¦ ¦Independent¦39 Brant St¦39 Brant ST Toronto ON M5V0M8¦236¦ ¦Independent¦The Wave¦4 Elsinore PATH Toronto ON M8V 4G7¦185¦ ¦Independent¦Clock Tower Lofts¦700 King ST Toronto ON M5V 2Y6¦216¦ ¦Independent¦The Boot¦75 Dalhousie ST Toronto ON M5B 2R9¦153¦ ¦Independent¦B.Street Condos¦783 Bathurst ST Toronto ON M6G 1K1¦ ¦ ¦Independent¦85 Bloor St¦85 Bloor ST Toronto ON M4W3G9¦252¦ | Bolton, Fiberstreamagreement | [12 empty] | 0¦i3hm73: | [7 empty] | 9.2234e+18 | [19 empty] | October 28th - Budget pending approval. March 13th - Project initiated, design and permit in progress. Aug 15/23 - City permit approved. Oct 3/23 - Construction scheduled to start Nov 1st Oct 11/23 - Construction rescheduled to start Oct 26th June 28th 2024 - CONST-29504 Oct 25/23 - Construction rescheduled to start Nov 9th. Due dates updated Dec 08/23 - Delay with construction schedule. Due dates updated. Feb 15/24 - Transferred $100.00 from construction to cable pull budget to send conduit build PO. Conduit build PO sent. Feb 21/24 - The City has asked us to check back with them in March to see if the contractor working in the area is complete. Due dates updated. Feb 22/24 - Conduit build completed. Invoice received. Mar 12/24 - City permit granted May 1, 2024 - Our team is ready to start construction in May 13th, however we still need the building approval to get the work started. May 7th, 2024 - We still dont have the green light to start construction yet. Project due date is temporarily pushed back to end of June 2024. June 20th, 2024 - Splicing is in progress. We are aiming to get this building onnet in June 2024. | [6 empty] | 3 - Normal | [19 empty] | Internal |  | 2023-03-13 | [5 empty] | 2024-06-27 | 37786 |  |  | https://buildings.beanfield.com/buildings/view/3131 |  | CONST-29504 | 3 - Normal | 2023-09-22 |  | 3744 | 20825
Construction | CONST-35824 | 2175 Keele St_Municipal Address 90-160 Cannon Jackson Drive, Phase 1, Toronto | Condo | Clean Up |  | Unresolved | James Mowers | Lorna Kurok | Olawale Olaniyan [X] | 2023-11-23 11:12 |  | 2025-03-17 13:06 |  |  | 2025-03-06 | 0 | 1 |  |  | CONST-35825, CONST-35826, CONST-38255, CONST-38444, CONST-38449, CONST-38450, CONST-38452, CONST-38454, CONST-38455, CONST-38456, CONST-38457, CONST-38458, CONST-38459, CONST-38460, CONST-38461, CONST-38462, CONST-38463, CONST-38464, CONST-38465, CONST-38770, CONST-38771, CONST-39319, CONST-39555, CONST-40248, CONST-40317 | CONST-39520, CONST-39529 | Daniel's FirstHome Keelesdale (Phase 1) Requested by Oliver Davies, ¦{color:#403294}*Update PM Information as of December 13, 2024*{color}:¦ *Saba Farokh* Condominium Manager ,M.A., B.A., OLCM-LL *GPM Property Management Inc.* 242 Applewood Crescent ¦ Unit 5 ¦ Concord ¦ Ontario ¦ L4K 4E5 # 905.669.0222 [keelesdalemanager@gpmmanagement.com¦mailto:keelesdalemanager@gpmmanagement.com]¦ ¦[sabaf@gpmmanagement.com¦mailto:sabaf@gpmmanagement.com] ¦ Can you please queue up tickets for an OSP plan & site walk at the “Daniels FirstHome Keelesdale” townhomes? There are 244 units here, and BF-0738 is nearby. PM Info: *Hossein Attaran,* Condominium Manager ¦ GL-0028694750 *GPM Property Management Inc.* 242 Applewood Crescent ¦ Unit 5 ¦ Concord ¦ Ontario ¦ L4K 4E5 T. 905.669.0222 {color:#134792}[hosseina@gpmmanagement.com¦mailto:hosseina@gpmmanagement.com]{color} Thank you, | NUA+MA | [12 empty] | 0¦i4gpq7: | [7 empty] | 9.2234e+18 | [19 empty] | Sept 12, 2024_A signed agreement is now in place. CA is approved Estimating Due date Jan 9, 2025. Oct 31, 2024_The PM informed Beanfield that the address of the building has changed from 2175 Keele St to reflect the Municipal address 90 -160 Cannon Jackson Drive. I am changing the address by adding 90 - 160 Cannon Jackson Drive to the Label. Nov 27, 2024 -Changed On Net date to February from January. Permits are still pending. Jan 7, 2025 - Locates submitted Jan 8, 2025 - City permit has been received 1004954001, Expiry July 8, 2025 Jan 20, 2025 - Conduit sketch is added Jan 20, 2025 - OSP splicing In progress - Hydro hole and testing expected to be done this week. Jan 21, 2025 - Locates are in, UG construction is being scheduled for Mid February. Jan 21, 2025 - Change in On Net date, Condo being moved up in the schedule from April to March 2025 Jan 21, 2025 - OSP Construction, is hoping to have there portion completed by the second week of Feb. Jan 24, 2025 - Email sent to Property Manager. Feb 11, 2025 - OSP Construction started feb 11, 2025. Feb 18, 2025 - Conduit & Core Build is scheduled for Feb 20th. March 4, 2025 - updated On net date to the 7 from the 5th, to align with the planned end date splicing has indicated March 6, 2025 - 2175 Keele Phase 1 is On Net. March 12, 2025 - Pending city asbuilt, Hyrdo asbuilt sent to THES. March 17, 2025 - Recd City Asbuilt, project requires sod in the spring of 2025, Asbuilt indicates there is no hard surface restorations. | [6 empty] | 3 - Normal | [20 empty] | 2025-03-06 | 2024-09-12 |  |  | 6 | 244 |  | 2025-03-06 |  |  |  | https://buildings.beanfield.com/buildings/view/18465 |  | CONST-35824 | 3 - Normal | 2025-01-09 | Toronto
Construction | CONST-36036 | 5131 Sheppard Ave E, Scarborough - Daniels FirstHome Markham Sheppard | Condo | Clean Up |  | Unresolved | James Mowers | Lorna Kurok | Olawale Olaniyan [X] | 2023-12-18 14:18 |  | 2025-03-17 11:52 |  |  | 2025-03-14 | 0 | 0 |  |  | CONST-36037, CONST-36038, CONST-37307, CONST-38207, CONST-38215, CONST-38216, CONST-38217, CONST-38218, CONST-38219, CONST-38220, CONST-38221, CONST-38222, CONST-38223, CONST-38224, CONST-38225, CONST-38226, CONST-38227, CONST-38228, CONST-38229, CONST-39074, CONST-39201, CONST-40166, CONST-40377 |  | Requested by Oliver Davies, Could you kindly queue up a site walk for 5131 Sheppard Ave E? The Daniels FirstHome Markham Sheppard townhomes include 328 residential units. We have yet to submit an agreement, however the board has indicated their approval for adding Beanfield from my initial discussions with them. PM info: *Joyce Santos* Condominium Manager *GPM Property Management Inc.* 242 Applewood Crescent ¦ Unit 5 ¦ Concord ¦ Ontario ¦ L4K 4E5 T. 905.669.0222 [jsantos@gpmmanagement.com¦mailto:jsantos@gpmmanagement.com] Thank you, | NUA+MA | [12 empty] | 0¦i4ikqn: | [7 empty] | 9.2234e+18 | [19 empty] | Aug 23rd, 2024 - Project started, City permit and Aerial hydro permit applications are in progress Jan 8, 2025_City Permit Update Note There is coordination to be completed with a city of toronto project in the area. Nbm has reached out for coordination and we are waiting for clearance. Once this is completed we will receive the permit) Jan 17, 2025 - Locates have been requested. Jan 31, 2025 - City Permit Note: the city said the review is over and they are waiting on confirmation on one item before issuing the permit. The street will be under moratorium so they are confirming information around this. even tho we are not working in the street February 7, 2025 - Property Manager Scheduling_Construction_ Email sent Feb 7, 2025 to schedule for Feb 18, 2025 for John M. We will need to return for cable pull and Fibre splicing. Noting Shawn's team is completed the Riser task. Feb 10, 2025 - We have confirmed with the Pm to schedule the Construction work for Feb 18, 2025. Feb 5, 2025 - We have Conditionally granted. (this is conditionally granted. It was sent to to be issued for the permit after review. ) Feb 7, 2025 - City permit is approved. March 3, 2025 - OSP construction in progress. March 5, 2025 - Project moved up in the schedule from April 15 to March 28, 2025. March 17, 2025 - Condo is On Net. Aerial and Cable Asbuilt completed. Pending City Asbuilt. Project in clean up, pending city asbuilt, and need to do Final reconcilation of SAP, left $15,000 in construction for any possible direct invoicing. | [6 empty] | 3 - Normal | [20 empty] | 2025-03-14 | 2024-08-22 |  |  | 6 | 328 |  | 2025-03-14 |  |  |  | https://buildings.beanfield.com/buildings/view/16659 |  | CONST-36036 | 3 - Normal | 2025-04-15 | Scarborough
Construction | CONST-32465 | 2067 Lake Shore Blvd W, Toronto, Lakeside Place Condos | Condo | Clean Up |  | Unresolved | James Mowers | Lorna Kurok | Jessica Markiewicz | 2022-12-21 10:56 |  | 2025-03-25 08:17 |  |  | 2025-03-12 | 0 | 5 |  |  | CONST-32466, CONST-32467, CONST-39907, CONST-39909, CONST-39914, CONST-39915, CONST-39916, CONST-39917, CONST-39918, CONST-39919, CONST-39924, CONST-39925, CONST-39926, CONST-39927, CONST-39928, CONST-39929, CONST-39930, CONST-39931, CONST-39932, CONST-40062, CONST-40063, CONST-40109, CONST-40375, CONST-40376 |  | Constructed in 2002 Units 92 Floors 13 Requested by Oliver Davies: I hope your week is going well! Can you please queue up a site walk for 2067 Lake Shore Blvd W (Lakeside Place)? This location is on the smaller side at only 92 units, however it _should_ tie in well with the other builds we have in this area. BB Link: [https://buildings.beanfield.com/buildings/view/2980] Existing PM information: {color:#134792}*Christina Towler*{color} Condominium Manager ¦ GL. 0017377981 *GPM Property Management Inc.* 242 Applewood Crescent ¦ Unit 5 ¦ Concord ¦ Ontario ¦ L4K 4E5 T. 905.669.0222 *24-Hour Emergency Line:* 905.669.0222 {color:#134792}[ctowler@gpmmanagement.com¦mailto:ctowler@gpmmanagement.com]{color} {color:#134792} {color} {color:#134792}(Christina is on-site on Thursdays, otherwise concierge has been advised to provide access).{color} | NUA+MA | [12 empty] | 0¦i3rl7j: | [7 empty] | 9.2234e+18 | [19 empty] | January 31st 2024- building marked as Not A Candidate. As per Oliver Davies January 29, 2025 - Approved CA budget and received signed agreement. January 30, 2025 - Estimating a short stream permit, units 92 small scale January 30, 2025 - Added to On Net scheduled for March 31, 2025, short stream permit, 92 units January 31 2025 - All sub task have been created, Project has been added to SAP. Jan 31, 2025 - Ca # FTTB-00901 dated jan 24, 2025, Approved Condo amount $17,881.81, High level Budget - $13,800.81, dated Aug 16, 2024, mixed with Internal and Contractor allocations. February 5, 2025 - Project has been submitted for locates, project is still pending permit but has been submitted. February 7, 2025 - SS City permit submitted. February 12, 2025 - Locates completed. Feb 18, 2025- Construction Notification email sent to Condo Manager, to notify UG work on Feb 24, 2025, and to gain parking garage access for feb 25, 2025 for the scan and core to install conduit. (No parking spots are affected.) Feb 28, 2025 - OSP Const Noted - that the wall was leaking prior to Beanfield work. Before and After pictures were taking. The core location was moved as do to the results of the scan, indicating there was a Ibean in the proposed location. March 3, 2025 - OSP Construction work in process. Construction asbuilt attached. There are No Hard surface restorations. Will need to return in the spring to replace sod. March 5, 2025 - Conduit build completed pictures added. March 10, 2025 - Cable pull is completed March 11, 2025 - Cable pull Asbuilt attached March 13, 2025 - Building On net. March 25, 2025- project is in clean up because, we should be receiving a direct invoice from the city of Toronto for the short stream permit fee. Permit #1008282001. | [6 empty] | 3 - Normal | [21 empty] | 2025-01-29 |  |  | 13 | 92 |  | 2025-03-12 |  |  |  | https://buildings.beanfield.com/buildings/view/2980 |  | CONST-32465 | 3 - Normal | 2025-03-31 | Toronto
Construction | CONST-29127 | 85 The Donway, Toronto - Reflections Residences at Don Mills | Condo | Clean Up |  | Unresolved | James Mowers | Lorna Kurok | Jessica Markiewicz | 2022-07-11 07:28 |  | 2025-03-25 13:36 |  |  | 2025-03-18 | 0 | 1 |  |  | CONST-29128, CONST-29129, CONST-32535, CONST-32537, CONST-32538, CONST-32539, CONST-32540, CONST-32541, CONST-32542, CONST-32543, CONST-32544, CONST-32545, CONST-32546, CONST-32547, CONST-32548, CONST-32549, CONST-32550, CONST-35535, CONST-35536, CONST-38074, CONST-39559, CONST-40251 | CONST-29124, CONST-26996, CONST-35829, CONST-38078 | {panel} Requested by Jay Fernandes Hi, I’ve gone through the remaining Fibrestream condos we have agreements for in the GTA and have grouped them in a way that I think makes sense for site visits and builds. There will be another list coming of buildings that don’t really fall into groups. Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. There are some current backbone (Sheppard) or NPOP (960 Lawrence) projects that will need to be completed to connect these but this will get everything into the system. Thanks! *PM: Nicole Roper* *nicole.roper@fsresidential.com* *416.444.8588* {panel} | Bolton, DonMills&Eg, FSactive, Fiberstreamagreement | [12 empty] | 0¦i3h5kf: | [7 empty] | 9.2234e+18 | [19 empty] | December 30th - Project initiated. Design and permits to be in progress. July 12/23 - City permit in progress. July 24/23 - City permit granted. Aug 15/23 - Pending City approval and schedule Sep 8/23 - Construction delay. Due dates updated. Oct 3/23 - Construction scheduled to start Oct 10th Oct 10/23 - Construction in progress Nov 23/23 - Due dates update. Waiting on building for construction approval Nov 27, 2024 - construction - Regarding Building request_(We've received a response from the corporation's solicitor with a number of requests, including having an engineer review. Josh Wignall and I will review today and provide our response to them. This project will likely need to wait until early Q1. ) Apr 03/24 - Still pending building construction approval. Due dates updated. July 23rd, 2023 - Still pending the approval from the building to start construction. Project due date is pushed back to Sep 2024. Sep 3rd, 2023 - We still dont have the approval from the building, pushing back this build to Oct 2024. Sep 9, 2024_ISP SOW Design has been revised. Oct 1, 2024 - Moved On Net schedule date to February 2025, due to 3rd party issue. Pending approval from building. Dec 3, 2024- Asbuilt notes No hard surface restoration Jan 6, 2025_Meeting Notes_Pushing 75 and 85 The Donway to March 2025 to allow more time to obtain approvals from Property Manager. Jan 28, 2025_On Net Schedule change. Moved both Donway (75 and 85) to May 2025 from March 2025. The reason is we are still waiting on permission form the Property Management. (this is with Josh Wignall) Josh has spoke again with PM, who would like to complete this by end of week Jan 31, 2025. But the challenge is with the board and the solicitor.)Updated Jira, SAP and the On Net schedule Feb 19, 2025 - Moved back to March 2025, construction is expected to be completed early march, so we believe we can complete this by the end of March. Feb 28, 2025 - COT Permit received. 1009294001 March 6, 2025 - OSP construction completed pictures attached March 11, 2025 - conduit build completed, pictures attached March 12, 2025 - Condo Concierge hours -85 The Donway concierge is on site 10 or 10:30 am, 75 The Donway Concierge is on site 10 am March 18, 2025 - OTDR / Ruby Testing Completed. March 18, 2025 - Condo is On Net, No Hard Surface Restoration (BF completed restored cookie cuts) March 24, 2025 - Project will need Sod in the spring of 2025. March 25, 2025 - Seed and topsoil completed, pics attached. | [6 empty] | 3 - Normal | [19 empty] | Internal | 2025-03-19 | 2022-12-30 |  |  | 12 | 105 | Integration | 2025-03-18 | 14000 |  |  | https://buildings.beanfield.com/buildings/view/15598 |  | 500527 | 3 - Normal | 2023-10-27 | North York | 2420 | 14535
Construction | CONST-35316 | 393 King St W, Toronto - The 393 On King | Condo | Clean Up |  | Unresolved | Lorna Kurok | Lorna Kurok | Olawale Olaniyan [X] | 2023-09-08 14:51 |  | 2025-03-26 09:59 |  |  | 2024-12-11 | 0 | 1 |  |  | CONST-35317, CONST-35318, CONST-36522, CONST-36538, CONST-37451, CONST-37452, CONST-37453, CONST-37454, CONST-37455, CONST-37456, CONST-37457, CONST-37458, CONST-37459, CONST-37460, CONST-37461, CONST-37462, CONST-37463, CONST-37464, CONST-37465, CONST-38902, CONST-39607, CONST-39608 | CONST-39794, PUR-45402 | Requested by Oliver Davies, *NEW PM Info:* *+Cristina Tudor+* *Condominium Manager* ICC Property Management Ltd. 2875 14th Avenue, Suite 300 Markham, ON, L3R 5H8 905.940.1234 ext. 90 [ctudor@iccpropertymanagement.com¦mailto:ctudor@iccpropertymanagement.com] PM: Melisa Da Graca, OLCM Condominium Manager ICC Property Management Ltd. Tel: (905) 940-1234 ext 222 [mgraca@iccpropertymanagement.com¦mailto:mgraca@iccpropertymanagement.com] | NUA+MA | [12 empty] | 0¦i4b3fr: | [7 empty] | 9.2234e+18 | [19 empty] | Feb 13/24 - PO sent to THES (AP) for vault access (site visit) Feb 14/24 - Invoice for vault access received May 21st, 2024 - Project started, Route drawing and survey to be in progress Oct 16, 2024 - Cable pull scheduled for Nov 7 Nov 7, 2024 - OSP splicing assigned to Litewave due to Hydro. | [6 empty] | 3 - Normal | [21 empty] | 2024-05-21 |  |  | 12 | 101 |  | 2024-12-11 | 15425 |  |  | https://buildings.beanfield.com/buildings/view/3186 |  | CONST-35316 | 3 - Normal |  | Toronto | 2205 | 9575
Construction | CONST-40044 | 10 Deerlick Crt, North York, The Ravine Condos | Condo | Clean Up |  | Unresolved | James Mowers | Lorna Kurok | Lorna Kurok | 2025-02-12 14:37 |  | 2025-03-27 08:23 |  |  | 2025-03-26 | 0 | 0 |  |  | CONST-40045, CONST-40046, CONST-40047, CONST-40048, CONST-40049, CONST-40052, CONST-40053, CONST-40054, CONST-40055, CONST-40056, CONST-40057, CONST-40058, CONST-40059, CONST-40060, CONST-40061, CONST-40180, CONST-40379, CONST-40517 | CONST-15175 | # of Units: *313* # of Floors: *29* Building Constructed Year: *2024* *PM Information as of February 12, 2025:* PM Contact Name: *Michael Liao (FS Residential)* PM Contact #: *437-246-6945* PM Email Address: [michael.liao@fsresidential.com¦mailto:michael.liao@fsresidential.com] Good Morning The below address was approved at the CAPEX meeting Wednesday, February 12th. CA with budget and Agreement attached MDU Address: *1 Deerlick Crt* City: *North York* Building Name: *The Ravine Condos* # of Units: *313* # of Floors: *29* Building Constructed Year: *2024* PM Contact Name: *Michael Liao (FS Residential)* PM Contact #: *437-246-6945* PM Email Address: [michael.liao@fsresidential.com¦mailto:michael.liao@fsresidential.com] Type of Contract (Fibre agreement or NUA & MA): *Access + Marketing* Building linked to other Buildings: *Yes - 1225 York Mills Rd (Rentals)* Bulk Related: *No* [https://buildings.beanfield.com/buildings/view/6811] | NUA+MA | [12 empty] | 0¦i5ir5j: | [7 empty] | 9.2234e+18 | [19 empty] | Feb 12, 2025_CA Approved Feb 12, 2025, FTTB-010006, Dated Feb 7, 2025. Received Marketing and Access Agreement. Feb 18, 2025 - Needed to Rename 1 Deerlick to 10 Deerlick feb 26, 2025 - Sending Pm request for Riser and Cable pull. Pm has approved this work. March 12, 2025 - Riser Panels All of the panels prepped and ready for splicing. Riser Fibre Pull completed. March 12, 2025 - Accessing the Telecom Room -The Team was able to enter the Telecom Room @ 1225 York Mills and confirmed there is no Yellow rope in any of the incoming Conduits . Call the PM for access to 1225 York Mills @ (647) 627-6895 March 14, 2025 - Moving building up from May to April , This project was put on schedule for april, then decided to move to May (the reason is it takes, a period of time to determine, if all the permits, and to get a feel of Condo PM, when permits move well and Condo Boards and Pm are more agreeable, then projects move quicker.) March 18, 2025 - Splicing SOW will be ready by the end of day Thursday March 20, 2025. March 20, 2025 - Cable pull has been completed. March 24, 2025 - On Net schedule planned date is April 2, 2025, changing schedule date to April 2, 2025 from April 28, 2025. March 25, 2025 - ISP Splicing is completed. March 25, 2025 - Panel prep note: All panels prepped and spliced March 25,2025 - OSP splicing - Outside testing is completed from the last location to 3.5km before splicing cable into building, still need to access into the consumers to complete testing. March 26, 2025 - On Net email set for March 26, 2025. The due date for this project was April 2, 2025 but they were able to complete this on March 26, 2025. March 27, 2025 - There are no restorations, as this is a cable pull. Cable pull has been completed. Building EOC-9131M BFMH16035 EOC-8780M Duct-8819M Total Fiber Used-351M | [6 empty] | 3 - Normal | [20 empty] | 2025-03-27 | 2025-02-12 |  |  | 29 | 313 |  | 2025-03-26 |  |  |  | https://buildings.beanfield.com/buildings/view/6811 |  | CONST-40044 | 3 - Normal | 2025-04-28 | North York
Construction | CONST-36745 | 36 Zorra St, Etobicoke | Condo | Clean Up |  | Unresolved | James Mowers | Lorna Kurok | Olawale Olaniyan [X] | 2024-03-05 10:23 |  | 2025-03-28 08:59 |  |  | 2025-03-28 | 0 | 1 |  |  | CONST-36746, CONST-36747, CONST-36978, CONST-39280, CONST-39287, CONST-39288, CONST-39289, CONST-39290, CONST-39291, CONST-39292, CONST-39293, CONST-39294, CONST-39295, CONST-39296, CONST-39297, CONST-39298, CONST-39299, CONST-39300, CONST-39301, CONST-39572, CONST-39707, CONST-40250, CONST-40557 |  | Team, Please be advised that this project is now funded to proceed, Lorna: please update JIRA with all the particulars of this project. Project Summary MDU Address: *36 Zorra St* City: *Etobicoke* Building Name: *Thirty Six Zorra* # of Units: *460* # of Floors: *36* Building Constructed Year: *2023* PM Contact Name: *Renata Balliu* PM Contact #: *416-255-8598* PM Email Address: *[36zorra.on@fsresidential.com¦mailto:36zorra.on@fsresidential.com]* Type of Contract (Fibre agreement or NUA & MA): *NUA & MA* Building linked to other Buildings: *N/A* Bulk Related: *N/A* [https://buildings.beanfield.com/buildings/view/17375] Attachments: * Fibre Estimate Request (FER): Attached detailing cost breakdown * Agreement: Signed * any pertinent comments such as phased build / spend Requested by Oliver Davies, Please proceed with creating a new ticket for an OSP plan & site walk at 36 Zorra St. The 'Thirty Six Zorra’ condos were recently occupied and include 460 residential units. *Updated PM information as of November 20, 2024:* ¦ *Renata Balliu* Property Manager 36 Zorra St \¦ Toronto, ON M8Z 0G5 Office 416.255.8598 24/7 Security 416.251.0224 Email _[36zorra.on@fsresidential.com¦mailto:36zorra.on@fsresidential.com]_¦ Old PM Info: Jennifer Gauke, OLCM Condominium Manager Agents for and on behalf of Thirty Six Zorra 36 Zorra Street, Toronto, ON M8Z 4Z7 Phone: 416-255-8598 Email: [36zorra@crossbridgecs.com¦mailto:36zorra@crossbridgecs.com] Thanks! | NUA+MA | [12 empty] | 0¦i4nw6f: | [7 empty] | 9.2234e+18 | [19 empty] | Nov 20, 2024 - Email Resi construction Schedule - This email indicates that we can mover forward and place this project In Progress. It communicates that we do have a signed agreement. Made a comment to Oliver to Confirm agreement. Nov 20, 2024 - Changes in processes, Agreement has been uploaded. Nov 22, 2024 On the On Net schedule for May 15, 2025 Dec 11, 2024 -NEW RESIDENTIAL BUILDING – CA APPROVED FTTB#00896 - 36 Zorra Jan 29, 2025 - Locates have submitted, permit should be received in a couple of weeks. Jan 2025 - Project has been submitted to the city for permits. Bore 162m, trench 12m Feb 4, 2025 - Conduit Build Sketch Note - This will be an approximately 60m build from our core @ spot V17 to an existing pull box. We will need spot V15 - V5 and also spot V17 blocked off for installation.A 8ft Ladder will be required to complete the installation. I am still waiting on the P1 electrical Drawings , once i receive them i will red line our route. Feb 6, 2025 - Riser Panels Install all of the panels as per diagram, dressed all panels. all panels dressed and prepped. Completed Feb 6, 2025 - Dressed POP Cables, pictures attached. completed Feb 10, 2025 - Locates completed. March 10, 2025 - OSP Construction scheduled for March 10 - 18 March 10, 2025 - Cable scheduled for March 21, Conduit scheduled for March 18, Internal riser build already completed. Property manager was easy going and approved our schedule right away. March 10, 2025 - Moving project up in schedule from May to April 2025. Pm has approved all of the pending work. March 12, 2025 - OSP construction in progress March 25, 2025 - Cable pull was scheduled for Friday March 21, 2025. This was not able to completed on this date, as construction is in progress. Need to reschedule cable pull with Pm. march 25, 2025 - The On Net Scheduled planned date is April 4, 2025. March 28, 2025 - Building is On Net. Pending City Asbuilt drawing and cable pull asbuilt. Need asbuilt to determine if there is Hard surface restorations. | [6 empty] | 3 - Normal | [20 empty] | 2025-03-28 | 2024-11-20 |  |  | 36 | 460 |  | 2025-03-28 |  |  |  | https://buildings.beanfield.com/buildings/view/17375 |  | CONST-36745 | 3 - Normal | 2025-05-15 | Etobicoke
Construction | CONST-3126 | 18 Stafford St - Wellington Sq Condos | Condo | Resolved |  | Complete | Oguz Avci [X] | Nadeem Haider | Samantha Russell | 2015-02-25 13:13 |  | 2019-09-25 11:03 | 2019-08-07 20:30 |  | 2019-08-02 | 0 | 3 | _thumb_134990.png _thumb_134988.png _thumb_134989.png _thumb_134985.png _thumb_134986.png _thumb_134987.png _thumb_172990.png |  | CONST-3127, CONST-3128, CONST-3129, CONST-8620, CONST-8621, CONST-8674, CONST-8675, CONST-8676, CONST-8677, CONST-8678, CONST-8679, CONST-8680, CONST-8681, CONST-8682, CONST-8683, CONST-8684, CONST-8685, CONST-8686, CONST-8687, CONST-8688, CONST-9526, CONST-10553, CONST-10554, CONST-10711, CONST-10819, CONST-13965 |  | Bring residential building onnet https://buildings.beanfield.com/buildings/view/2926 Lamali Rajab (lamali@goldview.ca) 172 Suites No Power in suites Telecom Room on Ground level in hydro room zone conduits and free riser sleeves | Residential | [12 empty] | 0¦i07rbr: | [7 empty] | 45253 | [26 empty] | 3 - Normal | [28 empty] | 16000 |  |  | https://buildings.beanfield.com/buildings/view/2926 |  | 500165 | 3 - Normal |  | King Spadina / Garment District | 1200 | 4200
Construction | CONST-5348 | One Bloor - 1 Bloor St. East | Condo | Resolved |  | Unresolved | Oguz Avci [X] | Russell Francey | Russell Francey | 2017-01-11 08:08 |  | 2019-09-06 09:19 |  |  | 2019-02-14 | 0 | 4 |  |  | CONST-2524, CONST-5349, CONST-5350, CONST-5351, CONST-5671, CONST-5672, CONST-5673, CONST-5674, CONST-6240, CONST-6241, CONST-6647, CONST-6900, CONST-6901, CONST-6930, CONST-6995, CONST-7145, CONST-7549, CONST-9190, CONST-9451, CONST-9457, CONST-9587, CONST-9588, CONST-9631, CONST-9736, CONST-9788, CONST-9789, CONST-9790 | CONST-5388, CONST-7180 | suzanne.toole@balancerm.com New site contact for Tucker HiRise. Martin Orbanic 416-206-1468 martin.orbanic@tuckerhirise.com | Sentrex | [12 empty] | 0¦i0neaf: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [28 empty] | 17000 |  |  | https://buildings.beanfield.com/buildings/view/2125 |  | 500106 | 3 - Normal | 2017-09-22 |  | 9000 | 3000
Construction | CONST-5147 | 219 Queen St W - Smart House | Condo | Resolved |  | Unresolved | Oguz Avci [X] | Samantha Russell | Samantha Russell | 2016-11-24 09:13 |  | 2019-09-06 09:19 |  |  | 2018-09-14 | 0 | 3 | _thumb_88784.png |  | CONST-5148, CONST-5149, CONST-5554, CONST-5555, CONST-5731, CONST-6270, CONST-6280, CONST-6939, CONST-7127, CONST-7418, CONST-7460, CONST-7502, CONST-7563, CONST-7602, CONST-7658, CONST-7928, CONST-8610, CONST-8653, CONST-8735, CONST-8891, CONST-8919, CONST-12386 | ACCT-30668, ACCT-36469 | Jay to confirm the contacts | [13 empty] | 0¦i0mbaf: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [28 empty] | 36000 |  |  | https://buildings.beanfield.com/buildings/view/5287 |  | 500109 | 3 - Normal | 2018-04-27 |  | 9000 | 7000
Construction | CONST-6562 | Trinity Lofts - 90 Trinity St | Condo | Resolved |  | Unresolved | Oguz Avci [X] | Russell Francey | Russell Francey | 2017-07-10 10:42 |  | 2019-09-06 09:19 |  |  | 2019-02-08 | 0 | 3 | _thumb_141144.png |  | CONST-6563, CONST-6662, CONST-7548, CONST-8181, CONST-8182, CONST-8359, CONST-8360, CONST-8361, CONST-8362, CONST-8363, CONST-8364, CONST-8365, CONST-8366, CONST-8367, CONST-8368, CONST-8369, CONST-8370, CONST-8371, CONST-8372, CONST-8780, CONST-9299, CONST-9632, CONST-9633, CONST-9761, CONST-12362 | CONST-8736 | Katia Savvaidou, RCM, Licensed Senior Property Manager Crossbridge Condominium Services As Agents for and on behalf of TSCC#2263 90 Trinity Street Toronto, Ontario Tel: 416-230-6501 trinityloftsmanagement@gmail.com | [13 empty] | 0¦i0sn67: | [7 empty] | 9.2234e+18 | [19 empty] | Condo's lawyers are insisting that Beanfield pay for the complimentary services hardware. Jory working with them to see if we can come to a agreement. | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/3479 |  | 500149 | 3 - Normal |  | King East
Construction | CONST-8166 | Grid Condos - 181 Dundas St E | Condo | Resolved |  | Complete | Danny Da Silva | Danny Da Silva | Russell Francey | 2018-06-14 10:53 |  | 2019-08-07 17:48 | 2019-08-07 17:48 |  | 2019-01-25 | 0 | 2 |  |  | CONST-8167, CONST-8206, CONST-8219, CONST-8228, CONST-8229, CONST-8230, CONST-8231, CONST-8232, CONST-8233, CONST-8234, CONST-8235, CONST-8236, CONST-8237, CONST-8238, CONST-8239, CONST-8240, CONST-8241, CONST-8242, CONST-8243, CONST-8244, CONST-9320, CONST-9342, CONST-9385, CONST-9436, CONST-9536, CONST-9548 | [15 empty] | 0¦i161wf: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [28 empty] | 26000 |  |  | https://buildings.beanfield.com/buildings/view/5737 |  |  | 3 - Normal |  | Yonge & Dundas | 1000
Construction | CONST-7913 | Rezen - 205 Fredrick St. | Condo | Resolved |  | Complete | Oguz Avci [X] | Russell Francey | Russell Francey | 2018-04-19 14:01 |  | 2019-09-06 09:19 | 2019-02-13 08:30 |  | 2019-02-28 | 0 | 4 | _thumb_120868.png _thumb_120869.png _thumb_120870.png |  | CONST-7914, CONST-7915, CONST-9133, CONST-9136, CONST-9137, CONST-9138, CONST-9139, CONST-9140, CONST-9141, CONST-9142, CONST-9143, CONST-9144, CONST-9145, CONST-9146, CONST-9147, CONST-9148, CONST-9149, CONST-9150, CONST-9181, CONST-9182, CONST-9698 |  | Melody Property Manager As Agents for and on Behalf of T.S.C.C. 2005 205 Frederick Street, Toronto, ON M5A 4V3 rezenpropertymanager@rogers.com Tel: 416 214 0887 Fax: 416 214 0886 Website: [www.rezencondo.ca¦http://www.rezencondo.ca/] | [13 empty] | 0¦i137u7: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [28 empty] | 0 |  |  | https://buildings.beanfield.com/buildings/view/2465 |  | 500175 | 3 - Normal |  | Downtown East | 2000 | 4100
Construction | CONST-5795 | 208 Queens Quay W - Waterclub Ⅱ | Condo | Resolved |  | Unresolved | Oguz Avci [X] | Russell Francey | Russell Francey | 2017-04-03 15:37 |  | 2019-09-16 11:36 |  |  | 2018-05-04 | 0 | 3 |  |  | CONST-5796, CONST-6956, CONST-6957, CONST-7116, CONST-7483, CONST-7882 | CONST-5550, CONST-7281, CONST-7903 | No Power in suites confirmed by James | NoPower | [12 empty] | 0¦i0ptpb: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/1493 |  | 500111 | 3 - Normal |  | Central Waterfront
Construction | CONST-5798 | 218 Queens Quay W - Waterclub Ⅲ | Condo | Resolved |  | Unresolved | Oguz Avci [X] | Russell Francey | Russell Francey | 2017-04-03 15:42 |  | 2019-09-16 11:36 |  |  | 2018-05-04 | 0 | 3 |  |  | CONST-5799, CONST-6960, CONST-6961, CONST-7117, CONST-7351, CONST-7487, CONST-7883, CONST-9243 | CONST-5550, CONST-7281, CONST-7903 | no power in suites confirmed by James | NoPower | [12 empty] | 0¦i0ptq7: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/1493 |  | 500111 | 3 - Normal |  | Central Waterfront
Construction | CONST-4361 | 210 Eastern Ave (170 Bayview) | Condo | Resolved |  | Unresolved | Oguz Avci [X] | Samantha Russell | Samantha Russell | 2016-04-04 09:27 |  | 2019-09-06 09:19 |  |  | 2018-06-01 | 0 | 2 | _thumb_67004.png |  | CONST-4879, CONST-5092, CONST-5093, CONST-5803, CONST-7028, CONST-7111, CONST-7125, CONST-7261, CONST-7295, CONST-7315, CONST-7420, CONST-7440, CONST-7464, CONST-7471, CONST-7575, CONST-7745, CONST-8004, CONST-8135, CONST-8136 | ACCT-30669 | Bring building onnet | BudgetPending | [12 empty] | 0¦i0g2mn: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [33 empty] | 500126 | 3 - Normal | 2018-03-02 |  | 14000
Construction | CONST-9289 | 501 Adelaide St W- Kingly Condos (attached to 620 King St W) | Condo | Resolved |  | Unresolved | Oguz Avci [X] | Oguz Avci [X] | Nadeem Haider | 2018-11-21 15:24 |  | 2020-11-13 11:20 |  |  | 2019-08-09 | 0 | 1 |  |  | CONST-9290, CONST-10161, CONST-10162, CONST-10163, CONST-10221, CONST-10241, CONST-10242, CONST-10243, CONST-10714, CONST-10814, CONST-11214 | CONST-5841 | Hi, It looks like we forgot about the condo that is attached to 620 King St W. We are finalizing the agreement for it but we should reach out as I think it’s pretty far along. I’ve attached the Ellis Don site contacts (Mohammad Danesh and Luke Williams) to this email. If they have any questions or concerns let them know that Michael Grunstra (Manager, Construction) from Allied gave us their contact information. *Mohammad Danesh(EllisDon Corporation)* Work: 647-351-0222 Mobile-647-649-8260 Email: [mdanesh@ellisdon.com¦mailto:mdanesh@ellisdon.com] *Luke Williams* Assistant Superintendent EllisDon Corporation Mobile: 437-929-6160‬ Email: lwilliams@ellisdon.com | [13 empty] | 0¦i1d5q7: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [28 empty] | 3000 |  |  | https://buildings.beanfield.com/buildings/view/8204 |  | 500178 | 3 - Normal |  |  | 2000
Construction | CONST-6907 | The Printing Factory - 201 Carlaw Ave. | Condo | Resolved |  | Unresolved | Oguz Avci [X] | Russell Francey | Russell Francey | 2017-10-04 08:58 |  | 2019-09-16 11:51 |  |  | 2018-10-12 | 0 | 4 | _thumb_118500.png _thumb_105323.png _thumb_105324.png _thumb_105325.png _thumb_105326.png _thumb_105327.png _thumb_105328.png _thumb_105329.png |  | CONST-6908, CONST-6909, CONST-6910, CONST-7803, CONST-7804, CONST-7805, CONST-7806, CONST-7807, CONST-7808, CONST-7809, CONST-7810, CONST-7811, CONST-7812, CONST-7813, CONST-7840, CONST-7841, CONST-7871, CONST-7901, CONST-7921, CONST-8333, CONST-8374, CONST-8411, CONST-11836 |  | Adrian Sebu, RCM Property Manager Crossbridge Condominium Services Ltd. As Agents for and on behalf of TSCC 2073 The Printing Factory Lofts - 201 Carlaw Ave. Toronto, ON, M4M 2S3 Tel: 647-340-4291 Fax:647-340-4304 theprintingfactory@rogers.com pop on p1 in main electrical room 44 townhouses fed from telephone room in unbridle room on east side of parking lot beside V19 riser in p1 south side of building for lower suites Bell prewired for fiber but have not brought their new trunk in yet zone conduits to suites | Onnetdate17Aug | [12 empty] | 0¦i0vzt3: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [28 empty] | 31000 |  |  | https://buildings.beanfield.com/buildings/view/2333 |  | 500146 | 3 - Normal | 2018-10-12 | Carlaw (Leslieville) | 3000 | 1000
Construction | CONST-4596 | 60 Bathurst - Sixty Lofts | Condo | Resolved |  | Unresolved | Oguz Avci [X] | Russell Francey | Russell Francey | 2016-06-24 12:48 |  | 2019-09-06 09:19 |  |  | 2018-11-30 | 0 | 1 | _thumb_124220.png _thumb_124221.png _thumb_124222.png _thumb_124223.png _thumb_124224.png |  | CONST-4597, CONST-4598, CONST-4599, CONST-8064, CONST-8106, CONST-8107, CONST-8293, CONST-8294, CONST-8295, CONST-8296, CONST-8297, CONST-8298, CONST-8299, CONST-8300, CONST-8301, CONST-8303, CONST-8304, CONST-8305, CONST-8306, CONST-8341, CONST-8504, CONST-9276, CONST-9291, CONST-9383 | [15 empty] | 0¦i0i7mv: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [28 empty] | 20600 |  |  | https://buildings.beanfield.com/buildings/view/1800 |  | 500148 | 5 - Very Low |  | West King West
Construction | CONST-3444 | 43 Hanna Lofts prewire | Condo | Resolved |  | Complete | Phil Sabourin | Phil Sabourin | Phil Sabourin | 2015-05-13 08:17 |  | 2015-06-24 14:09 | 2015-06-24 14:09 |  |  | 0 | 1 |  |  | CONST-3470 |  | [~danny][~perry]The following lofts 423, 439,440,441, 442 will be prewired Contractor is installing conduit from 4th floor electrical closet to each loft They should be ready for the week of May 18 - i will let you know dates when he calls me | [13 empty] | 0¦i08ypb: | [7 empty] | 52280 | [26 empty] | 3 - Normal | [34 empty] | 3 - Normal
Construction | CONST-3406 | Harbour View Estates | Condo | Resolved |  | Complete | Russell Francey | Jay Fernandes | Jay Fernandes | 2015-05-05 08:31 |  | 2017-05-12 13:43 | 2017-05-12 13:43 |  |  | 0 | 2 |  |  | CONST-3407, CONST-3408, CONST-3409, CONST-9323, CONST-36162 | CONST-5460, CONST-5463, CONST-5467, CONST-5920, CONST-5922 | TSCC#1694- 10 Navy Wharf Court and 9 Spadina ave TSCC#1713 – 35 mariner Terrace Tscc#1764 – 3 navy wharf court and 5 Mariner Terrace | [13 empty] | 0¦i08tnz: | [7 empty] | 51464 | [19 empty] | Apart of project blue jay | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/1168# |  |  | 5 - Very Low |  | Concord Cityplace
BC Construction | BCCONST-81 | 9873 King George Blvd, Surrey BC Century City | Condo | Resolved |  | Complete | Michael Tsamkiranis | Michael Tsamkiranis | Michael Tsamkiranis | 2023-05-15 15:00 |  | 2024-11-07 14:03 | 2024-03-27 17:11 |  | 2024-03-28 | 0 | 0 |  |  | BCCONST-82, BCCONST-83, BCCONST-128, BCCONST-490, BCCONST-491, BCCONST-492, BCCONST-637 | BCCONST-5, PUR-29622, PUR-29850 | Will require wiring to all suites. 243 Units - 3 CRUs Contacts: *REESE WILKINSON* Project Manager C 604.830.7797 BlueCity Construction 604.270.1889 +[www.BlueCity.ca¦http://www.bluecity.ca/]+ *JEREMY GRUMAN* (he/him/his) Director, Information Systems D 604.338.4268 Century Group 604.943.2203 [www.CenturyGroup.ca¦https://centurygroup.ca/] | Budget_Allocated, confirmed | [12 empty] | 0¦i419xz: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [20 empty] | 2024-03-27 | 2023-05-15 |  |  | 19 | 243 | [11 empty] | 28000 | 18000
Construction | CONST-27847 | Marine Parade Backbone | Condo | Resolved |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Harvey Tran | 2022-04-13 12:33 |  | 2024-12-10 10:41 |  |  |  | 0 | 0 |  |  | CONST-27848, CONST-27849 | CONST-25610, CONST-25612 | After meeting with James and Danny it was decided we needed to build some backbone along Marine Parade Drive in order to reduce costs and more importantly hydro duct rental costs. There is a $200K budget for this which we should include in the residential budget for this build. The high level build and budget are attached. The rest of these buildings are all approved. These all need the new NPOP at 30 Shorebreeze up which I just heard is signed. With the backbone included we’re still under $150 per unit which is great! | HumberBay, MysticPointe | [12 empty] | 0¦i3boon: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [26 empty] | Backbone | [7 empty] | 3 - Normal
BC Construction | BCCONST-762 | Site Walk - 947 E Hastings St | Condo | Resolved |  | Unresolved | Jasminder Boparai [X] | Jasminder Boparai [X] | Jasminder Boparai [X] | 2024-07-29 16:41 |  | 2024-10-10 17:33 |  |  |  | 0 | 0 | _thumb_970019.png _thumb_970020.png _thumb_970021.png _thumb_970022.png _thumb_970023.png |  |  |  | Site walk to determine if we can feed 947 E Hastings St from 955 E Hastings St. Nian P: 604-336-9230 | [13 empty] | 0¦i53bsn: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal
BC Construction | BCCONST-89 | 210 Salter Street, New Westminster, BC | Condo | Resolved |  | Complete | Yawn Paular | Yawn Paular | Yawn Paular | 2023-05-23 13:25 |  | 2024-12-20 21:23 | 2024-01-31 17:17 |  | 2024-01-31 | 0 | 0 |  |  | BCCONST-90, BCCONST-172, BCCONST-242, BCCONST-243, BCCONST-244, BCCONST-245, BCCONST-246, BCCONST-619 | ORDER-212079, ORDER-212084, ORDER-212089, ORDER-212094, ORDER-212099, ORDER-212104, ACCT-135174, PUR-25910 | Strong Lead request from a customer as per Michael Setting up Site check. Bridgenet maybe in the bldg already 164 units = 22 floors Terry Bunke EPS 4303 Peninsula Port Royal {color:#000000}Cell 604-418-3553{color} *MAHYAR ATTAR* Senior Strata Manager 200 Granville Street ¦ Suite 700 ¦ Vancouver, BC, Canada V6C 1S4 1.855.333.5149 ¦ Office 604.683.8900 ¦ Fax 604.689.4829 Toll Free 1.855.683.8900 ¦ Customer Care Centre 1.855.273.1967 Email [_Mahyar.Attar@fsresidential.com_¦mailto:Mahyar.Attar@fsresidential.com] [*www.fsresidential.com*¦http://www.fsresidential.com/] Follow us on ¦ [Facebook¦https://www.facebook.com/pages/Firstservice-Residential-BC/664991976868719#!%20/pages/Firstservice-Residential-BC/664991976868719] ¦ [LinkedIn¦http://www.linkedin.com/company/firstservice-residential-bc?trk=company_name] ¦ [YouTube¦http://www.youtube.com/FSResidential] | Bridgenet, Budget_Allocated, Pre-Sales, Pre-planning | [12 empty] | 0¦i41sjj: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [20 empty] | 2024-01-31 |  |  |  | 22 | 164 | [11 empty] | 7300 | 4200
BC Construction | BCCONST-92 | 3086 Lincoln Ave (1123 Westwood), Coquitlam BC | Condo | Resolved |  | Complete | Jasminder Boparai [X] | Yawn Paular | Yawn Paular | 2023-05-25 17:46 |  | 2024-12-20 21:25 | 2023-12-28 13:25 |  | 2023-12-08 | 0 | 0 |  |  | BCCONST-93, BCCONST-94, BCCONST-95, BCCONST-96, BCCONST-97, BCCONST-98, BCCONST-145, BCCONST-200, BCCONST-785 | PUR-25393 | 30 Com units 249 Resi units | Budget_Allocated, QNET, confirmed, conversion | [12 empty] | 0¦i4228n: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [20 empty] | 2023-11-20 |  |  |  | 30 | 249 | [11 empty] | 9230 | 6800
BC Construction | BCCONST-120 | 3007 Glen Dr (Evergreen), Coquitlam BC | Condo | Resolved |  | Complete | Jasminder Boparai [X] | Yawn Paular | Yawn Paular | 2023-05-25 19:37 |  | 2024-12-20 21:26 | 2023-12-28 13:24 |  | 2023-12-08 | 0 | 0 |  |  | BCCONST-121, BCCONST-122, BCCONST-123, BCCONST-124, BCCONST-125, BCCONST-126, BCCONST-141, BCCONST-194 | PUR-24768 | Evergreen - 3007 Glen Drive, Coquitlam, BC V3B 2P7, Canada. Strata plan number BCP45694. Crossroads are Pinetree Way and The High Street. Evergreen is 30 stories with 195 units. Estimated completion is September 2015. Developed by Bosa Properties Inc.. Architecture by Rafii Architects Inc.. Interior design by BYU Design | Budget_Allocated, QNET, confirmed, conversion | [12 empty] | 0¦i422k7: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [20 empty] | 2023-12-07 | 2023-05-31 |  |  | 30 | 195 | [11 empty] | 4800
BC Construction | BCCONST-317 | 10 Renaissance Sq, New Westminster | Condo | Resolved |  | Complete | Jasminder Boparai [X] | Yawn Paular | Yawn Paular | 2023-07-10 13:43 |  | 2024-12-20 21:24 | 2023-12-28 13:23 |  | 2023-12-29 | 0 | 0 |  |  | BCCONST-318, BCCONST-319, BCCONST-320, BCCONST-321, BCCONST-322, BCCONST-323, BCCONST-359, BCCONST-618 | PUR-29862 | 237 units for all 3 bldgs 8 Renaissance Sq and 7 Rialto Crt Bridgenet in the Bldg 154 units for this bldg, shared conduits in some closets | Bridgenet, Budget_Allocated | [12 empty] | 0¦i45u9b: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [20 empty] | 2023-12-28 |  |  |  |  | 154 | [11 empty] | 11250 | 3400
BC Construction | BCCONST-99 | 2979 Glen Drive (Altamonte), Coquitlam BC | Condo | Resolved |  | Complete | Jasminder Boparai [X] | Yawn Paular | Yawn Paular | 2023-05-25 18:06 |  | 2024-12-20 21:22 | 2024-03-19 13:45 |  | 2024-02-23 | 0 | 0 |  |  | BCCONST-100, BCCONST-101, BCCONST-102, BCCONST-103, BCCONST-104, BCCONST-105, BCCONST-144, BCCONST-213 |  | LEVELS: 30 SUITES: 165 STATUS: Completed BUILT: 2008 TYPE: Freehold Strata STRATA PLAN: BCS2656 BLDG#: 3575 Keith Cuyong SIte Manager 604-554-0115 altamontemanager@gmail.com | Budget_Allocated, QNET, confirmed, conversion | [12 empty] | 0¦i422b3: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [20 empty] | 2024-02-23 | 2023-06-06 |  |  | 30 | 165 | [11 empty] | 4460
BC Construction | BCCONST-626 | 188 Agnes St. (The Elliot), New Westminster, BC | Condo | Resolved |  | Complete | Yawn Paular | Yawn Paular | Yawn Paular | 2024-03-01 18:00 |  | 2024-12-20 21:31 | 2024-06-10 12:23 |  | 2024-06-28 | 0 | 0 | _thumb_909962.png |  | BCCONST-627, BCCONST-628, BCCONST-629, BCCONST-630, BCCONST-631, BCCONST-632, BCCONST-633, BCCONST-634, BCCONST-751 | PUR-35799 | 190 units - 9 townhouses 19 floors | Bridgenet, Budget_Allocated | [12 empty] | 0¦i4npjz: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [20 empty] | 2024-06-10 |  |  |  | 19 | 199 | [11 empty] | 5900 | 1200
BC Construction | BCCONST-113 | 2978 Glen Dr (Grand Central 1), Coquitlam BC | Condo | Resolved |  | Complete | Jasminder Boparai [X] | Yawn Paular | Yawn Paular | 2023-05-25 19:28 |  | 2024-12-20 21:28 | 2024-03-27 13:11 |  | 2024-03-28 | 0 | 0 |  |  | BCCONST-114, BCCONST-115, BCCONST-116, BCCONST-117, BCCONST-118, BCCONST-119, BCCONST-142, BCCONST-280 | BCCONST-249, BCCONST-250, PUR-25557 | Grand Central 1 is one of three Grand Central MDUs, total 625 units. LEVELS: 28 SUITES: 146 STATUS: Completed BUILT: 2009 TYPE: Freehold Strata STRATA PLAN: BCS3495 Bldg#: 5410 ***Please note that Jason Greene is not authorized to make any changes regarding the Grand Central building. *{*}Update: May 2022{*}* New Building manager - Amar 236-833-7998, [grandcentralpbs@gmail.com¦mailto:grandcentralpbs@gmail.com] | Budget_Allocated, QNET, confirmed, conversion | [12 empty] | 0¦i422if: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [20 empty] | 2024-03-27 |  |  |  | 28 | 146 | [11 empty] | 3900 | 2700
BC Construction | BCCONST-250 | 2975 Atlantic Ave (Grand Central 3), Coquitlam BC | Condo | Resolved |  | Complete | Jasminder Boparai [X] | Yawn Paular | Yawn Paular | 2023-06-14 14:23 |  | 2024-12-20 21:31 | 2024-06-17 12:53 |  | 2024-06-28 | 0 | 0 |  |  | BCCONST-258, BCCONST-259, BCCONST-260, BCCONST-261, BCCONST-262, BCCONST-263, BCCONST-264 | BCCONST-113, BCCONST-249, PUR-25660 | 37 Floors 248 Units Skips Floors 4, 13, 14, and 24 | Budget_Allocated, Conversion, QNET, confirmed | [12 empty] | 0¦i43ug7: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [20 empty] | 2024-06-17 |  |  |  | 37 | 248 | [11 empty] | 8600 | 4200
BC Construction | BCCONST-249 | 2968 Glen Dr (Grand Central 2), Coquitlam BC | Condo | Resolved |  | Complete | Jasminder Boparai [X] | Yawn Paular | Yawn Paular | 2023-06-14 14:23 |  | 2024-12-20 21:32 | 2024-07-22 11:15 |  | 2024-07-31 | 0 | 0 |  |  | BCCONST-251, BCCONST-252, BCCONST-253, BCCONST-254, BCCONST-255, BCCONST-256, BCCONST-257 | BCCONST-113, BCCONST-250, PUR-25645 | 32 Floors - 212 units Skips Floors 4, 13, 14, and 24 MTR all connected with FT6 12F 2 fibers to switch 6 each at GC2 and 3 12 available for each GC 2 and GC 3 from MTR outdoor cable | Budget_Allocated, QNET, confirmed, conversion | [12 empty] | 0¦i43ufr: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [20 empty] | 2024-07-22 |  |  |  | 32 | 212 | [11 empty] | 6200 | 3400
BC Construction | BCCONST-382 | 1188 Pinetree Way (MThree), Coquitlam BC | Condo | Resolved |  | Complete | Yawn Paular | Yawn Paular | Yawn Paular | 2023-08-14 17:02 |  | 2024-12-20 21:30 | 2024-05-24 18:42 |  | 2024-05-31 | 0 | 0 |  |  | BCCONST-391, BCCONST-392, BCCONST-393, BCCONST-394, BCCONST-395, BCCONST-396, BCCONST-397 | PUR-31458 | 42 floors 319 Units | Budget_Allocated, Migration, QNET | [12 empty] | 0¦i48unj: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [20 empty] | 2024-05-24 |  |  |  | 42 | 319 | [11 empty] | 14500 | 5200
BC Construction | BCCONST-427 | 200 Keary St, New Westminster | Condo | Resolved |  | Complete | Yawn Paular | Yawn Paular | Yawn Paular | 2023-10-18 17:33 |  | 2024-12-20 21:29 | 2024-04-19 15:56 |  | 2024-04-19 | 0 | 0 |  |  | BCCONST-428, BCCONST-429, BCCONST-430, BCCONST-431, BCCONST-432, BCCONST-433, BCCONST-434 | PUR-33255 | The Anvil - 100 units Bridgenet not in the bldg yet. Spare conduit found coming into MTR https://buildings.beanfield.com/buildings/view/19892 | Bridgenet, Budget_Allocated | [12 empty] | 0¦i4e11b: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [20 empty] | 2024-04-19 |  |  |  |  | 100 | [11 empty] | 6100 | 2900
BC Construction | BCCONST-383 | 2955 Atlantic Avenue (Oasis), Coquitlam BC | Condo | Resolved |  | Complete | Yawn Paular | Yawn Paular | Yawn Paular | 2023-08-14 17:04 |  | 2024-12-20 21:20 | 2024-03-13 17:42 |  | 2024-03-15 | 0 | 0 |  |  | BCCONST-384, BCCONST-385, BCCONST-386, BCCONST-387, BCCONST-388, BCCONST-389, BCCONST-390 | PUR-31459 | 255 units, 42 flrs According to Jas the extra fiber we're paying for GC is being used for backup that's connected to this bldg from GC | Budget_Allocated, Migraton, QNET | [12 empty] | 0¦i48uo7: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [20 empty] | 2024-03-13 |  |  |  | 42 | 255 | [11 empty] | 12100 | 5200
Construction | CONST-38230 | 7 King St E_Toronto_The Metropole | Condo | Resolved |  | Unresolved | Lorna Kurok | Lorna Kurok | Lorna Kurok | 2024-08-23 07:28 |  | 2024-12-24 12:45 |  |  |  | 0 | 0 |  |  | CONST-38231, CONST-38232 | CONST-4544 | _Requested by Oliver Davies_Aug 22, 2024_ *Units for 7 King St E is 314* {color:#0747a6}*PM Info:*{color}{*}{{*}} *Nancy Bijelic* President & CEO PropertyWright™ Management Inc. [Nancy.Bijelic@propertywright.ca¦mailto:Nancy.Bijelic@propertywright.ca] Office:416-549-1412 _Email Request:_ _Could you please proceed with creating a new ticket for an OSP plan & Site Walk at 7 King St E? There are 314 residential units at this condo._ _Note, a visit was previously conducted here in 2016 when it was deemed not a candidate due to the requirement of pre-wiring the suites (CONST-4544)_ _BB Link:_ _[https://buildings.beanfield.com/buildings/view/2577]_ _PM Info:_ *Nancy Bijelic* President & CEO PropertyWright™ Management Inc. [Nancy.Bijelic@propertywright.ca¦mailto:Nancy.Bijelic@propertywright.ca] Office:416-549-1412 | [13 empty] | 0¦i55di7: | [7 empty] | 9.2234e+18 | [19 empty] | Aug 22, 2024_Ticket created Cancel refer to ticket Const-4544 | [6 empty] | 3 - Normal | [24 empty] | 23 | 314 | [5 empty] | https://buildings.beanfield.com/buildings/view/2577 |  |  | 3 - Normal |  | Toronto
Construction | CONST-9078 | 10 York St - Ten York - ON HOLD | Condo | Resolved |  | Unresolved | Harvey Tran | Oguz Avci [X] | Russell Francey | 2018-10-26 12:02 |  | 2024-12-24 15:36 |  |  |  | 0 | 3 |  |  | CONST-9079, CONST-9080, CONST-12944, CONST-12945 | CONST-37687 | *+New PM info:+* Karolina Lesniowska, RCM, OLCM Condominium Manager TSCC 2708 10 York Street Toronto, ON M5J 0E1 Phone: 647-348-9521 Fax: 416-551-0879 E: [10york.pm@delcondo.com¦mailto:10york.pm@delcondo.com] +*Old PM info:*+ Agents for and on behalf of T.S.C.C. No. 2708 Phone: (647) 348-9521 Fax: (416) 551-0879 Email: +{color:#0000ff}[10York.APM@DelCondo.com¦mailto:10York.APM@DelCondo.com]{color}+ Cosmin Moraru Assistant Property Manager | OnHold | [12 empty] | 0¦i1c6bj: | [7 empty] | 9.2234e+18 | [19 empty] | Reference Jira Construction number Const-37687 | [6 empty] | 3 - Normal | [24 empty] | 65 | 725 | [5 empty] | https://buildings.beanfield.com/buildings/view/6900#!contacts |  |  | 3 - Normal |  | Toronto
Construction | CONST-39807 | 60 Fairfax Cres, Scarborough, Wilshire on the Green | Condo | Resolved |  | Unresolved | Unassigned | Lorna Kurok | Lorna Kurok | 2025-01-23 14:39 |  | 2025-01-24 08:08 |  |  |  | 0 | 0 |  |  |  |  | Condo Constructed in 2011 *Property Manager Contact Information as of Jan 22, 2025* PM Contact Name: Aleksia Bijelic PM Contact #: 416-752-5700 PM Email Address: [management@60fairfax.org¦mailto:management@60fairfax.org] *Newbuilds email January 22, 2025* Please see attached the signed agreements and CA/Budget form for 60 Fairfax that was approved today at CAPEX. MDU Address: 60 Fairfax Cres City: Scarborough Building Name: Wilshire on the Green # of Units:{*}198{*} # of Floors: 7 Building Constructed Year: 2011 Building First Occupancy Date or or time period of year, (eg. Mid 2026) PM Contact Name: Aleksia Bijelic PM Contact #: 416-752-5700 PM Email Address: [management@60fairfax.org¦mailto:management@60fairfax.org] Type of Contract (Fibre agreement or NUA & MA): A+M Building linked to other Buildings: n/a Bulk Related: No Comp Services on agreement: 2 internet, 2 phone lines Thank you Luke | [13 empty] | 0¦i5h8m7: | [7 empty] | 9.2234e+18 | [19 empty] | Jan 22, 2025_CA approved Closed this is a duplicate ticket please refer to CONST-28154 for the actually ticket | [6 empty] | 3 - Normal | [21 empty] | 2025-01-22 |  |  | 7 | 198 | [5 empty] | https://buildings.beanfield.com/buildings/view/16650 |  |  | 3 - Normal |  | Scarborough
Construction | CONST-35795 | 1603 Eglinton Ave W, York | Condo | Resolved |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2023-11-22 10:45 | 2025-03-04 17:52 | 2025-03-28 07:52 |  |  |  | 0 | 0 |  |  | CONST-35798, CONST-35799 | CONST-38108, CONST-37374 | Requested by Oliver Davies, Can you please create new tickets for an OSP plan for the 2x locations below? There is an (early) opportunity with Shannondale Developments for a 469 unit rental building that is being constructed at 775 Vaughan Rd. Occupancy is not expected until 2026-2027, but they are discussing telcos now. Also nearby is 1603 Eglinton Ave W, we have not received permission to complete a site walk, but I would like to determine what is involved outside of the building to connect them to our network. Thank you, | [13 empty] | 0¦i4gl73: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed 2018 Reference ticket Const-38108, this looks like a duplicate. | [6 empty] | 3 - Normal | [24 empty] | 16 | 219 | [5 empty] | https://buildings.beanfield.com/buildings/view/9988 |  |  | 3 - Normal |  | York
Construction | CONST-34079 | Warden Avenue & Hwy 7 - Markham Condos Backbone | Condo | Reopened |  | Unresolved | Denise King | Denise King | Denise King | 2023-05-30 09:30 |  | 2024-11-08 08:12 |  |  | 2024-09-24 | 0 | 0 |  |  | CONST-33158, CONST-34080, CONST-34086, CONST-34087, CONST-34088, CONST-34089, CONST-34090, CONST-34091, CONST-34092, CONST-34093, CONST-34094, CONST-34095, CONST-34096, CONST-34097, CONST-34098, CONST-34099, CONST-34100, CONST-34382, CONST-37221, CONST-37222 | CONST-29325, CONST-29425, CONST-26913, CONST-26914, PUR-26472, PUR-32357, PUR-40115, CONST-36969 | We encountered an issue that has changed our design to feed 268 Buchanan (CONST-26913) and 18 and 28 Uptown (CONST-26914) due to bridge reconstruction on Birchmount Rd crossing the Rouge River that would have significantly delayed the turn-up of these sites. Good news is that we have received an approved Bell SSA north up Warden and east across Hwy 7 to feed these sites. As part of the SSA we also applied for breakouts to service multiple existing condo’s not yet in our plans as well as condo’s in the development stages. This being said, we would like to create a separate project in Jira with it’s own sub-task’s separate from the Enterprise & Birchmount Build as the date for this new condo backbone will likely be completed a couple of months later. We will remove the budget amount from CONST-29425 to extension north up Birchmount crossing Hwy 7. The budget amount is similar because of the future breakouts to feed the several condo’s that exist and are in the development stages. [https://www.google.com/maps/d/edit?mid=1apyItX05rDnfcPDWs2lpwtGSLYq0KfQ&usp=sharing] | Backbone | [12 empty] | 0¦i42cn3: | [7 empty] | 9.2234e+18 | [19 empty] | June 7/23 - Bell SSA - Sent in 4721, SSA sent to Al Sproule to schedule with Gerry. June 14/23 - York Region permit (Hwy 7 & Uptown Drive / William Saville St - Bell breakout and 2 new manhole placement) - Circulations submitted. June 14/23 - City of Markham Permit - William Saville St - Circulations submitted. July 11/23 - York Region Permit (Hwy 7 & Uptown Drive / William Saville St - Bell breakout and 2 new manhole placement) - DFX followed up on circulations. July 13/23 - York Region permit (Warden Avenue & Cedarland Drive) - Bell breakout and new manhole placement) - DFX - In review, case #354698. July 13/23 - York Region permit (Warden Avenue & Hwy 7) - Bell breakout and new manhole placement) - DFX - In review, case #3546943. July 13/23 - York Region permit (Hwy 7 & Uptown Drive / William Saville St - Bell breakout and 2 new manhole placement) - DFX - In review, case #3546974 August 4/23 - York Region permit (Warden Avenue & Cedarland Drive) - Bell breakout and new manhole placement) DFX - Application being approved, pending issuance MC23-00400 August 4/23 - York Region Permit - Hwy 7 & Verclaire Gate - Bell breakout and new handwell placement - DFX - Followed up on status August 4/23 - York Region Permit - Warden Avenue & Hwy 7- Bell breakout and new handwell placement - DFX - Followed up on status August 14/23 -York Region Permit - Warden Avenue & Hwy 7- Bell breakout and new handwell placement - DFX - Revisions being done. August 29/23 - York Region Permit - Warden Avenue & Cedarland Drive - Bell breakout and new handwell placement - DFX - Update requested. August 29/23 - City of Markham Permit - Application submitted. August 31/23 - York Region Permit - Warden Avenue & Cedarland Drive - Bell breakout and new handwell placement - APPROVED, MC23-00400 September 5/23 - Wendy meeting with Sear from the city Sept 6, 2023 - Locates to be submitted. September 13/23 - York Region Permit - Warden Avenue & Hwy 7- Bell breakout and new handwell placement - Revisions sent back to the region September 18/23 - As per DK, GLB at HWY 7 & Verdale will not be installed. If building connection is needed at a later date, we will apply for conduit directly into building from the Bell chamber CONST-34095 & CONST-34090 tasks closed. September 27/23 - Locate packages complete for CONST-34088, CONST-34089 & CONST-34091 - Pending construction schedule. September 28/23 - City of Markham Permit - Revised drawings sent from DFX - Dave K to review. October 3/23 -City of Markham Permit - Revised drawings sent from DFX - Dave K approved. With DFX to resubmit to City of Markham. October 17/23 - York Region Permit - Warden Avenue & Hwy 7- Bell breakout and new handwell placement - DFX - Permit approved (MC23-00401 - Expires October 17, 2024 November 3/23 - City of Markham Permit - William Saville St - DFX - Submitted revised drawing on October 31, 2023. November 2/23 - York Region Permit - Hwy 7 & Uptown Drive / William Saville St - Bell breakout and 2 new manhole placement - DFX - Permit in progress November 6/23 - City of Markham Permit - William Saville St - DFX - Permit is approved pending city inspection. Nov 6/23 - Project moved to 2024. Nov 6/23 - City of Markham Permit - William Saville St - DFX - Submitted revised drawing to city for review. Nov 14/23 - York Region Permit - Hwy 7 & Uptown Drive / William Saville St - Bell breakout and 2 new manhole placement - DFX - Permit granted, expires November 9, 2024. February 13/24 - OSP Construction - Hwy 7 & Uptown Drive / William Saville St - Bell breakout and 2 new manhole placement - Bolton -- New locates submitted. March 1/24 - OSP Construction - Hwy 7 & Uptown Drive / William Saville St - Bell breakout and 2 new manhole placement - Bolton - Locates received. March 6/24 - Pending city site meet to start construction, dates may need to be adjusted. March 19/24 - Site meet scheduled for Wednesday March 27 @ 1:30pm. April 11/24 - Construction scheduled to start April 15th. May 2/24 - OSP Construction -Warden Avenue & Hwy 7- Bell breakout and new handwell placement - Locates Submitted. June 20/24 - OSP Construction -Warden Avenue & Hwy 7- Bell breakout and new handwell placement - Completed - NO RESTORATION REQUIRED June 27/24 - Construction York Region Permit - Warden Ave: Enterprise Blvd to Clegg Rd (CIK Joint Build) - Pending extension August 6/24 - Cable Pull - Warden Avenue & Hwy 7 - Bell Option - SENTREX - Crews are out today with Bell Canada inspector, should be completed by the end of week. July 30/24 - York Region MC - Cable Pull - Warden Avenue & Hwy 7 - Requested the extension on Permit MC23-00402. August 12/24 - Construction asbuilt attached CONST-34099 August 16/24 - Cable Pull - The crew could not get the last piece of 288 in on Warden due to elevation changes in the Bell structure to the Bell Manholes. Sentrex is putting in for rush locates to dig up the structure to complete the cable pull. Locates pending. August 21/24 - York Region MC - Cable Pull - Warden Avenue & Hwy 7 - Revised permit received - Extended until August 12, 2025 September 3/24 - Cable Pull - Warden Avenue & Hwy 7 - Bell Option - SENTREX - City of Markham and Zayo locates are still pending. September 11/24 - Locates are complete, Sentrex has reached out to Bell inspector for availability. Inspector is scheduled for Friday Sep 13/24 September 17/24 - Cable Pull - Warden Avenue & Hwy 7 - Bell Option - SENTREX - Cable placement complete September 23/24 - Last splice location will be completed today. September 24/24 - Splicing complete November 8/24 - Project reopened Financials Consolidated, project complete. | [6 empty] | 3 - Normal | [19 empty] | Internal | [6 empty] | Backbone | 2024-09-24 | 196000 |  |  |  |  | CONST-34079 | 3 - Normal |  | Markham | 67000 | 10000
Construction | CONST-4544 | 7 King St E_Toronto_The Metropole | Condo | Reopened |  | Unresolved | Lorna Kurok | Lorna Kurok | Jay Fernandes | 2016-06-09 18:56 |  | 2024-12-24 12:44 |  |  |  | 0 | 2 | _thumb_72543.png _thumb_72542.png _thumb_72541.png _thumb_72540.png _thumb_72539.png |  | CONST-4545, CONST-4546, CONST-4547, CONST-38233, CONST-38234 | CONST-38230 | _Requested by Oliver Davies_Aug 22, 2024_ *Units for 7 King St E is 314* {color:#0747a6}*PM Info:*{color}{*}{{*}} *Nancy Bijelic* President & CEO PropertyWright™ Management Inc. [Nancy.Bijelic@propertywright.ca¦mailto:Nancy.Bijelic@propertywright.ca] Office:416-549-1412 _Email Request August 22, 2024:_ _Could you please proceed with creating a new ticket for an OSP plan & Site Walk at 7 King St E? There are 314 residential units at this condo._ _Note, a visit was previously conducted here in 2016 when it was deemed not a candidate due to the requirement of pre-wiring the suites (CONST-4544)_ _BB Link:_ _[https://buildings.beanfield.com/buildings/view/2577]_ _PM Info:_ *Nancy Bijelic* President & CEO PropertyWright™ Management Inc. [Nancy.Bijelic@propertywright.ca¦mailto:Nancy.Bijelic@propertywright.ca] Office:416-549-1412 h4. *_Old Information Below:_* PM Georgina mtcc1170@bellnet.ca 23 floors approx 300 units 3rf floor telephone room in Parking garage at top of ramp - is for business and townhomes Rogers on 9th floor Bell on 10 floor no room in these risers but could alternate floors however we may have to scan and core floor Building services are daisy chained Main telephone room is on P2 beside parking spot 24 | PREWIRE | [12 empty] | 0¦i0hukn: | [7 empty] | 9.2234e+18 | [19 empty] | Condo not a candidate - Daisy Chained August 22, 2024_Reopened ticket September 3, 2024_Budget Added to site visit. The budget is based on a cable pull via the vault. We would need to confirm connectivity with the vault outside the the buildings vault. Well require Hydro escort for vault access, if project will be approved. | [6 empty] | 3 - Normal | [31 empty] | https://buildings.beanfield.com/buildings/view/2577#!contacts |  |  | 5 - Very Low |  | Toronto_King East
Construction | CONST-32806 | 15 & 25 Beverley Street_Toronto_12 Degrees | Condo | Reopened |  | Unresolved | Lorna Kurok | Lorna Kurok | Denise King | 2023-01-18 10:56 |  | 2024-12-24 16:08 |  |  |  | 0 | 2 |  |  | CONST-32807, CONST-32808, CONST-38344 |  | Requested by Oliver Davies: Can you please queue up a site walk for 15 Beverley St? This is a smaller MDU at 96 units, however my hope is that we can complete this build in conjunction with CONST-15132 which is directly across the street. PM Info: Pranvera Musaraj Condominium Manager *Crossbridge Condominium Services* Managing Agent for: 12 Degrees- TSCC 2497 15 Beverley St, Toronto ON, M5T 0B3, 416-519-9914 [Manager12degrees@rogers.com¦mailto:Manager12degrees@rogers.com] [12degrees@crossbridgecs.com¦mailto:12degrees@crossbridgecs.com] | [13 empty] | 0¦i3tdsv: | [7 empty] | 9.2234e+18 | [19 empty] | January 17th - as per Mark Houston and Oliver Davies project status was updated to Not a Candidate Sept 13, 2024 Note from site Visit (There is a connection between BFMH-0341 (john and Stephanie) and THES that I would like to complete . However It looks like the buildings are possible fed from the north and down the east side of Beverly. only the Audits will tell where we really need to go Beverly St.pdflink_attachment_7.gif) Constructed 2015 | [6 empty] | 3 - Normal | [24 empty] | 11 | 96 | [5 empty] | https://buildings.beanfield.com/buildings/view/3937 |  |  | 3 - Normal |  | Toronto
Construction | CONST-15661 | 25 The Esplanade, Toronto | Condo | Reopened |  | Unresolved | Harvey Tran | Harvey Tran | Harvey Tran | 2020-10-30 12:23 |  | 2024-12-24 16:16 |  |  |  | 0 | 1 |  |  | CONST-15662, CONST-38373, CONST-38374, CONST-38375 |  | Reopened by Oliver Sept 5, 2024 Reopened ticket to update site visit and reevaluate: Actual confirmed units is 571. Constructed in 1989 PM Info as per Sept 5, 2024: h2. Tessa Burrows, BA RCM Senior Licensed Condominium Property Manager ¦ ¦ Agents for and on behalf of MTCC 850 25 The Esplanade, Toronto , ON, M5E 1W5 Phone: 416-362-1582 Email: *[manager@25theesplanade.ca¦mailto:manager@25theesplanade.ca]* Could you please create tickets for a new OSP plan & site walk at 25 The Esplanade? This condo building includes 571 residential units, and was constructed in 1989. James had previously completed a site walk at this building in 2020 (CONST-15662) Though it sounds like the conduits may prove difficult to expand our network - with the increased appetite to complete older buildings, and the overall number of units, I think we should take another look to see if there is anything we can do to bring them On Net. James, if you know it's a firm no-go let us know and we'll pass. BB Link: [https://buildings.beanfield.com/buildings/view/765] PM Info: h2. Tessa Burrows, BA RCM Senior Licensed Condominium Property Manager ¦ ¦ Agents for and on behalf of MTCC 850 25 The Esplanade, Toronto , ON, M5E 1W5 Phone: 416-362-1582 Email: *[manager@25theesplanade.ca¦mailto:manager@25theesplanade.ca]* Old Data below: 25 The Esplanade Cristal Zak, Condo Manager [Cristal.Zak@crossbridgecs.com¦mailto:Cristal.Zak@crossbridgecs.com] Office: 416-362-1582 Mobile: 437-288-7250 | [13 empty] | 0¦i293hj: | [7 empty] | 9.2234e+18 | [19 empty] | Sept 5, 2024_ Reopening ticket to revisit the site and revise the budget. Sept 9, 2024_OSP plan completed | [6 empty] | 3 - Normal | [24 empty] | 31 | 571 | [5 empty] | https://buildings.beanfield.com/buildings/view/765#!contacts |  |  | 3 - Normal |  | Toronto
Construction | CONST-4629 | 330 Adelaide Street East- Imperial Square | Condo | Reopened |  | Unresolved | Lorna Kurok | Lorna Kurok | Russell Francey | 2016-06-29 09:20 |  | 2024-12-24 16:28 |  |  |  | 0 | 2 | _thumb_71096.png _thumb_71095.png _thumb_71094.png _thumb_71092.png _thumb_71093.png |  | CONST-4630, CONST-4631, CONST-4632, CONST-37819, CONST-37820 | CONST-3402 | +*New 2024 Project Information:*+ The Imperial Square condos were built in 2000 and include 95 residential units. Beanfield last investigated an expansion of service to this building in 2016 (https://tickets.beanfield.com/browse/CONST-4629), during this visit it was discovered that the suites are daisy chained and a pre-wire/ISW is required. As we are now beginning to target condos that require ISW - this location is close to our network and the work can very likely be approved. The condo board remains very interested in adding Beanfield for their residents. BB Link: [https://buildings.beanfield.com/buildings/view/3798] +Site Contact:+ Erin Property Management Associate Horizon Property Management Inc.416-332-4988 ¦ [info@330adelaideeast.com¦mailto:info@330adelaideeast.com] Direct: (416) 820-9720 +*Old Project Information:*+ STEPHEN W. MUNENE Property Manager Direct 416.847.7225 Email stephen.munene@fsresidentail.com | [13 empty] | 0¦i0ibz3: | [7 empty] | 9.2234e+18 | [19 empty] | Condo is daisy chained. | [6 empty] | 3 - Normal | [24 empty] | 11 | 96 | [5 empty] | https://buildings.beanfield.com/buildings/view/3798 |  |  | 3 - Normal |  | Toronto Downtown East
Construction | CONST-9971 | 27 Canniff St - Toronto, King West Village Towns | Condo | Reopened |  | Unresolved | Russell Francey | Russell Francey | Russell Francey | 2019-03-08 11:10 |  | 2025-03-11 14:43 |  |  |  | 0 | 2 |  |  | CONST-11456, CONST-11457, CONST-39746, CONST-39747 |  | {color:#000000}Condo Constructed in 2001{color} {color:#000000}27 Canniff St Units are 168{color} {color:#000000}Floors - 3{color} {color:#000000}Site Contact Information as of January 20, 2025:{color} Jarrod Stewart [jarrod@jtro.ca¦mailto:jarrod@jtro.ca] 647-830-3540 On behalf of the BOD MTCC1400 {color:#000000}Hi Lorna, Could you please create a new ticket for an OSP plan & site walk for {color}King West VillageTowns at 27 Canniff St{color:#000000}? This townhouse complex has 168 units and was built in 2001. {color} {color:#000000}There was a site walk done here in 2019 but we need to take another look.{color} {color:#000000} BB Link: {color}[https://buildings.beanfield.com/buildings/view/1962] {color:#000000}Site Contact:{color} Jarrod Stewart [jarrod@jtro.ca¦mailto:jarrod@jtro.ca] 647-830-3540 On behalf of the BOD MTCC1400 Thanks, -- ¦ ¦James Fox¦ ¦ maria.oldfield@gmail.com - borad member. She said the condo is current changing PMs *all free aired cables internally* | cancelled | [12 empty] | 0¦i1gpmv: | [7 empty] | 9.2234e+18 | [19 empty] | January 20, 2025 - Reopened Not a Candidate ticket, so we can take a second look. Was visited in 2019. Townhouses Constructed in 2001, and is 168 units January 24, 2025 - Board of directors is ok with paying to get us to service their complex but wants a high level description of how we are going to install. We've been invited to discuss at their next board meeting feb 4th. Jan 23, 2025_ OSP plan notes: moratorium on canniff expires at the end of 2025. building also lies within a metrolinx review zone. This was duplicated in sept and Oct. | [6 empty] | 3 - Normal | [24 empty] | 3 | 168 | [5 empty] | https://buildings.beanfield.com/buildings/view/1962 |  |  | 3 - Normal |  | Toronto
BC Construction | BCCONST-644 | 13387 Old Yale Rd, Holland Townline 2, Surrey BC | Condo | Reopened |  | Unresolved | Josh Wignall | Yawn Paular | Yawn Paular | 2024-04-04 16:57 |  | 2025-03-04 13:46 |  |  | 2025-12-26 | 0 | 0 |  |  | BCCONST-882 | BCCONST-873 | DES Conduit Entrance [Sergio.Jimenez@townline.com¦mailto:Sergio.Jimenez@townline.com] 308 units 32 Flrs In service date - June 1st | BudgetPending, DES | [12 empty] | 0¦i4q6tz: | [7 empty] | 9.2234e+18 | [19 empty] | Mar 4 - Re-opening this and waiting to see once it's transferred to Strata | [6 empty] | 3 - Normal | [24 empty] | 32 | 308 | [10 empty] | Surrey
Construction | CONST-29258 | 30 Canterbury Pl, Toronto - Dia Condominiums | Condo | Reopened |  | Unresolved | James Mowers | Lorna Kurok | Jessica Markiewicz | 2022-07-11 16:18 |  | 2025-03-27 12:20 |  |  | 2025-04-30 | 0 | 0 |  |  | CONST-29259, CONST-29260, CONST-34665, CONST-34672, CONST-34673, CONST-34675, CONST-34676, CONST-34677, CONST-34678, CONST-34679, CONST-34680, CONST-34681, CONST-34682, CONST-34683, CONST-34684, CONST-34685, CONST-34687, CONST-37660, CONST-39031, CONST-39174, CONST-39175, CONST-39199, CONST-39356, CONST-39552, CONST-40242 | CONST-29268 | Requested by Jay Fernandes Hi, I’ve gone through the remaining Fibrestream condos we have agreements for in the GTA and have grouped them in a way that I think makes sense for site visits and builds. There will be another list coming of buildings that don’t really fall into groups. Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. There are some current backbone (Sheppard) or NPOP (960 Lawrence) projects that will need to be completed to connect these but this will get everything into the system. Thanks! Farhad Taghipour, BBA, RCM, OLCM Senior Condominium Manager Goldview Property Management Ltd. 51 Toro Road, Suite 200 ¦ Toronto, Ontario ¦ M3J 2A4 T: 416-630-1234 Ext:223 ¦ F: 416-630-3132 E: [farhad@goldview.ca¦mailto:farhad@goldview.ca] ¦ W: [goldview.ca¦http://goldview.ca/] | FSactive, Fiberstreamagreement, Yonge&Finch | [12 empty] | 0¦i3h8w7: | [7 empty] | 9.2234e+18 | [19 empty] | July 04/23 - Project initiated. Design & Permit in progress. May 2nd, 2024 - Project is placed on-hold as per Oliver Davies in May 2nd, 2024. Nov 4, 2024 - Locates Complete Jan 6, 2025 - Construction Note: This will be done with 30 Canterbury and right now we are waiting for a permit before we can schedule. It's looking like early Feb to do OSP construction Jan 6, 2025_ Meeting Update_Construction 30 and 68 Canterbury requires a new permit due to expiry. Moving both buildings to March 2025 from february 2025. Jan 9, 2025 - City permit - Recirculation has been sent out. Jan 20, 2025 - Conduit Build Sketch Notes: (We will be building 30m of 1 1/4 EMT conduit from POE @ spot 30 to the existing pull box @ spot 39.A 6ft ladder will be required to complete the installation) Jan 21, 2025 - City Permit is in circulation at this time, but it is being estimated that we could receive this permit around February 28th, 2025. Jan 28, 2025 - Resubmitting City permit Jan 28, 2025. We expect that we can receive the permit in 2 weeks, Feb 12, 2025. Jan 28, 2025 - Locates valid until February. Also relocates have already been submitted. Jan 29, 2025 - City permit is submitted to the city. Hoping to receive permit by Feb 28, 2025, Locates have already been submitted. March 20, 2025 - Project is moved, from March 31, 2025 to May 7, 2025. We did not get the permit when we were expecting. Therefore the schedule needs to complete be changed. March 27, 2025 - City permit is granted. March 27, 2025 - Rodars are scheduled for to Begin April 7. 2025. OSP Construction planned start date is april 7, and the end date is expected to be april 17, 2025 | [6 empty] | 3 - Normal | [19 empty] | Internal |  | 2023-07-04 |  |  | 18 | 151 | Integration |  | 13887 |  |  | https://buildings.beanfield.com/buildings/view/15556 |  | CONST-29258 | 3 - Normal | 2024-04-26 | North York | 4950 | 11485
Construction | CONST-29425 | Birchmount and Enterprise Condo Backbone | Condo | In Progress |  | Unresolved | Denise King | Denise King | Harvey Tran | 2022-07-13 14:12 |  | 2025-01-12 21:25 |  |  | 2025-05-30 | 0 | 2 | _thumb_566872.png |  | CONST-29426, CONST-29444, CONST-29457, CONST-29458, CONST-29459, CONST-29460, CONST-29462, CONST-29464, CONST-31064, CONST-31065, CONST-33017, CONST-35781, CONST-38090 | CONST-29893, CONST-30021, CONST-26911, CONST-34079, CONST-26906, PUR-26383, PUR-26471, PUR-26473, PUR-28557, CONST-26909, CONST-26910, CONST-31856 | Residential backbone build for the Markham condos group. *NOTE May 30/23 - Birchmount Rd north of Verlaire Gt will not be built due to bridge rehab on Birchmount. New project on Warden & Hwy 7 will service the condos on Hwy 7, see CONST-34079.* !Birchmount & Enterprise BB Plan (CONST-29425) (1).png! | Backbone, Bolton | [12 empty] | 0¦i3hgfr: | [7 empty] | 9.2234e+18 | [16 empty] | 28960 |  |  | Dec 12/22 - Budget approved, issued to Sentrex for permits, design in progress. Feb 16/23 - 80% of the drawings sent back to Sentrex to revise and add a couple building feeds. Dave K is working with Markham on the bridge attachment on Birchmount. Feb 17/23 - Sentrex design being updated. Also, waiting on markups from CIK-Tel and York Net, conflicts with MDE, Bell and Enbridge. Feb 22/23 - Updated design received from Sentrex, Dave K to review. March 1/23 - Bell SSA application submitted. March 2/23 - Bell SSA requires revisions on dwg to show the coredrills on MH's, also need to agree to cost of coredrills (Approx $10,500) March 13/23 - Coredrill cost has been approved and has been sent back to Bell. March 14/23 - Bell SSA - 23-0065RO has been assigned, review should be completed by April 13 2023 (Two b/o removed, revised to $7500) March 21/23 - City permit - Sentrex received the detailed plans from MDE, still pending review from Dave K on how to proceed. April 6/23 - Dave K sent revisions. April 10/23 - Bell SSA granted, 4721 needs to be sent to Bell - Expires June 9 2023 April 17/23 - City permit revision are with Dave K to review. April 19/23 - City permit updated by Dave K - Crossing added, pending revision. May 3/23 - City permit - Sentrex is clearing Markham District Energy, Bell and Enbridge circulations that were re-submitted April 22nd May 23/23 - City permit - Sentrex received new conflicts with Gas and CIK Telecom - revisions being sent today. June 7/23 - York Region permit - Submitted pages 1-3 June 7/23 - City permit - Application submitted to The City Of Markham, confirmation #349042706366 - New drawings pages 3-21. July 4/23 - City permit approved. July 10 & July 14/23 - York region permit update requested. July 21/23 - York Region Permit - Birchmount and Enterprise Backbone - In review August 7/23 - York Region Permit - Ref#9192 case reference 3565259 was created. August 17/23 -York Region Permit - Birchmount and Enterprise Backbone - SENTREX - Update requested. August 18/23 - York Region Permit - Birchmount and Enterprise Backbone - SENTREX - Region will not approve the bus lane, it is the jurisdiction of Markham. Still pending regional road permit August 18/23 - City Permit - Birchmount and Enterprise Backbone - SENTREX - As per York Region, the bus lane on Enterprise Road should be reviewed by City of Markham - Email has been sent. August 25/23 - Locate package complete - See notes in CONST-29458 August 28/23 - City Permit - Birchmount and Enterprise Backbone - Sentrex followed up w/C.O Markham re: lane situation. August 31/23 -City Permit APPROVED with minor adjustments (bus lane) see CONST-29457 attachment. September 8/23 - York Region Permit - Birchmount and Enterprise Backbone (Sentrex) - Update requested. September 14/ 23 - York Region Permit - Birchmount and Enterprise Backbone - SENTREX - Approved September 14/23 - York region road occ requested September 25/23 - City Permit - Partial PRE Inspection completed (Pages 1-15) Line change added. Construction may start on pages 1-15 only September 26/23 - Jacquie has notified Bolton construction of partial redline. September 29/23 - York Region Road occ granted. October 30/23 - Dave K had a meeting w/ the PM of the condo build & it looks like we are going to be delayed until the 20th of Nov. They have trenched in several ducts including a 16 duct hydro structure down the sidewalk. We will need to wait for their ROP to expire & then call in locates & schedule a redline site walk w/ the city. Nov 21/23 - Splice Schematic/Add proposed cable to patch manager - Birchmount and Enterprise Condo Backbone (Phase 1) - Splice schematic added. Nov 21/23 - WO#20367, cables #39725, 39726 & 39727 has been added on patch manager Nov 22/23 - Pending SOW Project moved to 2024. Jan 24/24 - City Permit - Birchmount and Enterprise Backbone - Permit expired, needs extension. Jan 25/24 - City Permit - Birchmount and Enterprise Backbone - SENTREX - Extension request sent to the city - Permit extension granted, expires August 31, 2024. Feb 8/24 - Cable Pull - Cable 1 completed and cable 2 completed Feb 21/24 - Cable Pull - 576 has been pulled from CDSH10148 to our new BFHW at Enterprise and Birchmount. We need to pull one 125m section to the handwell north but is dependant on construction being completed in the spring. March 12/24 - Partial asbuilts attached CONST-29462 March 13/24 - Construction partial asbuilt added to PM. August 8/24 - Partial restoration completed for the priority required by the city. Remaining restoration will be sent to Ferpac once asbuilt is complete for an estimate. August 23/24 - CIK is currently waiting for the extended permit to continue. They have been told they should have it by the end of this month. August 30/24 - CIK have received all the approvals for Birchmount Rd but not for Verdale Xing. They have applied for this section and hopefully they have it back before they have finished Birchmount. They will be starting Warden week of September 3rd and Birchmount the week after. October 17/24 - CIK Telecom has completed and roped on conduit for the Backbone from Enterprise to the ViVa Bus-lane. And roped into 8081 Birchmount. Ent and cable pulls can be scheduled. This will let us pull into all building except 111 Upperduke. This is still on hold as per City of Markham until next spring. October 18/24 - Pending cable pull to be scheduled. October 21/24 - Remainder of cable pull scheduled for November 8th November 13/24 - Asbuilts added to patch manager December 9/24 - Moved to 2025, due to laterals needing to be completed on CONST-36911 | [6 empty] | 3 - Normal | [19 empty] | Internal | [6 empty] | Backbone |  | 150000 |  |  |  |  | 500399 | 3 - Normal |  | Markham | 54626 | 9435
Construction | CONST-26341 | 1925 Victoria Park Ave, Scarborough | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Harvey Tran | 2022-01-06 14:08 |  | 2025-01-06 15:21 |  |  | 2026-06-02 | 0 | 1 |  |  | CONST-26342, CONST-26343, CONST-38518, CONST-38519, CONST-38548 |  | Units - 185 Floors - 12 Greenfield Project_Greenfield Building Construction starts Dec 2024, Occupancy is expected Mid 2026 Building request by Katie Hodson. Property Manager: Jonathan Diamond VP - Terrace Manor LTD jonathan@wellgroundedrealestate.com 416-968-6555 ext 4 | [13 empty] | 0¦i34fgn: | [7 empty] | 9.2234e+18 | [19 empty] | Sept 18, 2024, Project updated from Not a Candidate to In Progress. This green Field project is expected to Occupy in 2026. Oliver has just been provided with a signed access & Marketing agreement. Sept 18, 2024- created revisit for James to review, expecting budget to be updated once we have the electrical drawings(expecting these to come in over the next 1 -2 months from mid Sept 2024) Sept 19, 2024, Agreements are uploaded, Noting the occupancy date for the building is estimated to be Mid 2026. We will not need to initiate this project until later 2025. The electrical drawing will be uploaded when received from developer. Start date reflects dates agreements received, Due date reflects estimated occupancy Date. | [6 empty] | 3 - Normal | [21 empty] | 2024-09-19 |  |  | 12 | 185 | [5 empty] | https://buildings.beanfield.com/buildings/view/16067#!contacts |  |  | 3 - Normal |  | Scarborough
Construction | CONST-33722 | Contractor Pre-Wiring - 131/151/181 Mill St. - Block 8 | Condo | In Progress |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2023-04-21 10:16 |  | 2025-01-27 09:51 |  |  |  | 0 | 1 |  |  | CONST-38237, CONST-39281 | CONST-15306, ACCT-136266 |  | Cybertec, PREWIRE, Rogers | [12 empty] | 0¦i3zn07: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [25 empty] | 664 |  |  | 20692 |  |  | https://buildings.beanfield.com/buildings/view/16126 |  | CONST-33722 | 3 - Normal |  | Toronto
Construction | CONST-33754 | Contractor Pre-Wiring - 425 Front St E, Toronto - Block 10 condos | Condo | In Progress |  | Unresolved | Olawale Olaniyan [X] | Olawale Olaniyan [X] | Olawale Olaniyan [X] | 2023-04-26 09:47 |  | 2025-01-27 09:48 |  |  |  | 0 | 0 |  |  | CONST-38203, CONST-38212 | CONST-30240 |  | Cybertec, PREWIRE, Rogers | [12 empty] | 0¦i3zxf3: | [7 empty] | 9.2234e+18 | [26 empty] | 3 - Normal | [24 empty] | 13 | 206 | [5 empty] | https://buildings.beanfield.com/buildings/view/16197 |  | CONST-33754 | 3 - Normal |  | Toronto
Construction | CONST-36371 | 38 Forest Manor Rd, North York | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Olawale Olaniyan [X] | 2024-01-30 15:58 |  | 2025-01-28 11:40 |  |  | 2025-06-17 | 0 | 0 |  |  | CONST-36372, CONST-36561, CONST-37371, CONST-37694, CONST-38684, CONST-38708, CONST-38709, CONST-38710, CONST-38711, CONST-38712, CONST-38713, CONST-38714, CONST-38715, CONST-38716, CONST-38717, CONST-38718, CONST-38719, CONST-38720, CONST-39066 | CONST-33772, CONST-35766 | Requested by Oliver Davies. Units 279 Floors 24 *PM Info:* _Manmeet Kaur, *OLCM- LL*_ _Property Manager on behalf of Tscc#2899_ _38 Forest Manor Road_ _Toronto, ON M2J 0H4_ _Tel: 416-551-3925_ _[Point.PM@delcondo.com¦mailto:Point.PM@delcondo.com]_ [https://tickets.beanfield.com/secure/AddComment!default.jspa?id=980693] | NUA+MA | [12 empty] | 0¦i4lglz: | [7 empty] | 9.2234e+18 | [19 empty] | Oct 2, 2024 Agreement in place Oct 7, 2024 Budget applied to SAP January 7, 2025_City permit note _If there is nothing that can be done with the developer, then we will have to push these three buildings back indefinitely as we can't build on an unassumed road without the developers permission. January 17, 2025 - Panel Prep - All panels are prepped and spliced January 21, 2025 - (Permit in 36 Forest Manor) Change On Net schedule date from April 2024 to March 2024. This is due to the complications of permits and the unassumed road. There is the risk that we will have to wait for the city's decision until Feb 21 and also a possibility that we might have to find another method. This permit affects 3 condo 32, 36 and 38 Forest Manor. Jan 28, 2025 - On Net Schedule Change_Moved condo from April 2025 to June 2025. Due to the unassumed road, affecting the construction and permits. Updated Jira, On Net schedule and SAP. | [6 empty] | 3 - Normal | [21 empty] | 2024-10-02 | [9 empty] | https://buildings.beanfield.com/buildings/view/17384 |  | CONST-36371 | 3 - Normal |  | North York
Construction | CONST-33772 | 32 Forest Manor Rd, North York | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Olawale Olaniyan [X] | 2023-05-01 08:34 |  | 2025-01-28 11:47 |  |  | 2025-06-17 | 0 | 0 |  |  | CONST-33773, CONST-33774, CONST-36369, CONST-38677, CONST-38682, CONST-38721, CONST-38722, CONST-38723, CONST-38724, CONST-38725, CONST-38726, CONST-38727, CONST-38728, CONST-38729, CONST-38730, CONST-39564, CONST-39605 | CONST-35766, CONST-36371, CONST-29078, CONST-29216, CONST-29219, CONST-29207, CONST-12142, CONST-29210, CONST-32361 | Requested by Oliver Davies, Units 372 floors 33 Could you kindly queue up a site walk & OSP plan for 32 Forest Manor Rd? This is the newest condo in this pocket of buildings. We have agreements for many of the neighbouring buildings on this street. Can you please link the below construction tickets together as a group (including 32 Forest Manor) so we can look at tackling them all at once? 36 Forest Manor Rd (No Agreement ([https://buildings.beanfield.com/buildings/view/15849]) 254 units 48 & 50 Forest Manor Rd (FS Agreement) (CONST-29207) 262 units 52 Forest Manor Rd (FS Agreement) (CONST-29210) 245 units 56 Forest Manor Rd (No agreement) ([https://buildings.beanfield.com/buildings/view/16441]) 344 units 62-76 Forest Manor Rd (FS Agreement) (CONST-29216) 327 units 66 Forest Manor Rd (FS Agreement) (CONST-32361) 404 units 70 Forest Manor Rd (FS Agreement) (CONST-29219) 479 units *NEW PM Info:* Akashdeep Mohan, OLCM-LL Property Manager on behalf of TSCC 2902 32 Forest Manor Road Toronto, ON M2J 0H2 416-551-4583 [Peak.PM@Delcondo.com¦mailto:Peak.PM@Delcondo.com] OR/ [Peak.Admin@Delcondo.com¦mailto:Peak.Admin@Delcondo.com] *PM Info:* Tracy Hernandez, OLCM Property Manager on behalf of TSCC 2902 32 Forest Manor Road Toronto, ON M2J 0H2 416-551-4583 [Peak.PM@delcondo.com¦mailto:Peak.PM@delcondo.com] Thanks! | NUA+MA | [12 empty] | 0¦i408jz: | [7 empty] | 9.2234e+18 | [19 empty] | May 01/23 - Forest Manor is under moratorium until the end of 2025. May 18/23 - As per Oliver Davies "We'll need to hold off for now. I'll work on getting visits scheduled with 36 & 38 Forest Manor so we have a shot of building off of Don Mills. Olawale Olaniyan Please mark this location as On Hold." Jan 30/24 - Budget approved. Pending building agreement Oct 2, 2024 the building agreement for 38 forest has been approved. This building was dependent on this. January 7, 2025_City permit note _If there is nothing that can be done with the developer, then we will have to push these three buildings back indefinitely as we can't build on an unassumed road without the developers permission. January 8, 2025 Riser Panels complete January 20, 2025 - Internal completed January 21, 2025 - (Permit in 36 Forest Manor) Change On Net schedule date from April 2024 to March 2024. This is due to the complications of permits and the unassumed road. There is the risk that we will have to wait for the city's decision until Feb 21 and also a possibility that we might have to find another method. This permit affects 3 condo 32, 36 and 38 Forest Manor. Jan 27, 2025_ISP Splicing Note:All work has been completed under the main ISP located in 38 Forest Manor - closing Ticket Jan 28, 2025 - On Net Schedule Change_Moved condo from April 2025 to June 2025. Due to the unassumed road, affecting the construction and permits. Updated Jira, On Net schedule and SAP. | [6 empty] | 3 - Normal | [21 empty] | 2024-10-02 |  |  | 33 | 372 | [5 empty] | https://buildings.beanfield.com/buildings/view/16603 |  | CONST-33772 | 3 - Normal |  | North York
Construction | CONST-40076 | 151 Village Green Square, Scarborough, Ventus I at Metrogate | Condo | In Progress |  | Unresolved | Unassigned | Lorna Kurok | Lorna Kurok | 2025-02-14 10:37 |  | 2025-02-18 09:57 |  |  |  | 0 | 0 |  |  | CONST-40078, CONST-40079, CONST-40080 | CONST-26336, CONST-32609, CONST-32622, CONST-32623, CONST-40077, CONST-26571, CONST-26574 | Condo Constructed in 2013 Units: 288 Floors: 31 {color:#0747a6}*Pm Contact Information as of February 14, 2025:*{color} {*}151 + 181 Village Green Sq{*}{*}{*} {*}Alice Wong{*}{*}{*} Alice Wong R.C.M. ; O.L.C.M. PROPERTY MANAGER *Phone:* 647-347-5775 *Fax: 647-347-5799Email:* [ventus.pm@DelCondo.com¦mailto:ventus.pm@DelCondo.com] | Cluster, Fibrestream | [12 empty] | 0¦i5ivvr: | [7 empty] | 9.2234e+18 | [19 empty] | Feb 12, 2025 - Cluster Build. Feb 13, 2025 Approved in Capax meeting, yes we have the agreement. | [6 empty] | 3 - Normal | [21 empty] | 2025-02-13 |  |  | 31 | 288 | [5 empty] | https://buildings.beanfield.com/buildings/view/15723 |  | CONST-40076 | 3 - Normal |  | Scarborough
Construction | CONST-39794 | Contractor Pre-Wiring - 393 King St W, Toronto - The 393 On King | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Lorna Kurok | 2025-01-22 15:29 |  | 2025-02-19 10:39 |  |  | 2025-04-15 | 0 | 0 |  |  | CONST-39795, CONST-39796 | CONST-35316 | Jan 22, 2025 - CA approved. *Cristina Tudor, RCM,* *OLCM* *Condominium Manager* ICC Property Management Ltd. 2875 14th Avenue, Suite 300 Markham, ON, L3R 5H8 905.940.1234 ext. 90 [ctudor@iccpropertymanagement.com¦mailto:ctudor@iccpropertymanagement.com] | PREWIRE | [12 empty] | 0¦i5h4x3: | [7 empty] | 9.2234e+18 | [19 empty] | Jan 22, 2025 - CA approved | [6 empty] | 3 - Normal | [20 empty] | 2024-12-11 | 2025-01-22 |  |  | 12 | 101 | [5 empty] | https://buildings.beanfield.com/buildings/view/3186 |  | CONST-39794 | 3 - Normal |  | Toronto
Construction | CONST-28344 | 422 Cherry St. - Block 7, Toronto | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Harvey Tran | 2022-05-11 14:09 |  | 2025-02-28 10:08 |  |  | 2025-12-09 | 0 | 0 |  |  | CONST-28376, CONST-28377, CONST-28393, CONST-33826, CONST-33827, CONST-33828, CONST-33829, CONST-33830, CONST-33831, CONST-33832, CONST-33833, CONST-33834, CONST-33835, CONST-33836, CONST-33837, CONST-33838, CONST-33839, CONST-33840, CONST-33841, CONST-37860, CONST-37910, CONST-37927, CONST-37928, CONST-37930 | ORDER-270600, CONST-28345, CONST-28346, CONST-33761 | We’ve got a bunch of buildings popping up in the West Don Lands so need to add them to our build schedule. Since we have the agreements already, feel free to create the full build of subtasks - including site walk, agreement and base building services. I think James has already done most of the site walks - he just needs a place to put the info. There are 2 groups of 3 towers going up but we should treat them as separate builds in JIRA - even if they can tie together through the underground. Then there are 2 additional, separate buildings. So 8 new tickets in total. Please use the municipal address as the title for each so it will tie into Building Browser. 131 Mill St. 151 Mill St. 181 Mill St. 422 Cherry 432 Cherry 65 Trinity Contact: ¦*_Alain Costa_* ¦ ¦MEP Manager, Toronto Division¦ ¦!https://mail.google.com/mail/u/0?ui=2&ik=e63ae99e5e&attid=0.53&permmsgid=msg-f:1805381308421027332&th=190e00bc1490b604&view=fimg&fur=ip&sz=s0-l75-ft&attbid=ANGjdJ_YuHvXw__tcyrHve9wYS8i9dMBxyqI969XpIIbXIWbqMZRmatWRSip8GCOY2dQDd6VCw0KWzyKMgfC_ByxqzUA4U2yLi5yLsPcTFIhMR1VtwqVfyfTBRUkncw&disp=emb!{*}C{*}: 416.356.1900¦ ¦!https://mail.google.com/mail/u/0?ui=2&ik=e63ae99e5e&attid=0.54&permmsgid=msg-f:1805381308421027332&th=190e00bc1490b604&view=fimg&fur=ip&sz=s0-l75-ft&attbid=ANGjdJ-UZIGZLlIkRJ180v7g8IePs5YmGhRxSY4__gMDWg6rHhFJdptk5S1uEkfVk7fPI51btvo_XQhCrN6wOI8kdJ1M43E3R-sRrN8UtLWAbbC1ZFXCLLjFX6NRJOE&disp=emb! [acosta@ellisdon.com¦mailto:acosta@ellisdon.com]¦ ¦!https://mail.google.com/mail/u/0?ui=2&ik=e63ae99e5e&attid=0.55&permmsgid=msg-f:1805381308421027332&th=190e00bc1490b604&view=fimg&fur=ip&sz=s0-l75-ft&attbid=ANGjdJ9_HxfIDzAc4rtO2HhfamZKKI8fmbQ-_qSMVy6X1yL41KzTICiIdOso4JUpSeT3Kt15nY5G-lXHVtJqpZdR5Zc1ztncyzdc_qI7XCtIJmQ7KbDxM2UwMh1XX9o&disp=emb! 1004 Middlegate Rd., Suite 1000, Mississauga, ON L4Y 1M4¦ ¦!https://mail.google.com/mail/u/0?ui=2&ik=e63ae99e5e&attid=0.56&permmsgid=msg-f:1805381308421027332&th=190e00bc1490b604&view=fimg&fur=ip&sz=s0-l75-ft&attbid=ANGjdJ_4an-FqDTHLuxVeDHSk8aGCLkh8i0JT3eBCdFT0lTcZFHutd_pxOFfDq0VquR5JbsTQ2nObCio0x8iXLYUmJhvcJgG8kwxDlMwGXGZXBUh_-28qaprcedRuyo&disp=emb! [www.ellisdon.com¦http://www.ellisdon.com/]¦ | PREWIRE | [12 empty] | 0¦i3dh8v: | [7 empty] | 9.2234e+18 | [19 empty] | May 04/23 - Project initiated, pending Permits & Design July 11/23 - City permit granted. Aug 15/23 - Pending road restriction and schedule Aug 24/23 - Construction tentatively scheduled to start Sept 5th Sep 8/23 - Construction completed. July 10th, 2023 - Ellis Don requested we need to complete this by end of July 2024. Pending approval to use contractor for cable pull and splicing. Building onnet is still in 2025 due to riser works. July 11th, 2024 - Design of Cable pull drawing completed, note that MainTelecom room located on 2nd floor July 12th, 2024 - OSP SOW plan has been completed. P;an includes Fibers needed for splitters in POP room as well as extra Fibers for the Elevator lines. July 24, 2024 - Was not able to gain access to the building to work on ISP Splicing. Building is still under construction. Sep 19, 2024 - All cables pulled to pop and dressed it. Riser Fiber Pull Completed Sep 19, 2024 - Riser Panels completed. Jan 6, 2025- Meeting Notes_ due to this Building Construction, we are moving these project to June 2025 from May 2025 Feb 28, 2025 Building need to be moved on schedule from June to Dec. Not likely to complete in June due to amount of work to be completed. | [6 empty] | 3 - Normal | [21 empty] | 2023-05-04 |  |  | 11 | 68 |  |  | 30874 |  |  | https://buildings.beanfield.com/buildings/view/16124 |  | CONST-28344 | 3 - Normal | 2025-05-30 | Toronto | 1710 | 8680
Construction | CONST-28345 | 432 Cherry St. - Block 4, Toronto | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Harvey Tran | 2022-05-11 14:10 |  | 2025-02-28 10:07 |  |  | 2025-12-09 | 0 | 0 |  |  | CONST-28378, CONST-28379, CONST-28473, CONST-33820, CONST-33821, CONST-33823, CONST-33824, CONST-33825, CONST-35351, CONST-37861, CONST-39176, CONST-39412, CONST-39413, CONST-39414, CONST-39436, CONST-39515, CONST-39701, CONST-39702, CONST-39703 | ORDER-269474, CONST-28344, CONST-28346, CONST-33762 | We’ve got a bunch of buildings popping up in the West Don Lands so need to add them to our build schedule. Since we have the agreements already, feel free to create the full build of subtasks - including site walk, agreement and base building services. I think James has already done most of the site walks - he just needs a place to put the info. There are 2 groups of 3 towers going up but we should treat them as separate builds in JIRA - even if they can tie together through the underground. Then there are 2 additional, separate buildings. So 8 new tickets in total. Please use the municipal address as the title for each so it will tie into Building Browser. 131 Mill St. 151 Mill St. 181 Mill St. 422 Cherry 432 Cherry 65 Trinity Contact: ¦*_Alain Costa_* ¦ ¦MEP Manager, Toronto Division¦ ¦!https://mail.google.com/mail/u/0?ui=2&ik=e63ae99e5e&attid=0.53&permmsgid=msg-f:1805381308421027332&th=190e00bc1490b604&view=fimg&fur=ip&sz=s0-l75-ft&attbid=ANGjdJ_YuHvXw__tcyrHve9wYS8i9dMBxyqI969XpIIbXIWbqMZRmatWRSip8GCOY2dQDd6VCw0KWzyKMgfC_ByxqzUA4U2yLi5yLsPcTFIhMR1VtwqVfyfTBRUkncw&disp=emb!{*}C{*}: 416.356.1900¦ ¦!https://mail.google.com/mail/u/0?ui=2&ik=e63ae99e5e&attid=0.54&permmsgid=msg-f:1805381308421027332&th=190e00bc1490b604&view=fimg&fur=ip&sz=s0-l75-ft&attbid=ANGjdJ-UZIGZLlIkRJ180v7g8IePs5YmGhRxSY4__gMDWg6rHhFJdptk5S1uEkfVk7fPI51btvo_XQhCrN6wOI8kdJ1M43E3R-sRrN8UtLWAbbC1ZFXCLLjFX6NRJOE&disp=emb! [acosta@ellisdon.com¦mailto:acosta@ellisdon.com]¦ ¦!https://mail.google.com/mail/u/0?ui=2&ik=e63ae99e5e&attid=0.55&permmsgid=msg-f:1805381308421027332&th=190e00bc1490b604&view=fimg&fur=ip&sz=s0-l75-ft&attbid=ANGjdJ9_HxfIDzAc4rtO2HhfamZKKI8fmbQ-_qSMVy6X1yL41KzTICiIdOso4JUpSeT3Kt15nY5G-lXHVtJqpZdR5Zc1ztncyzdc_qI7XCtIJmQ7KbDxM2UwMh1XX9o&disp=emb! 1004 Middlegate Rd., Suite 1000, Mississauga, ON L4Y 1M4¦ ¦!https://mail.google.com/mail/u/0?ui=2&ik=e63ae99e5e&attid=0.56&permmsgid=msg-f:1805381308421027332&th=190e00bc1490b604&view=fimg&fur=ip&sz=s0-l75-ft&attbid=ANGjdJ_4an-FqDTHLuxVeDHSk8aGCLkh8i0JT3eBCdFT0lTcZFHutd_pxOFfDq0VquR5JbsTQ2nObCio0x8iXLYUmJhvcJgG8kwxDlMwGXGZXBUh_-28qaprcedRuyo&disp=emb! [www.ellisdon.com¦http://www.ellisdon.com/]¦ | [13 empty] | 0¦i3dhaf: | [7 empty] | 9.2234e+18 | [19 empty] | May 04/23 - Project initiated, Cable Pull only. Nov 15, 2024 - Pulled rope from 422 Cherry to Main Pop through 2 pull boxes. Jan 6, 2025- Meeting Notes_ due to this Building Construction, we are moving these project to June 2025 from May 2025 Feb 28, 2025 Building need to be moved on schedule from June to Dec. Not likely to complete in June due to amount of work to be completed. | [6 empty] | 3 - Normal | [24 empty] | 12 | 388 | [5 empty] | https://buildings.beanfield.com/buildings/view/16125 |  | CONST-28345 | 3 - Normal | 2025-05-30 | Toronto | 38682
Construction | CONST-33763 | Contractor Pre-Wiring - 65 Trinity - Block 3, Toronto | Condo | In Progress |  | Unresolved | Lorna Kurok | Lorna Kurok | Olawale Olaniyan [X] | 2023-04-27 13:28 |  | 2025-02-28 10:11 |  |  | 2025-12-09 | 0 | 1 | _thumb_1128848.png |  | CONST-38143, CONST-38210 | CONST-28346, CONST-33762 |  | Cybertec, PREWIRE, Rogers | [12 empty] | 0¦i401v3: | [7 empty] | 9.2234e+18 | [19 empty] | Feb 28, 2025 - change due date to December 9, 2025. | [6 empty] | 3 - Normal | [25 empty] | 397 |  |  | 5161 |  |  | https://buildings.beanfield.com/buildings/view/16123 |  | CONST-33763 | 3 - Normal | 2025-05-30 | Toronto
Construction | CONST-33761 | Contractor Pre-Wiring - 422 Cherry St. - Block 7, Toronto | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Olawale Olaniyan [X] | 2023-04-27 13:24 |  | 2025-02-28 10:13 |  |  | 2025-12-09 | 0 | 1 |  |  | CONST-38186, CONST-38209 | CONST-28344 |  | Cybertec, PREWIRE, Rogers | [12 empty] | 0¦i401un: | [7 empty] | 9.2234e+18 | [19 empty] | Sep 11, 2024_Cybertec contractor has indicated that all the cables have been completed up to the 5th floor, and nothing above this is ready for any in-suit work. Sept 11, 2024_Contractor status notes:Contractor has informed SC that 1ct cables have been completed up to the 5th floor, and I. Suite InSuite jacks are completed up to the 7th floor. Nothing above this is ready to be pulled currently. Nov 15, 2024_ 1 floor remains to be pulled for the Homeruns. Feb 28, 2025 - Changed due date to Dec 9, 2025 | [6 empty] | 3 - Normal | [24 empty] | 11 | 68 |  |  | 844 |  |  | https://buildings.beanfield.com/buildings/view/16124 |  | CONST-33761 | 3 - Normal | 2025-05-30 | Toronto
Construction | CONST-33762 | Contractor Pre-Wiring - 432 Cherry St. - Block 4, Toronto | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Olawale Olaniyan [X] | 2023-04-27 13:26 |  | 2025-02-28 10:12 |  |  | 2025-12-09 | 0 | 1 |  |  | CONST-38201, CONST-38211 | CONST-38143, CONST-28345, CONST-33763 |  | Cybertec, PREWIRE, Rogers | [12 empty] | 0¦i401uv: | [7 empty] | 9.2234e+18 | [19 empty] | FEb 28, 2025 - Changed due date to dec 9, 2025 | [6 empty] | 3 - Normal | [24 empty] | 12 | 388 |  |  | 5044 |  |  |  |  | CONST-33762 | 3 - Normal | 2025-05-30 | Toronto
Construction | CONST-29495 | 85 Bloor St, Toronto - 85 Bloor | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Jessica Markiewicz | 2022-07-15 10:32 |  | 2025-03-03 09:13 |  |  | 2025-08-29 | 0 | 4 |  |  | CONST-29496, CONST-29497, CONST-31400, CONST-31419, CONST-31420, CONST-31421, CONST-31422, CONST-31423, CONST-31424, CONST-31425, CONST-31426, CONST-31427, CONST-31428, CONST-31429, CONST-31430, CONST-31431, CONST-31432, CONST-31433, CONST-31434, CONST-35380, CONST-36733, CONST-37288, CONST-37289 |  | Requested by Jay Fernandes Hi, These are the Fibrestream condos we have agreements for that don’t seem to fit into any groups (although I maybe wrong). Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. ¦Group¦Building Name¦Address¦suites¦ ¦Independent¦Eleven Superior¦11 Superior AVE Etobicoke ON M8V 0A7¦130¦ ¦Independent¦The James Club¦1135 Royal York RD Toronto ON M9A 4A7¦209¦ ¦Independent¦Independence Way¦115 George Appleton WAY North York ON M3M 2E9¦244¦ ¦Independent¦Danforth Village Estates¦1346 Danforth RD Toronto ON M4J1M9¦249¦ ¦Independent¦beBloor¦1369 Bloor ST Toronto ON M6P 4J3¦238¦ ¦Independent¦Ion Condos¦15 James Finlay WAY Toronto ON M3M 0B3¦200¦ ¦Independent¦Paradice at the Oasis¦1720 Eglinton AVE Toronto ON M4A2X9¦190¦ ¦Independent¦Havenon the Bluffs¦20 East Haven DR Toronto ON M1N1M2¦259¦ ¦Independent¦Kilgour Estate II¦21 Burkebrook PL Toronto ON M4G4K8¦228¦ ¦Independent¦Canvas Condos¦2301 Danforth AVE Toronto ON M4C 1L5¦156¦ ¦Independent¦3018 Yonge Condos¦3018 Yonge ST Toronto ON M4N 0A5¦188¦ ¦Independent¦Cranbrooke Village¦35 Saranac BLVD Toronto ON M6A 2G4¦341¦ ¦Independent¦39 Brant St¦39 Brant ST Toronto ON M5V0M8¦236¦ ¦Independent¦The Wave¦4 Elsinore PATH Toronto ON M8V 4G7¦185¦ ¦Independent¦Clock Tower Lofts¦700 King ST Toronto ON M5V 2Y6¦216¦ ¦Independent¦The Boot¦75 Dalhousie ST Toronto ON M5B 2R9¦153¦ ¦Independent¦B.Street Condos¦783 Bathurst ST Toronto ON M6G 1K1¦ ¦ ¦Independent¦85 Bloor St¦85 Bloor ST Toronto ON M4W3G9¦252¦ | Bolton, FSactive, Fiberstreamagreement | [12 empty] | 0¦i3hl6n: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2005 December 13th - Manhole Surveys completed. Hydro permit submitted. February 2nd - Building On-Hold, city is planning a water main replacement at this location. As per Troy Browne and James Mowers. February 9th - Hydro permit conditionally granted. March 9th - Building In-Progress, pending city permit. May 16/23 - CoT is currently doing a watermain project and has informed us that we cannot do any work until Sept 2023. Project due date revised. Aug 9/23 - Hydro permit extension issued Aug 22/23 - City permit granted. Oct 25/23 - Locates completed. Jan 17/24 - Delay with construction schedule. Due dates updated Mar 01/24 - Vault access (site visit) PO sent to AP to be paid Mar 05/24 - Vault access invoice received. Apr 03/24 - Delay with construction schedule. Due dates updated. Apr 04/24 - Vault access requested Apr 09/24 - Transferred $200.00 from Cable Pull to vault access budget. Apr 17/24 - Vault access invoice received May 13th, 2024 - Project is placed on-hold due to TTC roadwork blocking our access to the building. Removing due date for now. Feb 19, 2025 - We are directed to put on On schedule. Lorna scheduled for Due date of August 19, 2025. Feb 20, 2025 - there is discussion to confirm with higher level about the budget, instructed to take off schedule until we have a stronger plan. Need to reconfirm budget amount. Feb 26, 2025 - Instructed on Webex to put this one back in the schedule. Feb 27, 2025 - Danny is attending a board meeting in April. | [6 empty] | 3 - Normal | [19 empty] | Internal |  | 2022-10-25 |  |  | 20 | 252 | Integration |  | 35691 |  |  | https://buildings.beanfield.com/buildings/view/3124 |  | 500487 | 3 - Normal | 2023-06-09 | Toronto | 5858 | 12440
Construction | CONST-5558 | 9 & 11 Bogert Ave, North York, Emerald Park Condos | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Russell Francey | 2017-02-02 15:18 |  | 2025-02-14 08:02 |  |  | 2025-08-14 | 0 | 1 |  |  | CONST-5559, CONST-5560, CONST-5561, CONST-39820 |  | MDU Address: 9 Bogert Ave City: North York Building Name: Emerald Park # of Units: 573 # of Floors: 42 Building Constructed Year: 2015 Building First Occupancy Date or or time period of year, (eg. Mid 2026) PM Contact Name: *Karolina Mierzwa* PM Contact #: 416-730-8761 PM Email Address: [karolina.mierzwa@fsresidential.com¦mailto:karolina.mierzwa@fsresidential.com] Type of Contract (Fibre agreement or NUA & MA): A+M Building linked to other Buildings: n/a Bulk Related: no | [13 empty] | 0¦i0nxjz: | [7 empty] | 9.2234e+18 | [19 empty] | Old existing note, NA as of 2025_Never heard back from PM Jan 22, 2025_ CA Approved FTTB-00570 date Jan 21, 2025 ($25,690.47 includes $394.56 of Resto.), Agreements signed Jan 22, 2025 Jan 30, 2025 - On Net Schedule changes, James advised this could be moved from sep to aug. Feb 7, 2025 Site visit note -The current proposed tie-in point is THEP15652FA | [6 empty] | 3 - Normal | [21 empty] | 2025-01-22 |  |  | 40 | 573 | [5 empty] | https://buildings.beanfield.com/buildings/view/5582 |  | CONST-5558 | 3 - Normal | 2025-09-04 | North York Yonge & Eglinton (incl. North Yonge)
Montreal Construction | MTLCONST-9767 | Westwalk - Lifestyle Apartments - 45 Brunswick Blvd., Dollard-Des-Ormeaux | Condo | In Progress |  | Unresolved | Marianne Yanni | Marianne Yanni | Marianne Yanni | 2024-02-27 16:32 |  | 2025-02-03 09:49 |  |  | 2025-04-30 | 0 | 3 | _thumb_841840.png |  | MTLCONST-9768, MTLCONST-9769, MTLCONST-9927, MTLCONST-9928, MTLCONST-9929, MTLCONST-9930, MTLCONST-9931, MTLCONST-9932, MTLCONST-9933, MTLCONST-9934, MTLCONST-10034, MTLCONST-10397, MTLCONST-10699, MTLCONST-10700 | PUR-35001, PUR-35134, PUR-35251, PUR-35287, PUR-35827, PUR-39514, PUR-40774 | *{color:#333333}WBS-MTLCONST-9767-2 (Matertals){color}* {color:#333333}This is a rather urgent and unique request as we have an opportunity to bid on a bulk-service agreement to have Beanfield included for all of the 393 residential units that makeup this new Greenfield rental development. The project is still in the early stages of development, so we cannot access to the site to complete a traditional budget. We will need to create a high-level estimate for expanding Beanfield’s fibre network to the buildings. There are 3x towers here all connected with a common parking level.{color} {color:#333333} {color} {color:#333333}PA4386 would likely be our access point to enter the building, per the attached image.{color} {color:#333333}!Screenshot 2024-02-27 at 9.26.45 AM.png¦thumbnail!{color} {color:#333333}*Sébastien Gauthier* - +Courlem Électrique+ - (Surintendant) 438-994-7908 [sebastien.gauthier@courlem.com¦mailto:sebastien.gauthier@courlem.com]{color} {color:#333333}*Simon Labelle* - +Quadrax+ (Directeur de chantier) 514-206-3087 [slabelle@quadrax.com¦mailto:slabelle@quadrax.com]{color} {color:#333333}*Felix Allaire* - +Devmont+ (Directeur de projets) 514-525-2929 ext 223 [fallaire@devmont.ca¦mailto:fallaire@devmont.com]{color} {color:#333333}*Alioune Gueye* - +Devmont+ (Chargé de projets) 514-727-9049 [agueye@devmont.ca¦mailto:agueye@devmont.ca]{color} {color:#333333}B1 (12 Davignon) : 147 units JAN 2025 occupancy {color} {color:#333333}B3 (55 Brunswick) : 130 units May 2025 occupancy {color} {color:#333333}B2 (10 Davignon) : 116 units June 2025 occupancy{color} | BulkDeal | [12 empty] | 0¦i4ncdr: | [7 empty] | 9.2234e+18 | [19 empty] | 2024.04.10 Project initiated. Design and Permits to be in progress. 2024.04.11 Design request sent to TD 2024.04.19 Interior SOW is prepped 2024.05.06 Permits requests sent on May 2nd 2024.05.24 Bell permit received 2024.08.27 HQ permit received. Construction drawing received. NPOP SOW is requested. 2024.08.28 Cable pull is assigned to the contractor. NPOP SOW is ready 2024.08.29 NPOP SOW is assigned to the contractor 2024.09.09 Cable pull is pending Hydro-Québec's RDT to plan the installation. 2024.09.17 Lignex planned the work jointly with Hydro-Québec for Sept. 19. 2024.09.24 LigneX has a meeting on Sept 30 with Hydro-Québec to carry out the work. 2024.10.23 Ext. Cable installation is scheduled for next week. 2024.10.29 Exterior Cable pull is completed. Awaiting for as built 2024.11.04 NPOP splicing is completed. 2025.02.03 Interior cables installation is scheduled this week. | [6 empty] | 3 - Normal | [21 empty] | 2024-04-10 | [6 empty] | 311590.19 |  |  | https://buildings.beanfield.com/buildings/view/19954 |  | MTLCONST-9767 |  |  |  | 13504.25
Construction | CONST-39511 | 215 Lakeshore Blvd E, Toronto, Pinnacle Lakeside | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Lorna Kurok | 2024-12-17 12:13 |  | 2025-02-04 14:01 |  |  | 2026-07-01 | 0 | 1 |  |  | CONST-39512, CONST-39514, CONST-39516, CONST-39600 |  | Newbuilds, Please launch the project for 215 Lakeshore. Attached is the approved CA form with the associated budget. This should be allocated to the FY25 Residential Construction budget. Building Type: Greenfield Choice Units: 1147 Required Date: July 2026 First Occupancy Expected: July 2026 MDU Address: [215 Lakeshore Blvd¦https://www.google.com/maps/search/215+Lakeshore+Blvd+City:+Toronto?entry=gmail&source=g] [City: Toronto¦https://www.google.com/maps/search/215+Lakeshore+Blvd+City:+Toronto?entry=gmail&source=g] Building Name - Pinnacle Lakeside # of Units: 1147 # of Floors: 49 Building First Occupancy Date or or time period of year, (eg. Mid 2026): July 2026 PM Contact Name: Anson Kwok PM Contact #: 416-925-3354 x 226 PM Email Address: [akwok@pinnacleinternational.ca¦mailto:akwok@pinnacleinternational.ca] Type of Contract (Fibre agreement or NUA & MA): Access & Marketing Building linked to other Buildings: No Bulk Related: No -- | GreenfieldChoice, PREWIRE | [12 empty] | 0¦i5enfz: | [7 empty] | 9.2234e+18 | [19 empty] | Dec 17, 2024 - Newbuilds email received. 215 Lakeshore - Residential Building Approved. Jan 9, 2025_OSP plan -no fiber capacity in CC6551 (S SIDE OF LAKESHORE BLVD E_ 20M W OF LOWER SHERBOURNE ST), Tie moved to CC6550. Jan 2025 note_ please note the Due date is based on the expected First Occupancy date of July 2026. | [6 empty] | 3 - Normal | [21 empty] | 2024-12-17 |  |  |  | 1147 | [5 empty] | https://buildings.beanfield.com/buildings/view/21044 |  | CONST-39511 | 3 - Normal |  | Toronto
Construction | CONST-24514 | 200 Bloor St West - Exhibit Residences | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Harvey Tran | 2021-08-25 10:14 |  | 2025-03-10 09:38 |  |  | 2025-04-29 | 0 | 1 | _thumb_1124386.png |  | CONST-24515, CONST-24516, CONST-24759, CONST-24760, CONST-38258, CONST-39137, CONST-39138, CONST-39139, CONST-39140, CONST-39141, CONST-39142, CONST-39143, CONST-39144, CONST-39145, CONST-39146, CONST-39147, CONST-39148, CONST-39149, CONST-39150, CONST-39177, CONST-39571, CONST-39695, CONST-40255 |  | Constructed in 2017 PM info: Julia Kalisperas [tscc2598admin@royalegrande.com¦mailto:tscc2598admin@royalegrande.com] 416-353-4641 BB: [https://buildings.beanfield.com/buildings/view/5608#!contacts] | NUA+MA | [12 empty] | 0¦i2vxrj: | [7 empty] | 9.2234e+18 | [19 empty] | Aug 25, 2021 - Created ticket Nov 12, 2024 - Due date April 22, 2025, put into In progress from Agreement. Nov 8, 2024_Project approved, SAP Budget created, Sub task have been created. Added to the On Net schedule for April 22, 2024. Dec 17, 2024 - Riser Fiber Pull Completed Jan 8, 2025_PM would like Beanfield to set up an appointment to complete Panel prep work as well as the ISP SOW. JAN 15, 2025 - Panel Prep - All panels prepped and spliced January 17, 2025 - Hydro Permit Granted_D2024-00353 Expiry July 17, 2025 January ISP splicing in progress January 20, 2025- Progress of this building is going well, it is being moved up on the On Net schedule from April to February 2025. January 21, 2025, Vault Access appointment Confirmed from Scheduler for Feb 4, 10 am (Cable Pull details) Due to the fact, the PM will not allow us to gain access we are forced to reschedule this Vault Access appointment. January 21, 2025 - Unfortunatly, we had moved this condo up but the Condo PM, has informed Beanfield that they contractors working on the elevators until the end of March and do not want more then one contractor working in the building at the same time. Therefore we can not schedule internal work until the end of March. January 31, 2025 - OSP Splicing - Splicing completed up to the cable pull, need to return when cable pull is completed February 3, 2025 - Cable Pull is in process feb 3, 2025. Feb 11, 2025 - OSP Splicing Completed March 4, 2025 - THES asbuilt sent to Toronto hydro. March 6, 2025 - Connected with the Pm March 6, 2025, the Contractors working on the elevator are now not expected to be completed until April 7, 2025. This will change are planned date for the conduit build. Therefore we are moving the due date from April 16 to the end of April 29, 2025 March 7, 2025 - Cable pull asbuilt has been attached. | [6 empty] | 3 - Normal | [21 empty] | 2024-11-08 |  |  | 22 | 204 | [5 empty] | https://buildings.beanfield.com/buildings/view/5608#!contacts |  | CONST-24514 | 3 - Normal | 2025-04-22 | Toronto
Construction | CONST-38017 | 165 Legion Rd_Toronto_Califonia Condos | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Lorna Kurok | 2024-07-29 11:26 |  | 2025-03-10 14:20 |  |  | 2025-04-09 | 0 | 0 |  |  | CONST-27257, CONST-27258, CONST-30492, CONST-30493, CONST-30852, CONST-30854, CONST-30856, CONST-39192, CONST-39325, CONST-39326, CONST-39333, CONST-39334, CONST-39335, CONST-39336, CONST-39815, CONST-39816, CONST-39821 | CONST-27231, CONST-27235, CONST-27237, CONST-35974, CONST-37940, CONST-38015, CONST-38018, CONST-27238 | Units 372 July 29, 2024_155, 165 and 185 Legion are combined on one budget. *Property Manager Contact Information as of January 21, 2025:* Sylvia Dydyszko Condominium Manager 647-748-5757 [SDydyszko@mrcm.ca¦mailto:SDydyszko@mrcm.ca] | FSactive, Fiberstreamagreement | [12 empty] | 0¦i539tj: | [7 empty] | 9.2234e+18 | [19 empty] | November 11th - Project on hold. New backbone required. July 17, 2024_Project is Active and no longer on hold, New Backbone has been approved and in progress. Jan 6, 2025_Meeting Notes_ projects are moving well so we are moving these up in the schedule from July 2025 to May 2025 March 10, 2025 - Moved project to the beginning of April. Backbone to be completed March 21. Project moving well, splicing to be completed. | [6 empty] | 3 - Normal | [21 empty] | 2024-07-17 |  |  | 30 | 372 | [5 empty] | https://buildings.beanfield.com/buildings/view/2338 |  | 500469(sub) | 3 - Normal | 2025-07-14 | Etobicoke
Construction | CONST-29268 | 68 Canterbury Pl, Toronto - Celsius | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Jessica Markiewicz | 2022-07-11 16:26 |  | 2025-03-11 09:04 |  |  | 2025-05-07 | 0 | 0 |  |  | CONST-29269, CONST-29270, CONST-36863, CONST-36906, CONST-36907, CONST-36908, CONST-36909, CONST-36910, CONST-36911, CONST-36912, CONST-36913, CONST-36914, CONST-36915, CONST-36916, CONST-36917, CONST-36918, CONST-36919, CONST-36920, CONST-39045, CONST-39046, CONST-39171, CONST-39173, CONST-39553, CONST-40213, CONST-40245 | CONST-29258 | Requested by Jay Fernandes Hi, I’ve gone through the remaining Fibrestream condos we have agreements for in the GTA and have grouped them in a way that I think makes sense for site visits and builds. There will be another list coming of buildings that don’t really fall into groups. Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. There are some current backbone (Sheppard) or NPOP (960 Lawrence) projects that will need to be completed to connect these but this will get everything into the system. Thanks! ** *Vida Ardalan, RCM, GL* Condominium Manager AS AGENT FOR AND ON BEHALF OF TSCC 2465 Tel: (416) 227 9677 Email: [manager@celsiuscondos.com¦mailto:manager@celsiuscondos.com] {*}{*}{*}{*} | FSactive, Fiberstreamagreement, Yonge&Finch | [12 empty] | 0¦i3h90n: | [7 empty] | 9.2234e+18 | [19 empty] | Mar 26/24 - Project initiated. Design & Permit in progress. May 2nd, 2024 - Project is placed on-hold as per Oliver Davies in May 2nd, 2024. Oct 30, 2024 - Project activated and no longer On Hold. Oct 30, 2024 - This project is added to the Resid - On Net schedule for the month of January 2025. This project share construction with 30 Canterbury Const-29258. Jan 6, 2025 - this project is On the OnNet schedule for February 2025 Jan 6, 2025 - Construction Note: This will be done with 30 Canterbury and right now we are waiting for a permit before we can schedule. It's looking like early Feb to do OSP construction Jan 6, 2025_ Meeting Update_Construction 30 and 68 Canterbury requires a new permit due to expiry. On Net Schedule_Moving both buildings to March 2025 for the from February 2025. Jan 7, 2025_Need to set up appointment with PM to be approved access when it is time for OTDR / Ruby Testing. Jan 21, 2025 - related to 30 Canterbury. Pending permit extension, there is the possiblilty that this might be moved out a month but if the permit is received earlier than hypothesized then the date is fine. Jan 22, 2025 - 68 Canterbury is on the scheduled to go On Net for March 2025 Feb 11, 2025 - We expecting the permit to be received feb 28, 2025 for the OSP Construction for 30 Canterbury. Const affects both 30 and 68. Feb 27, 2025 - Changed On net date to March 31, 2025. March 6, 2025 - Pm contacted us after we sent the approval email for construction, please note we are still waiting on the permit. PM wants board approval due to core into the foundation wall. Verbal conversation with James. Changed the On Net schedule due date from March 31, 2025 to May 7, 2025, because the PM wants an engineer to review our drawings, Beanfield will need to cover the cost of this service, also the Condo Board will need to approve. | [6 empty] | 3 - Normal | [19 empty] | Internal |  | 2024-03-26 |  |  | 18 | 228 | Integration |  | 33966 |  |  | https://buildings.beanfield.com/buildings/view/15410 |  | CONST-29268 | 3 - Normal | 2024-11-29 | Toronto | 5348 | 13435
Construction | CONST-27235 | 300 Manitoba St, Toronto - Warehouse Lofts at Mystic Pointe_Shared Budget | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Harvey Tran | 2022-03-09 14:36 |  | 2025-03-12 11:14 |  |  | 2025-04-08 | 0 | 2 |  |  | CONST-27412, CONST-27413, CONST-27616, CONST-37979, CONST-38014, CONST-38059, CONST-39346, CONST-39347, CONST-39348, CONST-39349, CONST-39350, CONST-39351, CONST-39352, CONST-39353, CONST-39354, CONST-39544, CONST-39545, CONST-39748, CONST-39749, CONST-40165 | CONST-27231, CONST-27237, CONST-33547, CONST-35974, CONST-38015, CONST-38017, CONST-38018, CONST-27238 | Units for 300 Manitoba 82 July 29, 2024_250 Manitoba and 300 Manitoba have a Combined budget. The parent tickets were combined but they have been separated into separate parent tickets for clarity. Jan 6, 2025_Meeting Notes_ projects are moving well so we are moving these up in the schedule from July 2025 to May 2025. Jan 16, 2025 - Conduit build sketch completed -If/when we receive floor plans, you can use this as a reference. PM information as of December 2024: Name: Kris Thomai email:[warehouselofts@crossbridgecs.com¦mailto:warehouselofts@crossbridgecs.com] phone number:416-252-5897 | Fiberstreamagreement, HumberBay | [12 empty] | 0¦i393fb: | [7 empty] | 9.2234e+18 | [19 empty] | Jan 27, 2025 - Installed all panel as per diagram except 5th( west North ca5) move to 7th floor Jan 27, 2025 - At 300 and 250 Manitoba, we were only able to fish one riser. The remaining riser need a bigger fish due to the distances involved, ranging from 75m to 120m. Our fish is not long enough, Jan 30, 2025 - Riser Panels completed. Fiber pull completed, pending panel prep. Building services completed Feb 4, 2025 - Riser fibre note -please move these notes to the 250 Manitoba ticket i am going to close the tickets for 300 Manitoba. make all your notes under that address to not confuse anything, they are technically one address. March 10, 2025 - Moving project up from May to April. Back bone to be completed March 21, 2025. Condo Splicing to be completed. March 11, 2025 - Panel Prep - All panels prepped and spliced | [6 empty] | 3 - Normal | [21 empty] | 2024-07-17 |  |  | 4 | 82 | [5 empty] | https://buildings.beanfield.com/buildings/view/531 |  | CONST-27235 | 3 - Normal | 2025-07-14 | Etobicoke
Construction | CONST-38018 | 185 Legion Rd_Toronto_The Tides at Mystic Pointe | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Lorna Kurok | 2024-07-29 11:56 | 2025-03-02 17:03 | 2025-03-12 11:13 |  |  | 2025-04-09 | 0 | 0 | _thumb_1122978.png _thumb_1122977.png _thumb_1122976.png _thumb_1122975.png _thumb_1122972.png |  | CONST-27259, CONST-27260, CONST-30494, CONST-30495, CONST-30853, CONST-30855, CONST-30857, CONST-39191, CONST-39327, CONST-39328, CONST-39329, CONST-39330, CONST-39331, CONST-39332, CONST-39805, CONST-40214 | CONST-27231, CONST-27235, CONST-27237, CONST-33547, CONST-35974, CONST-38015, CONST-38017, CONST-27238 | Unit 304 July 29, 2024_155, 165 and 185 Legion are on a combined budget. Created a separate parent ticket for 165 and 185 Legion to help with clarity. PM contact: Sam manager.tides manager.tides () [manager.tides@rogers.com¦mailto:manager.tides@rogers.com] | FSactive, Fibrestream | [12 empty] | 0¦i539zr: | [7 empty] | 9.2234e+18 | [19 empty] | November 11th - Project on hold. New backbone required. July 17, 2024_Project is Active and no longer on hold, New Backbone has been approved and in progress. Jan 6, 2025_Meeting Notes_ projects are moving well so we are moving these up in the schedule from July 2025 to May 2025 Jan 9, 2025_ John Molendyk sent email to Sam (PM condo) to gain access on January 20, 2025. Waiting for reponse. January 20, 2025 - John M. has site meet with PM on Jan 21, 2025 at 10:30 to discuss work plan and concerns. January 31, 2025 - Riser Panel update -all panels are installed per diagram January 31, 2025 - Riser Fibre Pull - Completed March 10, 2025 - Moved project to the beginning of April. Backbone to be completed March 21. Project moving well, Panel prep and splicing to be completed. March 11, 2025 - ISP splicing completed | [6 empty] | 3 - Normal | [21 empty] | 2024-07-17 |  |  | 22 | 304 | [5 empty] | https://buildings.beanfield.com/buildings/view/2909 |  | 500469(sub) | 3 - Normal | 2025-07-14 | Toronto
Construction | CONST-26911 | 111 / 131 / 151 Upper Duke Cres, Markham - The Verdale I, II, Ⅲ | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Harvey Tran | 2022-02-22 12:13 |  | 2025-03-04 12:51 |  |  | 2025-07-02 | 0 | 1 |  |  | CONST-26928, CONST-26929, CONST-29794, CONST-29913, CONST-29914, CONST-29915, CONST-29916, CONST-29917, CONST-29918, CONST-29919, CONST-29920, CONST-29921, CONST-29922, CONST-29923, CONST-29924, CONST-29925, CONST-35055, CONST-37444, CONST-37541, CONST-38496, CONST-39617 | CONST-29425, CONST-26905, CONST-26906, CONST-26907, CONST-26908, CONST-26913, CONST-26914, CONST-26909, CONST-26910, CONST-31856 | *DELIO MARQUES* Property Manager, OLCM *YRSCC 1192 - The Verdale* 2645 Skymark Avenue Suite 101 ¦ Mississauga, ON L4W 4H2 Direct 905.479.3008 ¦ Cell phone 437.231.1116 Email [delio.marques@fsresidential.com¦mailto:delio.marques@fsresidential.com] | Bolton, Fiberstreamagreement, Markham | [12 empty] | 0¦i37s6v: | [7 empty] | 9.2234e+18 | [19 empty] | August 10th - Project started. Design and Permits to be in progress. Sep 14/23 - Construction scheduled to start on CONST-29425 Sep 21st Oct 12/23 - Construction started Oct 3rd on CONST-29425 May 8th, 2024 - Construction is delayed till end of Aug 2024 due to the other work is still in progress and the site is not ready for our work. Project is pushed back to end of Sep 2024. Sept 19, 2024_Email dated Sept 19, 2024, indicated this project needed to be rescheduled to July 2025, due to the City of Markham. Reference notes in the Backbone OSP Construction Sub-task Jan 6, 2025_Meeting Notes- This project is in the Construction stage. The Moratorium project is holding up this work from being completed. The city of Markham has indicated to Beanfield that the Moratorium work will be be completed April 15, 2025. Jan 15, 2025 - Splicing SOW have been completed Jan 15, 2025 - Po for Sentrex to design City permit was approved. Jan 27, 2025 - OSP splicing completed, but still waiting for cable pull to be completed. January 31, 2025 - OSP splicing is completed up to Cable pull. to return when cable pull is completed Feb 3, 2025 - OSP Splicing - Messy FOSC location, made attempt to fix it up. (this location the fosc here is very messy and difficult to work with.fixed it up as best as i could but trays have fibres that cannot be secured down and when you move the trays it cause outages) March 4, 2025 - City Permit - Troy followed up with Sentrex, they have recd markups and need to resolve some conflicts with design. | [6 empty] | 3 - Normal | [19 empty] | Internal |  | 2022-08-10 |  |  | 14 | 450 |  |  | 8524 |  |  | https://buildings.beanfield.com/buildings/view/3675 |  | 500422 | 3 - Normal | 2023-10-13 | Markham | 13263 | 33385
BC Construction | BCCONST-650 | 13725 & 13745 George Junction (Plaza One and Two, PCI Phase D (D&D1,D2)), Surrey BC | Condo | In Progress |  | Unresolved | John Thomson | Yawn Paular | Yawn Paular | 2024-04-04 19:55 | 2025-03-02 17:03 | 2025-03-06 12:29 |  |  | 2025-05-30 | 0 | 0 |  |  | BCCONST-651, BCCONST-659, BCCONST-676, BCCONST-677, BCCONST-678, BCCONST-730, BCCONST-741, BCCONST-831, BCCONST-832, BCCONST-835, BCCONST-836 | PUR-42170 | DES Conduit Entrance Actual Address 13745 & 13725 George Junction ¦Hendrik Vanderloo [Hendrik.Vanderloo@ledcor.com¦mailto:Hendrik.Vanderloo@ledcor.com]¦ Hendrik got back to me and will forward the right contact info Tower D1 439 units Tower D2 447 units Paul Wong from PCI - Director of Construction [pwong@pci-group.com¦mailto:pwong@pci-group.com] +778 892 9804+ cell *Omri Eliyahu* B.Sc. Eng., PMP CONSTRUCTION MANAGER *PCI DEVELOPMENTS* 300 – 1030 West Georgia Street, Vancouver, BC Canada V6E 2Y3 604 323 3441 cell [oeliyahu@pci-group.com¦mailto:oeliyahu@pci-group.com] [www.pci-group.com¦http://www.pci-group.com/] Occupancy target date for phase 1 (tower D1, amenity and parkade) is aimed for Feb 14{^}th{^}. Occupancy target date for phase 2 (D2 tower) is aimed for April 31{^}st{^}. | Budget_Allocated, DES | [12 empty] | 0¦i4q773: | [7 empty] | 9.2234e+18 | [19 empty] | Jan 31 - D1 is now on-net. Waiting for D2 riser work to be completed. Occupancy date is now Feb 14th for D1 and April/May for Tower D2 Jan 24 - D2 Occupany date was brought in to the end of the month. LayerOne will be finishing Patching splitters today and Erik to complete OLT patching Tue/Wed next weekJan 9 - ISP for D2 completed. It will be a month until D1's riser closets are completed. Horizontal connection between D1 and D2 still in progress. Yawn to follow up with scheduling for horizontal, provide patching information to Tony and Erik for the OLT and Splitter side | [6 empty] | 3 - Normal | [13 empty] | 2025-05-16 18:28 | [11 empty] | 886 | [11 empty] | 38500 | 18500
Construction | CONST-36323 | Contractor Pre-Wiring - 155 Merchants' Wharf - Aqualuna, Toronto | Condo | In Progress |  | Unresolved | Lorna Kurok | Lorna Kurok | Olawale Olaniyan [X] | 2024-01-26 14:17 |  | 2025-03-07 13:30 |  |  | 2025-03-31 | 0 | 2 |  |  | CONST-36511, CONST-38208, CONST-39908 | CONST-35943, ACCT-136267, CONST-19082 |  | Cybertec, PREWIRE, Rogers | [12 empty] | 0¦i4l6nr: | [7 empty] | 9.2234e+18 | [19 empty] | Feb 07/24 - Quote from Cybertec approved under CONST-36323. Feb 08/24 - Transferred $7,500.00 from CONST-19082 (restoration budget) to CONST-36323 (design and permits budget). Sent PO to Cybertec. Nov 22, 2024 Move In date January 2024 January 17, 2025 _1st occupancy inspection is now scheduled for Feb. 18, with the building inspectors, for all below-grade levels, ground floor, and residential floors from L2 to L7 with life-safety on L8, and mechanical penthouses. | [6 empty] | 3 - Normal | [24 empty] | 16 | 225 |  |  | 7500 |  |  | https://buildings.beanfield.com/buildings/view/13366 |  | CONST-36323 | 3 - Normal | 2024-05-31 | Toronto
Construction | CONST-36836 | Contractor Pre-Wiring - 45 Strachan Ave, Toronto | Condo | In Progress |  | Unresolved | Unassigned | Lorna Kurok | Olawale Olaniyan [X] | 2024-03-13 14:40 |  | 2025-03-07 13:32 |  |  |  | 0 | 1 |  |  | CONST-38424, CONST-38425 | CONST-36518 | Requested by James Mowers *Updated Property Manager Information: January 22, 2025* Damon Thomas 647-660-1769 [Damon.Thomas-Anderson@bentallgreenoak.com¦mailto:Damon.Thomas-Anderson@bentallgreenoak.com] | CCS, PREWIRE | [12 empty] | 0¦i4ogyv: | [7 empty] | 9.2234e+18 | [19 empty] | January 16, 2025 First Occupancy June 2025 as per super. Occupancy schedule is attached. | [6 empty] | 3 - Normal | [33 empty] | CONST-36518(SUB) | 3 - Normal |  | Toronto
Construction | CONST-35766 | 36 Forest Manor Rd, North York - Lumina at Emerald City | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Olawale Olaniyan [X] | 2023-11-20 07:44 |  | 2025-03-13 15:17 |  |  | 2025-06-17 | 0 | 1 |  |  | CONST-35767, CONST-35768, CONST-36370, CONST-38581, CONST-38683, CONST-38731, CONST-38732, CONST-38733, CONST-38734, CONST-38735, CONST-38736, CONST-38737, CONST-38738, CONST-38739, CONST-38740, CONST-38741, CONST-38742, CONST-38743, CONST-38744, CONST-38745, CONST-39362, CONST-39568, CONST-39601, CONST-39826 | CONST-33772, CONST-36371, CONST-33774 | Requested by Oliver Davies, Units 254 Floors 15 Can you please create a new ticket for an OSP Plan & Site Walk at 36 Forest Manor Road, the “Lumina at Emerald City” Condos? We may be able to enter this building off of Don Mills to the West, or using the new Helen Lu Rd to the North which would allow us to circumvent the roadwork moratorium that is blocking us on Forest Manor Rd until 2025. Ideally it will give us a connection into the neighbouring [32 Forest Manor Rd¦https://buildings.beanfield.com/buildings/view/16603] (CONST-33774) and [38 Forest Manor Rd¦https://buildings.beanfield.com/buildings/view/17384] as well. PM Info: Arpad Kovacs, OLCM, RCM Condominium Manager TSCC 2903 36 Forest Manor Road Toronto, ON, M2J 0H3 416.551.0665 [luminapm@iccpropertymanagement.com¦mailto:luminapm@iccpropertymanagement.com] Thank you, | NUA+MA | [12 empty] | 0¦i4gcn3: | [7 empty] | 9.2234e+18 | [19 empty] | Jan 30/24 - Budget approved. Pending building agreement Sept 20, 2024 Building agreement signed_ Note from Agreement task_(The signed agreement is now in place for this location. As Beanfield's point of entry is into 38 Forest Manor - we will need to wait for the agreement for 38 Forest Manor to be signed to initiate the project - it is expected to come in next week (last week of sept 2024).) January 7, 2025_City permit note _If there is nothing that can be done with the developer, then we will have to push these three buildings back indefinitely as we can't build on an unassumed road without the developers permission. January 21, 2025 - City Permit - need updates to determine when to put this on the On Net schedule January 21, 2025 - Change On Net schedule date from April 2024 to March 2024. This is due to the complications of permits and the unassumed road. There is the risk that we will have to wait for the city's decision until Feb 21 and also a possibility that we might have to find another method. This permit affects 3 condo 32, 36 and 38 Forest Manor. January 21, 2025_Panel PrepAll Panels prepped and Spliced Jan 27, 2025_Isp All ISP has been completed under the main OSP address 38 Forest Manor - closing ticket Jan 28, 2025 - On Net Schedule Change_Moved condo from April 2025 to June 2025. Due to the unassumed road, affecting the construction and permits. Updated Jira, On Net schedule and SAP. Feb 4, 2025 - Building Base services IN progress. March 13, 2025- Locates have been submitted | [6 empty] | 3 - Normal | [21 empty] | 2024-10-02 |  |  | 15 | 254 | [5 empty] | https://buildings.beanfield.com/buildings/view/15849 |  | CONST-35766 | 3 - Normal |  | North York
Construction | CONST-40040 | 50 Dunfield Ave, North York, Plaza Midtown Condos | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Lorna Kurok | 2025-02-12 13:13 | 2025-03-07 11:33 | 2025-03-13 10:26 |  |  | 2025-08-15 | 0 | 0 |  |  | CONST-40041, CONST-40042, CONST-40043, CONST-40122, CONST-40123, CONST-40124, CONST-40125, CONST-40126, CONST-40127, CONST-40128, CONST-40129, CONST-40130, CONST-40131, CONST-40132, CONST-40133, CONST-40134, CONST-40135, CONST-40136, CONST-40137, CONST-40138, CONST-40139 | CONST-40110 | Units: *545* Floors: *34* Building Constructed Year: *2024* *PM Contact information as of February 12, 2025:* PM Contact Name: *Brett Doiron (Melbourne PM)* PM Contact #: *416-546-2126 x207* PM Email Address: [brett.doiron@melbournepm.ca¦mailto:brett.doiron@melbournepm.ca] *Newbuild Email From Luke Baxter, Feb 12, 2025:* Good Morning The below address was approved at the CAPEX meeting Wednesday, February 12th. CA with budget and Agreement attached MDU Address: *50 Dunfield Ave & 25 Holly St* City: *North York* Building Name: *Plaza Midtown Condos* # of Units: *545* # of Floors: *34* Building Constructed Year: *2024* PM Contact Name: *Brett Doiron (Melbourne PM)* PM Contact #: *416-546-2126 x207* PM Email Address: [brett.doiron@melbournepm.ca¦mailto:brett.doiron@melbournepm.ca] Type of Contract (Fibre agreement or NUA & MA): *Access + Marketing* Building linked to other Buildings: *N/A* Bulk Related: *No* [https://buildings.beanfield.com/buildings/view/19907] | NUA+MA | [12 empty] | 0¦i5iqr3: | [7 empty] | 9.2234e+18 | [19 empty] | Feb 12, 2025 - Ca approved FTTB-00881, Dated Feb 11, 2025, Agreement received. Lorna put this On the On net schedule 6 months from the capex approval date. August 15, 2025. This has been added to the CAPEX financial tracker and budget is added to SAP. February 18, 2025 - separated 25 Holly into it own ticket. Const-40110. The 545 units includes both 50 Dunfield and 25 Holly. March 13, 2025- Emailed PM to request approval for Riser Build March 24th for both 50 Dunfeild Ave, 25 Holly. CONST-40139 | [6 empty] | 3 - Normal | [21 empty] | 2025-02-12 |  |  | 34 | 545 | [5 empty] | https://buildings.beanfield.com/buildings/view/19907 |  | CONST-40040 | 3 - Normal | 2025-08-15 | North York
Construction | CONST-26336 | 181 Village Green Square, Scarborough, Ventus II at Metrogate | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Harvey Tran | 2022-01-06 10:30 |  | 2025-03-18 10:13 |  |  |  | 0 | 0 |  |  | CONST-26337, CONST-26338, CONST-40072, CONST-40073 | CONST-32609, CONST-32622, CONST-32623, CONST-40076, CONST-40077, CONST-26571, CONST-26574 | Constructed in 2012 Units: 314 Floors: 30 {color:#0747a6}*Pm Contact Information as of February 14, 2025:*{color} {*}151 + 181 Village Green Sq{*}{*}{*} {*}Alice Wong{*}{*}{*} Alice Wong R.C.M. ; O.L.C.M. PROPERTY MANAGER *Phone:* 647-347-5775 *Fax: 647-347-5799Email:* [ventus.pm@DelCondo.com¦mailto:ventus.pm@DelCondo.com] May I get a site walk for 151 and 181 Village Green Sq - is it possible to add a note to James, if he’s able to provide a high level opinion from James prior to actually going on site? If the budget is way too high it will be less complicated for the PM/Corporation if we continue to have them work with FibreStream until the announcement has been made about our acquisition. PM info for both corps: Alice Wong Email: ventus.pm@DelCondo.com Phone: 647-347-5775 BB Link: [https://buildings.beanfield.com/buildings/view/15740#!contacts] | Cluster, Fiberstreamagreement | [12 empty] | 0¦i34erz: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2012 February 2025- This is scheduled to go on Net November 15, 2025. February 18, 2025 - Budget Applied to SAP, Added to Capex tracker. | [6 empty] | 3 - Normal | [21 empty] | 2025-02-13 |  |  | 30 | 314 | [5 empty] | https://buildings.beanfield.com/buildings/view/15740 |  | CONST-26336 | 3 - Normal |  | Scarborough
Construction | CONST-32623 | 135 Village Green Square, Scarborough - Solaris ⅠI | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Denise King | 2023-01-09 14:28 |  | 2025-03-17 10:58 |  |  |  | 0 | 2 |  |  | CONST-32626, CONST-32627, CONST-40068, CONST-40069 | CONST-26336, CONST-32609, CONST-32622, CONST-40076, CONST-40077, CONST-26571, CONST-26574 | Constructed in 2011 Units 453 Floors 41 {color:#0747a6}*PM contact information as of February 14, 2025:*{color} {*}125 + 135 Village Green Sq{*}{*}{*} {*}Laney Choi, OLCM{*}{*}{*} Senior Property Manager {*}Agents for and on behalf of: T.S.C.C. No. 2151 & 2166 Solaris 1 & 2 at Metrogate{*}{*}{*} *Phone:* 416-335-7131 *Fax:* 416-335-0423 *Email:* [solaris2.pm@delcondo.com¦mailto:solaris2.pm@delcondo.com] Requested by Oliver Davies: These are active on third-party circuits w/ FibreStream. PM for both locations: Laney Choi, R.C.M. Senior Property Manager 416-335-7131 [solaris2.pm@delcondo.com¦mailto:solaris2.pm@delcondo.com] | Cluster, FSactive, Fiberstreamagreement | [12 empty] | 0¦i3sccv: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2011 | [6 empty] | 3 - Normal | [21 empty] | 2025-02-13 |  |  | 41 | 453 | Integration |  |  |  |  | https://buildings.beanfield.com/buildings/view/15474 |  | CONST-32623 | 3 - Normal |  | Scarborough
Construction | CONST-32622 | 125 Village Green Square, Scarborough -Solaris Ⅰ | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Denise King | 2023-01-09 14:27 |  | 2025-03-17 11:03 |  |  | 2025-11-18 | 0 | 2 |  |  | CONST-32624, CONST-32625, CONST-40070, CONST-40071 | CONST-26336, CONST-32609, CONST-32623, CONST-40076, CONST-40077, CONST-26571, CONST-26574 | Constructed in 2011 Units: 435 Floors: 41 {color:#0747a6}*PM contact information as of February 14, 2025:*{color} {*}125 + 135 Village Green Sq{*}{*}{*} {*}Laney Choi, OLCM{*}{*}{*} Senior Property Manager {*}Agents for and on behalf of: T.S.C.C. No. 2151 & 2166 Solaris 1 & 2 at Metrogate{*}{*}{*} *Phone:* 416-335-7131 *Fax:* 416-335-0423 *Email:* [solaris2.pm@delcondo.com¦mailto:solaris2.pm@delcondo.com] Requested by Oliver Davies: These are active on third-party circuits w/ FibreStream. PM for both locations: Laney Choi, R.C.M. Senior Property Manager 416-335-7131 [solaris2.pm@delcondo.com¦mailto:solaris2.pm@delcondo.com] | Cluster, FSactive, Fiberstreamagreement | [12 empty] | 0¦i3sccn: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2011 February 14, 2025 - List on Capex financial tracker, Added to On Net schedule for November 18, 2025 February 18, 2025 - Budget added to SAP. | [6 empty] | 3 - Normal | [21 empty] | 2025-02-13 |  |  | 41 | 435 | Integration |  |  |  |  | https://buildings.beanfield.com/buildings/view/15473 |  | CONST-32622 | 3 - Normal | 2025-11-18 | Scarborough
BC Construction | BCCONST-487 | 13618 100 Avenue (Infinity), Surrey BC | Condo | In Progress |  | Unresolved | John Thomson | Yawn Paular | Yawn Paular | 2023-11-16 17:27 |  | 2025-03-17 12:02 |  |  | 2025-07-25 | 0 | 0 |  |  | BCCONST-493, BCCONST-494, BCCONST-495, BCCONST-756, BCCONST-841, BCCONST-848, BCCONST-850, BCCONST-851, BCCONST-888 | BCCONST-488, BCCONST-485, BCCONST-486 | 345 units BCS2785 Strata agreed pending signed copy Carmen Zheng - [czheng@ranchogroup.com¦mailto:czheng@ranchogroup.com] 604-684-4508 Site Contact: Walter 604-329-4887 | Budget_Allocated | [12 empty] | 0¦i4g8pz: | [7 empty] | 9.2234e+18 | [19 empty] | Feb 19 - PO's have been issued. LayerOne will line up this building once work at 9887 Whalley Blvd is completed. HighAngle have OSP work pencilled in for week of 3-7th March. Jan 31 - P408 Approved by TELUS Jan 29 - Cable drawing completed John to add budget into SAP Jan 1 - P408 submitted to the TELUS portal for review | [6 empty] | 3 - Normal | [22 empty] | 421 |  |  | 345
Construction | CONST-29393 | 115 George Appleton Way, North York - Independence Way | Condo | In Progress |  | Unresolved | Jessica Markiewicz | Lorna Kurok | Jessica Markiewicz | 2022-07-13 11:51 |  | 2025-03-17 12:17 |  |  |  | 0 | 1 |  |  | CONST-29394, CONST-29395, CONST-40364 | CONST-40330, CONST-40331, CONST-40332, CONST-40333, CONST-40334, CONST-40335, CONST-40336, CONST-29402 | Building Constructed in 2019 Requested by Jay Fernandes Hi, These are the Fibrestream condos we have agreements for that don’t seem to fit into any groups (although I maybe wrong). Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. ¦Group¦Building Name¦Address¦suites¦ ¦Independent¦Eleven Superior¦11 Superior AVE Etobicoke ON M8V 0A7¦130¦ ¦Independent¦The James Club¦1135 Royal York RD Toronto ON M9A 4A7¦209¦ ¦Independent¦Independence Way¦115 George Appleton WAY North York ON M3M 2E9¦244¦ ¦Independent¦Danforth Village Estates¦1346 Danforth RD Toronto ON M4J1M9¦249¦ ¦Independent¦beBloor¦1369 Bloor ST Toronto ON M6P 4J3¦238¦ ¦Independent¦Ion Condos¦15 James Finlay WAY Toronto ON M3M 0B3¦200¦ ¦Independent¦Paradice at the Oasis¦1720 Eglinton AVE Toronto ON M4A2X9¦190¦ ¦Independent¦Havenon the Bluffs¦20 East Haven DR Toronto ON M1N1M2¦259¦ ¦Independent¦Kilgour Estate II¦21 Burkebrook PL Toronto ON M4G4K8¦228¦ ¦Independent¦Canvas Condos¦2301 Danforth AVE Toronto ON M4C 1L5¦156¦ ¦Independent¦3018 Yonge Condos¦3018 Yonge ST Toronto ON M4N 0A5¦188¦ ¦Independent¦Cranbrooke Village¦35 Saranac BLVD Toronto ON M6A 2G4¦341¦ ¦Independent¦39 Brant St¦39 Brant ST Toronto ON M5V0M8¦236¦ ¦Independent¦The Wave¦4 Elsinore PATH Toronto ON M8V 4G7¦185¦ ¦Independent¦Clock Tower Lofts¦700 King ST Toronto ON M5V 2Y6¦216¦ ¦Independent¦The Boot¦75 Dalhousie ST Toronto ON M5B 2R9¦153¦ ¦Independent¦B.Street Condos¦783 Bathurst ST Toronto ON M6G 1K1¦ ¦ ¦Independent¦85 Bloor St¦85 Bloor ST Toronto ON M4W3G9¦252¦ | FSactive, Fiberstreamagreement, GeorgeAppletonCluster, Migration | [12 empty] | 0¦i3hfgv: | [7 empty] | 9.2234e+18 | [19 empty] | March 11, 2025 - Budget approved as a George Appleton Way Cluster.This cluster was approved last week for migration from FS to BF. March 17, 2025 - Scheduling on the On Net schedule for Aug 2025. Aug 21, 2025 | [6 empty] | 3 - Normal | [21 empty] | 2025-03-11 |  |  | 21 | 244 | Integration |  |  |  |  | https://buildings.beanfield.com/buildings/view/15582 |  | CONST-40330(SUB) | 3 - Normal | 2025-08-21 | North York
Construction | CONST-40331 | 125 George Appleton Way, North York, Independence Way | Condo | In Progress |  | Unresolved | Unassigned | Lorna Kurok | Lorna Kurok | 2025-03-14 09:24 |  | 2025-03-17 12:20 |  |  | 2025-08-21 | 0 | 0 |  |  | CONST-40338, CONST-40365 | CONST-29393, CONST-40330, CONST-40332, CONST-40333, CONST-40334, CONST-40335, CONST-40336, CONST-29402 | Building Constructed in 2014 125 George Appleton Way, units 32 Cluster combined units is 244 | FSactive, FibreStream, GeorgeAppletonCluster, Migraton | [12 empty] | 0¦i5l6en: | [7 empty] | 9.2234e+18 | [19 empty] | March 11, 2025 - George Appleton Way Cluster Approved. Migration from FS to BF. March 17, 2025 - Added to On Net Schedule for Aug 21, 2025. | [6 empty] | 3 - Normal | [21 empty] | 2025-03-11 |  |  |  | 32 | Integration |  |  |  |  | https://buildings.beanfield.com/buildings/view/15582 |  | CONST-40330(sub) | 3 - Normal | 2025-08-21 | North York
Construction | CONST-40334 | 75 George Appleton Way, North York, Independence Way | Condo | In Progress |  | Unresolved | Unassigned | Lorna Kurok | Lorna Kurok | 2025-03-14 09:57 |  | 2025-03-17 12:30 |  |  | 2025-08-21 | 0 | 0 |  |  | CONST-40368 | CONST-29393, CONST-40330, CONST-40331, CONST-40332, CONST-40333, CONST-40335, CONST-40336, CONST-29402 | Building Constructed in 2006 75 George Appleton Way units 24 Cluster units are 244 | FSactve, FibreStream, GeorgeAppletonCluster, Migraton | [12 empty] | 0¦i5l6lr: | [7 empty] | 9.2234e+18 | [19 empty] | March 11, 2025 - George Appleton Way Cluster Approved. Migration from FS to BF. March 17, 2025 - Applied condo to the On net schedule for August 21, 2025. | [6 empty] | 3 - Normal | [21 empty] | 2025-03-11 |  |  |  | 24 | Integration |  |  |  |  | https://buildings.beanfield.com/buildings/view/15582 |  | CONST-40330(SUB) | 3 - Normal | 2025-08-21 | North York
Construction | CONST-40336 | 95 George Appleton Way, North York, Independence Way | Condo | In Progress |  | Unresolved | Unassigned | Lorna Kurok | Lorna Kurok | 2025-03-14 10:11 |  | 2025-03-17 12:34 |  |  | 2025-08-21 | 0 | 0 |  |  | CONST-40370 | CONST-29393, CONST-40330, CONST-40331, CONST-40332, CONST-40333, CONST-40334, CONST-40335, CONST-29402 | Building Constructed in 2006 95 George Appleton units 32 Cluster Units are 244 | FSactve, Fibrestream, GeorgeAppletonCluster, Migration | [12 empty] | 0¦i5l6pb: | [7 empty] | 9.2234e+18 | [19 empty] | March 11, 2025 - George Appleton Way Cluster Approved. Migration from FS to BF. March 17, 2025 - Applied to On Net Schedule for August 21, 2025 | [6 empty] | 3 - Normal | [21 empty] | 2025-03-11 |  |  |  | 32 | Integration |  |  |  |  | https://buildings.beanfield.com/buildings/view/15582 |  | CONST-40330(SUB) | 3 - Normal | 2025-08-21 | North York
Construction | CONST-40335 | 85 George Appleton Way, North York, Independence Way | Condo | In Progress |  | Unresolved | Unassigned | Lorna Kurok | Lorna Kurok | 2025-03-14 10:05 |  | 2025-03-17 12:31 |  |  | 2025-08-21 | 0 | 0 |  |  | CONST-40369 | CONST-29393, CONST-40330, CONST-40331, CONST-40332, CONST-40333, CONST-40334, CONST-40336, CONST-29402 | Building Constructed in 2006 85 George Appleton Way units 24 Cluster Units 244 | FSactive, FibreStream, GeorgeAppletonCluster, Migration | [12 empty] | 0¦i5l6n3: | [7 empty] | 9.2234e+18 | [19 empty] | March 11, 2025 - George Appleton Way Cluster Approved. Migration from FS to BF. March 17, 2025 - Applied condo to On net schedule for August 21, 2025 | [6 empty] | 3 - Normal | [21 empty] | 2025-03-11 |  |  |  | 24 | Integration |  |  |  |  | https://buildings.beanfield.com/buildings/view/15582 |  | CONST-40330(SUB) | 3 - Normal | 2025-08-21 | North York
Construction | CONST-40110 | 25 Holly St, North York, Plaza Midtown Condos | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Lorna Kurok | 2025-02-18 13:53 |  | 2025-03-13 10:26 |  |  | 2025-08-15 | 0 | 0 |  |  | CONST-40111, CONST-40112, CONST-40113, CONST-40140, CONST-40141, CONST-40142, CONST-40143, CONST-40144, CONST-40145, CONST-40146, CONST-40147, CONST-40148, CONST-40149, CONST-40150, CONST-40151, CONST-40381 | CONST-40040 | Units: *545 is for both 50 Dunfield and 25 Holly St* Floors: *34* Building Constructed Year: *2024* *PM Contact information as of February 12, 2025:* PM Contact Name: *Brett Doiron (Melbourne PM)* PM Contact #: *416-546-2126 x207* PM Email Address: [brett.doiron@melbournepm.ca¦mailto:brett.doiron@melbournepm.ca] *Newbuild Email From Luke Baxter, Feb 12, 2025:* Good Morning The below address was approved at the CAPEX meeting Wednesday, February 12th. CA with budget and Agreement attached MDU Address: *50 Dunfield Ave & 25 Holly St* City: *North York* Building Name: *Plaza Midtown Condos* # of Units: *545* # of Floors: *34* Building Constructed Year: *2024* PM Contact Name: *Brett Doiron (Melbourne PM)* PM Contact #: *416-546-2126 x207* PM Email Address: [brett.doiron@melbournepm.ca¦mailto:brett.doiron@melbournepm.ca] Type of Contract (Fibre agreement or NUA & MA): *Access + Marketing* Building linked to other Buildings: *N/A* Bulk Related: *No* [https://buildings.beanfield.com/buildings/view/19907] | NUA+MA | [12 empty] | 0¦i5j2hb: | [7 empty] | 9.2234e+18 | [19 empty] | Feb 12, 2025 - Ca approved FTTB-00881, Dated Feb 11, 2025, Agreement received. Lorna put this On the On net schedule 6 months from the capex approval date. August 15, 2025. This has been added to the CAPEX financial tracker and budget is added to SAP. February 18, 2025 - the 545 units includes both 50 Dunfield and 25 Holly St. March 13, 2025- Emailed PM to request approval for Riser Build March 24th for both 50 Dunfeild Ave, 25 Holly. CONST-40139 | [6 empty] | 3 - Normal | [21 empty] | 2025-02-12 |  |  | 34 | 0 | [5 empty] | https://buildings.beanfield.com/buildings/view/19907 |  | CONST-40040(Sub) | 3 - Normal | 2025-08-15 | North York
Construction | CONST-28346 | 65 Trinity - Block 3, Toronto | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Harvey Tran | 2022-05-11 14:12 |  | 2025-03-13 14:52 |  |  | 2025-12-09 | 0 | 0 |  |  | CONST-28375, CONST-28381, CONST-28474, CONST-33802, CONST-33803, CONST-33804, CONST-33805, CONST-33806, CONST-33807, CONST-33808, CONST-33809, CONST-33810, CONST-33811, CONST-33812, CONST-33813, CONST-33814, CONST-33815, CONST-33816, CONST-33817, CONST-33936, CONST-37862, CONST-39364, CONST-39415, CONST-39435, CONST-39513, CONST-40378 | CONST-28344, CONST-28345, CONST-33763 | We’ve got a bunch of buildings popping up in the West Don Lands so need to add them to our build schedule. Since we have the agreements already, feel free to create the full build of subtasks - including site walk, agreement and base building services. I think James has already done most of the site walks - he just needs a place to put the info. There are 2 groups of 3 towers going up but we should treat them as separate builds in JIRA - even if they can tie together through the underground. Then there are 2 additional, separate buildings. So 8 new tickets in total. Please use the municipal address as the title for each so it will tie into Building Browser. 131 Mill St. 151 Mill St. 181 Mill St. 422 Cherry 432 Cherry 65 Trinity Contact: ¦*_Alain Costa_* ¦ ¦MEP Manager, Toronto Division¦ ¦!https://mail.google.com/mail/u/0?ui=2&ik=e63ae99e5e&attid=0.53&permmsgid=msg-f:1805381308421027332&th=190e00bc1490b604&view=fimg&fur=ip&sz=s0-l75-ft&attbid=ANGjdJ_YuHvXw__tcyrHve9wYS8i9dMBxyqI969XpIIbXIWbqMZRmatWRSip8GCOY2dQDd6VCw0KWzyKMgfC_ByxqzUA4U2yLi5yLsPcTFIhMR1VtwqVfyfTBRUkncw&disp=emb!{*}C{*}: 416.356.1900¦ ¦!https://mail.google.com/mail/u/0?ui=2&ik=e63ae99e5e&attid=0.54&permmsgid=msg-f:1805381308421027332&th=190e00bc1490b604&view=fimg&fur=ip&sz=s0-l75-ft&attbid=ANGjdJ-UZIGZLlIkRJ180v7g8IePs5YmGhRxSY4__gMDWg6rHhFJdptk5S1uEkfVk7fPI51btvo_XQhCrN6wOI8kdJ1M43E3R-sRrN8UtLWAbbC1ZFXCLLjFX6NRJOE&disp=emb! [acosta@ellisdon.com¦mailto:acosta@ellisdon.com]¦ ¦!https://mail.google.com/mail/u/0?ui=2&ik=e63ae99e5e&attid=0.55&permmsgid=msg-f:1805381308421027332&th=190e00bc1490b604&view=fimg&fur=ip&sz=s0-l75-ft&attbid=ANGjdJ9_HxfIDzAc4rtO2HhfamZKKI8fmbQ-_qSMVy6X1yL41KzTICiIdOso4JUpSeT3Kt15nY5G-lXHVtJqpZdR5Zc1ztncyzdc_qI7XCtIJmQ7KbDxM2UwMh1XX9o&disp=emb! 1004 Middlegate Rd., Suite 1000, Mississauga, ON L4Y 1M4¦ ¦!https://mail.google.com/mail/u/0?ui=2&ik=e63ae99e5e&attid=0.56&permmsgid=msg-f:1805381308421027332&th=190e00bc1490b604&view=fimg&fur=ip&sz=s0-l75-ft&attbid=ANGjdJ_4an-FqDTHLuxVeDHSk8aGCLkh8i0JT3eBCdFT0lTcZFHutd_pxOFfDq0VquR5JbsTQ2nObCio0x8iXLYUmJhvcJgG8kwxDlMwGXGZXBUh_-28qaprcedRuyo&disp=emb! [www.ellisdon.com¦http://www.ellisdon.com/]¦ | Bolton, ExecutionAgreement, PREWIRE | [12 empty] | 0¦i3dhb3: | [7 empty] | 9.2234e+18 | [19 empty] | May 04/23 - Project initiated, pending Permits & Design Aug 3/23 - No permit required. Aug 15/23 - Waiting on building for approval to schedule construction. Feb 23/24 - Construction scheduled to start Feb 26th Feb 29/24 - Construction completed. Jan 2, 2024 - Tie cables completed on both sides. Jan 6, 2025- Meeting Notes_ due to this Building Construction, we are moving these project to June 2025 from May 2025 Jan 13, 2025 - noting that the OSP has already been pulled. Jan 10, 2025_ OSP SOW Jan 21, 2025 - OSP Sow pending redesign, due to embargo Hydro CC2911 Feb 28, 2025 Building need to be moved on schedule from June to Dec. Not likely to complete in June due to amount of work to be completed. March 13, 2025 - Riser Fibre Pull inprogress pulled ropes, riser panels in progress | [6 empty] | 3 - Normal | [25 empty] | 397 |  |  | 37911 |  |  | https://buildings.beanfield.com/buildings/view/16123 |  | CONST-28346 | 3 - Normal | 2025-05-30 | Toronto | 39064 | 13240
Construction | CONST-29124 | 75 The Donway, Toronto - Liv Lofts | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Jessica Markiewicz | 2022-07-11 07:26 |  | 2025-03-19 09:15 |  |  | 2025-03-18 | 0 | 1 |  |  | CONST-29125, CONST-29126, CONST-32536, CONST-32554, CONST-32555, CONST-32556, CONST-32557, CONST-32558, CONST-32559, CONST-32560, CONST-32561, CONST-38078, CONST-39558, CONST-40249, CONST-40300 | CONST-35829, CONST-38074, CONST-29127 | Requested by Jay Fernandes Hi, I’ve gone through the remaining Fibrestream condos we have agreements for in the GTA and have grouped them in a way that I think makes sense for site visits and builds. There will be another list coming of buildings that don’t really fall into groups. Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. There are some current backbone (Sheppard) or NPOP (960 Lawrence) projects that will need to be completed to connect these but this will get everything into the system. Thanks! *PM: Nicole Roper* *nicole.roper@fsresidential.com* *416.444.8588* | DonMills&Eg, FSactive, Fiberstreamagreement | [12 empty] | 0¦i3h5jr: | [7 empty] | 9.2234e+18 | [19 empty] | December 30th - Project initiated. Only ISP work. Will be fed from 85 The Donway. Nov 27, 2024 - construction - Regarding Building request_(We've received a response from the corporation's solicitor with a number of requests, including having an engineer review. Josh Wignall and I will review today and provide our response to them. This project will likely need to wait until early Q1. ) Nov 23/23 - Due dates update. Waiting on building for construction approval Apr 03/24 - Still pending building construction approval. Due dates updated. July 19th, 2024 - Korey has followed up with the building, they are still working out internally in order to provide us a go ahead for our work. Jul 23rd, 2023 - Still pending the approval from the building to start construction to 85 Donway. Project due date is pushed back to Sep 2024. Sep 3rd, 2023 - We still dont have the approval from the building, pushing back this build to Otc 2024. Oct 1, 2024_ pushing On Net due date to November 2024 Oct 1, 2024 - pushing 75 The Donway and 85 The Donway to February 2025, to pending property manager approval Jan 6, 2025_Meeting Notes_Pushing 75 and 85 The Donway to March 2025 to allow more time to obtain approvals from Property Manager. Jan 28, 2025_On Net Schedule change. Moved both Donway (75 and 85) to May 2025 from March 2025. The reason is we are still waiting on permission form the Property Management. (this is with Josh Wignall) Josh has spoke again with PM, who would like complete this by end of week Jan 31, 2025. But the challenge is with the board and the solicitor.) Updated Jira, SAP and the On Net schedule Feb 19, 2025 - Moved back to March 2025, construction is expected to be completed early march, so we believe we can complete this by the end of March. Feb 28, 2025 - ISP plan is under ticket 85 The Donway March 11, 2025 - Conduit build is completed, pictures attached March 12, 2025 - Condo Concierge hours -85 The Donway concierge is on site 10 or 10:30 am, 75 The Donway Concierge is on site 10 am March 18, 2025 - Condo is On Net. March 19, 2025 - City Permit is on another ticket 75 The Donway. Asbuilt Note:Hard surface restoration completed by Beanfield. | [6 empty] | 3 - Normal | [19 empty] | N/A | 2025-03-18 | 2022-12-30 |  |  | 14 | 171 | Integration | 2025-03-18 |  |  |  | https://buildings.beanfield.com/buildings/view/15517 |  | 500528 | 3 - Normal | 2023-10-27 | Toronto | 5727
Construction | CONST-40206 | 25 Greenview Avenue, North York, Meridian II | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Lorna Kurok | 2025-02-26 14:59 |  | 2025-03-19 12:39 |  |  | 2025-08-27 | 0 | 0 |  |  | CONST-40207, CONST-40208, CONST-40209, CONST-40228, CONST-40229, CONST-40230, CONST-40231, CONST-40232, CONST-40233, CONST-40234, CONST-40235, CONST-40236, CONST-40237, CONST-40238, CONST-40239, CONST-40297 | CONST-40202 | Constructed in 2008 Units 349 Floors 27 *PM Information as of February 26, 2025:* PM Contact Name: Bal Pandeya (Del) PM Contact #: 416-637-6301 PM Email Address: [meridian.pm@DelCondo.com¦mailto:meridian.pm@DelCondo.com] Good Morning The attached was approved at this mornings capex meeting. MDU Address: 15 and 25 Greenview Ave City: North York Building Name: Meridian I and Meridian II # of Units: 788 Units (439 and 349) # of Floors:32 and 27 Building Constructed Year: 2007 and 2008 PM Contact Name: Bal Pandeya (Del) PM Contact #: 416-637-6301 PM Email Address: [meridian.pm@DelCondo.com¦mailto:meridian.pm@DelCondo.com] Type of Contract (Fibre agreement or NUA & MA): A+M Building linked to other Buildings: Bulk Related: no -- ¦ ¦Luke Baxter¦ ¦ | NUA+MA | [12 empty] | 0¦i5jryn: | [7 empty] | 9.2234e+18 | [19 empty] | Feb 26, 2025 - CA approved along with 15 Greenview Ave. Double checking if the building agreement for 15 Greenview Ave also applies to 25 Greenview Ave. March 5, 2025 -25 Greenview will be feed from 15 Grenview POP March 19, 2025 - Requested Access to begin Riser build on March 31 to April 4. PM has approved these dates for the riser build. | [6 empty] | 3 - Normal | [21 empty] | 2025-02-26 |  |  | 27 | 349 | [5 empty] | https://buildings.beanfield.com/buildings/view/18155 |  | CONST-40206 | 3 - Normal | 2025-08-27 | North York
Construction | CONST-40202 | 15 Greenview Avenue, North York, Meridian I | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Lorna Kurok | 2025-02-26 14:35 |  | 2025-03-18 12:04 |  |  | 2025-08-27 | 0 | 0 |  |  | CONST-40203, CONST-40204, CONST-40205, CONST-40216, CONST-40217, CONST-40218, CONST-40219, CONST-40220, CONST-40221, CONST-40222, CONST-40223, CONST-40224, CONST-40225, CONST-40226, CONST-40227, CONST-40289, CONST-40290, CONST-40291, CONST-40292, CONST-40293, CONST-40294, CONST-40295, CONST-40296 | CONST-40206 | Constructed in 2007 Units 439 Floors 32 *PM Information as of Feb 26, 2025:* PM Contact Name: Bal Pandeya (Del) PM Contact #: 416-637-6301 PM Email Address: [meridian.pm@DelCondo.com¦mailto:meridian.pm@DelCondo.com] Good Morning The attached was approved at this mornings capex meeting. MDU Address: 15 and 25 Greenview Ave City: North York Building Name: Meridian I and Meridian II # of Units: 788 Units (439 and 349) # of Floors:32 and 27 Building Constructed Year: 2007 and 2008 PM Contact Name: Bal Pandeya (Del) PM Contact #: 416-637-6301 PM Email Address: [meridian.pm@DelCondo.com¦mailto:meridian.pm@DelCondo.com] Type of Contract (Fibre agreement or NUA & MA): A+M Building linked to other Buildings: Bulk Related: no -- ¦ ¦Luke Baxter¦ ¦ | NUA+MA | [12 empty] | 0¦i5jrtr: | [7 empty] | 9.2234e+18 | [19 empty] | Feb 26, 2025 - CA approved and attached. Agreement attached new format. March 5, 2025 -Tie in point will be MH665, 200m Hydro permit, we will be breaking out of MH756, 40m trench to building wall scan/core. 15 feds 25 Greenview Ave (Duct pull, small trench) March 13, 2025 - Route drawing prepared. | [6 empty] | 3 - Normal | [21 empty] | 2025-02-26 |  |  | 32 | 439 | [5 empty] | https://buildings.beanfield.com/buildings/view/13648 |  | CONST-40202 | 3 - Normal | 2025-08-27 | North York
Construction | CONST-28120 | 38 Lee Centre Dr, Toronto | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Harvey Tran | 2022-04-28 08:25 |  | 2025-03-20 14:43 |  |  | 2026-04-08 | 0 | 1 |  |  | CONST-28121, CONST-28122, CONST-37986, CONST-39121, CONST-39302, CONST-39303, CONST-39304, CONST-39305, CONST-39306, CONST-39307, CONST-39308, CONST-39309, CONST-39310, CONST-39311, CONST-39312, CONST-39313, CONST-39314, CONST-39315, CONST-39316, CONST-39317, CONST-39318, CONST-39576, CONST-40253 |  | +*Updated PM information as of February 12, 2025*+ [ellipse2@rogers.com¦mailto:ellipse2@rogers.com] Tony Okorn PropertyWright Management 38 Lee Centre Dr ([https://buildings.beanfield.com/buildings/view/4981]) ** *PM: Ismail Alli,* OLCM,RCM 38 Lee Centre Drive, Scarborough, ON M1H 3J7 Telephone: (416) 438-6043 E-mail: *[ismail.alli@crossbridgecs.com¦mailto:ismail.alli@crossbridgecs.com]* | NUA+MA | [12 empty] | 0¦i3cl0v: | [7 empty] | 9.2234e+18 | [19 empty] | Sept 25, 2024_Agreement attached Nov 20, 2024 - We have been given the go ahead to move forward with this building. Feb 12, 2025 - the original tie in location is at capacity, building was moved to 2026. It might need Overbuild, need confirmation from planning. March 20, 2025 - OSP splicing is completed, (Testing noted: tested by Johnny Khuu, looks like we have a bad splice on one and an open on the other will return to fix once cable pull is complete.) | [6 empty] | 3 - Normal | [21 empty] | 2024-11-20 |  |  | 24 | 383 | [5 empty] | https://buildings.beanfield.com/buildings/view/4981 |  | CONST-28120 | 3 - Normal | 2026-04-08 | Toronto
Construction | CONST-33948 | 88 Sheppard Ave E, North York - EI8HTY8 Condos | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Olawale Olaniyan [X] | 2023-05-16 13:28 |  | 2025-03-20 14:44 |  |  | 2025-07-11 | 0 | 0 | _thumb_1131133.png |  | CONST-33949, CONST-33950, CONST-39870, CONST-39873, CONST-39874, CONST-39875, CONST-39876, CONST-39877, CONST-39878, CONST-39879, CONST-39880, CONST-39881, CONST-39882, CONST-39883, CONST-39884, CONST-39885, CONST-39886, CONST-39887, CONST-40115, CONST-40276 |  | {color:#0747a6}*Updated PM information as of February 14, 2025:*{color} PM Name: Colleen Todd PM Email: <[Colleen.Todd@fsresidential.com¦mailto:Colleen.Todd@fsresidential.com]> PM Information: ¦JAMES LAU¦ ¦Property Manager¦ ¦88 Sheppard Ave East \¦ Toronto, ON M2N 0G9¦ ¦Direct 647.346.7683 \¦ Toll Free 1.855.244.8854¦ ¦james.lau@fsresidential.com¦ Requested by Jay Fernandes, Believe it or not we’ve missed 4 more Fibrestream buildings we need to build into. As we’re fully integrating everything these were discovered. Can we set up site visits and budgets for these? Curve Condos - 170 Sudbury Street - Old Jira Ticket -CONST-3019- Building Browser [Link¦https://buildings.beanfield.com/buildings/view/2294]. The Continental - 509 Beecroft Road - Building Browser [Link¦https://buildings.beanfield.com/buildings/view/14605]. The Yorkville - 32 Davenport Road - Old JIRA Ticket -CONST-5694- Building Browser [Link¦https://buildings.beanfield.com/buildings/view/3382]. Ei8GHTY8 Condos - 88 Sheppard Avenue E - Building Browser [LINK¦https://buildings.beanfield.com/buildings/view/7169]. Thanks, — Jay | FSactive, Fiberstreamagreement | [12 empty] | 0¦i41d5j: | [7 empty] | 9.2234e+18 | [19 empty] | Jan 22, 2025 - Received Email approval for Condo Budget. Jan 22, 2025 Condo Constructed in 2015. January 30, 2025 - On Net Schedule changed, Moved up on the schedule from Sept to July after being advisement with James. Est. Scope before design Bore 140m, Trench 40m February 12, 2025 - Emailed PM to request access to build Risers and Electrical drawings. Riser build request date: March 3, 2025. February 14, 2025, - First email bounced back, was able to obtain New Pm contact information (Colleen Todd), resent the Access request email February 14, 2025. This Pm wants more information. Feb 26, 2024 PM has be notified and approves the the March 3 work date for the Riser Build. March 10, 2025 - 75 % of the riser work is completed. March 18, 2025 - Isp Splicing All trays spliced, OSP tray prepped March 20, 2025 - OSP splicing, splicing is almost all completed, need cable pull to complete the last portion. | [6 empty] | 3 - Normal | [21 empty] | 2025-01-22 |  |  | 35 | 374 | Integration |  |  |  |  | https://buildings.beanfield.com/buildings/view/7169 |  | CONST-33948 | 3 - Normal | 2025-09-02 | North York
Construction | CONST-29399 | 1369 Bloor St, Toronto - beBloor | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Jessica Markiewicz | 2022-07-13 12:21 |  | 2025-03-20 15:12 |  |  | 2025-06-19 | 0 | 1 |  |  | CONST-29400, CONST-29401, CONST-31402, CONST-31436, CONST-31437, CONST-31438, CONST-31439, CONST-31440, CONST-31441, CONST-31442, CONST-31444, CONST-31445, CONST-31446, CONST-31447, CONST-31448, CONST-31449, CONST-31450, CONST-37657, CONST-37658, CONST-37914, CONST-38037, CONST-39358, CONST-39551, CONST-40259 | CONST-36570, CONST-35199 | Requested by Jay Fernandes Hi, These are the Fibrestream condos we have agreements for that don’t seem to fit into any groups (although I maybe wrong). Can we get the tickets created for these for the design, site walks and budgets? I believe Mark Houston has been working on the designs in the back ground already. This is the list but I’ve also attached an Excel document. ¦Group¦Building Name¦Address¦suites¦ ¦Independent¦Eleven Superior¦11 Superior AVE Etobicoke ON M8V 0A7¦130¦ ¦Independent¦The James Club¦1135 Royal York RD Toronto ON M9A 4A7¦209¦ ¦Independent¦Independence Way¦115 George Appleton WAY North York ON M3M 2E9¦244¦ ¦Independent¦Danforth Village Estates¦1346 Danforth RD Toronto ON M4J1M9¦249¦ ¦Independent¦beBloor¦1369 Bloor ST Toronto ON M6P 4J3¦238¦ ¦Independent¦Ion Condos¦15 James Finlay WAY Toronto ON M3M 0B3¦200¦ ¦Independent¦Paradice at the Oasis¦1720 Eglinton AVE Toronto ON M4A2X9¦190¦ ¦Independent¦Havenon the Bluffs¦20 East Haven DR Toronto ON M1N1M2¦259¦ ¦Independent¦Kilgour Estate II¦21 Burkebrook PL Toronto ON M4G4K8¦228¦ ¦Independent¦Canvas Condos¦2301 Danforth AVE Toronto ON M4C 1L5¦156¦ ¦Independent¦3018 Yonge Condos¦3018 Yonge ST Toronto ON M4N 0A5¦188¦ ¦Independent¦Cranbrooke Village¦35 Saranac BLVD Toronto ON M6A 2G4¦341¦ ¦Independent¦39 Brant St¦39 Brant ST Toronto ON M5V0M8¦236¦ ¦Independent¦The Wave¦4 Elsinore PATH Toronto ON M8V 4G7¦185¦ ¦Independent¦Clock Tower Lofts¦700 King ST Toronto ON M5V 2Y6¦216¦ ¦Independent¦The Boot¦75 Dalhousie ST Toronto ON M5B 2R9¦153¦ ¦Independent¦B.Street Condos¦783 Bathurst ST Toronto ON M6G 1K1¦ ¦ ¦Independent¦85 Bloor St¦85 Bloor ST Toronto ON M4W3G9¦252¦ | FSactive, Fiberstreamagreement | [12 empty] | 0¦i3hfqv: | [7 empty] | 9.2234e+18 | [19 empty] | November 29th - Route Drawing completed. June 05/23 - Manhole survey completed. Hydro permit in progress. Aug 7/23 - Hydro permit granted. Sep 3rd 2024 - We still dont have the agreement to complete the conduit build and cable pull. Sep 4, 2024_SOW Design Details have been uploaded. Sep 10, 2024_Requires Vault Access, hoping to Schedule Friday October 4th between 10 am to 1 pm, Vault Loc Z2040 Sep 10, 2024_OSP splicing Completed. Sep 13, 2024_Booking Vault access, Vault ID: LZ2040 For Friday October 4th 10 am to 1 pm Sep 17, 2024_Vault access payment is confirmed. Confirmed appointment time with Scheduler. Oct 7, 2024 Cable pull asbuilt attached Jan 6, 2025_Meeting update- this building is being moved to March 2025 on the ON net schedule. This building requires the agreement to approved for CONST-36570 1/11/21 Ruttan. Condo 1/11/21 Ruttan is blocking 1369 Bloor from being completed. Therefore we have moved 1369 Bloor was rescheduled to March 2025. Jan 28, 2025 - Change to On Schedule- Moved from March 2025 to May 2025 due to other Condo as noted above. (Oliver has been working on this issue.) Updated change in Jira, On Net schedule, and SAP. March 20, 2025 - Moving on On Net schedule from May 19, 2025 to June 19, 2025. This condo is dependent on the condo agreement for 1/11/21 Ruttan. This agreement is not signed so we need to move 1369 Bloor St. | [6 empty] | 3 - Normal | [19 empty] | N/A |  | 2022-10-25 |  |  | 15 | 238 | Integration |  | 20490 |  |  | https://buildings.beanfield.com/buildings/view/3078 |  | 500488 | 3 - Normal | 2023-12-29 | Toronto | 7873 | 16030
Construction | CONST-36759 | 10 Wilby Cres, York - The Humber | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Olawale Olaniyan [X] | 2024-03-06 08:00 |  | 2025-03-19 14:42 |  |  | 2025-06-23 | 0 | 1 |  |  | CONST-36760, CONST-36761, CONST-39637, CONST-39638, CONST-39706, CONST-39708, CONST-39709, CONST-39710, CONST-39711, CONST-39712, CONST-39713, CONST-39714, CONST-39715, CONST-39716, CONST-39717, CONST-39718, CONST-39719, CONST-39720, CONST-39721, CONST-39722, CONST-40167, CONST-40277 |  | Requested by Oliver Davies, {color:#403294}*PM information updated as of December 17, 2024:*{color} Pauline Kelley Relief Manager *TSCC 2982* *10 Wilby Crescent* *Toronto, Ontario* *M9N 0B6* *Phone:* 1 437-880-5546 *Email:* +[TheHumber.pm@Delcondo.com¦mailto:TheHumber.pm@Delcondo.com]+ {color:#0747a6}*Condominium Manager as of February 12, 2025:*{color} Donika Nushi Condominium Manager *TSCC 2982* *10 Wilby Crescent* *Toronto, Ontario* *M9N 0B6* *Phone:* 1 437-880-5546 *Email:* [TheHumber.pm@Delcondo.com¦mailto:TheHumber.pm@Delcondo.com] *DEL is a proud, perennial award-winning company.* Could you please proceed with creating a new ticket for an OSP plan & site walk at 10 Wilby Cres near Weston Rd & Lawrence Ave W in Toronto? “The Humber” condos were recently occupied and include 232 residential units. The board has already provided a verbal approval for Beanfield to proceed. The nearest access point appears to be CDSM10565. We will likely need to explore an aerial route or rent existing duct space to get into the building. Nearby, there is a development underway at 1695 + 1705 Weston Rd for the “Charlton Residences” that will contain 240 residential units. There is also a neighbouring condo at 1 Hickory Ridge Rd that will require a pre-wire. No need to plan for this one. PM Info: Bujar Sinaj OLCM. IHM. Condominium Manager *Phone:* 1 437-880-5546 *Email:* +[TheHumber.pm@Delcondo.com¦mailto:TheHumber.pm@Delcondo.com]+ Thank you, {color:#00875a}*New Residential Building Email_January 9, 2025*{color} MDU Address: *10 Wilby Crescent* City: *North York* Building Name: *The Humber Condos* # of Units: *232* # of Floors: *22* Building Constructed Year: *2023* PM Contact Name: *Pauline Kelley* PM Contact #: *437-880-5546* PM Email Address: [thehumber.pm@delcondo.com¦mailto:thehumber.pm@delcondo.com] Type of Contract (Fibre agreement or NUA & MA): *NUA & MA* Building linked to other Buildings: *N/A* Bulk Related: *N/A* [https://buildings.beanfield.com/buildings/view/18680] | NUA+MA | [12 empty] | 0¦i4nz2f: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2023 January 9, 2025, Received New Residential Building email CA Approved 00128, we compared the existing site visit budget exceeds the CA approved budget. Therefore I stopped placing the project In Progress so the budgets can reviewed and the increase can be approved. January 30, 2025 -Wilbly is scheduled to be under moratorium starting summer 2025, ending 2030. We are going to try and coordinate and start work before the planned city work is started. Troy has reached out to the City. Feb 4, 2025 - City permit note:(As there is a future moratorium in place on this road, we will still get pushback from the city for the permit. Not saying that we won't be able to do this, but we will face additional review/approval and delays in getting the cut permit. There is also a possibility that we will be denied a permit completely.) February 12, 2025 - Emailed Condo PM to request Eletrical drawings and access request for Building riser to begin on Monday May 17, 2025. PM Donika Nushi replied that this date is fine and sent a link to the Electrical drawings. https://we.tl/t-aUvpdtUtxR Feb 28, 2025 - Building is being moved up to July from sept, there will be third party construction work in July, which may affect our ability to succeed in september. March 19, 2025 - Riser Panel all the panels are prepped and ready to be spliced | [6 empty] | 3 - Normal | [21 empty] | 2025-01-15 |  |  | 22 | 232 | [5 empty] | https://buildings.beanfield.com/buildings/view/18680 |  | CONST-36759 | 3 - Normal |  | York
Construction | CONST-28209 | 106 Dovercourt Rd, Toronto - Ten93 Queen West Condos | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Harvey Tran | 2022-05-04 10:44 |  | 2025-03-19 14:48 |  |  | 2025-05-13 | 0 | 1 |  |  | CONST-28210, CONST-28211, CONST-28491, CONST-28492, CONST-28493, CONST-28494, CONST-28495, CONST-28496, CONST-28497, CONST-28498, CONST-28499, CONST-28500, CONST-28501, CONST-28502, CONST-28503, CONST-28504, CONST-30291, CONST-39367, CONST-39368, CONST-39369, CONST-40301 |  |  | FSactive, Fiberstreamagreement | [12 empty] | 0¦i3czqf: | [7 empty] | 9.2234e+18 | [19 empty] | November 15th - Hydro Permit granted. City Permit to be submitted soon. Mar 15/23 - Build was moved to 2026 due to a moratorium as per Troy Browne Jul 26/23 - Project put on hold, will need to revisit when the moratorium ends. Feb 5, 2025 - Requires a site visit to determine the Moratorium situation. March 6, 2025 - Troy was able to obtain, SSA approval from Rogers, so we are putting this project back into In Progress, as it was on Hold. Adding it to the ON Net schedule for May 2025 March 10, 2025 - Troy has submitted the SSA to Rogers. Troy has been informed that Rogers has approved and we should receive the formal soon. March 14, 2025 - Locates Submitted March 19, 2025 - City Permit Notes: Comment From the city of Toronto: Since the Dovercourt Rd is under moratorium and your project is specifically on the road, we would have to refuse your application. The moratorium ends in 2026. | [6 empty] | 3 - Normal | [21 empty] | 2022-05-19 |  |  | 8 | 131 | Integration |  |  |  |  | https://buildings.beanfield.com/buildings/view/7360 |  | 500380 | 3 - Normal | 2023-06-02 | Toronto
BC Construction | BCCONST-488 | 9887 Whalley Blvd (Park Boulevard), Surrey BC | Condo | In Progress |  | Unresolved | John Thomson | Yawn Paular | Yawn Paular | 2023-11-16 17:28 |  | 2025-03-20 12:25 |  |  | 2025-06-27 | 0 | 0 |  |  | BCCONST-621, BCCONST-622, BCCONST-623, BCCONST-636, BCCONST-802, BCCONST-803, BCCONST-804, BCCONST-815, BCCONST-818, BCCONST-849, BCCONST-871, BCCONST-872, BCCONST-889 | BCCONST-487, BCCONST-485, BCCONST-486 | 419 units 41 flrs EPS7405 Rancho Mgmt - 604-684-4508 Contact: Gus Ramirez [GRamirez@ranchogroup.com¦mailto:GRamirez@ranchogroup.com] Site Contact: Eric Ray 778-875-7606 eray@rservice.ca | Budget_Allocated | [12 empty] | 0¦i4g8q7: | [7 empty] | 9.2234e+18 | [19 empty] | Feb 18th - ISP work has started. OSP work has been pencilled in for 1st week of March Feb 6th - Checked EMT build, confirmed end to end. Jan 28 - LayerOne started EMT conduit work | [6 empty] | 3 - Normal | [24 empty] | 41 | 419 | [11 empty] | 69100 | 61000
Construction | CONST-35778 | 120 Varna Dr, North York - Yorkdale Condos Phase II | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Olawale Olaniyan [X] | 2023-11-21 10:58 |  | 2025-03-21 08:52 |  |  | 2025-09-23 | 0 | 1 |  |  | CONST-35779, CONST-35780, CONST-40405, CONST-40406, CONST-40410, CONST-40411, CONST-40412, CONST-40413, CONST-40414, CONST-40415, CONST-40416, CONST-40417, CONST-40418, CONST-40419, CONST-40420, CONST-40421 | CONST-40402, CONST-17429 | Hi Please see attached the agreement and CA approved form and budget for 120 Varna. Please note the connected building, 160 Flemington/1 Leila has not been signed yet. MDU Address: *120 Varna Dr* City: *North York* Building Name: *The Yorkdale Condos II* # of Units: *306* # of Floors: *15* Building Constructed Year: *2022* PM Contact Name: *Ismail Pathan (Goldview Management)* PM Contact #: *416-782-1313* PM Email Address: [manager.yorkdalecondo@gmail.com¦mailto:manager.yorkdalecondo@gmail.com] Type of Contract (Fibre agreement or NUA & MA): *Access + Marketing* Building linked to other Buildings: *Yes - 160 Flemington Rd* Bulk Related: *No* [https://buildings.beanfield.com/buildings/view/7765] Requested by Oliver Davies, When you have a moment, can you please proceed with creating a new OSP plan and Site Walk ticket for 120 Varna Dr “The Yorkdale Condos Phase II”? This location connects to Phase I at 160 Flemington Rd. A site walk was previously completed there in late 2020 (CONST-17429). We should now be capable of feeding these buildings via the 960 Lawrence Ave W NPOP. Phase I = 314 units Phase II = 306 units PM Info: Ismail Pathan ¦ On-Site Condominium Manager TSCC 2937 ¦ 120 Varna Drive, North York, M6A 0B3 {*}T{*}: 416-782-1313 {*}E{*}: [manager.yorkdalecondo@gmail.com¦mailto:manager.yorkdalecondo@gmail.com] Thank you, | NUA+MA | [12 empty] | 0¦i4ggyn: | [7 empty] | 9.2234e+18 | [19 empty] | constructed in 2022, Might be connected with 106 Varna Dr, 217 Ranee Ave March 19, 2025 - Ca approved FTTB-01005, Dated feb 6, 2025 (Revised $$ are being applied) and signed Agreements received they are dated Feb 4, 2025. March 20, 2025 - Please note this 120 Varna Dr, is link to 160 Flemington / 1 Leila, these agreements have not been signed as of yet. March 21, 2025- Scheduling on the On Net tracker for Sept 23, 2025. 2 factors, that may change this due date are 1) the site visit which will determine the permits required to bring the feed into the building, 2nd factor is the status of the agreement for 160 Flemington. March 21, 2025 - SAP Budget created, Condo logged on the Financial Capex tracker, Condo and Restoration budget from Ca is logged on the Resto tracker 2027. March 21, 2027 - General Task codes created (Riser, Splicing), will create permit and construction task, after site visit is completed. | [6 empty] | 3 - Normal | [21 empty] | 2025-03-19 |  |  | 15 | 306 | [5 empty] | https://buildings.beanfield.com/buildings/view/18351 |  | CONST-35778 | 3 - Normal | 2025-09-23 | North York
Construction | CONST-40424 | 2 Aberfoyle Cres, Etobicoke, Town & Country II | Condo | In Progress |  | Unresolved | Unassigned | Lorna Kurok | Lorna Kurok | 2025-03-21 09:34 | 2025-03-31 09:58 | 2025-03-21 13:57 |  |  | 2025-11-21 | 0 | 1 |  |  | CONST-40425, CONST-40426, CONST-40427, CONST-40428, CONST-40429, CONST-40430, CONST-40431, CONST-40432, CONST-40433, CONST-40434, CONST-40435, CONST-40436, CONST-40437, CONST-40438, CONST-40440 |  | Building Constructed Year: 2001 Aerial Feed. *+PM informations as of March 19, 2025:+* PM Contact Name: Alina Nima (FS Residential) PM Contact #: 416-233-9995 PM Email Address: [alina.nima@fsresidential.com¦mailto:alina.nima@fsresidential.com] Please see attached approved CA form and agreement. MDU Address: *2 Aberfoyle Cres* City: *Etobicoke* Building Name: *Town & Country II* # of Units: *116* # of Floors: *12* Building Constructed Year: *2001* PM Contact Name: *Alina Nima (FS Residential)* PM Contact #: *416-233-9995* PM Email Address: [alina.nima@fsresidential.com¦mailto:alina.nima@fsresidential.com] Type of Contract (Fibre agreement or NUA & MA): *Access + Marketing* Building linked to other Buildings: *1 Lomond Dr* Bulk Related: *No* [https://buildings.beanfield.com/buildings/view/16543] | NUA+MA | [12 empty] | 0¦i5ls1j: | [7 empty] | 9.2234e+18 | [19 empty] | March 19, 2025 - Ca budget approved FTTB-00134, March 7, 2025, (Aerial) $40,080.00, Agreements signed March 4, 2025, Effective date March 31, 2025, Term 10 years March 19, 2025 - This Building is linked to 1 Lomond Dr, there is no existing ticket for this location.March 21, 2025 - Budget Added to SAP, Project added to Financial Capex tracker, Project is aerial, therefore there is no restoration budget, but it is listed on the Rest 2027 tracker, incase design changes. March 21, 2025 - The general sub task (Riser, Splicing, Financial) have been created because we have signed agreements and approved budget. Permit and Construction sub task will created upon the completion of the site visit. | [6 empty] | 3 - Normal | [21 empty] | 2025-03-19 |  |  | 12 | 116 | [5 empty] | https://buildings.beanfield.com/buildings/view/16543 |  | CONST-40424 | 3 - Normal | 2025-11-21 | Etobicoke
Construction | CONST-37677 | 108 Peter St , Toronto - Peter & Adelaide | Condo | In Progress |  | Unresolved | Lorna Kurok | Lorna Kurok | Harvey Tran | 2024-06-10 12:29 |  | 2025-03-13 14:50 |  |  | 2025-06-24 | 0 | 1 | _thumb_1123365.png |  | CONST-37678, CONST-37679, CONST-37712, CONST-39754, CONST-39755, CONST-39756, CONST-39757, CONST-39758, CONST-39759, CONST-39760, CONST-39761, CONST-39762, CONST-39763, CONST-39764, CONST-39765, CONST-39766, CONST-39767, CONST-39768, CONST-39769, CONST-39770, CONST-39771, CONST-39943, CONST-40444 |  | h3. {color:#00875a}PM Contact Information January 20, 2025:{color} PM Contact Name: *Erlis Lleshi* PM Contact #: *416-979-3375* PM Email Address: [peteradelaide.pm@delcondo.com¦mailto:peteradelaide.pm@delcondo.com] MDU Address: *102 - 108 Peter St & 350 Adelaide St W* City: *Toronto* Building Name: *Peter & Adelaide Condos* # of Units: *696* # of Floors: *47* Building Constructed Year: *2024* PM Contact Name: *Erlis Lleshi* PM Contact #: *416-979-3375* PM Email Address: [peteradelaide.pm@delcondo.com¦mailto:peteradelaide.pm@delcondo.com] Type of Contract (Fibre agreement or NUA & MA): *NUA & MA* Building linked to other Buildings: *N/A* Bulk Related: *N/A* [https://buildings.beanfield.com/buildings/view/4618] Requested by Oliver Davies. Could you please proceed with queuing up a new OSP plan & Site Walk for the new Peter & Adelaide Condos located at 102 & 108 Peter St / 350 Adelaide St W? I believe a new BFMH was just installed at this intersection which should make this project much easier. There are 696 residential units in this building. BB Link: [https://buildings.beanfield.com/buildings/view/4618] PM Info: *Erlis Lleshi, OLCM* Condominium Manager *Agents for and on behalf of:* *Peter & Adelaide Condos - TSCC No. 3008,* *108 Peter Street, Toronto ON, M5V 0W2* *Phone:* *416.979.3375* *Email:* [PeterAdelaide.PM@DelCondo.com¦mailto:PeterAdelaide.PM@DelCondo.com] | NUA+MA | [12 empty] | 0¦i4xjen: | [7 empty] | 9.2234e+18 | [19 empty] | January 20, 2025, Ca Approved FTTB-00744 Dec 18, 2024, Agreements signed January 20, 2025 - Conduit Build Sketch Note we have recd the electrical drawing and are attached. These will be used as a tool to create conduit build sketch and the riser diagram. January 21, 2025 - OSP Team would like to priortize this one as it is only a Duct Pull and we hope to get it on ON NET ASAP. Feb 4, 2025 - Conduit build sketch -drawing complete. we will need to build roughly 20m of conduit to the comm room. 8ft ladder will be required for this build. Feb 4, 2025 - Riser Diagram has been added. Feb 4, 2025 - Route drawing has been completed Feb 14, 2025 - Riser PanelsInstalled backboard on 21st floor panels. Dressed rest of the 7 panels, pictures are attached. All of the panels are prepped Finished rest of the in betweens.Pulled both sides of cables to pop. Installed fire rated backboard in POP. Dressed POP cables, pictures are attached. Feb 21 2025 - There is a potential Commercial Customer looking for connectivity at 102 Peter St, on the 2 nd floor (GroceryStore). March 10, 2025 - Manhole Surveys have been completed March 12, 2025 - Panel Prep 7 of 14 panels prepped and spliced March 13, 2025 - Hydro permit Submitted | [6 empty] | 3 - Normal | [21 empty] | 2025-01-20 |  |  | 47 | 696 | [5 empty] | https://buildings.beanfield.com/buildings/view/4618 |  | CONST-37677 | 3 - Normal |  | Toronto
Construction | CONST-39520 | 2175 Keele St_Municipal Address 85 - 165 Canon Jackson Drive, Phase 2, Toronto | Condo | In Progress |  | Unresolved | Unassigned | Lorna Kurok | Lorna Kurok | 2024-12-18 08:49 |  | 2025-03-12 09:22 |  |  | 2025-03-11 | 0 | 1 |  |  | CONST-39521, CONST-39522, CONST-39523, CONST-39524, CONST-39525, CONST-39526, CONST-39527, CONST-39528, CONST-39529, CONST-39530, CONST-39531, CONST-39532, CONST-39533, CONST-39534, CONST-39535, CONST-39536, CONST-39537, CONST-39556, CONST-40210, CONST-40211, CONST-40247, CONST-40519 | CONST-35824 | Daniel's FirstHome Keelesdale (Phase 2) December 17, 2024_Can we get a ticket set up with subtasks for Phase 2, 85-165 Cannon Jackson. Can you link it with Phase 1 ticket ¦{color:#403294}*Update PM Information as of December 13, 2024*{color}:¦ *Saba Farokh* Condominium Manager ,M.A., B.A., OLCM-LL *GPM Property Management Inc.* 242 Applewood Crescent ¦ Unit 5 ¦ Concord ¦ Ontario ¦ L4K 4E5 # 905.669.0222 [keelesdalemanager@gpmmanagement.com¦mailto:keelesdalemanager@gpmmanagement.com]¦ [sabaf@gpmmanagement.com¦mailto:sabaf@gpmmanagement.com] | NUA+MA | [12 empty] | 0¦i5eq93: | [7 empty] | 9.2234e+18 | [19 empty] | Dec 17, 2024 - Phase 2 agreement has been signed. Jan 21, 2025 - Locates are in, UG construction is being scheduled for Mid February. Jan 21, 2025 - Change in On Net date, Condo being moved up in the schedule from April to March 2025 Jan 27, 2025 - Riser Panel notes: All of the panels are installed except some of them needs backboard details. Feb 14, 2025 - ISP Splicing - All trays spliced to corresponding pigtails with 6F.All trays labeled accordingly. OSP tray prepped and ready for when the cable is pulled in. XCs not installed March 4, 2025 - ISP splicing is completed March 4, 2025 - Updated On Net date from the march 7 to the march 12, to align with the date planned end date indicated by splicing. March 10, 2025, Updated Due date to March 21, 2025. to reflect the OTDR planned end date. March 12, 2025 - Building was put On Net. No city permit for this ticket. But city permit is in linked ticket. | [6 empty] | 3 - Normal | [20 empty] | 2025-03-12 | 2024-12-18 |  |  | 3 | 208 |  | 2025-03-11 |  |  |  | https://buildings.beanfield.com/buildings/view/21005 |  | CONST-35824 (sub) | 3 - Normal |  | Toronto
Construction | CONST-40330 | 105 George Appleton Way, North York, Independence Way | Condo | In Progress |  | Unresolved | Unassigned | Lorna Kurok | Lorna Kurok | 2025-03-14 09:06 |  | 2025-03-17 11:07 |  |  | 2025-08-21 | 0 | 1 |  |  | CONST-40363 | CONST-29393, CONST-40331, CONST-40332, CONST-40333, CONST-40334, CONST-40335, CONST-40336 | George Appleton Cluster 105 George Appleton Way Suites 24 Cluster Units 244 Floors 21 Building Year 2013 | FSactive, FibreStream, GeorgeAppletonCluster, Migration | [12 empty] | 0¦i5l6an: | [7 empty] | 9.2234e+18 | [19 empty] | March 11, 2025 - George Appleton Way Cluster Approved. Migration from FS to BF. | [6 empty] | 3 - Normal | [21 empty] | 2025-03-11 |  |  | 21 | 24 | Integration |  |  |  |  | https://buildings.beanfield.com/buildings/view/15582 |  |  | 3 - Normal | 2025-08-21 | North York
Construction | CONST-40333 | 65 George Appleton Way, North York, Independence Way | Condo | In Progress |  | Unresolved | Unassigned | Lorna Kurok | Lorna Kurok | 2025-03-14 09:53 |  | 2025-03-17 12:25 |  |  | 2025-08-21 | 0 | 1 |  |  | CONST-40367 | CONST-29393, CONST-40330, CONST-40331, CONST-40332, CONST-40334, CONST-40335, CONST-40336, CONST-29402 | Building Constructed in 2006 65 George Appleton Way - 40 Units Cluster Units 244 | FSactive, Fibrestream, GeorgeAppletonCluster, Migration | [12 empty] | 0¦i5l6l3: | [7 empty] | 9.2234e+18 | [19 empty] | March 11, 2025 - George Appleton Way Cluster Approved. Migration from FS to BF. March 17, 2025 - Applied to the On Net schedule for August 21, 2025. | [6 empty] | 3 - Normal | [21 empty] | 2025-03-11 |  |  |  | 40 | Integration |  |  |  |  | https://buildings.beanfield.com/buildings/view/15582 |  | CONST-40330(SUB) | 3 - Normal | 2025-08-21 | North York
Construction | CONST-40332 | 55 George Appleton Way, North York, Independence Way | Condo | In Progress |  | Unresolved | Unassigned | Lorna Kurok | Lorna Kurok | 2025-03-14 09:46 |  | 2025-03-17 12:23 |  |  | 2025-08-21 | 0 | 1 |  |  | CONST-40366 | CONST-29393, CONST-40330, CONST-40331, CONST-40333, CONST-40334, CONST-40335, CONST-40336, CONST-29402 | Building Constructed in 2006 55 George Appleton Way Unit 36 Cluster Units 244 | FSactive, Fibrestream, GeorgeAppletonCluster, Migration | [12 empty] | 0¦i5l6jr: | [7 empty] | 9.2234e+18 | [19 empty] | March 11, 2025 - George Appleton Way Cluster Approved. Migration from FS to BF March 17, 2025 - Applied to the On Net schedule for August 21, 2025. | [6 empty] | 3 - Normal | [21 empty] | 2025-03-11 |  |  |  | 36 | Integration |  |  |  |  | https://buildings.beanfield.com/buildings/view/15582 |  | CONST-40330(SUB) | 3 - Normal | 2025-08-21 | North York
Construction | CONST-40343 | 55 Lombard St, 80 Adelaide St E, Toronto, The Bentley (BULK) | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Lorna Kurok | 2025-03-14 12:01 |  | 2025-03-26 13:31 |  |  | 2025-09-18 | 0 | 1 |  |  | CONST-40344, CONST-40346, CONST-40347, CONST-40348, CONST-40349, CONST-40350, CONST-40351, CONST-40352, CONST-40353, CONST-40354, CONST-40355, CONST-40356, CONST-40357, CONST-40358, CONST-40359, CONST-40372, CONST-40373, CONST-40374, CONST-40441 | CONST-35437 | MDU Address: 55 Lombard St, 80 Adelaide St E City:Toronto Building Name: *The Bentley* # of Units: *77* # of Floors: *6* Building Constructed Year: *1982* PM Contact Name:David Martins *(Brilliant)* PM Contact #: *416-363-4297* PM Email Address: *_[manager@thebentley.ca¦mailto:manager@thebentley.ca]_* Type of Contract (Fibre agreement or NUA & MA): *Access + Bulk Agreement* Building linked to other Buildings:n/a Bulk Related: *Yes* *Building Browser link:* [https://buildings.beanfield.com/buildings/view/3015] (55 Lombard St) 61 units [https://buildings.beanfield.com/buildings/view/4060] (80 Adelaide St E) 16 units | BulkDeal, NUA+Bulk, Rewire | [12 empty] | 0¦i5l7f3: | [7 empty] | 9.2234e+18 | [19 empty] | March 14, 2025_Project approved. Access agreement and Bulk service agreement signed March 13, 2025 March 17, 2025- Site Notes_Budget has been added, We will first try and pull from our BFMH0065 and into the building via the vault, if this is note possible then a 25m trench will be needed. March 21, 2025 - 55 Lombard MUST ON NET OCT 1ST, 2025, the Rogers services will be disconnected On November 1st. 2025 March 26, 2025 - Rewire issued to Solutions401 | [6 empty] | 3 - Normal | [21 empty] | 2025-03-14 |  |  | 6 | 77 | [5 empty] | https://buildings.beanfield.com/buildings/view/3015 |  | CONST-40343 | 1 - Very High | 2025-09-18 | Toronto
Construction | CONST-27237 | 200 Manitoba St, Etobicoke - Mystic Pointe - Skylofts Ⅱ | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Harvey Tran | 2022-03-09 14:51 |  | 2025-03-27 11:17 |  |  | 2025-05-29 | 0 | 0 | _thumb_1123883.png _thumb_1123884.png |  | CONST-27414, CONST-27415, CONST-29731, CONST-37976, CONST-38060, CONST-39266, CONST-39267, CONST-39268, CONST-39269, CONST-39270, CONST-39271, CONST-39272, CONST-39273, CONST-39274, CONST-39275, CONST-39432, CONST-39433, CONST-39562, CONST-39727 | CONST-27231, CONST-27235, CONST-33547, CONST-35974, CONST-38015, CONST-38017, CONST-38018, CONST-27238 | ¦[James Fox¦https://tickets.beanfield.com/secure/ViewProfile.jspa?name=jfox] ¦ ¦*Simone (New PM as of November 27, 2024.)*¦ ¦-Jennifer Milligan.(Old PM infor)-¦ ¦Assistant Property Manager¦ ¦Mareka Properties Ltd. 2000 Ltd¦ ¦278 Manitoba Street¦ ¦Etobicoke, Ontario M8Y 4G9¦ ¦Tel: (416) 255 7300 Ext. 225 Fax: (416) 255-7722¦ ¦[mysticpointe@marekapm.com¦mailto:mysticpointe@marekapm.com]¦ Units 206 | Fiberstreamagreement, HumberBay | [12 empty] | 0¦i393i7: | [7 empty] | 9.2234e+18 | [19 empty] | Jan 03/24 - This is "On-Hold" because the backbone CONST-35974 budget is still pending Backbone budget approved Jan 6, 2025_Meeting Notes_ projects are moving well so we are moving these up in the schedule from July 2025 to May 2025 Jan 15, 2025_Cable Pull DRAWING ready January 21, 2025 - John M. emailed property manager for Scheduling. January 27, 2025 - still trying to reach the PM of the condo. January 31, 2025 - Still waiting for access from Condo Feb 10, 2025 _ Condo PM note: James Fox, spoke with the PM Simone this morning(feb 10). She has a meeting with the board this evening at 6pm(feb 10) and doesn't want to move forward before she has their blessing.I have a follow up call with her scheduled for tomorrow. March 6, 2025 Build Blocked by Condo Board_ Board meeting is on March 10, 2025 March 12, 2025 Still blocked by Condo Board, we are still attempting to negotiate approval | [6 empty] | 3 - Normal | [21 empty] | 2024-07-17 |  |  | 6 | 206 | [5 empty] | https://buildings.beanfield.com/buildings/view/4443 |  | CONST-27237 | 3 - Normal |  | Etobicoke
Construction | CONST-40494 | 17 Kenaston Gardens, North York, NY Place Condos | Condo | In Progress |  | Unresolved | Unassigned | Lorna Kurok | Lorna Kurok | 2025-03-26 11:10 |  | 2025-03-27 11:48 |  |  | 2025-06-17 | 0 | 1 |  |  | CONST-40495, CONST-40496, CONST-40497, CONST-40498, CONST-40499, CONST-40500, CONST-40501, CONST-40502, CONST-40503, CONST-40504, CONST-40505, CONST-40506, CONST-40507, CONST-40508, CONST-40509, CONST-40512, CONST-40521, CONST-40522, CONST-40523, CONST-40524 |  | *PM information as of March 26, 2025:* PM Contact Name: *Lee Boros (Performance PM)* PM Contact #: *416.645.3755 x512* PM Email Address: [lee@performancepm.com¦mailto:lee@performancepm.com] MDU Address: *17 Kenaston Gardens* City: *North York* Building Name: *NY Place Condos* # of Units: *135* # of Floors: *8* Building Constructed Year: *2012* PM Contact Name: *Lee Boros (Performance PM)* PM Contact #: *416.645.3755 x512* PM Email Address: [lee@performancepm.com¦mailto:lee@performancepm.com] Type of Contract (Fibre agreement or NUA & MA): *Access + Marketing* Building linked to other Buildings: *N/A* Bulk Related: *No* [https://buildings.beanfield.com/buildings/view/4756] | NUA+MA | [12 empty] | 0¦i5m72f: | [7 empty] | 9.2234e+18 | [19 empty] | March 26, 2025 - CA Budget approved and signed agreements attached. March 26, 2025 - Ca budget added SAP, Project has been added to the Financial tracker. CA restoration budget has been added to Restoration tracker 2027. March 27, 2025 - Meeting with James, this will be a Small Short stream City Permit, therefore we moved it up from September 30, 2025 to June 17, 2025. If the project moves will, and the permit is recd, we might move it up to May. March 27, 2025 - Site visit is scheduled for April 1, 2025. | [6 empty] | 3 - Normal | [21 empty] | 2025-03-26 |  |  | 8 | 135 | [5 empty] | https://buildings.beanfield.com/buildings/view/4756 |  | CONST-40494 | 3 - Normal | 2025-09-30 | North York
Construction | CONST-27459 | 16 Brookers Lane, Toronto - Nautilus at Waterfront | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Harvey Tran | 2022-03-28 08:01 |  | 2025-03-27 12:29 |  |  | 2025-04-25 | 0 | 2 |  |  | CONST-27460, CONST-27461, CONST-27656, CONST-27657, CONST-27658, CONST-27659, CONST-27660, CONST-27661, CONST-27662, CONST-27663, CONST-27664, CONST-27665, CONST-27666, CONST-27667, CONST-29020, CONST-39865, CONST-39866, CONST-39867, CONST-39869, CONST-40116, CONST-40154, CONST-40188 | CONST-27170, CONST-27183, CONST-27184, CONST-33745 | Constructed in 2012 [16 Brookers Lane¦https://www.southetobicokecondo.com/16-brookers-lane-nautilus-condos] Property Management Phone Number: *647-350-2755* | FSactive, Fiberstreamagreement | [12 empty] | 0¦i3aefz: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2012 June 28th - City permit is still pending due to the City's decision is not confirmed. ON HOLD DUE TO UNASSUMED ROADS. January 22, 2025 - Condo Approved email sent from Luke Baxter. January 30, 2025 - On Net Change, Moved from Sept to April, Short stream permit will not take as long to put on Net. Est Scope before Design 25m Feb 8, 2025- City Permit was submitted to the City of Toronto Feb 17, 2025 - City Permit is Granted. Feb 26, 2026 - Spoke with property manager. She informed that the agreement indicates, that we need Board approval. She asked that I send over the agreement, and I also supplied her with the tentative dates which we will not likely have approval for as there is not enough time to approach the board. I also provided city permit, drawings, picture an conduit sketch. Feb 28, 2025 - Not able to move project up, need condo board approval Condo Board meeting is March 25, 2025. March 25, 2025 - James emailed the PM, to determine if we can schedule this for April. Pm replied, "The information provided is with the TSCC 2264 Board of Directors. Once they decide if the construction is approved or not, I will get back to you." Waiting on Condo Board of Directors for approval. We may have to move this. Will determine next week. | [6 empty] | 3 - Normal | [21 empty] | 2025-01-22 |  |  | 39 | 389 | Integration |  | 35485 |  |  | https://buildings.beanfield.com/buildings/view/1743 |  | CONST-27459 | 3 - Normal | 2025-09-01 | Toronto | 4395 | 13260
BC Construction | BCCONST-704 | 13573 98A Avenue, Surrey BC (Century Holland Park) | Condo | In Progress |  | Unresolved | John Thomson | Yawn Paular | Yawn Paular | 2024-05-28 16:44 |  | 2025-03-25 20:08 |  |  | 2025-08-01 | 0 | 0 |  |  | BCCONST-705, BCCONST-706, BCCONST-707, BCCONST-886, BCCONST-887, BCCONST-894, BCCONST-895, BCCONST-904 |  | Phase 2 Building next to Century City Century City Ph 2 bldgs - Sep 2025 Occupancy Date - no CRUs AWM - Ph2 condo 409 units, 39 flrs DUNCAN JORDAN Senior Superintendent C 604.830.3843 h3. duncan.jordan@bluecity.ca BlueCity Construction 604.270.1889 [www.BlueCity.ca¦http://www.bluecity.ca/] | Budget_Allocated | [12 empty] | 0¦i4wczz: | [7 empty] | 9.2234e+18 | [19 empty] | Jan 10 - With Luke and Steven for CA creation and approval. Will be the first priority to possibly meet occupancy date Feb 19 - Josh has meeting with Jeremy Feb 21st | [6 empty] | 3 - Normal | [23 empty] | 2025-09-01 |  | 409 | [10 empty] | Surrey | 17700 | 17600
Construction | CONST-28414 | 832 Bay St, Toronto | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Harvey Tran | 2022-05-16 13:37 |  | 2025-03-26 07:40 |  |  | 2025-04-16 | 0 | 1 |  |  | CONST-28415, CONST-28416, CONST-28629, CONST-38419, CONST-38422, CONST-38423, CONST-38426, CONST-38427, CONST-38428, CONST-38429, CONST-38430, CONST-38431, CONST-38432, CONST-38434, CONST-38435, CONST-38436, CONST-38437, CONST-38438, CONST-38439, CONST-38923, CONST-38924, CONST-39078, CONST-39079, CONST-39363, CONST-39569, CONST-39833, CONST-40252 |  | PM Info: _Denajda Dhrimaj O.L.C.M.¦ ** Condominium Manager *¦* DUKA Property Management Inc._ _As Agents for and on Behalf of T.S.C.C. No. 2278_ _832 Bay Street, Suite # 219, Toronto, ON M5S 1Z6_ _Tel: 416.353.4764_ _[Burano.cm@dukamanagement.com¦mailto:Burano.cm@dukamanagement.com]_ | Bolton, NUA+MA | [12 empty] | 0¦i3dqr3: | [7 empty] | 9.2234e+18 | [19 empty] | Sept 11, 2024_Agreement is now signed and ready to proceed. Sept 12, 2024_Scheduling On-Net due for March 2025 Sept 12, 2024_Construction to be completed by Bolton Construction Nov 8, 2024_ Route drawing is ready. Dec 19, 2024 - Panel Prepped and Spliced Feb 6, 2025 - Conduit Build Sketch completed. March 19, 2025 - Cable Pull is scheduled for March 26. March 19, 2025 - Splicing is being issued to Litewave due to the multiple Hydro CCs Kevin has requested quote. March 19, 2025 - Conduit build scheduled for March 19 to 20. March 20, 2025 - conduit build completed pictures attached. March 25, 2025 - All Manholes have been roped and distance confirmed, Cable pull will occur March 26, 2025. Then splicing will be required. | [6 empty] | 3 - Normal | [21 empty] | 2024-09-11 |  |  | 50 | 486 | [5 empty] | https://buildings.beanfield.com/buildings/view/2129 |  | CONST-28414 | 3 - Normal |  | Toronto
Construction | CONST-40382 | 300 Balliol Street, Toronto | Condo | In Progress |  | Unresolved | Unassigned | Lorna Kurok | Lorna Kurok | 2025-03-19 15:06 |  | 2025-03-26 07:38 |  |  | 2025-11-24 | 0 | 1 |  |  | CONST-40383, CONST-40384, CONST-40385, CONST-40386, CONST-40387, CONST-40388, CONST-40389, CONST-40390, CONST-40391, CONST-40392, CONST-40393, CONST-40394, CONST-40395, CONST-40396, CONST-40397 |  | Building Year: 1999 *PM contact information as of March 19, 2025:* PM Contact Name: Diana Zarafa (Goldview) PM Contact #: [(416) 630-1234¦https://www.google.com/search?q=goldview+property+management&rlz=1C5GCEM_enCA1115CA1115&oq=goldview&gs_lcrp=EgZjaHJvbWUqCggAEAAYyQMYgAQyCggAEAAYyQMYgAQyBggBEEUYOTIKCAIQABiSAxiABDIHCAMQABiABDIHCAQQABiABDIHCAUQABiABDIHCAYQABiABDIGCAcQRRg90gEIMTM3MWowajSoAgCwAgE&sourceid=chrome&ie=UTF-8#] PM Email Address: [diane@goldview.ca¦mailto:diane@goldview.ca] Good Afternoon Please see below details and attached agreements MDU Address: 300 Balliol St City: *Toronto* Building Name: *300 Balliol St condos* # of Units: *118* # of Floors: *9* Building Constructed Year: *1999* PM Contact Name: Diana Zarafa (Goldview) PM Contact #: [(416) 630-1234¦https://www.google.com/search?q=goldview+property+management&rlz=1C5GCEM_enCA1115CA1115&oq=goldview&gs_lcrp=EgZjaHJvbWUqCggAEAAYyQMYgAQyCggAEAAYyQMYgAQyBggBEEUYOTIKCAIQABiSAxiABDIHCAMQABiABDIHCAQQABiABDIHCAUQABiABDIHCAYQABiABDIGCAcQRRg90gEIMTM3MWowajSoAgCwAgE&sourceid=chrome&ie=UTF-8#] PM Email Address: [diane@goldview.ca¦mailto:diane@goldview.ca] Type of Contract (Fibre agreement or NUA & MA): *Access + Marketing* Building linked to other Buildings:n/a Bulk Related: *No* *Building Browser link:* [https://buildings.beanfield.com/buildings/view/3801] – ¦Luke Baxter¦ ¦_Sr. Director, Strategy & Planning_¦ ¦ ¦*Office: 416.532.1555*¦ | NUA+MA, Rewire | [12 empty] | 0¦i5lm8f: | [7 empty] | 9.2234e+18 | [19 empty] | March 19, 2025 - Condo approved Ca FTTB-01020, Dated March 14, 2025 and we has signed Access agreement, Dated March 11, 2025 and signed Marketing Agreement dated March 11, 2025 March 20, 2025 - Project added to Financial Capex tracker, Budget added to SAP, $40,340, Project has no restoration, but I did list it on the tracker. March 20, 2025 - Due to project having signed Agreements and approved budgets from the board, I am adding the general task tickets, (Riser, Splicing, Asbuilt), but I will add the other tickets (Permit, Construction, Conduit) when the High level budget is completed. March 20, 2025 - Approval Notes -Approval Note from Danny: This building will require a rewire due to the age of the building. We have received approval to build a new rewire team which is currently in motion. I'm sure this building will be pushed out till the end of the year, so we should have a team hired and working by then. Flag as Rewire. Changing due date from Sept 23, 2025(sep date 6months from approval date) to November 24, 2025 (November date reflection of additional work required-Rewire). March 25, 2025 - Requires Hydro Maps | [6 empty] | 3 - Normal | [24 empty] | 9 | 118 | [5 empty] | https://buildings.beanfield.com/buildings/view/3801 |  | CONST-40382 | 3 - Normal | 2025-09-23 | Toronto
Construction | CONST-33594 | 2772 Keele St, North York, The Max Condos | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Olawale Olaniyan [X] | 2023-04-06 12:16 |  | 2025-03-14 10:46 |  |  | 2025-06-16 | 0 | 0 |  |  | CONST-33595, CONST-33596, CONST-39889, CONST-39890, CONST-39891, CONST-39892, CONST-39893, CONST-39894, CONST-39895, CONST-39896, CONST-39897, CONST-39898, CONST-39899, CONST-39900, CONST-39901, CONST-39902, CONST-39903, CONST-39904, CONST-39905, CONST-39906, CONST-39922, CONST-39923, CONST-40511 |  | Approved at CAPEX meeting Wednesday, January 2025: MDU Address: *2772 Keele St* City: *North York* Building Name: *The Max Condos* # of Units: *140* # of Floors: *10* Building Constructed Year: *2007* PM Contact Name: *Nasrin Mir (Papak Management)* PM Contact #: *416-630-3020* PM Email Address: *[tscc1879.themax@papakmanagement.com¦mailto:tscc1879.themax@papakmanagement.com]* Type of Contract (Fibre agreement or NUA & MA): *Access + Marketing* Building linked to other Buildings: *No* Bulk Related: *No* [https://buildings.beanfield.com/buildings/view/18187] *Condominium Manager as of February 12, 2025:* Jam Haghi, OLCM-LL Condominium Manager, Papak Management Services Inc, the email address is the same as tscc1879.themax@papakmanagement.com Requested by Oliver Davies Can you please create a new ticket for an OSP plan & site walk at 2772 Keele St “The Max” Condos? *PM Info:* Phil [themax.pm@delcondo.com¦mailto:themax.pm@delcondo.com] 416.630.3020 Phil is on-site on Mondays until 12pm or Wednesdays all day. If Phil is unavailable, please contact Yassaman Assadi (Regional Manager - Del Condo) 416.917.2464 [yassadi@delcondo.com¦mailto:yassadi@delcondo.com] This location is directly south of 2800 Keele St ([https://buildings.beanfield.com/buildings/view/7610]) where a fibre build was just initiated. Thank you, | [13 empty] | 0¦i3ynhb: | [7 empty] | 9.2234e+18 | [19 empty] | June 06/23 - As per Oliver Davies, marked as Not a Candidate Jan 29, 2025 - Approval Email received Jan 29, 2025. Ca budget approved FTTB-00078, Date Jan 24, 2025, ($22,140.48) includes Laterial feed drawing. Applying a Due date of Aug 8, 2025 January 31, 2025 - Site Visit Note -we should consider starting from the GLB in front of the library and drilling south on the east side of Keele and cross Keele to the west when we get to 2772. Feb 12, 2025 - Access Request & Electrical Drawings- sent email request to access building for Riser Build on March 10, 2025 and to obtain P1 Electrical Drawings. PM responded that they only have hard copies of the drawings, which we can pick up at the building office anytime between 9am and 4pm daily. March 6, 2025 - Moved up on the On Net schedule, only city permit required. Was scheduled for Aug 2025 is now June 2025 March 12, 2025 Riser Panels - Installed remaining panels & dressed all the panels. Pictures are attached. March 14, 2025 Riser Fibre Pull, Riser Panels completed | [6 empty] | 3 - Normal | [21 empty] | 2025-01-29 |  |  | 10 | 140 | [5 empty] | https://buildings.beanfield.com/buildings/view/18187 |  | CONST-33594 | 3 - Normal | 2025-08-08 | North York
Construction | CONST-36665 | 15-35 Mercer St, Toronto - Nobu Residences | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Olawale Olaniyan [X] | 2024-02-28 10:53 | 2025-03-07 11:16 | 2025-03-26 14:46 |  |  | 2025-05-16 | 0 | 1 |  |  | CONST-36666, CONST-36667, CONST-39618, CONST-39619, CONST-39620, CONST-39621, CONST-39622, CONST-39623, CONST-39624, CONST-39625, CONST-39626, CONST-39627, CONST-39628, CONST-39629, CONST-39630, CONST-39631, CONST-39632, CONST-39633, CONST-39634, CONST-39635, CONST-39646, CONST-40260, CONST-40408 |  | Requested by Oliver Davies, When you have a moment, if you could also queue up a site walk for the new Nobu Residences at 15-35 Mercer St? There are 660 residential units and the board has just been elected. PM Info: Adam S. Rapp, R.C.M., O.L.C.M., General Licence. ¦ ¦ ¦_Senior Property Manager_ NOBU Residences Toronto 15-35 Mercer Street Toronto, ON M5V 1H2 CMRAO No 0007096314-GL¦ ¦ PM Office: 289-813-9486 Concierge: East: 416-526-9266, West: 416-951-7397 [noburesidences.pm@fhkipling.com¦mailto:noburesidences.pm@fhkipling.com]¦ Thanks! Below is the information from the CA Approved email_FTTB#00927 MDU Address: *15-35 Mercer St.* City: *Toronto* Building Name: *Nobu Residences* # of Units: *657* # of Floors: *45* Building Constructed Year: *2024* PM Contact Name: *Adam Rapp* PM Contact #: {*}289{*}{*}-813-9486{*} PM Email Address: [noburesidences.pm@fhkipling.com¦mailto:noburesidences.pm@fhkipling.com] Type of Contract (Fibre agreement or NUA & MA): *NUA & MA* Building linked to other Buildings: *N/A* Bulk Related: *N/A* [https://buildings.beanfield.com/buildings/view/16431] | NUA+MA | [12 empty] | 0¦i4ndnr: | [7 empty] | 9.2234e+18 | [19 empty] | Constructed in 2024 Jan 9, 2025_Ca approved_FTTB#00927, this project had an existing site visit. Missing Due date tab_. On Net Schedule due date is July 17, 2025 Jan 21, 2025 - Manhole survey required (this is a cable pull via the building vault, escort required. Please confirm connectivity to Hydro CC on Mercer) Jan 23, 2025_Route Drawing completed, Survey needs to be scheduled. Jan 31, 2025 - Manhole Survey Pay duty officer booked for feb 10 9:30am to 2:30 at Perer st and Wellington St W. Access vault not required. Feb 11, 2025_Moving project from July to May. February 12, 2025 - Condo Access for Riser Build. Sent email to Pm to request access for Monday March 10, 2025 and copies of the P1 Electrical drawings. PM responded and indicate the the site contact will be the Site-Superintendent and the Super name is Adam Formosa. Adam@fhgmaintenance.com Drawings were attached in the email. Emailed Super Feb 12 to confirm access on Feb 12, 2025. Adam Formosa Granted Beanfield access for March 10.2025. We asked to change the start date to Feb 20, 2025. Adam granted us permission to start on Feb 20, 2025 as of email feb 14, 2025. March 26, 2025 - Hydro permit is granted. | [6 empty] | 3 - Normal | [21 empty] | 2025-01-09 |  |  | 45 | 657 | [5 empty] | https://buildings.beanfield.com/buildings/view/16431 |  | Const-36665 | 3 - Normal |  | Toronto
Montreal Construction | MTLCONST-10012 | Westbury 9 - 4955/5055 Courtrai – 2 phases, 12 stories + parking, +/- 330 units | Condo | In Progress |  | Unresolved | Marianne Yanni | Marianne Yanni | Marianne Yanni | 2024-04-29 14:16 |  | 2025-03-26 16:21 |  |  | 2026-07-17 | 0 | 1 |  |  | MTLCONST-10016, MTLCONST-10017, MTLCONST-10713, MTLCONST-10723, MTLCONST-10724, MTLCONST-10725, MTLCONST-10726, MTLCONST-10727, MTLCONST-10728, MTLCONST-10729, MTLCONST-10730, MTLCONST-10790, MTLCONST-10799 | PUR-44209, MTLCONST-10011, MTLCONST-10013 | *For materials : WBS-MTLCONST-10012-2* bulk-internet services - residential projects being constructed by Devwah. * *_Westbury 9 - 4955/5055 Courtrai – 2 phases, 12 stories + parking, +/- 330 units_* Estimated Construction Start Date : Demolition of the existing buildings began on Monday, January 6, 2025. Estimated First Occupancy Date : August 2026 Site / Project Manager contact from Devwah : Service entrance : David Brault, dbrault@devwah.com, 514-516-2723. Building : Davide Boemio, dboemio@devwah.com, 514-651-4570. | [13 empty] | 0¦i4swqf: | [7 empty] | 9.2234e+18 | [19 empty] | 2025.01.06 Agreement is signed. 2025.01.13 Project started 2025.01.20 The basement of the 2 phases will be done at the same time, then they will build the 2 towers in 2 phases.Preliminary timelines: 1st tour: End of 2025 - Beginning of 2026, 2nd tour Summer 2026. Cable and P3000 equipment should be available in fall 2025. Design request sent to Trigenex 2025.02.26 Permit requests sent to VL and Hydro. 2025.03.04 Hydro permits received. 2025.03.26 VL Permit receievd. MC requests sent | [6 empty] | 3 - Normal | [21 empty] | 2025-01-14 |  |  | 12 | 330 | Order |  | 43906.52 |  |  | https://buildings.beanfield.com/buildings/view/20187 |  | MTLCONST-10012 |  |  |  | 75243.55
Construction | CONST-38015 | 250 Manitoba St_Toronto_The Warehouse Lofts l Mystic Pointe | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Lorna Kurok | 2024-07-29 10:36 |  | 2025-03-26 21:40 |  |  | 2025-04-08 | 0 | 0 |  |  | CONST-27410, CONST-27411, CONST-37977, CONST-38016, CONST-39195, CONST-39337, CONST-39338, CONST-39339, CONST-39340, CONST-39341, CONST-39342, CONST-39343, CONST-39344, CONST-39345, CONST-39726 | CONST-27231, CONST-27235, CONST-27237, CONST-33547, CONST-35974, CONST-38017, CONST-38018, CONST-27238 | Units 151_250 Manitoba St July 29, 2024_250 Manitoba & 300 Manitoba was Orginal created March 9, 2022. They were on a combined parent ticket. The budget for both condos is combined. For future clairty the 250 Manitoba was moved to its own Parent ticket. *PM Informations as of November 27, 2024* Name: Kris Thomai email:[warehouselofts@crossbridgecs.com¦mailto:warehouselofts@crossbridgecs.com] phone number:416-252-5897 | Fiberstreamagreement | [12 empty] | 0¦i539k7: | [7 empty] | 9.2234e+18 | [19 empty] | Jan 6, 2025_Meeting Notes_ projects are moving well so we are moving these up in the schedule from July 2025 to May 2025 Jan 27, 2025 -Riser Panels - Installed all panel as per diagram except 5th( west North ca5) move to 7th floor Jan 27, 2025 - Riser Fiber Pull -At 300 and 250 Manitoba, we were only able to fish one riser. The remaining riser need a bigger fish due to the distances involved, ranging from 75m to 120m. Our fish is not long enough, Jan 31, 2025 - All panels are dressed an prepped and ready for splicing. Jan 31, 205 - Internal work almost completed March 10, 2025 - Condo being moved up in the schedule from May 14, 2025 to April 8, 2024. Backbone to be completed March 21, 2025, Condo splicing to be completed March 11, 2025 - ISP Splicing - All remaing work completed XC's installed ready for testing | [6 empty] | 3 - Normal | [21 empty] | 2024-07-29 |  |  | 8 | 151 | [5 empty] | https://buildings.beanfield.com/buildings/view/5792 |  | CONST-27235(sub) | 3 - Normal | 2025-07-14 | Etobicoke
Construction | CONST-37753 | 15 Valhalla Inn Rd, Etobicoke - One Valhalla | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Harvey Tran | 2024-06-19 11:13 |  | 2025-03-25 14:17 |  |  | 2025-05-22 | 0 | 0 |  |  | CONST-37756, CONST-37757, CONST-37836, CONST-39098, CONST-39237, CONST-39238, CONST-39239, CONST-39240, CONST-39241, CONST-39242, CONST-39243, CONST-39244, CONST-39245, CONST-39664, CONST-39665, CONST-39811, CONST-39812, CONST-39813, CONST-40258 | CONST-37569, CONST-37752, CONST-39666 | Requested by Oliver Davies. James recently completed a site walk & budget for 5 Valhalla Inn Rd (CONST-37569). This location shares a common parking level with 2x other MDUs. Can you please create Site Walk tickets for both of the following locations for James? The visit is already complete, but the tickets are needed so that the 2x additional budgets can be uploaded. 9 Valhalla Inn Rd (298 units): [https://buildings.beanfield.com/buildings/view/7536 ¦https://buildings.beanfield.com/buildings/view/7536] 1-15-27 Valhalla Inn Rd (284 units): [https://buildings.beanfield.com/buildings/view/3119] Please also link all 3x MDUs/Tickets together as these should be completed as a group. | NUA+MA | [12 empty] | 0¦i4y8cv: | [7 empty] | 9.2234e+18 | [19 empty] | January 13, 2025 - Riser panels Install all panels as per riser diagram January 19, 2025 - Riser panels - Dressed all panels January 19, 2025 - Riser Fiber Pull in progress January 24, 2025 - 1 Valhalla Riser has been completed, Townhome cables and Tie Cable require conduit January 28, 2025- On Net schedule change, moved project up May 2025 to April 2025. updated On Net Schedule, SAP and Jira. Feb 3, 2025 - Panel prep in progess 5 of 7 panels spliced, waiting on conduit. Feb 10, 2025 - Riser Fiber pull completed March 6, 2025 - Riser work Internal work is completed. March 14, 2025 - Moved On Net date from April 8 to April 25, expecting MTO permit March 31. March 25, 2025 - Moving building from April 25, 2025 to May 22, 2025. The MTO permit will increase the amount of time required to get approval for the Rodars at least 2 weeks. Therefore we are moving the date. | [6 empty] | 3 - Normal | [21 empty] | 2024-10-03 |  |  | 22 | 284 | [5 empty] | https://buildings.beanfield.com/buildings/view/3119 |  | CONST-37753 | 3 - Normal | 2025-05-21 | Etobicoke
Construction | CONST-37752 | 9 Valhalla Inn Rd, Etobicoke - Triumph at Valhalla | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Harvey Tran | 2024-06-19 11:13 |  | 2025-03-25 14:15 |  |  | 2025-05-22 | 0 | 0 |  |  | CONST-37754, CONST-37755, CONST-37837, CONST-39099, CONST-39204, CONST-39229, CONST-39230, CONST-39231, CONST-39232, CONST-39233, CONST-39234, CONST-39235, CONST-39236, CONST-39573, CONST-39666, CONST-39814, CONST-40257 | CONST-37569, CONST-37753 | Requested by Oliver Davies. James recently completed a site walk & budget for 5 Valhalla Inn Rd (CONST-37569). This location shares a common parking level with 2x other MDUs. Can you please create Site Walk tickets for both of the following locations for James? The visit is already complete, but the tickets are needed so that the 2x additional budgets can be uploaded. 9 Valhalla Inn Rd (298 units): [https://buildings.beanfield.com/buildings/view/7536 ¦https://buildings.beanfield.com/buildings/view/7536] 1-15-27 Valhalla Inn Rd (284 units): [https://buildings.beanfield.com/buildings/view/3119] Please also link all 3x MDUs/Tickets together as these should be completed as a group. | NUA+MA | [12 empty] | 0¦i4y8cn: | [7 empty] | 9.2234e+18 | [19 empty] | January 13, 2025_ Riser Panels Install all panels except for 16th floor, it requires a backboard. January 14, 2025 - Riser Fibre Pull In progress January 19, 2025 - Riser Panels - Dressed all panels January 28, 2025- On Net schedule change, moved project up May 2025 to April 2025. updated On Net Schedule, SAP and Jira. January 30, 2025 - Panel Prep - All panels prepped and Spliced Feb 10, 2025 - Riser Fibre Pull completed March 14, 2025 - Moved On Net date from April 8 to April 25, expecting MTO permit March 31. March 25, 2025 - Moving building from April 25, 2025 to May 22, 2025. The MTO permit will increase the amount of time required to get approval for the Rodars at least 2 weeks. Therefore we are moving the date. | [6 empty] | 3 - Normal | [21 empty] | 2024-10-03 |  |  | 29 | 298 | [5 empty] | https://buildings.beanfield.com/buildings/view/7536 |  | CONST-37752 | 3 - Normal | 2025-05-21 | Etobicoke
Construction | CONST-37569 | 5 Valhalla Inn Rd, Etobicoke | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Harvey Tran | 2024-05-30 13:10 |  | 2025-03-25 14:15 |  |  | 2025-05-22 | 0 | 1 | _thumb_1129515.png _thumb_1121324.png |  | CONST-37570, CONST-37571, CONST-38761, CONST-38762, CONST-39097, CONST-39216, CONST-39217, CONST-39218, CONST-39219, CONST-39220, CONST-39221, CONST-39222, CONST-39223, CONST-39224, CONST-39225, CONST-39226, CONST-39227, CONST-39228, CONST-39392, CONST-39729, CONST-39942, CONST-40256 | CONST-37752, CONST-37753 | Requested by Oliver Davies. Could you kindly queue up a new ticket for an OSP plan & Site Walk at 5 Valhalla Inn Rd? The "Thunderbird at One Valhalla" condos include 335 residential units. {color:#000000}CDSH13399 is nearby at Gibbs Rd & The East Mall.{color} BB Link: [https://buildings.beanfield.com/buildings/view/3933] Site Contact: *JAY MEHTA* Assistant Property Manager, OLCM-L {color:#58595b}Valhalla Towns and Condos 2645 Skymark Avenue ¦ Mississauga, ON L4W4H2{color} {color:#58595b}Direct 416.551.6051{color} [jay.mehta@fsresidential.com¦mailto:garima.bhatt@fsresidential.com] {color:#58595b}&{color} Rehana Haniff <[Rehana.Haniff@fsresidential.com¦mailto:Rehana.Haniff@fsresidential.com]> | NUA+MA | [12 empty] | 0¦i4wj1r: | [7 empty] | 9.2234e+18 | [19 empty] | Jan 13, 2025_ Riser Panel - Installed all panels Jan 13, 2025 _Riser Fibre Pull Roped run to pop distance is 75m + 10m Coil. Jan 20, 2025 - Riser fibre Pull - Pulled tie cable from p1 to 5th floor. Jan 21, 2025 - Need to prepare traffic planJanuary 28, 2025- On Net schedule change, moved project up May 2025 to April 2025. updated On Net Scehdule, SAP and Jira. Jan 31, 2025 - Panel prep - All remaining panels spliced. Feb 7, ISP Splicing In process work ready for when cable is pulled in. Feb 10, 2025 Riser Panel completed Feb 10, 2025 Riser Fibre Pull completed Feb 11, 2025 ISP Splicing In progress:All trays spliced to corresponding pigtails with 6F.All trays labeled accordingly.All work completed. XCs installed March 6, 2025 - Riser Fibre Pull completed, Riser Internal work is completed March 10, 2025 - MTO Permit is pending, all comments have been addressed and returned to MTO. Pending response March 14, 2025 - Moved On Net date from April 8 to April 25, expecting MTO permit March 31. March 14, 2025 - Locates completed. March 19, 2025 - OSP splicing is almost completed, once the cable pull is done, then it can be completed. March 25, 2025 - OSP Construction note:if we receive the MTO permit on March 31st, it will most likely take two weeks to arrange the closure/occupancy permits on-line with MTO. Our construction should take two weeks max. So if start April 14th, we should be done by April 25th (then will need to complete cable pull, splicing) March 25, 2025 - Moving building from April 25, 2025 to May 22, 2025. The MTO permit will increase the amount of time required to get approval for the Rodars at least 2 weeks. Therefore we are moving the date. | [6 empty] | 3 - Normal | [19 empty] | Internal |  | 2024-10-09 |  |  | 35 | 335 | [5 empty] | https://buildings.beanfield.com/buildings/view/3933 |  | CONST-37569 | 3 - Normal | 2025-05-21 | Etobicoke
Construction | CONST-38628 | 633 Bay St, Toronto, Horizon on Bay | Condo | In Progress |  | Unresolved | Lorna Kurok | Lorna Kurok | Lorna Kurok | 2024-09-24 13:24 |  | 2025-03-27 13:49 |  |  | 2025-10-22 | 0 | 0 |  |  | CONST-38629, CONST-38630, CONST-38631, CONST-40520, CONST-40525, CONST-40526, CONST-40528, CONST-40529, CONST-40530, CONST-40531, CONST-40532, CONST-40533, CONST-40534, CONST-40535, CONST-40536, CONST-40537, CONST-40538, CONST-40539, CONST-40540, CONST-40541, CONST-40542, CONST-40543 |  | Requested By Oliver Davies_Sep 24, 2024 Units 475 Floors 26 Constructed in 1987 PM info Updated January 17, 2025: *Val El Hadi. General License* *Senior Property Manager¦ City Sites Property Management Inc.* *Tel: 416-340-8439 x 3 ¦ Fax: 905-232-1270* *Email: +[velhadi@citysitespm.com¦mailto:velhadi@citysitespm.com]+* *633 Bay Street, Toronto. ON M5G 2G4* +*PM Information as of Sept 24, 2024:*+ Lucy Martins *[lmartins@citysitespm.com¦mailto:lmartins@citysitespm.com]* Hi Lorna, Can you please create a ticket with an OSP plan & site walk for 633 Bay St? The Horizon on Bay includes 475 units and was constructed in 1987. BB Link: [https://buildings.beanfield.com/buildings/view/1404] PM info: Lucy Martins [lmartins@citysitespm.com¦mailto:lmartins@citysitespm.com] Thank you, | NUA+MA, Rewire | [12 empty] | 0¦i57slz: | [7 empty] | 9.2234e+18 | [19 empty] | Sept 24, 2024_Site Walk email received. Jan 6, 2025 - Location just signed an agreement with Beanfield. Need to Review Conduit situation(to be done by Steve Buckley's team), may need a revisite. Jan 17, 2025 Pm information has been updated. March 26, 2025 - CA approved FTTB-71_ON_M5G_2025, dated March 26, 2025, Signed Upgrade Access agreement and Marketing agreement. March 27, 2025 - Project added to Financial Capex tracker. Project budget added to SAP. | [6 empty] | 3 - Normal | [19 empty] | Internal |  | 2025-03-26 |  |  | 26 | 475 | [5 empty] | https://buildings.beanfield.com/buildings/view/1404 |  | CONST-38628 | 3 - Normal | 2025-10-22 | Toronto
Construction | CONST-27231 | 155 Legion Rd_Toronto_iLofts | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Harvey Tran | 2022-03-09 14:17 |  | 2025-03-27 15:23 |  |  | 2025-04-10 | 0 | 1 | _thumb_1121752.png _thumb_1121753.png _thumb_1121754.png _thumb_1121758.png _thumb_1121759.png |  | CONST-27255, CONST-27256, CONST-30490, CONST-30491, CONST-30842, CONST-30843, CONST-30844, CONST-30845, CONST-30846, CONST-30847, CONST-30848, CONST-30849, CONST-30850, CONST-30851, CONST-30862, CONST-30863, CONST-30864, CONST-37940, CONST-39190, CONST-39324, CONST-39430, CONST-39561, CONST-39725 | CONST-27235, CONST-27237, CONST-33547, CONST-35974, CONST-38015, CONST-38017, CONST-38018, CONST-27238 | *PM information as of January 21, 2025:* Sylvia Dydyszko Condominium Manager 647-748-5757 [SDydyszko@mrcm.ca¦mailto:SDydyszko@mrcm.ca] | FSactive, Fiberstreamagreement, HumberBay | [12 empty] | 0¦i3938f: | [7 empty] | 9.2234e+18 | [19 empty] | November 11th - Project on hold. New backbone required. July 17, 2024_Project is Active and no longer on hold, New Backbone has been approved and in progress. Nov 18, 2024 - Riser Diagram completed for the 3 buildings Jan 6, 2025_Meeting Notes_ projects are moving well so we are moving these up in the schedule from July 2025 to May 2025. Feb 7, 2025 - We have been having issues with the Board at this location approving access for us to complete our work on-site. Feb 12, 2025 - OSP splicing in progress March 6, 2025 - Build Blocked by Board. March 10, 2025 - Agreement note. we have the go ahead to move forward with this work, I believe this is approval from the condo board. We can contact the PM to schedule the Riser work. Email sent to Pm to schedule riser build march 24, 2025. pending confirmation. March 10, 2025 - Moving project to the end of April from May. As sales gave us the go ahead to schedule work with the pm. Riser build to be completed, along with splicing. Pm was holding up this work. March 19, 2024 - Riser Build is scheduled with PM approval for March 24 to the 28. March 25, 2025 - OTDR / Ruby Testing - Test results have been added. March 25 2025- Riser Panel In process, installed 5 of 6 panels, need panel 21 inch backboard for panel 19. March 25, 2025 - Riser Fiber pull in progress, all remaining cable has been pulled. March 27, 2025 - Updated Due date to April 10, 2025 from April 29, 2025 as per On Net planned date. March 27, 2025 - Riser Panel In progress | [6 empty] | 3 - Normal | [21 empty] | 2022-09-14 |  |  | 27 | 254 |  |  | 51517 |  |  | https://buildings.beanfield.com/buildings/view/4020 |  | 500469 | 3 - Normal | 2025-07-31 | Etobicoke | 16683
Construction | CONST-33547 | 251 Manitoba St, Etobicoke | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Olawale Olaniyan [X] | 2023-03-31 08:33 |  | 2025-03-27 15:22 |  |  | 2025-04-14 | 0 | 1 |  |  | CONST-33548, CONST-33549, CONST-34294, CONST-37788, CONST-37789, CONST-37790, CONST-37791, CONST-37792, CONST-37793, CONST-37794, CONST-37889, CONST-37980, CONST-39189, CONST-39262, CONST-39263, CONST-39264, CONST-39265, CONST-39563, CONST-39728, CONST-40518 | CONST-27231, CONST-27235, CONST-27237, CONST-35974, CONST-38015, CONST-38018, CONST-27238 | Units 499 Requested by Oliver Davies Can you please create a ticket for an OSP Plan & Site Walk at 251 Manitoba St? This is a newly registered condo with 499 units. The buildings on Manitoba St / Legion Rd will require approval for backbone to be built, and it is costly. However, we will need to tackle these eventually, and this location would provide some additional buffer for the overhead costs associated with bringing fibre to this neighbourhood. +*New PM Info as of November 27, 2024:*+ *Name: Maggie WU* Email: [maggie.wu@fsresidential.com¦mailto:maggie.wu@fsresidential.com] Phone number: 647-868-8568 +*OLd PM Info:*+ *Aron Mats* Property Manager TSCC 2957- ** *Phoenix Condos* 251 Manitoba St, Toronto, ON. M8Y 0A7 Management Office: 647-438-3701 Concierge: 647-438-3700 Direct: 647-638-9733 Email [aron.mats@fsresidential.com¦mailto:aron.mats@fsresidential.com] +*Old PM Info:*+ *Jonilda Ibro* Condominium Manager 251 Manitoba Street Tel: 647.438.3701 #2383 Etobicoke, ON M8Y 0C7 [www.dukamanagement.com¦https://can01.safelinks.protection.outlook.com/?url=http%3A%2F%2Fwww.dukamanagement.com%2F&data=05%7C01%7Cfjuma%40empirecommunities.com%7Cc0beb473dff04f69077408da23aa7fdf%7C791f3cd25cdc4357ae9649bd9477d60a%7C0%7C0%7C637861512730293005%7CUnknown%7CTWFpbGZsb3d8eyJWIjoiMC4wLjAwMDAiLCJQIjoiV2luMzIiLCJBTiI6Ik1haWwiLCJXVCI6Mn0%3D%7C3000%7C%7C%7C&sdata=0jiDjTF009PC63PvdqZicy5Xd%2BtbsAsljpSUB0Mdp2U%3D&reserved=0] Email: _+{color:#800080}[phoenix.cm@dukamanagement.com¦mailto:phoenix.cm@dukamanagement.com]{color}+_ _++_ Thank you, | HumberBay, NUA+MA | [12 empty] | 0¦i3y8tz: | [7 empty] | 9.2234e+18 | [19 empty] | Jun 25th, 2024 - Project started. Design is in progress no permit required. We will schedule the cable pull and conduit build soon. Jan 6, 2025_Meeting Notes_ projects are moving well so we are moving these up in the schedule from July 2025 to May 2025. January 31, 2025 - Still waiting for access from Condo March 6, 2025 - OSP SOW has been uploaded March 10, 2025 - Signed agreement attached. March 17, 2025 - Riser Panel Note - All of the panels are installed as per riser diagram Except for 3 (requires backboard) March 18, 2025 - Construction completed. March 18, 2025 - Condo is being moved up in the schedule from May 14, 2025 to Mid April. The OSP construction completed, we only need to complete, the cable pull, and splicing. Also, the we have approval to work in the Condo from the Pm and we are working on the Riser builds. March 21, 2025 - Panel prep All of the panels are dressed and prepped, ready to Splice, Riser Fiber pull is completed March 25, 2025 - Panel prep note: All panels prepped and spliced March 26, 2025 - ISP Splicing - All trays spliced, OSP tray prepped and ready for when the cable is pulled in. March 27, 2026 Cable pull scheduled for March 28, 2025. | [6 empty] | 3 - Normal | [21 empty] | 2024-06-25 |  |  | 29 | 499 |  |  | 25028 |  |  | https://buildings.beanfield.com/buildings/view/16851 |  | CONST-33547 | 3 - Normal | 2025-07-14 | Etobicoke | 6427
BC Construction | BCCONST-479 | 13655 Fraser Highway (Hub Two), Surrey BC | Condo | In Progress |  | Unresolved | Yawn Paular | Yawn Paular | Yawn Paular | 2023-11-16 17:08 |  | 2025-03-27 18:11 |  |  | 2025-07-25 | 0 | 1 |  |  | BCCONST-672, BCCONST-673, BCCONST-674, BCCONST-883, BCCONST-891, BCCONST-893 | BCCONST-897, BCCONST-478 | EPS7632 300 units 29 flrs PM Contact Name: *Dominic Aikman Ext 6* PM Contact #: 604-914-2135 PM Email Address: [teamaikman@westcoastpm.ca¦mailto:teamaikman@westcoastpm.ca] [@Karanvir Singh¦mailto:KSingh@warringtonpci.com] (604-802-4147) - For all the building access (5) | Budget_Allocated, DES | [12 empty] | 0¦i4g8nb: | [7 empty] | 9.2234e+18 | [19 empty] | Feb 3 - BAA Approved, contacted Dominic left a message to setup a site check | [6 empty] | 3 - Normal | [24 empty] | 29 | 300 | Backbone | [9 empty] | Surrey
Construction | CONST-38108 | 1603 Eglinton Ave W, 66 & 78 Lanark Ave_York-Empire Midtown | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Lorna Kurok | 2024-08-12 08:50 | 2025-03-04 17:52 | 2025-03-28 08:39 |  |  | 2025-08-06 | 0 | 2 |  |  | CONST-38109, CONST-38110, CONST-38111, CONST-38676, CONST-39246, CONST-39247, CONST-39248, CONST-39249, CONST-39250, CONST-39251, CONST-39252, CONST-39253, CONST-39254, CONST-39255, CONST-39256, CONST-39257, CONST-39258, CONST-39259, CONST-39260, CONST-39261, CONST-39636, CONST-40448 | CONST-35795 | _{color:#172b4d}Requested by Oliver{color}_ *{color:#403294}Units 219 ofr 1603 Eglinton Ave W, 66 & 78 Lanark Ave{color}* {color:#172b4d}Units 219{color} {color:#172b4d}Floors 16{color} h3. {color:#0747a6}*Contact Information:*{color} PM Info: *Francis Dike (Dee Kay) ¦ General License ¦ OLCM* Condominium Manager *As Agents for and on behalf of TSCC 2819* 1603 Eglinton Ave W. York, ON, M6E 0A1 Tel: 416-551-0765 Fax: 416-551-0774 Concierge Phone: 416-551-0752 Email: [francis.dike@crossbridgecs.com¦mailto:francis.dike@crossbridgecs.com] Email: [empire.midtown@crossbridgecs.com¦mailto:empire.midtown@crossbridgecs.com] _{color:#00875a}*Opening Email:*{color}_ Could you please proceed with creating tickets for a new OSP plan & site walk at the "Empire Midtown" condos at 1603 Eglinton Ave W? This condo includes 219 residential units. I have been working on getting access approved here for the past 12 months, the PM had consistently denied our requests for a site walk / proposal, but after connecting with a board member recently, the PM just followed up to let me know that they have approved the addition of Beanfield at their meeting last night. Hopefully we can get a budget in place soon so that access to the building can be finalized. BB Link: [https://buildings.beanfield.com/buildings/view/9988] PM Info: *Francis Dike (Dee Kay) ¦ General License ¦ OLCM* Condominium Manager *As Agents for and on behalf of TSCC 2819* 1603 Eglinton Ave W. York, ON, M6E 0A1 Tel: 416-551-0765 Fax: 416-551-0774 Concierge Phone: 416-551-0752 Email: [francis.dike@crossbridgecs.com¦mailto:francis.dike@crossbridgecs.com] Email: [empire.midtown@crossbridgecs.com¦mailto:empire.midtown@crossbridgecs.com] | NUA+MA | [12 empty] | 0¦i54fq7: | [7 empty] | 9.2234e+18 | [19 empty] | Aug 9, 2024_Opening email received for Jira ticket. Ticket opened Aug 12, 2024. Aug 12, 2024_OSP plan completed Aug 12, 2024 Oct 4, 2024 - Agreement is signed, but we need to determine if a cable chamber needs to be added, James has requested Troy to look into if we use a Handwell? Under site visit. Jan 6, 2025_Meeting Notes Project requires Aerial permit and City permit, These permits have been outsourced to DFX and are in process. Jan 8, 2025 - City Permit This is with DFX to be sent out for circulation. Jan 20, 2025 - Locates requested(Submitted) from ontario one call. February 12, 2025 - Emailed PM to request access to build Risers and Electrical drawings. Riser build request date: March 3, 2025. PM has prefers Tuesday March 4th, 2025 and sent electrical drawings. Lorna confirmed this date. Feb 13, 2025 - Aerial Hydro Permit - Permit sent to reviewer. March 6, 2025 - Project moved up in the schedule, when permits are progressing well, dates can be moved up. It was August 2025 and moved to June 18, 2025. March 6, 2025 - after reflection on Troy note, that traditional the Hydro permit takes 6 months but only recently have experienced the 4 month timeline is was decided to move it back to august and move it up if we receive the permit at the 4 month mark. March 14, 2025- City permit Note: Dfx followed up on the 14th of March with Metrolinx and the BIA. we are waiting for their response. March 17, 2025 -Metrolinx Signoff attached. It specifically mentions the construction period March 18, 2025 - the city permit here has been conditionally granted . It still has to be sent to the main city office for the permit to be issued. City MEMO# 1005759.pdf March 19, 2025 - OSP const: OSP construction is tentatively scheduling this for the week of March 31st, this is dependent on when we receive the permit. March 19, 2025 - Noted in OSP const- this was submitted for relocates, therefore the locates are good until May. March 21, 2025 - City permits fully granted 1005759001, 1005759002,RoDARs has been requested for March 31st to April 11th. March 26, 2025 - RoDar has been approved to start work for March 31. March 28, 2025 - PM does not like having vendors in the building on Mondays. | [6 empty] | 3 - Normal | [21 empty] | 2024-10-04 |  |  | 16 | 219 | [5 empty] | https://buildings.beanfield.com/buildings/view/9988 |  | CONST-38108 | 3 - Normal | 2025-08-06 | York
Construction | CONST-6559 | 11 Charlotte St, Toronto - King Charlotte | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Russell Francey | 2017-07-10 09:23 |  | 2025-03-29 21:51 |  |  | 2025-06-18 | 0 | 1 | _thumb_111841.png _thumb_111805.png _thumb_111806.png _thumb_111807.png _thumb_111808.png |  | CONST-7341, CONST-7378, CONST-27691, CONST-27692, CONST-28543, CONST-28544, CONST-28545, CONST-28546, CONST-28547, CONST-28548, CONST-28549, CONST-28550, CONST-28551, CONST-28552, CONST-28553, CONST-28556, CONST-28557, CONST-28558, CONST-28960, CONST-29656, CONST-30290, CONST-37163, CONST-39366, CONST-39370, CONST-39575 | CONST-3326 | King Charlotte TSCC #2546 Phone: 416-597-0268 Email: trish@iconpm.ca Fed from BFMH at Peter and Adelaide Break out from Hydro CC36457 into south west corner of building 32 stories 1 riser room in riser conduits room in zone conduits, Bell and Rogers present with fibre room in POP power not confirmed amenities on 3rd floor | FSactive, Fiberstreamagreement | [12 empty] | 0¦i0sn27: | [7 empty] | 9.2234e+18 | [19 empty] | October 12th - Moratorium until 2023 on Charlotte St. Mar 29/23 - Due dates will be reaccessed when moratorium ends. Jan 10/24 - Moratorium expired end of 2023. Designs and permits in progress. Apr 09/24 - Manhole survey completed Apr 25/24 - Hydro permit PO sent May 3, 2024 - Project is placed on hold as per Oliver Davies in May 2nd. Feb 20, 2025 - this building is on the east side, this is a cable pull going through Hydro duct. Feb 20, 2025 - Scheduled On Net date for June 18, 2025 March 20, 2025 - Route Drawing is attached. March 28, 2025 -We will be adding a 4x4 MH at this location, we will pull a 144f from Peter and Adelaide MH to new BFMH and then 48f into 8 Charlotte and 48f into 11 Charlotte | [6 empty] | 3 - Normal | [19 empty] | Internal |  | 2022-05-24 |  |  | 32 | 232 | Integration |  | 44199 |  |  | https://buildings.beanfield.com/buildings/view/911 |  | 500402 | 3 - Normal | 2023-08-25 | Toronto King West | 4442 | 18865
Construction | CONST-3326 | 8 Charlotte St, Toronto - Charlie Condos | Condo | In Progress |  | Unresolved | James Mowers | Lorna Kurok | Jay Fernandes | 2015-04-06 15:27 |  | 2025-03-29 21:54 |  |  | 2025-07-23 | 0 | 5 | _thumb_142461.png _thumb_142464.png _thumb_142465.png |  | CONST-3327, CONST-3328, CONST-3329, CONST-9222, CONST-27785, CONST-28559, CONST-28560, CONST-28561, CONST-28562, CONST-28563, CONST-28564, CONST-28565, CONST-28566, CONST-28567, CONST-28568, CONST-29609, CONST-29610, CONST-29655, CONST-37659, CONST-39365, CONST-39574, CONST-40241, CONST-40244 | CONST-6559 | Nena - manager@8charlotte.com 314 Suites Phones from riser to suites Power in suites low rise has 6 floors and 1 Riser- HiRise has 36 floors and 2 risers- 2-4" conduits in each riser Pop in sw corner of P1 level by parking spot V4 | FSactive, Fiberstreamagreement | [12 empty] | 0¦i08cbj: | [7 empty] | 48654 | [19 empty] | Constructed 2013 September 13th - Moratorium until 2023 on Charlotte St. Mar 29/23 - Due dates will be reaccessed when moratorium ends. Jan 10/24 - Moratorium expired end of 2023. Designs and permits in progress. May 3, 2024 - Project is placed on hold as per Oliver Davies in May 2nd. March 4, 2025 - Note this buildings are now offically back in progress. March 25, 2025 - City Permit comment: We are feeding 11 Charlotte via the buildings vault, no need for MH. New building can be fed from KIng street, IF we get an agreement. March 28, 2025 - noted form 11 Charlotte - We will be adding a 4x4 MH at this 11 charlotte, we will pull a 144f from Peter and Adelaide MH to new BFMH and then 48f into 8 Charlotte and 48f into 11 Charlotte | [6 empty] | 3 - Normal | [19 empty] | External |  | 2022-05-24 |  |  | 36 | 314 | Integration |  | 65340 |  |  | https://buildings.beanfield.com/buildings/view/1460 |  | 500404 | 5 - Very Low | 2023-08-25 | Toronto King Spadina / Garment District | 4350 | 15205
Generated at Mon Mar 31 09:59:20 EDT 2025 by Mojgan Rafiei using Jira 8.20.24#820024-sha1:e6f6b79207289027656f61dbd8f030d34397d2c7.